## TAS SLA with Mgmt Plans
If a calendar day falls on a Saturday, Sunday, or Federal or State Holiday, the next business day is used when calculating the number of calendar days.
SLA Number | Category | Topic / Item | RFP Section | SLA Description | Criteria (When this condition is met …) | Liquidated Damages (LD)
SLA - 01 | Staffing | Vacancies | 4.3.3.2 | Time period to replace a staff member exceeds 45 business days. | The vacancy date of a staff member plus 45 business days. | $500 per business day, each position is vacant beyond 45 business days.
SLA - 02 | Staffing | Staff Management Plan Requested Update | 4.3.3.1 | Staff Management Plan shall be updated within 10 business days of when key and supplemental staff are added or leave the project, and Staffing Plan shall be updated within 10 business days of when the Department makes a request. | Updated plan is not received by Supplemental staff start date or leave date, plus 10 business days. Updated plan is not received by 10 business days of Department request date. | $500 per day for each business day the plan is late.
SLA - 03 | Status Reports | MES Program Status Reports | 4.4 and 4.5 | Biweekly Status reports reporting on the progress of MES Portfolio of Projects (work items), summary of staff resource status, SLAs, Risks and issues, etc. See list RFP Sections 4.4 and 4.5.1. | Contract start date +14 calendar days and every 14 calendar days through contract term. | $ 500 per business day the status report is late.
SLA - 04 | Facilities | Facilities Management Plan | 4.3.3.3 and Attachment L | Initial Facilities Management Plan due 30 calendar days after first day of occupying the facility. | Date staff occupy the facility + 30 calendar days. | $500 per day for each business day the plan is late.
SLA - 05 | Facilities | Facilities Management Plan | 4.3.3.3 and Attachment L | The Facilities Management Plan shall be updated annually. | Date staff occupy the facility + 365 calendar days.
SLA - 06 | Facilities | Physical Security Management Plan | 4.3.3.3 and Attachment L | Initial Physical Security Plan must be submitted within 30 calendar days of the occupying the facility. | Date staff occupy the facility + 30 calendar days.
SLA - 07 | Facilities | Physical Security Management Plan | 4.3.3.3 and Attachment L | Physical Security Plan annually for review and approval by the Department. | Date staff occupy the facility + 365 calendar days.
SLA - 08 | Transition | Transition Plan | 4.9 | Initial Transition Plan is due 180 calendar days after contract start date. | Contract start date + 180 calendar days | $500 per calendar day Transition Plan is overdue
SLA - 09 | Transition | Annual Transition Plan Update and Documentation Audit | 4.9 | The Transition Plan shall be updated annually. | Initial Transition Plan approval date (see SLA -08) plus 365 days. | $500 per calendar day Transition Plan is overdue
SLA - 10 | Transition | Transition Plan Update before contract end | 4.9 | Regardless of reason, contract end date identified. No less than four (4) months, (120 calendar days) before that end date, the Transition Plan is updated and weekly transition meetings begin. | No later than 4 months, i.e., 120 calendar days, before identified contract end date. | $ 1000 per business day the Transition is not updated prior to 120 calendar days before identified contract end date.
SLA - 11 | Transition | Transition Weekly Status meetings | 4.9 | At a minimum, Transition weekly status meetings are with the Department staff, starting within two weeks of identified contract end date. | No later than 4 months before identified contract end date. | $ 1000 per week (5 business days) that the contractor does not meet with the Department on status of Transition Plan activities, unless otherwise approved by the department to skip a week.
SLA - 12 | Transition | Annual Documentation Audit | 4.9.1 | Annual internal audit, lead by TAS Team with Department, to confirm all documentation, deliverables, and work products (solutions, data, files, reports, plans and diagrams, historical versions of data and documents, and records generated) to verify that most up-to-date versions of these documents are stored in the Department’s repository. | Annually (365 calendar days) based on contract start date. | $300 per document found to be out of date or missing from repository during annual review.
SLA - 13 | Payment | Invoices | 5.4 | Timely receipt of Invoices - Invoices are to be received within thirty(30) days from the close date of the preceding month. | Invoices received 30 or more calendar days after the close date of the preceding month. | 10% 5% of preceding preceding month invoice amount.
SLA - 14 | Payment | Invoices | 5.4 | Accuracy of Invoices - Department rejected invoice due to material issue. | Department rejected invoice due to a material issue. | .5% of the invoice amount.
SLA - 15 | Payment | Invoices | 5.4 | Accuracy of Invoices - Department rejected invoice for 2nd time, or more, due to material issue | Second rejection (or more) of invoice with material issue. | 2% of the invoice amount.
Initial Strategic Management Plans
SLA # | Category | Plan Name | RFP Section | Initial Plan Due Date = Number of Days from contract start | Criteria (When this condition is met …) | Liquidated Damages (LD)
SLA - 16 | Staffing | Initial Custom Staff Management Plan | 4.1 and 4.3.3 | 45 days | Contract start date +45 calendar days | $500 per business day for each calendar day the plan is late.
SLA - 17 | Program and Contract Management | Initial Custom MES Program and Contract Management Plan | 4.1 and 4.4 | 60 days | Contract start date +60 calendar days
SLA - 18 | Program and Project Management | Initial Custom Documentation Management Plan | 4.1 and 4.5.5 | 75 days | Contract start date +75 calendar days.
SLA - 19 | Program and Project Management | Initial Custom Project Management Standards | 4.1 and 4.2.2 | 75 days | Contract start date +75 calendar days.
SLA - 20 | Program and Project Management | Initial Custom Portfolio and Project Management Plan | 4.1 and 4.2.2 | 90 days | Contract start date +90 calendar days.
SLA - 21 | Program and Project Management | Initial Custom Certification Management Plan | 4.1 and 4.2.2 | 90 days | Contract start date +90 calendar days.
SLA - 22 | Contract Management | Initial Custom Budget, IT Assets and Procurement Management Plan | 4.1 and 4.2.3 | 90 days | Contract start date +90 calendar days.
SLA - 23 | Organizational Change Management | Initial Custom Organizational Change Management Plan | 4.1 and 4.2.4 | 120 days | Contract start date +120 calendar days.
SLA - 24 | Enterprise Architecture | Initial Custom MES Enterprise Technical and Interoperability Architecture Management Plan | 4.1 and 4.2.1 | 120 days | Contract start date +120 calendar days.
SLA - 25 | Enterprise Architecture | Initial Custom MES Security Architecture Management Plan | 4.1 and 4.2.1 | 120 days | Contract start date +120 calendar days.
SLA - 26 | Enterprise Architecture | Initial Custom MES Enterprise Architecture Management Plan | 4.1 and 4.2.1 | 150 days | Contract start date +150 calendar days.
SLA - 27 | Enterprise Architecture | Initial Custom MES Enterprise Information Architecture, Data Management and Governance Plan | 4.1 and 4.2.1 | 150 days | Contract start date +150 calendar days.
SLA - 28 | MES Strategic Roadmap (Detailed Roadmap) | Initial Custom MES Strategic Roadmap (Detailed Roadmap) | Entire RFP | 180 days | Contract start date +180 calendar days.
Strategic Management Plans - Quarterly Update
SLA # | Category | Plan Name | RFP Section | Quarterly Plan Update Due Date | Criteria (When this condition is met …) | Liquidated Damages (LD)
SLA - 29 | Staffing | Initial Custom Staff Management Plan | 4.1 | Update each Strategic Management Plan on a quarterly interval (90 days). | Contract Start date +45 days, plus every 90 calendar days thereafter. | $500 per business day for each calendar day the plan is late.
SLA - 30 | Program and Contract Management | Initial Custom MES Program and Contract Management Plan | 4.1 and 4.4 |  | Contract Start date +60 days plus every 90 calendar days thereafter.
SLA - 31 | Program and Project Management | Initial Custom Documentation Management Plan | 4.1 and 4.5.5 |  | Contract start date +75 calendar days plus every 90 calendar days thereafter.
SLA - 32 | Program and Project Management | Initial Custom Project Management Standards | 4.1 and 4.2.2 |  | Contract start date +75 calendar days, plus 90 calendar days
SLA - 33 | Program and Project Management | Initial Custom Portfolio and Project Management Plan | 4.1 and 4.2.2 |  | Contract start date +90 calendar days plus every 90 calendar days thereafter.
SLA - 34 | Program and Project Management | Initial Custom Certification Management Plan | 4.1 and 4.2.2 |  | Contract start date +90 calendar days plus every 90 calendar days thereafter.
SLA - 35 | Contract Management | Initial Custom Budget, IT Assets and Procurement Management Plan | 4.1 and 4.2.3 |  | Contract start date +90 calendar days plus every 90 calendar days thereafter.
SLA - 36 | Organizational Change Management | Initial Custom Organizational Change Management Plan | 4.1 and 4.2.4 |  | Contract start date +120 calendar days plus every 90 calendar days thereafter.
SLA - 37 | Enterprise Architecture | Initial Custom MES Enterprise Technical and Interoperability Architecture Management Plan | 4.1 and 4.2.1 |  | Contract start date +120 calendar days plus every 90 calendar days thereafter.
SLA - 38 | Enterprise Architecture | Initial Custom MES Security Architecture Management Plan | 4.1 and 4.2.1 |  | Contract start date +120 calendar days plus every 90 calendar days thereafter.
SLA - 39 | Enterprise Architecture | Initial Custom MES Enterprise Architecture Management Plan | 4.1 and 4.2.1 |  | Contract start date +150 calendar days plus every 90 calendar days thereafter.
SLA - 40 | Enterprise Architecture | Initial Custom MES Enterprise Information Architecture, Data Management and Governance Plan | 4.1 and 4.2.1 |  | Contract start date +150 calendar days plus every 90 calendar days thereafter.
SLA - 41 | MES Strategic Roadmap (Detailed Roadmap) | Initial Custom MES Strategic Roadmap (Detailed Roadmap) | Entire RFP |  | Contract start date +180 calendar days plus every 90 calendar days thereafter.