## Phase 3 original (hidden)
MRT Project # | Project/Task Description | Status | Remarks and Updates to associated documents
Catch-All Workplan
6001 | Gold STAMP Program to Reduce Pressure Ulcers | Completed
6002 | Balance Incentive Program (BIP) | Merged #8010 | 9/17 No Division listed (Mark Kissinger listed in field)
6003 | Federal Revenue from Additional Emergency Medicaid Claiming and Other Possible Efforts | Completed
6004 | PCMH Savings | Completed
6005 | Increase Efficiency of Transportation Utilization by Transportation Manager | Completed
6006 | Accelerate BHO Managed Care Efficiency Adjustment | Merged into VBP | Pending 2015-2016 budget
6007 | Managed Care Efficiency Adjustment Reduce Accounts Receivable Balances | In Progress | No Division listed (John Ulberg/Ann Foster listed in field) *During WP meeting discussed options for changing legislation.
6008 | Reduce Accounts Receivable Balances (Part B) | In Progress | 9/17 No Division listed (John Ulberg/Ann Foster listed in field) *During WP meeting discussed options for changing regulation and requiring a facility to notify DOH when they are in process of closing.
6009 | Accelerate MLTC Enrollment | Completed
6010 | Develop Initiatives to Integrate and Manage Care for Dual Eligibles (Fully Integrated Duals Advantage - FIDA) | In Progress
6011 | OPWDD Fully Integrated Duals Advantage - FIDA | Completed | #6012 removed per Deanna
6013 | NYCOTB | Completed | after 2/25 update.
6014 | Family Health Plus Program discontinuation | Completed
6015 | Home Care Workers Benefits | Completed | No Division listed (Robert Loftus listed in field)
6016 | Inappropriate Suboxone (buprenophrine/naloxone) Utilization | Completed
6017 | Provider on Review (edit 1142) | Completed
6018 | Upcoding and Billing Inconsistencies in Assisted Living Programs (ALP) | Completed
6019 | Salient Challenge - High Opiod Prescriber Awareness | Cancelled
6020 | Salient Challenge - Dose Optimization | Completed
6021 | Enforce billing restrcition to prevent Nurse Practitioners, Physician Assistants, and Nurse-Midwives from being paid separately for practioner claims for services provided in (Article 28) hospitals. | In Progress
6022 | Restrict reimbursement to providers for incompatible rate code and/or Category of Service combinations. | Completed
Affordable Housing Work Group
6101 | Health Homes Supportive Housing Pilot Project | Completed | 9/17 No Division listed (Lana Earle and Mark Kissinger listed in the field)
6102 | OMH Supported Housing Services Supplement | Completed | 9/17 Update Affordable Housing Work Plan to include the Team Lead field (Bob and Moira were listed in the Div Lead field)
6103 | Homeless Senior Placement Pilot Project | Completed | 9/17 Update Affordable Housing Work Plan to include the Team Lead field
6104 | Health Home HIV + Rental Assistance Pilot Project | Completed | 9/17 Update Affordable Housing Work Plan to include the Team Lead field
6105 | Senior Supportive Housing Pilot Project | Completed | Update Affordable Housing Work Plan to include the Division Lead field
6106 | Step-Down/Crisis Residence Capital Conversion Pilot Project | Completed | 9/17Update Affordable Housing Work Plan to include the Team Lead field
6107 | Nursing Home to Independent Living Rapid Transition | Completed | Update Affordable Housing Work Plan to include the Team Lead field
Operations Workplans
6201 | Activating Ordering/Prescribing/Referring/Attending Edits | Completed | 9/17 Update Operations Work Plan to reflect Completed status.
6202 | Incontinence Supply Contractor | In Progress
6203 | Increase Manual Review of Claims | Completed
6204 | Hearing Aid Administrative Streamlining | Completed
Pharmacy Workplans
6301 | Implement Appropriateness Edits on Emergency Medicaid Claims | Completed
6302 | Expand Prescriber Prevails to additional classes in Managed Care | Completed
6303 | Mail Order Pharmacy | Completed
6304 | Merge P&T Committee and DUR Board | Completed
Health Homes Workplans
6401 | Develop and Implement Health Home Portal (Move Tracking System off HCS Platform) | In Progress
6402 | Enrolling Children into Health Homes (HH) | In Progress
6403 | Guidance for Hospitals to Refer Patients to the HH Program | In Progress
6404 | Oversight of Grievances/Complaints, Incident Reporting, and Site Visits | Completed
6405 | Health Home Implementation Grants | Completed
6406 | Shared Savings SPA 12-09 | In Progress
Basic Benefit Work Group
6501 | Lumbar Discography | Completed
6502 | Trancutaneous Nerve Stimulation (TENS) for Treatment of Pain | Completed
6503 | Implantable Infusion Pumps for Non-Cancer Pain | Completed
6504 | Functional Electrical Stimulators (FES) | Completed

## Phase 3
MRT Phase 3 Project Status
MRT Project # | Project/Task Description | Status
Catch-All Workplan
6001 | Gold STAMP Program to Reduce Pressure Ulcers | Completed
6002 | Balance Incentive Program (BIP) | Merged #8010
6003 | Federal Revenue from Additional Emergency Medicaid Claiming and Other Possible Efforts | Completed
6004 | PCMH Savings | Completed
6005 | Increase Efficiency of Transportation Utilization by Transportation Manager | Completed
6006 | Accelerate BHO | Merged into VBP
6007 | Managed Care Efficiency Adjustment | Merged #10201
6008 | Reduce Accounts Receivable Balances (Part B) | Merged #10201
6009 | Accelerate MLTC Enrollment | Completed
6010 | Develop Initiatives to Integrate and Manage Care for Dual Eligibles (Fully Integrated Duals Advantage - FIDA) | Completed
6011 | OPWDD Fully Integrated Duals Advantage - FIDA | Completed
6013 | NYCOTB | Completed
6014 | Family Health Plus Program discontinuation | Completed
6015 | Home Care Workers Benefits | Completed
6016 | Inappropriate Suboxone (buprenophrine/naloxone) Utilization | Completed
6017 | Provider on Review (edit 1142) | Completed
6018 | Upcoding and Billing Inconsistencies in Assisted Living Programs (ALP) | Completed
6019 | Salient Challenge - High Opiod Prescriber Awareness | Cancelled
6020 | Salient Challenge - Dose Optimization | Completed
6021 | Enforce billing restrcition to prevent Nurse Practitioners, Physician Assistants, and Nurse-Midwives from being paid separately for practioner claims for services provided in (Article 28) hospitals. | Merged #11002
6022 | Restrict reimbursement to providers for incompatible rate code and/or Category of Service combinations. | Completed
Affordable Housing Work Group
6101 | Health Homes Supportive Housing Pilot Project | Completed
6102 | OMH Supported Housing Services Supplement | Completed
6103 | Homeless Senior Placement Pilot Project | Completed
6104 | Health Home HIV + Rental Assistance Pilot Project | Completed
6105 | Senior Supportive Housing Pilot Project | Completed
6106 | Step-Down/Crisis Residence Capital Conversion Pilot Project | Completed
6107 | Nursing Home to Independent Living Rapid Transition | Completed
Operations Workplans
6201 | Activating Ordering/Prescribing/Referring/Attending Edits | Completed
6202 | Incontinence Supply Contractor | Completed
6203 | Increase Manual Review of Claims | Completed
6204 | Hearing Aid Administrative Streamlining | Completed
Pharmacy Workplans
6301 | Implement Appropriateness Edits on Emergency Medicaid Claims | Completed
6302 | Expand Prescriber Prevails to additional classes in Managed Care | Completed
6303 | Mail Order Pharmacy | Completed
6304 | Merge P&T Committee and DUR Board | Completed
Health Homes Workplans
6401 | Develop and Implement Health Home Portal (Move Tracking System off HCS Platform) | Completed
6402 | Enrolling Children into Health Homes (HH) | Completed
6403 | Guidance for Hospitals to Refer Patients to the HH Program | Completed
6404 | Oversight of Grievances/Complaints, Incident Reporting, and Site Visits | Completed
6405 | Health Home Implementation Grants | Completed
6406 | Shared Savings SPA 12-09 | Cancelled
Basic Benefit Work Group
6501 | Lumbar Discography | Completed
6502 | Trancutaneous Nerve Stimulation (TENS) for Treatment of Pain | Completed
6503 | Implantable Infusion Pumps for Non-Cancer Pain | Completed
6504 | Functional Electrical Stimulators (FES) | Completed
Phase 3
|  | Cancelled | 2
|  | Completed | 39
|  | Merged | 5
|  | Included in MRT Waiver | 0
|  | Substantively complete | 0
|  | Suspended | 0
|  | In Progress | 0
|  | Total | 46
|  |  | 0% | Remain open