## Ph. 7 Catch All
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2017-2018 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
| 2018-10-24 |  |  |  | P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
10001 |  |  |  |  | Project Name: Establish Rebates for High Cost Drugs Division Lead: DPDM Team Lead: Tony Merola Additional Staff: John Ulberg, Janet Zachary-Elkind, Mike Ogborn, Mike Dembrosky, Mike Colabufo, Mark Shutts, Donna Cater, Phyllis Stanton, Melissa Kamal, Tony Merola, John Naioti, Bob Sheehan, Linda VanAmburgh, Kelly Ketz, Philomena Reish, Monica Toohey, Tracy Berger, Carol Lindley, Amir Bassiri, Dan Tarantino, Barbara Rogler. Description: Establishes a Medicaid drug cap as a separate component of the global cap w/year to year spending targets. If it is determined that expenditures will exceed annual growth limitation, the Commissioner may identify and refer drugs to the Drug Utilization Review (DURB) for a recommended target supplemental rebate. | -55 | Effective Date: 4/1/17
| 2017-04-21 | P | P | P | Finalize MCO rates |  | Prescription Drug Cap Modeling - DFRS
| 2017-04-28 | P | P | P | Build prescription drug cap model |  | Prescription Drug Cap Modeling - DFRS
| 2017-05-05 | P | P | P | Project/Estimate net prescription drug expenditures |  | Prescription Drug Cap Modeling - DFRS
| 5/5/2017 9/1/17 | P | P | P | Determine if prescription drug expenditure will exceed the cap |  | Prescription Drug Cap Modeling - DFRS
| 5/30/2017 9/30/17 | P | P | P | Submit State Plan Amendment |  | State Plan Amendment - DPDM
| 6/30/2017 10/31/17 | P | P | P | CMS approval of State Plan Amendment |  | State Plan Amendment - DPDM
| 2017-04-14 | P | P | P | Build analytical model to identify prescription drugs responsible for exceeding the cap |  | Analytics - DPDM & DFRS
| 5/5/2017 5/24/17 7/1/17 8/1/17 9/1/17 | P | P | P | Identify prescription drugs/drug classes responsible for exceeding the drug cap |  | Analytics - DPDM & DFRS
| 5/5/2017 6/1/17 7/15/17 8/15/17 9/10/17 | P | P | P | Notify pharmaceutical manufacturers regarding the prescriptions drugs that have been identify as or contributed to exceed the drug cap |  | Supplemental Rebate Contracting - DPDM
| 2017-05-15 | P | P | P | Identify new DURB members - actuaries, health care economists, department of financial services representatives |  | DURB - DPDM
| 5/31/2017 6/15/17 7/20/17 9/1/17 10/1/17 | P | P | P | First Attempt at rebate negotiations/agreements |  | Supplemental Rebate Contracting - DPDM
| 6/15/2017 6/30/17 7/31/17 9/15/17 10/15/17 11/1/17 12/31/17 | P | P | P | Receive First Attempt supplemental rebate contract from pharmaceutical manufacturers |  | Supplemental Rebate Contracting - DPDM
| 2017-06-01 | P | P | P | Submit vetting packet for new DURB members - 1 actuary, 1 DFS representative, 2 healthcare economists |  | DURB - DPDM & OGA
| 6/15/2017 7/31/17 8/15/17 | P | P | P | Appoint new DURB members - 1 actuary, 1 DFS representative, 2 healthcare economists |  | DURB - DPDM & OGA
| 6/20/2017 8/15/17 9/30/17 10/30/17 11/15/17 1/15/18 3/1/18 | P | P | P | Submit supplemental rebate contracts from pharmaceutical manufacturers to BOC |  | Supplemental Rebate Contracting - DPDM
| 2017-05-31 | P | P | P | Schedule DURB Board Meeting |  | If Supplemental Rebate Agreement cannot be reached: DURB Activities - DPDM
| 8/1/2017 9/15/2017 10/15/17 11/3/17 | P | P | P | Finalize financial/value based modeling approach/ methodology/ analysis (via SUNY UB) |  | DURB Activities- DPDM
| 6/30/2017 9/1/17 9/19/17 10/15/17 11/15/17 1/1/18 3/31/18 | P | P | P | Post DURB agenda (to include high cost drug items as needed) |  | DURB Activities- DPDM
| 7/21/2017 9/15/17 10/30/17 11/22/17 1/15/18 3/15/18 4/13/18 | P | P | P | Final DURB meeting materials including clinical and financial information |  | DURB Activities- DPDM
| 7/31/17 10/1/17 10/19/17 11/15/17 12/7/17 2/15/18 4/26/18 | P | P | P | DURB Meeting held |  | DURB Activities- DPDM
| 8/7/2017 10/15/17 10/30/17 11/7/17 12/15/17 2/28/18 5/4/18 | P | P | P | Post DURB recommendations to the DOH web-site including target rebate/benchmark |  | DURB Activities- DPDM
| 8/30/2017 10/30/17 11/15/17 12/20/17 3/7/18 5/18/18 6/13/18 7/13/18 8/1/18 | P | P | P | Post Commissioner's final recommendations (associated with the DURB recommendations) to the DOH web-site |  | DURB Activities- DPDM
| 9/10/2017 11/17/17 3/15/18 5/31/18 7/1/18 10/1/18 | P | P | P | Second Attempt rebate negotiation/agreement based on DURB target rebate benchmark |  | Rebate Contracting- DPDM
| 9/15/2017 11/30/17 5/1/18 8/1/18 10/1/18 1/1/19 3/1/19 | 8 | 8 | 8 | For drugs/drugs classes under the Prescriber Prevails (PP) provision - for which the 75% of the DURB target rebate amount is not attainable - remove/waive PP protections |  | Analytics - DPDM & DFRS
| 9/30/2017 11/30/17 1/1/18 3/1/18 5/31/18 6/30/18 7/31/18 9/15/18 | P | P | P | Receive Second Attempt supplemental rebate contract(s) from pharmaceutical manufacturer |  | Rebate Contracting- DPDM
| 10/7/2017 12/10/17 1/15/18 3/15/18 6/8/18 7/11/18 8/15/18 9/30/18 | P | P | P | Submit Second Attempt supplemental rebate contract(s) from pharmaceutical manufacturers to BOC |  | Rebate Contracting- DPDM
| 9/30/2017 12/10/17 1/31/18 4/1/18 5/18/18 7/18/18 8/15/18 9/30/18 11/1/18 12/1/18 | 8 | 8 | 8 | Pharmaceutical Manufacturers to provide cost information upon unsuccessful Second Attempt rebate contract(s) |  | Rebate Contracting- DPDM
| 10/10/2017 1/1/18 2/15/18 4/1/18 5/31/18 7/25/18 9/1/18 11/1/18 12/15/18 | 8 | 8 | 8 | Final Attempt at rebate negotiations/agreements based on pharmaceutical manufacturer submitted cost information. |  | Rebate Contracting- DPDM
| 10/20/2017 1/10/18 3/1/18 5/1/18 6/6/18 7/31/18 9/15/18 11/15/18 12/1/18 12/31/18 | 8 | 8 | 8 | Receive Final Attempt supplemental rebate contract(s) from pharmaceutical manufacturers |  | Rebate Contracting- DPDM
| 1/1/2018 1/15/18 3/15/18 5/31/18 6/8/18 8/1/18 10/1/18 1/1/19 2/1/19 | 8 | 8 | 8 | Upon failure of Final Attempt at supplemental rebate negotiations, Commissioner to notify Legislature 30 days prior to removing prescription drug/drug class formulary coverage |  | OHIP
| 11/7/2017 1/15/18 3/15/18 5/15/18 6/15/18 8/1/18 10/1/18 12/1/18 1/10/19 | 8 | 8 | 8 | Submit Third and Final Attempt supplemental rebate contracts from pharmaceutical manufacturers to BOC |  | Rebate Contracting- DPDM
| 11/30/2017 1/15/18 3/15/18 5/31/18 8/1/18 10/1/18 1/1/19 3/1/19 | 8 | 8 | 8 | Notify MCOs of drug coverage limitations, formulary status or presciber prevails changes. |  | DPDM
| 11/30/2017 1/15/18 3/1/18 5/31/18 8/1/18 11/1/18 1/1/19 3/1/19 | 8 | 8 | 8 | Notify Providers (prescibers and pharmacies) of drug coverage limitations, formulary status or presciber prevails changes. |  | DPDM
| 12/31/2017 2/1/18 4/1/18 7/1/18 10/1/18 1/1/19 2/1/19 5/1/19 | 8 | 8 | 8 | Implement drug coverage changes in FFS and MCO |  | DPDM
| 11/30/2017 1/15/18 3/1/18 6/1/18 Ongoing | P | P | P | Execute supplemental rebate contract(s) |  | Rebate Contracting- DPDM
| 11/30/2017 1/1/18 2/1/18 | P | P | P | Finalize and implement rebate invoice system specifications/processes |  | Invoicing - DFRS
| 2018-01-31 | P | P | P | Generate and release supplemental rebate invoices |  | Invoicing - DFRS
| 3/31/2018 Ongoing | P | P | P | Collect/receive supplemental rebates from pharmaceutical manufacturers |  | Invoicing - DFRS
10002 |  |  |  |  | Project Name: NYC Administrative Funding Division Lead: DFRS Team Lead: Ann Foster Additional Staff: Liz Misa, Ron Bass, Judy Arnold, Mike Ogborn, Mike Dembrosky Description: This proposal would require NYC to submit a savings plan to DOH to achieve $55 million in savings, subject to a MOU. If such plan fails to achieve $55 million in savings, the Department will reduce payments to the City totaling $55 million. NYC will develop a plan demonstrating payment to the State Medicaid program of $55 million dollars | -55 | Effective Date: 4/1/17
| 2017-05-05 | P | P | P | Initial meeting with HRA to discuss this savings initiative; schedule weekly meetings to discuss options
| 2017-05-12 | P | P | P | Weekly meeting with HRA; HRA provided several proposals
| 2017-05-17 | P | P | P | Meeting with HRA, OMB, NYCDOE and SSHSP team to discuss savings proposal related to SSHSP
| 2017-05-19 | P | P | P | Weekly meeting with HRA
| 5/31/2017 6/30/17 7/31/17 | 8 | 8 | 8 | NYC to develop and submit to the Department a shared savings allocation plan to generate $55 million in State savings to the Medicaid program
| 6/30/2017 7/31/17 | 8 | 8 | 8 | Approval of submitted plan by DOH/Effectuated MOU between Department and NYC
| 2017-10-01 | 8 | 8 | 8 | DOH evaluation of ongoing activities under the shared savings allocation plan to determine whether the targeted dollar amount (savings) will likely be achieved within the applicable state fiscal year
10003 |  |  |  |  | Project Name: Fiscal Intermediary (FI) Authorization Division Lead: DLTC Team Lead: Karis Browder Additional Staff: Andrew Segal, Krista McNally, Jennifer Alhart, Beth Ringer, Diamonds Zagadou Description: The development of an authorization process for fiscal intermediaries. Requires DOH to regulate entities that provide fiscal intermediary services to CDPAP consumers through an application for authorization process.
COMMUNICATIONS
| 4/28/17 6/1/17 8/1/17 | _ | _ | _ | Publish a press release detailing the new statutory language |  | Press release issuance is based on the new legislation getting signed by the governor. We are unsure of when/if this will get signed by the governor.
| 5/5/17 5/26/17 7/26/17 | P | P | P | Submit final Medicaid Update article for inclusion in the Medicaid Update
| 5/19/17 6/1/17 8/1/17 9/1/17 | P | P | P | Medicaid Update article published
FORMS
| 2017-04-21 | P | P | P | Review and revise the Consumer Agreement package for FFS and MC
| 2017-04-28 | P | P | P | Finalize the Consumer Agreement for FFS
| 5/3/17 6/30/17 9/1/17 12/1/17 4/1/18 8/1/18 10/1/18 12/1/18 | 8 | 8 | 8 | Distribute the Consumer Agreement to LDSS and MCOs along with a Companion Policy
| 2017-04-28 | P | P | P | Finalize the Consumer Agreement for MC
| 6/30/17 9/1/17 12/1/17 4/1/18 8/1/18 10/1/18 12/1/18 | 8 | 8 | 8 | Distribute the Consumer Agreement to MCOs along with a Companion Policy
| 2017-05-05 | P | P | P | Develop a Personal Assistant Agreement for FFS and MC
| 5/12/17 5/26/17 | P | P | P | Finalize the Personal Assistant Agreement for FFS
| 5/17/17 5/31/17 9/1/17 12/1/17 3/1/18 | 8 | 8 | 8 | Distribute the Personal Assistant Agreement to LDSS and MCOs
| 2017-05-19 | P | P | P | Develop a Personal Assistant Agreement for MC
| 2017-05-26 | P | P | P | Finalize the Personal Assistant Agreement for MC
| 5/31/17 9/1/17 12/1/17 3/1/18 | 8 | 8 | 8 | Distribute the Personal Assistant Agreement to MCOs
| 2017-05-19 | 8 | 8 | 8 | Review and revise the Physician's Order Form for CDPAP/CDPAS
| 2017-05-26 | 8 | 8 | 8 | Finalize the Physician's Order Form
| 2017-05-31 | 8 | 8 | 8 | Distribute the Physician's Order Form to LDSS and MCOs
| 6/2/17 6/16/17 7/16/17 | P | P | P | Develop a Back-Up and Emergency Contact Information Form for CDPAP/CDPAS
| 6/9/17 6/23/17 7/23/17 | P | P | P | Finalize the Back-Up and Emergency Contact Information Form
| 6/14/17 6/28/17 9/1/17 12/1/17 3/1/18 | 8 | 8 | 8 | Distribute the Back-Up and Emergency Contact Information Form to LDSS and MCOs
CONTRACTS
| 2017-05-05 | P | P | P | Review and revise CDPAS Administrative Agreement for MCOs
| 10/1/17 1/1/18 4/1/18 10/1/18 12/1/18 | 8 | 8 | 8 | Finalize the CDPAS Administrative Agreement
| 10/6/17 1/8/18 4/9/18 11/1/18 | 8 | 8 | 8 | Distribute the CDPAS Administrative Agreement to MCOs with a Companion Policy
| 2017-05-05 | P | P | P | Draft a model contract for LDSS for CDPAP
| 10/1/17 1/1/18 4/1/18 10/1/18 12/1/18 | 8 | 8 | 8 | Finalize the model contract for LDSS
| 10/6/17 1/8/18 4/9/18 11/1/18 | 8 | 8 | 8 | Distribute the model contract to LDSS
POLICIES
| 2017-04-21 | P | P | P | Full review of all policies and guidance materials that have been released to MCOs on CDPAS
| 2017-04-21 | P | P | P | Full review of all ADMs that have been released to LDSS on CDPAP
| 2017-04-21 | P | P | P | Determine what information has been provided through Medicaid Updates since the inception of CDPAP and CDPAS
| 2017-04-28 | 8 | 8 | 8 | Draft a policy for MCOs that addresses who can be a personal assistant.
| 2017-04-28 | 8 | 8 | 8 | Draft an ADM for LDSS that addresses who can be a personal assistant.
| 2017-05-05 | 8 | 8 | 8 | Finalize the policy and the ADM
| 2017-05-10 | 8 | 8 | 8 | Distribute the policy to the MCOs and the ADM to the LDSS
| 5/12/17 6/30/17 9/1/17 10/1/17 12/1/17 3/1/18 | 8 | 8 | 8 | Draft a policy guidance for MCOs and LDSS that affirms the scope of CDPAS/CDPAP, the appropriateness of CDPAS/CDPAP, and the FI authorization process
| 2017-05-12 | 8 | 8 | 8 | Draft an ADM for LDSS that affirms the scope of CDPAP, the appropriateness of CDPAP, and the FI authorization process
| 7/7/17 9/8/17 10/1/17 12/1/17 3/1/18 | 8 | 8 | 8 | Start the guidance through the executive clearance process
| 5/19/17 8/1/17 10/1/17 1/1/18 6/1/18 | 8 | 8 | 8 | Finalize the guidance for MCOs and LDSS policy and the ADM
| 5/24/17 8/2/17 10/1/17 1/8/18 6/8/18 | 8 | 8 | 8 | Distribute the guidance policy to the MCOs and the ADM to the LDSS
OVERSIGHT AND MONITORING
| 5/26/17 7/26/17 9/1/17 11/1/17 4/1/18 | P | P | P | Develop policies and procedures for CDPAS surveillance
| 6/9/17 9/1/17 12/1/17 3/1/18 | 8 | 8 | 8 | Receive approval on the policies and procedures for CDPAS surveillance
| 6/16/17 4/1/18 11/1/18 | 8 | 8 | 8 | Conduct oversight and surveillance on FIs providing service to CDPAS recipients
| 6/16/17 4/1/18 11/1/18 | 8 | 8 | 8 | Conduct oversight and surveillance on all MCOs providing CDPAS
REGULATORY
| 2017-06-23 | P | P | P | Perform a detailed crosswalk of the CDPAP statute and CDPAP regulation
| 7/7/17 10/1/17 4/1/18 | 8 | 8 | 8 | Draft new CDPAP regulation that aligns with the CDPAP statute
| 7/21/17 10/15/17 5/1/18 | 8 | 8 | 8 | Finalize CDPAP regulation
| 9/1/17 11/1/17 6/15/18 | 8 | 8 | 8 | DOH Executive approval
| 10/1/17 12/1/17 7/15/18 | 8 | 8 | 8 | Final CDPAP regulation posted for public comment
| 1/1/18 3/1/18 11/1/18 | 8 | 8 | 8 | Compile comments and release FAQ document
| 4/1/18 12/1/18 | 8 | 8 | 8 | CDPAP regulation promulgated
AUTHORIZATION
| 2017-04-21 | P | P | P | Meet with DOH waiver staff to determine their internal review and approval process for service providers
| 2017-04-28 | P | P | P | Meet with DOH provider enrollment staff to determine their internal review and approval process for service providers
| 2017-05-05 | P | P | P | Determine the data sources for the required data to be included in the application for authorization as an FI
| 2017-05-19 | P | P | P | Secure the data sources for the required data to be included in the application for authorization as an FI
| 6/2/17 8/2/17 | P | P | P | Draft application for authorization as an FI
| 6/30/17 9/15/17 10/1/17 11/1/17 | P | P | P | Receive approval from DOH Executive Staff on the application
| 7/7/17 10/1/17 11/1/17 | P | P | P | Release the application to the public and notify all external and internal stakeholders of the release
REVOCATION OF AUTHORIZATION
| 2017-07-01 | P | P | P | Start the development of the revocation process
10004 |  |  |  |  | Project Name: Eliminate Bed Hold Payment Division Lead: DLTC DFRS Team Lead: Kirk Dobson; Jada Eberle Additional Staff: Andrew Segal, John Ulberg Description: Nursing Homes are reimbursed through the Medicaid rate for reserved bed days related to leaves of absence for temporary hospitalizations. This proposal would eliminate the payment for bed hold days related to hospitalization. | -10.25 | Effective Date: 4/1/17 Currently with the Exec Chamber for next step determination
Emergency Regulation
| 2017-06-21 | P | P | P | Draft Emergency Regultations for 18 NYCRR 505.9
| 2017-06-21 | P | P | P | Draft Emergency Regultations for 10 NYCRR 86-2.40
| 2017-06-21 | P | P | P | Get DLA approval for emergency package
| 2017-06-21 | P | P | P | Get DLTC approval for emergency package
| 2017-06-30 | T | T | T | Bed Hold Emergency Regulations in Effect
| 2017-07-01 | T | T | T | Reduction of Payment from 50% to 0% begins
SAPA Package
| 2017-06-23 | P | P | P | Complete Regulatory Impact Statement
| 2017-06-23 | P | P | P | Complete Job Impact Statemetn
| 2017-06-23 | P | P | P | Complete Rural Area Flexibility Statement
| 2017-06-23 | P | P | P | Complete Emergency Justification
| 2017-06-23 | P | P | P | Complete Regulation Changes for Package
| 2017-06-23 | P | P | P | Complete State Environmental Quality Review
| 2017-06-23 | P | P | P | Complete DOH Proposed Rule Transmittal
| 2017-06-23 | P | P | P | Complete Executive Order 17
| 2017-06-23 | P | P | P | Get DLTC approval on completed packgage
| 2017-06-23 | P | P | P | Send to DLA for review
| 2017-06-28 | P | P | P | DLA Approval
| 2017-06-28 | P | P | P | EDC Approval
| 2017-06-28 | P | P | P | Commissioner Approval
| 2017-06-29 | T | T | T | DOB Approval
| 2017-06-30 | T | T | T | Governor's Office Approval
| 2017-06-30 | T | T | T | Delivery to Department of State/Enactment of Emergency Regulation and Notice of Rule Adoption
Communicaiton
| 2017-05-10 | P | P | P | Draft Temporary DAL for 4/1 - 7/1 continued billing allowance
| 2017-05-12 | P | P | P | Release Temporary DAL for 4/1-7/1 continue billing allowance
| 2017-05-10 | P | P | P | Create BML to address inquires
| 2017-06-26 | P | P | P | Draft Official DAL for updated policy
| 2017-07-01 | T | T | T | Release Official DAL for updated policy
| 2017-07-18 | T | T | T | Stakeholder Conference Call to discuss billing
EMedNY Edits
| 2017-06-20 | P | P | P | Review Edit 0183 (Therapeutic)
| 2017-06-20 | P | P | P | Review Edit 0185/0189 (Hospitlization and Others)
| 2017-06-26 | T | T | T | Submit Transmittal to Edit 0185 and 0189 to reflect changes
| 2017-07-01 | T | T | T | Edit Changes are effective in the system
SPA
| 2017-07-31 | T | T | T | Draft changes for SPA 4.19 C and D
| 2017-09-30 | T | T | T | Submit changes to CMS for approval
10005 |  |  |  |  | Project Name: Realign Children's SPA and MC implementation Division Lead: OMH Team Lead: Emil Slane Additional Staff: Description: The State recently updated the schedule for implementation of the expanded Medicaid benefit package for children to realign the rollout of the six new State Plan Amendment (SPA) services with the integration of children’s services into Medicaid managed care under the Children’s 1115 Waiver. | -10 | Effective Date: 4/1/17
|  | 8 | 8 | 8 | The work related to this implementation will be reflected in MRT # 10006, which covers 1115 waiver activities
10006 |  |  |  |  | Project Name: MRT 1115 Deliverables Division Lead: DPDM Team Lead: Phil Alotta Additional Staff: Jason Chura, Simone Yingling Description: To ensure compliance with 1115 deliverables per the STCs |  | Effective Date: 4/1/17
| 2017-05-25 | P | P | P | 1115 Quarterly Report Submission to CMS (Q2) |  | WMU
| 2017-08-31 | P | P | P | 1115 Quarterly Report Submission to CMS (Q3) |  | WMU
| 12/31/2017 12/20/17 | P | P | P | 1115 Quarterly Report Submission to CMS (Q4/Annual) |  | WMU
| 2/28/2018 2/26/18 | P | P | P | 1115 Quarterly Report Submission to CMS (Q1) |  | WMU
| 2018-05-31 | P | P | P | 1115 Quarterly Report Submission to CMS (Q2) |  | WMU
| 2018-08-31 | P | P | P | 1115 Quarterly Report Submission to CMS (Q3) |  | WMU
| 2018-05-01 | P | P | P | Notice of Forum sent to State Register for 5/16/18 Publication |  | WMU
| 2018-05-01 | P | P | P | Upstate Public Forum notice posted on DOH website |  | WMU
| 5/1/2018 5/19/18 | P | P | P | Upstate Public Forum sent out via DOH Listserv |  | WMU Michelle Golden
| 2018-06-19 | P | P | P | 1115 Public Forum (Upstate, Empire State Plaza) |  | WMU
| 7/16/2018 7/6/18 | P | P | P | 1115 Albany Public Forum slides and video of live webcast posted on 1115 webpage. |  | WMU
| 2018-09-15 | P | P | P | 1115 Public Forum (finalize time and location for upstate & downstate) |  | WMU
| 10/9/2018 10/3/18 | P | P | P | Notice for Forum sent to State Register for 10/24/18 Publication |  | WMU
| 10/9/2018 10/19/18 | P | P | P | Downstate Public Forum notice posted to the DOH Website |  | WMU
| 2018-11-29 | 8 | 8 | 8 | 1115 Public Forum (Downstate, NYC Acadamy of Medicine) |  | WMU
| 2018-12-31 | 8 | 8 | 8 | 1115 Quarterly Report Submission to CMS (Q4/Annual Report) |  | WMU
| 2017-06-27 | P | P | P | Notice of Forum sent to State Register for Mid-July 7/12/17 Publication |  | WMU
| 2017-07-13 | P | P | P | Upstate Public Forum notice posted on DOH website |  | WMU
| 2017-07-18 | P | P | P | Upstate Public Forum sent out via DOH Listserv |  | WMU
| 2017-08-14 | P | P | P | 1115 Albany Post-award Public Forum |  | WMU
| 2017-08-17 | P | P | P | 1115 Albany Public Forum slides and video of live webcast posted on 1115 webpage. |  | WMU
| 2017-10-01 | P | P | P | Downstate Public Forum notice posted on DOH website |  | WMU
| 2017-10-11 | P | P | P | Downstate Public Forum notice published in State Registry. |  | WMU
| 2017-10-20 | P | P | P | Downstate Public Forum notice sent via DOH Listserv. |  | WMU
| ~7/15/2017 | 8 | 8 | 8 | 1115 Public Forum Albany, NY; publish date of forum 30 days prior to the planned date of forum |  | Michelle Golden/WMU
| ~11/15/17 11/16/17 | P | P | P | 1115 NYC Post-award Public Forum |  | WMU
| 2017-11-21 | P | P | P | 1115 NYC Public Forum slides and video of live webcast posted on 1115 webpage. |  | WMU
| 2017-12-14 | P | P | P | Email containing link to 1115 Public Forum slides, video, transcript, comments, and summary sent to attendees. |  | WMU
Project Name: Children's Behavioral Health Amendment CMS- Facing Deadlines and Deliverables Division Lead: DPDM Team Lead: Lana Earle Additional Staff: Tonya Roloson, Caitlin Kennedy, Faith Schlesinger, Hope Goldhaber Description: Obtain CMS approval and implement per negotiated STCs
| 2017-05-09 | P | P | P | Childrens Behavioral Health Amendment Proposal Submit to CMS |  | Lana Earle/Hope Goldhaber/WMU
| 2017-05-16 | P | P | P | Childrens Behavioral Health Amendment Proposal approved as complete by CMS |  | Lana Earle/Hope Goldhaber/WMU
| 2017-06-19 | P | P | P | CMS Feedback on Amendment Proposal Received |  | Lana Earle/Hope Goldhaber/WMU
| ~7/19/17 ~7/31/17 7/26/17 | P | P | P | DOH Response to CMS Feedback |  | Lana Earle/Hope Goldhaber/WMU
| 2017-08-15 | P | P | P | Childrens Transformation plan posted to DOH Website. |  | Lana Earle/Hope Goldhaber/WMU
| ~8/30/2017 9/7/2017 | P | P | P | BN call with Mercer, CMS and, DOH to walk through MEG structure and specifications |  | Jason Chura/Carlos Cuevas
| 2018-04-24 | P | P | P | Call wth CMS to discuss new timeline for children's BH transition to 1115 |  | Lana Earle
| ~10/15/2017 ~12/15/2017 2/15/18 | T | T | T | BN call with Mercer, CMS and, DOH Follow-up call | ON HOLD | Jason Chura/Carlos Cuevas
| 9/1/2017 10/1/17 11/10/17 11/15/17 | P | P | P | Submit Transition Plan to CMS for moving recipients by waiver termination date |  | Lana Earle/Hope Goldhaber/WMU
| 9/28/2018 10/3/18 | P | P | P | Submit updated Budget Neutrality to CMS |  | Jason Chura
| 9/1/2017 4/1/18 3/15/18 3/15/18 12/15/18 | 8 | 8 | 8 | Tribal Notice to terminate 1915c waivers / consolidate into one 1915c |  | Lana Earle/Hope Goldhaber/WMU
| 9/15/2017 11/15/17 11/1/18 11/15/18 | 8 | 8 | 8 | Draft Letter to 1915c Waiver participants |  | Lana Earle/Hope Goldhaber
| 2018-11-22 | 8 | 8 | 8 | Sent Send letter to 1915c waiver participants for translation |  | Lana Earle/Hope Goldhaber
| 12/15/2017 1/15/18 12/15/18 | 8 | 8 | 8 | Finalized Finalize letter to 1915c Waiver participants |  | Lana Earle/Hope Goldhaber
| 10/1/2017 9/27/17 4/15/18 12/11/18 | 8 | 8 | 8 | Public Notice to terminate 1915c waivers / consolidate into one 1915c sent to State Registry |  | Lana Earle/Hope Goldhaber/WMU
| 2018-12-07 | 8 | 8 | 8 | Draft Tribal Notice Sent regarding termination of 1915c/consolidation into one 1915c |  | Lana Earle/ Hope Goldhaber/WMU
| 12/11/2018 12/26/18 | 8 | 8 | 8 | Public Notice Published in State Registry |  | Lana Earle/ Hope Goldhaber/WMU
| 2018-12-15 | 8 | 8 | 8 | Obtain Waiver Participants addresses |  | Lana Earle/ Hope Goldhaber/WMU
| 2018-12-30 | 8 | 8 | 8 | Letter to Print Shop |  | Lana Earle/Hope Goldhaber/WMU
| 2019-01-06 | 8 | 8 | 8 | Letter to Mailroom |  | Lana Earle/Hope Goldhaber/WMU
| 10/1/2017 5/31/18 5/15/18 1/6/19 2/15/19 | 8 | 8 | 8 | Letter to 1915c Waiver participants mailed |  | Lana Earle/Hope Goldhaber
| 12/1/2017 6/1/18 5/15/18 2/7/19 | 8 | 8 | 8 | Waiver amendments amend to terminate six five 1915c waivers submitted to CMS |  | Lana Earle/Hope Goldhaber
| 12/31/2017 6/30/18 3/31/19 | 8 | 8 | 8 | Waiver Termination of the five 1915c waivers and consolidate waivers into one |  | Lana Earle/Hope Goldhaber
| 1/18/2018 1/1/18 7/1/18 4/1/19 | 8 | 8 | 8 | Start to transition kids 1915c Kids start 1115 Waiver Five 1915c Children's Waivers populations transition to one 1915c waiver (CAH I/II) |  | Lana Earle/Hope Goldhaber/WMU
Project Name: 1915c waivers transition to 1115 CMS- Facing Deadlines and Deliverables Division Lead: OPWDD Team Lead: Kate Marley Additional Staff: Lauren Porter, Lisa Kennedy Description: Obtain CMS approval and implement per negotiated STCs
| 2017-05-16 | P | P | P | OPWDD 1915c Waivers transition to 1115 Waiver Proposal submitted to DOH for review |  | Kate Marley
| 2017-06-06 | P | P | P | Tribal Notice Sent |  | Kate Marley
| 2017-06-14 | P | P | P | Public Notice Published |  | Kate Marley
| 2017-07-24 | P | P | P | OPWDD Proposal published on DOH website. |  | Kate Marley
| 2017-09-01 | P | P | P | Submit 1115 amendment proposal for OPWDD amendment. |  | Kate Marley
| 2017-09-12 | P | P | P | Received letter of completeness from CMS; posted to DOH website |  | Kate Marley/WMU
| ~9/30/2017 ~12/15/17 2/15/18 4/1/18 3/21/18 | P | P | P | BN call with CMS, Mercer, DOH, & OPWDD to walk through MEG structure and Specifications |  | Kate Marley/Mercer/ Jason Chura
| 2017-12-05 | P | P | P | Transition plan posted for public comment |  | Kate Marley
| 2018-02-21 | P | P | P | Response to Public Comment on Draft Transition Plan |  | Kate Marlay
| 2018-02-21 | P | P | P | Final Transiton Plan posted on DOH website |  | Kate Marlay
| 12/31/2017 2/1/18 2/23/18 | P | P | P | Transition plan submission to CMS |  | Kate Marley
| 2018-02-22 | P | P | P | Received CMS RAI on Draft Amendment 03 to 1915 Waiver |  | Kate Marlay
| 2018-01-25 | P | P | P | Tribal Notice to terminate the 1915c waivers regarding the 03 amendment transitioning to the 1115. |  | Kate Marley
| ~9/27/17 5/1/18 4/15/18 2/14/18 | P | P | P | Public Notice to terminate 1915c waivers regarding the 03 amendment transitioning to the 1115. |  | Kate Marley
| 9/30/17 6/1/18 5/15/18 3/29/18 | P | P | P | Waiver amendment to terminate close 1915c approved by submitted to CMS |  | Kate Marley
| 2018-04-19 | P | P | P | Submitted IAAF and TAC/Y proposals to CMS |  | Kate Marley/Donna Cater
| 2018-03-29 | P | P | P | CMS approval of waiver amendment to terminate 1915c (Amendment 03) |  | Kate Marley/Lana Earle
| ~10/1/2017 5/31/18 5/15/18 | 8 | 8 | 8 | Letter to 1915c Waiver participants | ON HOLD | Kate Marley
| 1/18/2018 1/1/18 7/1/18 | 8 | 8 | 8 | OPWDD 1915c Waivers population transition to 1115 Waiver | ON HOLD | Kate Marley
| 6/30/2018 6/30/18 | P | P | P | CMS approved OPWDD 1915c Waiver to extend to 3/31/19 9/30/19 |  | Kate Marley/Lana Earle
| 2018-07-09 | P | P | P | Submitted to CMS draft Amended STC's for 1115 Managed Care Authority for OPWDD submitted to CMS |  | Kate Marlay/Lana Earle
| 2018-08-01 | P | P | P | State submits draft Amendments to Comprehensive Waiver |  | Kate Marlay/Lana Earle
| 2018-09-17 | P | P | P | Submitted final Budget Neutrality documentation to CMS |  | Jason Chura
| 2018-10-04 | P | P | P | Draft OPWDD STCs resubmitted on revised updated 1115 document to CMS |  | Kate Marlay/Lana Earle
| 9/1/2018 11/1/18 | 8 | 8 | 8 | CMS Approval of STCs for implementing concurrent 1915c and 1115 Waiver |  | Kate Marlay/Lana Earle
10007 |  |  |  |  | Project Name: HARP Rates Division Lead: DFRS Team Lead: John Ulberg Additional Staff: Donna Cater, Mike Ogborn Description: HARP & HCBS rates |  | Completed - January 2018
| 2017-09-30 | P | P | P | HARP Behavioral Health Fee for Service HCBS Rates; The review and supporting documentation must be received by CMS no later than September 30, 2017. CMS & NY agree to the removal of 2 STCs from the 1115 waiver requiring this time study. However, CMS reserves the right to request that the reviews specified in the STCs be performed at a later date. See CMS letter dated 7/11/17. |  | Donna Cater
| 2015-07-23 | P | P | P | NYC HARP rates submitted to CMS. |  | Mike Ogborn
| 2017-02-15 | P | P | P | Rest-of-State HARP rates submitted to CMS. |  | Mike Ogborn
| 2017-12-31 | P | P | P | Managed Care Rates Transition for HARPs;The state must submit HARP capitation rates to CMS for approval no later than December 31, 2017. |  | Mike Ogborn
10008 |  |  |  |  | Project Name: 1115 Budget Neutrality Division Lead: DFRS Team Lead: Donna Cater Additional Staff: Ann Foster, Mbuyi Mbuyi, Jason Chura, Alan Maughan Description: To implement per STCs
| 9/30/2017 12/31/17 | P | P | P | Budget Neutrality Remediation Project (DY14-17Q23, reconcilled; DY17 Q3&Q4 expenditures) |  | John Ulberg/Carlos Cuevas Ann Foster/ Jason Chura
| 9/30/17 12/31/2016 | P | P | P | Updated Specifications Manual |  | Mbuyi Mbuyi/ Carlos Cuevas
| 2017-02-28 | P | P | P | DY14 Initial Calculations |  | Carlos Cuevas/PCG Team
| 2017-04-14 | P | P | P | DY15 Initial Calculations |  | Carlos Cuevas/PCG Team
| 2017-06-30 | P | P | P | DY16 Initial Calculations |  | Carlos Cuevas/PCG Team
| 2017-08-31 | P | P | P | DY17 Initial Calculations |  | Carlos Cuevas/PCG Team
| 12/31/2017 3/31/18 2/16/18 | P | P | P | DY17 Q4 Reconcilled Report Expenditures Reporting DY17 Q3/Q4 |  | Ann Foster/Jason Chura
| 9/30/2017 ~11/15/17 11/30/17 12/31/17 3/31/18 5/15/18 7/1/18 10/1/18 12/31/18 | 8 | 8 | 8 | DY18 and DY19 to date, Initial Calculations 3 mo lag data processed |  | Jason Chura/PCG Team
| 2017-04-21 | P | P | P | Timely Filing Waiver Request Letter to CMS |  | Carlos Cuevas/Jason Chura
| 2017-05-11 | P | P | P | Timely Filing Waiver Request Letter Approval |  | Carlos Cuevas/Jason Chura
| 8/25/2017 ~10/15/17 10/19/17 | P | P | P | Reach agreement with CMS on resolution of New Adult Group issue |  | Carlos Cuevas/Jason Chura
| 2017-08-25 | 8 | 8 | 8 | Remediation Project Extension Request Letter to CMS |  | Carlos Cuevas/Jason Chura
| 9/15/2017 ~10/15/17 10/19/17 | P | P | P | Reach agreement with CMS on new deadline for final CMS-64 Reports |  | Carlos Cuevas/Jason Chura
| 2017-09-21 | P | P | P | CMS Letter Received-grants deadline extension/ time allowance for open quarters |  | Carlos Cuevas/Jason Chura
| 2017-09-22 | 8 | 8 | 8 | Timely Filing Waiver Request Letter- updated with new deadline |  | Carlos Cuevas/Jason Chura
| 12/31/2017 3/31/18 5/30/18 | P | P | P | Resume Quarterly Budget Neutrality Reports |  | Carlos Cuevas Jason Chura/PCG Team
| 2017-12-31 | P | P | P | Finalize CMS-64 for the Remediation Period through DY17 Q3 |  | Carlos Cuevas Jason Chura/FMG/PCG Team
| 2018-07-01 | 8 | 8 | 8 | Reconciled DY17 Q3, Q4 Reports due |  | Carlos Cuevas Jason Chura/PCG Team
| 12/31/2017 7/1/18 | P | P | P | Final Budget Neutrality Assessment Report to CMS |  | Carlos Cuevas/Jason Chura
| 2017-08-11 | P | P | P | Finalize Performance Audit Contractor Ad
| 2017-08-14 | P | P | P | Send to Candidate Firms
| 2017-09-08 | P | P | P | Complete Selection Process
| 2017-09-30 | P | P | P | Budget Neutrality Auditor Contracted |  | John Ulberg/Carlos Cuevas
| 2017-11-01 | P | P | P | Meeting w/ KPMG to review BN Documents |  | Carlos Cuevas/PCG Team
| 11/29/2017 1/8/18 1/31/18 | P | P | P | Meeting w/ KPMG to review Draft Audit plan. |  | KPMG/Jason Chura
| ~12/15/2017 1/15/18 2/15/18 | P | P | P | Submit Draft Audit Plan to CMS. |  | KPMG/Jason Chura
| 11/30/2017 ~12/30/2017 1/31/18 3/31/18 4/30/18 6/1/18 | P | P | P | Finalize Audit Plan with CMS. |  | KPMG/Jason Chura
| 8/22/2018 9/20/18 | P | P | P | Review Preliminary Audit Findings with KPMG |  | Jason Chura/Ann Foster
| 9/27/2018 10/5/18 | P | P | P | Present Preliminary Audit Findings to CMS |  | Jason Chura/Ann Foster
| 2018-12-31 | 8 | 8 | 8 | Address Audit Findings |  | Jason Chura/Ann Foster
| 3/31/2018 3/31/19 | 8 | 8 | 8 | Final Budget Neturality Remediation Project Performance Audit Report |  | KPMG/Jason Chura
10009 |  |  |  |  | Project Name: 1115 Demonstration Evaluation Design Division Lead: OQPS Team Lead: Ann Schettine Additional Staff: Jackey Matson, Susan Anderson, Kevin Malloy Description: To implement per STCs |  | Completed July 2018
| 2017-05-12 | P | P | P | 1115 Demontration Final Draft Evaluation Submission to CMS |  | Ann Schettine/Jackey Matson/OQPS
| 2017-06-14 | P | P | P | CMS Feedback on Draft Evaluation Received |  | Ann Schettine/Jackey Matson/OQPS
| ~7/14/17 7/13/17 | P | P | P | DOH Response to CMS Feedback |  | Ann Schettine/Jackey Matson/OQPS
| 2017-10-13 | P | P | P | Sent CMS revised version of draft evaluation. |  | Ann Schettine/Jackey Matson/OQPS
| 3/31/18 3/7/18 | P | P | P | Self-directed Pilot draft evaluation design submitted to CMS. |  | Don Zalucki/OMH
| 2018-05-03 | P | P | P | CMS Approval of Self Direction Draft Evaluation |  | Don Zalucki/OMH
| 2018-04-20 | P | P | P | NY response to CMS feedback regarding Self Direction Pilot evaluation submitted to CMS |  | Don Zalucki/OMH
| 2018-03-08 | P | P | P | Call with CMS to discuss CMS feedback |  | Ann Schettine/Jackey Matson/OQPS
| 2018-03-20 | P | P | P | Internal call to discuss next steps |  | Ann Schettine, JackeyMattson OQPS & WMU
| 2018-04-18 | P | P | P | CMS Approves 1115 evaluation timeline |  | Phil Alotta/WMU/OQPS
| 2018-05-17 | P | P | P | DOH OHIP/OQPS internal meeting to discuss procurement of Independent Evaluator |  | Ann Schettine, JackeyMattson OQPS & WMU
| 2018-06-22 | P | P | P | Submitted Draft Evaluation Design to CMS for Review & Approval |  | Ann Schettine, Jay Cooper JackeyMattson OQPS & WMU
| 8/31/2017 10/1/17 11/15/17 12/15/17 1/15/18 2/15/18 3/15/18 5/31/18 7/31/18 | P | P | P | Draft Evaluation finalized & approved by CMS |  | Ann Schettine/Jackey Matson/OQPS
10010 |  |  |  |  | Project Name: HARP Evaluation Division Lead: DPDM Team Lead: Lana Earle Additional Staff: Alyssa Altchul Description: To implement per STCs |  | Completed June 2017
| 2017-02-28 | P | P | P | HARP Evaluation Plan Pending CMS Approval |  | Lana Earle/Alyssa Altchul
| 2017-05-10 | P | P | P | HARP Evaluation Plan Approved by CMS |  | Lana Earle/Alyssa Altchul
10011 |  |  |  |  | Project Name: Managed Care Transition Division Lead: Managed Care Team Lead: Jonathon Bick Additional Staff: Hope Goldhaber Description: Examine possible MC transition options. During the demonstration period, the state will evaluate which portions of the demonstration could be transitioned to authorities other than section 1115 authority. By December 31, 2017 the state must submit to CMS an analysis and plan for transitioning demonstration programs from 1115 to Title XIX authority, such as 1915(b), 1915(c), or 1932. |  | Completed December 2017
| 12/15/2017 12/7/17 | P | P | P | Template responses to be prepared and submitted to CMS; will recommend no transition of programs from the 1115. Pending sign off. |  | Jonathan Bick
| 12/31/2017 12/20/18 | P | P | P | Medicaid Managed Care Authorities Transition Analysis submitted to CMS. |  | Jonathan Bick
| 2017-11-06 | P | P | P | Internal meeting to discuss MC Transition review. |  | Jonathan Bick
| 2017-11-29 | P | P | P | Internal meeting to discuss draft MC Transition review. |  | Jonathan Bick
10012 |  |  |  |  | Project Name: I/DD Targeted HCBS services and I/DD populations are moved under the 1115 Demonstration. Initiation of application and readiness for new Specialized Plans for I/DD Team Lead: Kate Marlay Additional Staff: Allison McCarthy Description: Develop managed care systems using risk/bearing (Specialized Plans for I/DD), Integrated Delivery Systems (IDSs), and/or Care Coordination Organization Health Homes (CCO/HHs), consistent with MRT recommendation #93?? and State statutes.
| 2017-03-23 | P | P | P | Stakeholder Meeting - Managed Care Joint Advisory Council (JAC)
| 2017-04-19 | P | P | P | Stakeholder Meeting - Developmental Disabilities Advisory Council (DDAC)
| 2017-06-28 | P | P | P | Stakeholder Meeting - Developmental Disabilities Advisory Council (DDAC)
| 2017-06-29 | P | P | P | Stakeholder Meeting - Managed Care Joint Advisory Council (JAC)
| 2017-06-01 | P | P | P | Obtain actuarial and consulting contract resources from Mercer
| 2017-06-07 | P | P | P | Tribal Notifications Sent by DOH
| 2017-06-14 | P | P | P | Public Notice to Transition HCBS services and I/DD population to 1115 Waiver
| 2017-06-15 | P | P | P | OPWDD Commissioner published managed care transition Policy Paper and led Statewide WebEx
| 2017-06-29 | P | P | P | Stakeholder Meeting - Managed Care Joint Advisory Council (JAC)
| 2017-06-30 | P | P | P | Determine preliminary eligibility criteria for I/DD MCOs
| 2017-06-30 | P | P | P | Review preliminary I/DD MCO eligibility, service and benefit data
| 2017-07-15 | P | P | P | OPWDD with DOH finalize benefit package provided by I/DD MCOs (pending federal approval)
| 2017-07-16 | P | P | P | OPWDD with DOH finalize selection of I/DD managed care models and transition phases beginning with voluntary enrollment/early innovators
| 2017-07-17 | P | P | P | DOH with OPWDD submit high level overview of necessary revisions to 1115 waiver as necessary to CMS
| 2017-07-21 | P | P | P | Publish DRAFT 1115 Waiver Amendment for I/DD Population
| 2017-08-01 | P | P | P | Public Notice on HCBS Comprehensive 1115c Waiver Amendment 02 and Notice to Tribes
| 2017-08-31 | P | P | P | Publish response to comment on Draft 1115 Waiver Amendment
| 2017-08-31 | P | P | P | Submit 1115 Waiver Amendment to CMS
| 2017-09-13 | P | P | P | Stakeholder Meeting - Developmental Disabilities Advisory Council (DDAC)
| 2017-09-14 | P | P | P | Stakeholder Meeting - Managed Care Joint Advisory Council (JAC)
| 2017-09-30 | P | P | P | Publish OPWDD Repsonse to Comment on 1915c Waiver Amendment
| 10/1/2017 8/1/18 9/1/18 | P | P | P | Draft Specialized I/DD Provider Led Plan (SIPs-PL) Qualifications document and Model Contract and shared publicly
| 10/1/2017 2/5/18 3/26/18 | P | P | P | Submission to CMS of 1915c Waiver application with transition plan
| 12/1/2017 6/30/18 9/1/18 | P | P | P | Target CMS approval of 1115 Amendment for concurrent 1915c/1115 Waivers to transition HCBS services authorize Managed Care authority for and I/DD individuals population
| 2017-12-05 | P | P | P | I/DD 1115 Waiver Transition Plan posted to web for public comment
| 2017-12-06 | P | P | P | Stakeholder Meeting - Developmental Disabilities Advisory Council (DDAC)
| 2017-12-14 | P | P | P | Stakeholder Meeting - Managed Care Joint Advisory Council (JAC)
| 1/1/18 7/1/18 | 8 | 8 | 8 | Phase 1: 1/DD Targeted HCBS services and I/DD populations are moved under the Demonstration. Initiation of application and readiness for new specialized I/DD Managed Care Plans
| 2018-02-01 | 8 | 8 | 8 | Distribute HIT standards for Specialized plans for I/DD to stakeholders for review and comment (ongoing coordination with DOH on HIT standards and RHIO implementation).
| 2018-02-01 | 8 | 8 | 8 | Distribute proposed I/DD model to stakeholders (JAC/DDAC) for review.
| 3//1/18 | 8 | 8 | 8 | Finalize Year 1 I/DD plan performance metrics.
| 5/1/2018 11/1/18 | 8 | 8 | 8 | Post to Qualify Final SIP-PL Qualification document released Specialized Plan for I/DD Managed Care Plans released on website for at least 30 days (per enacted legislation)
| 2018-07-01 | P | P | P | I/DD populations receiving HCBS will transition to health homes
| 7/1/18 8/1/18 10/1/18 | P | P | P | Presentations for interested parties (bidders, stakeholders)
| 2018-10-17 | P | P | P | Close of public comment period for Draft SIP-PL Qualification document
| 2019-02-01 | 8 | 8 | 8 | Deadline for submission of SIP-PL Applications
| 2018-07-01 | 8 | 8 | 8 | Pilot test interRAI assessment process (CAS?)
| 2019-02-01 | 8 | 8 | 8 | DOH with OPWDD propose rates to CMS
| 2019-03-01 | 8 | 8 | 8 | First date for selecting "early adopter" SIPs-PL I/DD MCOs
| 2019-03-01 | 8 | 8 | 8 | Distribute Readiness Review Information Request
| 2019-04-01 | 8 | 8 | 8 | Finalize Model contract requirements for DOH review
| 2019-04-01 | 8 | 8 | 8 | Desk review of SIP-PL readiness information
| 2019-05-01 | 8 | 8 | 8 | Onsite Readiness Review for I/DD MCOs Begin
| 7/1/2019 8/1/19 | 8 | 8 | 8 | Begin voluntary passive enrollment of SIPs-PL downstate I/DD MCOs
| 2019-07-01 | 8 | 8 | 8 | Phase 2: Downstate - Voluntary Enrollment
| 2020-07-01 | 8 | 8 | 8 | Phase 2: Rest of State Voluntary Enrollment
| 2021-07-01 | 8 | 8 | 8 | Phase 3: Downstate – Mandatory Enrollment
| 2022-07-01 | 8 | 8 | 8 | Phase 3: Rest of State – Mandatory Enrollment
[5 empty] | Project Name: I/DD populations receiving HCBS will transition to I/DD health homes Division Lead: Office for People with Developmental Disabilities Team Lead: Kate Marlay Additional Staff: Allison McCarthy Description: Develop a Care coordination model for the I/DD Population | $0 | Completed - September 2018
| 2016-10-01 | P | P | P | Draft I/DD HH design recommendations and plan
| 2016-11-01 | P | P | P | Workgroups completes review of draft plan
| 2017-01-01 | P | P | P | Workgroups meet to finalize document
| ?? | P | P | P | Meet with Stakeholder Groups (JAC) to discuss design recommendations and obtain feedback
| 2017-02-01 | P | P | P | Initiate work with Mercer to develop provider network data summaries
| 2017-03-23 | P | P | P | Stakeholder Meeting - Managed Care Joint Advisory Council (JAC)
| 2017-04-01 | P | P | P | Begin meeting with stakeholder groups (JAC/DDAC) and present plan for feedback
| 2017-04-19 | P | P | P | Stakeholder Meeting - Developmental Disabilities Advisory Council (DDAC)
| 2017-05-01 | P | P | P | Finalize model and implement work plan
| 2017-06-01 | P | P | P | Finalize year 1 performance metrics specific to I/DD HH
| 2017-06-14 | P | P | P | Begin Tribal Notification and Public Notice to Transition I/DD HCBS population to I/DD Health Homes
| 2017-06-15 | P | P | P | Draft 1115 waiver for internal review
| 2017-06-28 | P | P | P | Stakeholder Meeting - Developmental Disabilities Advisory Council (DDAC)
| 2017-06-29 | P | P | P | Stakeholder Meeting - Managed Care Joint Advisory Council (JAC)
| 2017-06-30 | P | P | P | Draft I/DD Health Home Application Released for public comment
| 2017-07-12 | P | P | P | Stakeholder input meeting
| 2017-07-21 | P | P | P | SAMHSA Consult
| 2017-08-01 | 8 | 8 | 8 | Develop draft Start-up grant application for release with application publication in fall 2017
| 2017-08-11 | P | P | P | Due Date to Submit Comments on Draft Health Home Application to Serve Individuals with I/DD
| 2017-08-04 | P | P | P | Due Date to Submit Letter of Interest
| 2017-08-15 | P | P | P | Reignite VBP Work Group focus on I/DD measures
| 2017-12-08 | P | P | P | Submit DRAFT HH SPA to add I/DD diagnoses to CMS
| 2017-09-13 | P | P | P | Stakeholder Meeting - Developmental Disabilities Advisory Council (DDAC)
| 2017-09-14 | P | P | P | Stakeholder Meeting - Managed Care Joint Advisory Council (JAC)
| 2017-10-06 | P | P | P | Final Health Home Application to Serve Individuals with I/DD Released, Start-Up Grant Application Released
| 2017-10-06 | P | P | P | Response to Public Comment on Draft CCO/HH Application
| 2017-11-30 | P | P | P | Due Date to Submit Health Home Application to Serve Individuals with I/DD
| 2017-12-01 | P | P | P | Review and Approval of Health Home Applications to Serve Individuals with I/DD by the State, Award of Start-Up Grants
| 2017-12-06 | P | P | P | Stakeholder Meeting - Developmental Disabilities Advisory Council (DDAC)
| 2017-12-14 | P | P | P | Stakeholder Meeting - Managed Care Joint Advisory Council (JAC)
| 2018-01-16 | P | P | P | CMS sent IDD HH Formal RAI to State
| 1/22/2018 1/25/18 | P | P | P | Response to CMS RAI and update SPA for Portal Submission
| 2/27/2018 3/26/18 | P | P | P | Submission of HH SPA to CMS MacPro Portal
| 2/28/2018 1/12/18 | P | P | P | Initial Designation of IDD HHs
| 4/1/2018 5/31/18 | P | P | P | Health Home and Network Partner Readiness Activities
| 2018-04-15 | P | P | P | HH Informational Letter sent to Individuals
| 4/30/2018 4/9/18 | P | P | P | CMS approval of IDD HH SPA
| 2018-06-01 | P | P | P | Final Designation of IDD HHs
| 2018-07-01 | P | P | P | State Webinars, Training, and Other Readiness Activities
| 2018-07-01 | P | P | P | IDD HH Enrollment begins

## Ph. 7 Eligibility & Market Int
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2017-2018 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
10101 |  |  |  |  | Project Name: Require Medicare Coverage as a Condition of Medicaid Eligibility Division Lead: DEMI Team Lead: William Emery Additional Staff: Lisa Zulauf, Rich Brown, Cindy Krueger-Farley, Mary K. Houlihan , Emily Steinbach; Judy Arnold Description: Require Medicare coverage as a condition of Medicaid eligibility for those eligible. This proposal would require Medicare coverage as a condition of Medicaid eligibility for those eligible. The Department will notify the 60,000 Medicare eligible enrollees on Medicaid that they should obtain Medicare coverage. | -16.6 | Effective Date: 1/1/18
1. End Stage Renal Disease (ESRD)
| 2017-04-07 | P | P | P | A. Enhance DOH website with ESRD and Medicare information
| 2016-07-11 | P | P | P | B. Submit emedny EP request. Identify individuals receiving ESRD services, create based on claims data.
| 2017-05-01 | P | P | P | 1. Finalize an informational letter for ESRD patients
| 2017-05-01 | P | P | P | 2. Finalize new language for existing Medicare Warning letter
| 2017-12-27 | P | P | P | 3. emedny will mail ESRD letters
| 11/1/2017 12/27/17 | P | P | P | a. Back-log
| 12/1/2017 1/27/17 | P | P | P | b. Monthly on-going
| 2017-07-26 | P | P | P | 4. Submit Evolution Project to create Mobius report of ESRD patients for vendor to conduct outreach
| 10/1/2017 12/22/17 | P | P | P | 5. Projected implementation date, EP 2125
2. Finalize Policy Decisions
| 2017-04-06 | P | P | P | A. Submit WMS System Change Request form
1. Individuals over age 65 (Back-log)
| 11/1/2017 12/15/17 12/16/17 1/10/18 | P | P | P | a. Send notices of Medicare requirement (NYC saggered)
| 2017-11-15 | P | P | P | b. Send notices of Medicare reuirement (Upstate)
2. Individuals turning age 65: (Undercare) Develop processes to identify those turning age 65, notify them of Medicare requirement, close for failure to comply
| 11/1/2015 12/15/17 12/16/17 | P | P | P | B. Downstate WMS: Utilize current milestone renewal (at age 65) to communicate the Medicare requirement. Close for failure to comply
| 2017-11-15 | P | P | P | C. Upstate WMS: Identify people at age 65+ 3 months to recieve a notice of the Medicare requirement (This is not done at renewal. It uses the back-log letter). Close for failure to comply.
D. Medicaid Applications
| 2017-09-08 | P | P | P | 1. Draft changes to the DOH 4220.
| 408494 | 8 | 8 | 8 | 2. PAG Approval
| 6/30/18 10/22/18 2/18/19 | 8 | 8 | 8 | 3. Promote changes to 4220
| 2017-09-08 | P | P | P | 4. Draft changes to the Comm Medicaid application LDSS 2921.
| 408494 | 8 | 8 | 8 | 5. OTDA approval
| 2017-11-01 | P | P | P | 6. Promote changes to 2921 Supplement
E. Administrative Directive
| 2017-10-01 | P | P | P | 1. Submit draft ADM for clearance
| 2017-10-24 | P | P | P | 2. Issue ADM
F. Customer Service
| 2017-10-01 | P | P | P | 1. Draft a Q&A
| 2017-11-03 | P | P | P | 2. Issue Q&A
3. New York State of Health (NYSOH):
| 2017-05-19 | P | P | P | 1. Submit System Change Request to identify who is required to meet the Medicare requirement based on age, case type, citizenship code, coverage code (CR 1710)
| 9/1/2017 2/1/2018 | P | P | P | 2. Scope document drafted
| 4/30/2018 5/31/18 8/31/18 10/12/18 | 8 | 8 | 8 | 3. Finalize TSD and RSD
| 10/31/18 1/1/19 2/6/19 | 8 | 8 | 8 | 2. Project Implementation date
4. eMedNY: Develop an automated process to accrete to Buy-in during post eligibility
| 2017-05-19 | P | P | P | 1. Submit EP request to accept from WMS a file of individuals, corresponding MSP codes, and Buy-in begin dates for eMedNY to accrete to Buy-in
| 3/31/2018 1/1/19 | 8 | 8 | 8 | 2. Project Implementation date
5. Outreach
| 1/1/2018 2/1/18 3/1/2018 6/1/18 8/1/18 | 8 | 8 | 8 | A. Facilitated Enrollment of Medicare

## Ph. 7 Finance & Rate Setting
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2017-2018 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
10201 |  |  |  |  | Project Name: A/R Payment Medicaid Accounts Receivable Division Lead: DFRS Team Lead: Adele Compton Additional Staff: John Ulberg, Michael Ogborn, Donna Cater, Laura VanValkenburg Description: This proposal relates to the bank financing of collectible accounts receivable balances. Reduce Outstanding Medicaid Accounts Receivable Balances | -10.07 | Effective Date: 4/1/17
Part A |  |  |  |  | Project Name: Reduce Accounts Receivable Balances - Part A Description: Implement an aggressive recovery program to reclaim Collectible Accounts Receivable liabilities from providers by December 2018 | $250M
Top 30 PROVIDERS - 50M
| 2017-06-01 | P | P | P | Identified Top 30 Providers with highest A/R balance - that will not full pay liabilities by December 2018 at the current rate of recoupment
| 2017-07-01 | P | P | P | Refresh bucket list with current A/R liabilities and balances
| 8/1/17 10/1/17 12/01/17 | P | P | P | Negotiate repayment agreements - set up conference calls. Of the Top 30, 13 agreements have been established, negotiations with remaining 7 4 to establish repayment agreements
| 2017-08-01 | P | P | P | Identify additional 13 providers to be included in Top 30. Request conference calls and begin negotiations.
Collectible A/R Accounts - Not included in Top 30 - 30M
| 2017-08-01 | P | P | P | Send letter to providers in following buckets - Paying - Will result in full paid by 12/18 if recoupment is increased, AND Paying - Will not result in full payment if recoupment is increased.
| 2017-09-01 | P | P | P | Respond to letters, negotiate repayment agreements.
Uncollectible A/R Accounts - Not submitting claims to Medicaid/No repayment 20M
| 2017-08-01 | P | P | P | Send letter to providers who are not repaying through recoupment. Status unknown Due to volume - split and mail letters weekly
| 2017-09-01 | P | P | P | 700 letters mailed 8/17 - Total due 10M - Respond to letters, negotiate repayment agreements. | 1.5M
| 2017-11-20 | P | P | P | 450 letters mailed 11/15/17 - 4.6M Respond to letters, negotiate repayment agreements.
| 2017-12-20 | P | P | P | 82 responses rcvd from Nov 17 letter. 48 cases resolved - total 900K | 900K
| 2018-02-01 | P | P | P | Collection letters will be mailed by 2/1/18 on balances > 1k not resulting in payment thru recoupment
| 2018-03-23 | P | P | P | 901 letters mailed 1/22/18 = $ 9M due, Received 264 responses, and collected $300K | 300K
| 2018-04-03 | P | P | P | 850 letters mailed on 4/03/18 = 37M due. 134 Responses rcvd as of 4-18-18, 13.2M payment in process | 13.2M
Include Medicaid A/R in DTF SWOP program
| 2017-07-01 | P | P | P | Identify contact person within DTF to enable Medicaid A/R balances to be included in the Statewide Offset Program (SWOP) which provides for offset of all $ generated from DTF
| 2017-07-01 | P | P | P | Obtained DOH contact person from DTF, request conference call to discuss steps needed to submit liabilities to DTF
| 8/1/17 9/15/17 10/15/17 12/01/17 2/01/18 5/01/18 7/15/18 8/15/18 9/15/18 12/01/18 | 8 | 8 | 8 | Submit liabilities to DTF SWOP Program Meeting scheduled to discuss with DLA - Update inquiry on process sent to DLA waiting for response. 11/22 Update - email sent to DLA, setting up conference call for next steps. Update 1-22-18 will request meeting with DLA to discuss process. Update 4/8/18 - Em sent to Michael Bass DLA requesting information. Update 5/16/18 - Conference call with DLA and ITS scheduled for 5/25/18.
| 7/01/18 8/15/18 | P | P | P | Meeting Held with DLA 6-15-18. Follow up with WIC program this week to discuss process used previously.
| 9/1/2018 11/01/18 | 8 | 8 | 8 | contact WIC program for direction
Part B |  |  |  |  | Project Name: Reduce Accounts Receivable Balances (Part B) Description: Implement a process to resolve Uncollectible Accounts Receivable liabilities - Providers that are not submitting Medicaid claims | 200M
[5 empty] | Obtain refund of Fed Share on Uncollectible A/R accounts in following 3 buckets: Closed Providers, Bankruptcy, Sold - New operator not responsible. 150M gross 40M Fed Share | 40M
| 2017-04-01 | P | P | P | Otain CMS approval to accept affidavits signed by DLA
| 2017-05-01 | P | P | P | Meet with DLA to discuss format of Matrix which summarizes providers liabilities and documentation obtained to substantiate uncollectible status
| 2017-06-20 | P | P | P | Prepare draft of affidavit for DLA
| 2017-07-04 | P | P | P | DLA will provide Sample of Affidavit that will be used in submission to CMS.
| 7/10/2017 9/01/17 | P | P | P | Submit example of 2 uncollectible A/R accounts to CMS with Matrix and Affidavit.
| 7/15/2017 8/15/17 9/15/17 10/15/17 | P | P | P | Submit uncollectible account(s) with Matrix & documentation to DLA and CMS for review. Samples of Matrix and 2 Uncollectible accounts sent to CMS - follow up conference call will be set up in next 2 wks to discuss any issues or questions.
| 8/1/2017 9/1/17 11/01/17 12/01/17 1/15/18 2/15/18 | P | P | P | Obtain signed Affidavit from DLA, and submit request to CMS for refund of Fed Share 40M. Update: 11/22 - Conference call held with CMS to discuss sample of 2 uncollectible A/R accounts and Affidavits, updating list of liabilities to be sent to CMS by 1/10/18. Conference call to discuss will follow. Update: 3/23/18 - list of uncollectible liabilities submitted to CMS, with Affidavits signed by J. Ulberg & D. Cater. Total Fed Share refund requested is $ 37M. Waiting for Affidavit from DLA, following up this week.
| 4/15/2018 7/01/18 | P | P | P | CMS requested NYS Policy on uncollectible A/R - Responded with Em containing D.O.B. policy on 4/15/18. Requested next steps and follow up conference call. Update 5/16/18 Additional documentation requested from CMS 5-14-18, Request forwarded to MFCU. Will submit to CMS upon receipt. Update 6/22/18: Meeting scheduled with MFCU 6-26-18.
| 12/1/2017 2/01/18 3/01/18 5/01/18 6/01/18 7/15/18 8/15/18 10/01/18 2/01/19 | 8 | 8 | 8 | Obtain refund of Fed Share - 40M 37M
| 10/1/2017 1/01/18 | 8 | 8 | 8 | Work with MFM to write off remaining balance of liabilities (state share) and additonal liabilities without Fed Share on the accounts. 110M
| 8/1/18 9/15/18 1/01/19 | 8 | 8 | 8 | Prepare 2nd list of uncollectible liabilities to be submitted to CMS for refund of Fed Share. On hold pending discussions and decision on 1st submission | 10M
Submit Referral to AG against providers in business without Medicaid claims to recoup
| 2018-08-15 | P | P | P | Submit 100 providers (300K due total) from the - Uncollectible - Open No Claims bucket to DLA for Referral to AG - sent 8/12/18 | 300K
| 2018-09-01 | P | P | P | Meeting scheduled 8/31/18 with DLA & Liz Misa to discuss eMedNY notification process to providers when new liabilities resulting from change in Medicaid program occur, and dunning letters
| 2018-10-01 | P | P | P | Discussions with DLA/DOS/CSRA to issue - automated 1 time notification to providers with uncollectible A/R liabiltiies within statute & develop automated letters for all new liabilities when issued including follow up 30,90 day letters.
| 2019-01-01 | 8 | 8 | 8 | Develop evolution request to enhance eMedNY remittance advice to include additional details of outstanding A/R & remittance instructions.
Develop protocol to write off uncollectible A/R accounts
| 2017-07-15 | P | P | P | Submit request to CMS MFM to write off balances < $25.00 > 2 years old - No Medicaid claim or payment within the past 2 years. (3,500 liabilities totaling 21K)
| 8/1/17 9/1/17 11/01/17 | P | P | P | Meet with DLA/Andy Ruby/MFM to discuss revision of protocol that would allow for write off of uncollectible A/R accounts < $ 25.00 - created prior to conversion to eMedNY in March 2005 - Meeting scheduled for October 13
| 2017-11-01 | P | P | P | Meeting with DLA scheduled for 10/13 - discuss writing off liabilities < $25.00 over 2 yrs no claim/ statute of limitations/ notices to providers on negative balances 11/22 Update: Unable to obtain consensus from DLA and FMG to remove uncollectible A/R balances from eMedNY - resolution decision is to "flag" uncollectible A/R balances on eMedNY. Evolution request needs to be submitted to Div of Systems to request change to eMedNY to add flag.
| 2018-10-01 | P | P | P | Re-opened discussions with MFM to write off uncollectible liabilities < 25.00. Initial meeting held, MFM will clarify policy with DOB, follow up meeting scheduled for 2 weeks.
Establish process to submit claim to OSC for unclaimed funds
| 7/1/17 8/1/17 9/1/17 10/15/17 12/01/17 1/15/18 2/01/18 5/01/18 7/01/18 8/01/18 10/01/18 12/01/18 | 8 | 8 | 8 | Obtain contact person at OSC from DLA Meeting scheduled for week of 8/28 - Inquiry sent to DLA, waiting for response UPDATE 11/22/17 - Em sent to DLA requesting conference call to discuss next steps and process. Update 12/20/17 - Will follow up with DLA, Update: 4/18/18 Em sent to Michael Bass DLA to discuss process. Update 5/16/18 Michael pointed us to Susan Cartier, will request conference call to discuss. Update: 6-22-18 Meeting scheduled with DLA 7/2/18. 9-01-18. F/u 10/15/18 - Unable to obtain contact person at OSC. Will inquire with AG.
| 7/15/2017 8/10/17 9/15/17 11/01/17 12/15/17 1/15/18 2/15/18 5/01/18 6/01/18 7/15/18 8/15/18 9/15/18 12/01/18 | 8 | 8 | 8 | Set up confernce call with OSC to determine steps necessary to submit claims.
| 8/15/17 10/01/17 11/15/17 01/01/18 2/01/18 3/01/18 6/01/18 7/15/18 8/15/18 9/15/18 12/15/18 | 8 | 8 | 8 | Identify funds available, and submit claim to OSC.
Uncollectible A/R - Open No Claims - determine course of action against providers who are open - not submitting Medicaid claims
| 7/15/2017 8/15/17 9/15/17 11/01/17 | P | P | P | Determine if providers are in Managed Care plans. Develop plan for those that are. Meeting held with M Ogborn, list sent for review.
| 7/15/2017 8/15/17 9/15/17 11/01/17 | P | P | P | Discuss Referral to AG - for out of state providers and those not in managed care plan
Part C |  |  |  |  | Project Name: Reduce Accounts Receivable Balances (Part C) Description: Obtain financing from outside source on Collectible A/R Accounts | 250M 100M
| 2017-03-31 | P | P | P | Include legislation in budget to allow sale of Medicaid A/R
| 2017-04-01 | P | P | P | Meet with PRAG to develop RFQ, provide PRAG with porfolio of A/R accounts, current balances and payment terms
| 2017-05-01 | P | P | P | Meet with DOB to discuss RFQ and proposal
| 2017-06-05 | P | P | P | Prepare overview of transaction for DOB, answer all questions/concerns
| 6/10/2017 9/1/17 12/01/17 | 8 | 8 | 8 | Go out with RFQ to financial institutions |  | On Hold
| 6/20/2017 9/1/17 2/01/18 | 8 | 8 | 8 | Review quotes, Negotiate terms, finalize sale |  | On Hold
| 7/1/17 10/1/17 3/01/18 | 8 | 8 | 8 | Obtain funds from purchaser |  | On Hold
| 7/15/2017 11/1/17 4/01/18 | 8 | 8 | 8 | Work with MFM on mechanics to identify liabilities included in sale on eMedNY, establish lockbox, develop tracking system. |  | On Hold
| 2017-12-15 | P | P | P | Discussed effort to obtain financing of A/R with Deloitte 11/15/17. Follow up meeting set up for 12/10 to discuss financing/collection options . Update 12/20/17 - Lists of collectible liabilities were sent to Deloitte for review. Follow up meeting will be scheduled to discuss options by 1/10/18. |  | On Hold
| 2018-01-15 | P | P | P | Follow up meeting held with Deloitte 1/15/18. Preparing power point presentation to Division of plan of action & including development of tool box of collection activities to implement. |  | On Hold
10202 |  |  |  |  | Project Name: Separate Rate Cells for Specific Populations High Cost/ High Needs Populations in Managed Care Division Lead: DFRS Team Lead: Reneta Robinson Additional Staff: Description: The Executive commits to exploring separate rate cells or risk adjustments for the nursing home, high cost / high need home and personal care, and Health and Recovery Plan (HARP) populations. The Department will re-engage the Centers for Medicare and Medicaid Services (CMS) regarding this reimbursement methodology with the assistance of health care industry stakeholders impacted by these changes (e.g. advocates, providers and managed care organizations). Create separate rate-cells vs risk-adjusting high cost enrollees | 0 | Effective Date: 4/1/17
| 2017-05-17 | P | P | P | Gather background information; Obtain side letter for more information on the initiative
| 2017-05-24 | P | P | P | Determine the specifics that didn't go over well with on the initial presentation to CMS |  | CMS preferred more in depth data by (diagnosis codes) to determine the necessity and benefit of separate rate cells
| 2017-05-31 | P | P | P | Narrow down specific Managed Care Programs/products implicated in the initiative, i.e. MLTC-P, FIDA, PACE, MA, MAP, HARP etc. |  | NHTD/TBI (Oct 2018) and ALP populations are slated for inclusion.
| 2017-06-22 | P | P | P | Draft separate rate cell 1-pager/fact sheet that will be shared with Mercer, CMS, the Legislature, and the public
| 2017-07-14 | P | P | P | Research the methodology and benefit package for each program/product that is implicated in the phase 7 initiative
| 2017-07-21 | P | P | P | Create a chart for existing rate cell populations for each program/product implicated
| 2017-08-15 | P | P | P | Reach out to ITS for evolution requests for new rate codes
| 2017-09-01 | P | P | P | Meet with Provider/Plan community for a discussion on their high cost/high needs enrollees | Are there high cost groups that should be additionally considered?
| 2017-10-01 | P | P | P | Explore which criteria will be used to identify the high cost/high need populations: The High Cost/High Needs Populations under consideration for separate rate cells include: 1) Nursing Home residents in MLTC; 2) HARP- eligible members in MMC; and 3) other high risk populations in MLTC (Ventilator patients, 12-24 hour live-in home care patients, Alzheimer's/Dementia patients). Further discussions for consideration on separate rate cells for the NHTD/TBI Waiver, and ALP populations that will enter Managed Care in the future.
| 2017-10-15 | P | P | P | Enlist our consulting Actuaries (Mercer) (Deloitte) to run statistical summaries and associated costs of populations in identified cross sections.
| 2017-11-17 | P | P | P | Meet with Consumer Advocate groups for their feedback on exploring separate rate cells for various High Cost/High Needs Populations
The course for exploring separate rate cells vs risk-adjustments for each of the three sub-populations has taken different directions. The process and workplan for each will therefore be listed separately:
High Cost High Need Rate Cell
| 2018-02-23 | P | P | P | Solicit a 1-pager proposal from plan associations on a structure or approach to creating a separate HCHN rate cell that will meet Actuarially sound criteria
| 2018-02-28 | P | P | P | Send HCHN data request (survey) out to sample plan(s) to ensure validity of the data requested
| 2018-03-09 | P | P | P | Receive proposal from plan associations
| 2018-04-24 | P | P | P | Meeting with CMS to discuss status prior to moving forward.
| 12/29/2017 4/1/18 4/24/18 | P | P | P | Come to a consensus on the criteria to be used to identify HCHN members, and either risk adjust the high cost/high needs sub-population OR create a separate rate cell
| 4/2/2018 6/1/18 | P | P | P | Disseminate HCHN survey to all MLTC plans
| 4/5/2018 6/4/18 | P | P | P | Webinar with plans and plan associations regarding the HCHN survey
| 4/20/18 6/15/18 7/6/18 | P | P | P | Receive completed surveys from plans
| 10/15/2017 11/17/17 12/22/17 3/1/18 6/22/18 7/31/18 10/31/18 | 8 | 8 | 8 | High Cost High Need feasibility analysis with calculation support | To determine if further rate cell detail is indicated
| 8/1/2018 9/17/18 10/31/18 | 8 | 8 | 8 | Form a collaborative workgroup in conjunction with Providers/Provider Asoociations/Actuarial Consultants to propose the best risk-adjustment model for the MLTC HCHN sub-population.
| 10/15/2017 11/17/17 12/22/17 3/1/18 6/22/18 7/31/18 10/31/18 11/30/18 | 8 | 8 | 8 | High Cost High Need feasibility analysis with calculation support | To determine if further rate cell detail is indicated
| 3/15/18 4/6/18 12/31/18 | 8 | 8 | 8 | Review the feasibility of the proposal with Actuarial Consultants
| 1/19/2018 7/13/18 1/4/19 | 8 | 8 | 8 | Share justification/methods document with CMS/ Update 1-pager previously shared with CMS
| 2/23/2018 8/13/18 1/25/19 | 8 | 8 | 8 | Manage the negotiation process with CMS, i.e. follow up information, documents etc.
| 3/16/2018 2/8/19 | 8 | 8 | 8 | Gain CMS approval for separate rate cells, if that is the chosen direction risk-adjustment model
| 2018-03-16 | 8 | 8 | 8 | Finalize "Change for Request" process to create new rate codes for the new rate cells if needed.
| 3/23/2018 2/22/19 | 8 | 8 | 8 | Send rates to DOB for approval
| 4/1/2018 4/1/19 | 8 | 8 | 8 | Enter new rates in to EMedNY
Nursing Home Rate Cell
| 2017-11-22 | P | P | P | Industry study on separate rate cells - What has worked for other states
| 2018-02-28 | P | P | P | Send NH data request (survey) out to sample plan(s) to ensure validity of the data requested
| 2018-04-24 | P | P | P | Meeting with CMS to discuss status prior to moving forward.
| 2018-04-24 | P | P | P | After the discussion with CMS, and based on budget initiatives established in the FY 18/19 enacted budget, we reached a concensus that it will not be feasible to establish separate rate cells for the MLTC Nursing Home sub-population.
| 2018-04-02 | 8 | 8 | 8 | Disseminate NH survey to all MLTC plans
| 2018-04-06 | 8 | 8 | 8 | Webinar with plans and plan associations regarding the NH survey
| 2018-04-20 | 8 | 8 | 8 | Receive completed surveys from plans
| 10/15/2017 11/17/17 12/22/17 3/1/18 6/22/18 | 8 | 8 | 8 | Nursing Home feasibility analysis with calculation support | To determine if further rate cell detail is indicated
| 2018-07-06 | 8 | 8 | 8 | Come to a consensus to either risk adjust for members in the NH sub-population OR create a separate rate cell with the inclusion of community integration incentives
| 1/19/2018 7/13/18 | 8 | 8 | 8 | Share justification/methods document with CMS/ Update 1-pager previously shared with CMS
| 2/23/2018 8/13/18 | 8 | 8 | 8 | Manage the negotiation process with CMS, i.e. follow up information, documents etc.
| 3/16/2018 TBD | 8 | 8 | 8 | Gain CMS approval for separate rate cells, if that is the chosen direction
| 3/16/2018 TBD | 8 | 8 | 8 | Finalize "Change for Request" process to create new rate codes for the new rate cells.
| 3/23/2018 TBD | 8 | 8 | 8 | Send rates to DOB for approval
| 4/1/2018 TBD | 8 | 8 | 8 | Enter new rates in to EMedNY
HARP-Eligible Rate Cell
| 2018-04-24 | P | P | P | Meeting with CMS to discuss status prior to moving forward.
| 2018-05-30 | P | P | P | Implement systems fix project that will include HARP on the NY State of Health panel of options during the Medicaid re-certification process. This could ultimately eliminate the need for a separate HARP- eligible rate cell in Medicaid Managed Care.
| 2018-06-01 | P | P | P | DOH will send letters to pre-determined HARP- eligible members who are currently enrolled in Medicaid Managed Care notifying them of passive enrollment into HARP and the qualifying time-frame to opt-out if HARP is not their desired program.
| 7/1/2018 8/1/18 | P | P | P | Passive enrollment for masses of HARP- eligible members in to HARP will commence.
| 2018-10-01 | 8 | 8 | 8 | Actuaries will conduct an analysis of residual members remaining in Mainstream Managed Care and impact on rates.
| 2018-10-30 | 8 | 8 | 8 | The final result of the systems fix project will determine if a separate HARP- eligible rate is still indicated.
| 2018-10-30 | 8 | 8 | 8 | If the NYSOH systems fix is unsuccessful, a separate rate cell for HARP- eligible members will continue to be explored.
10203 |  |  |  |  | Project Name: Quarterly Meetings with Legislature on Medicaid Managed Care Rates Division Lead: DFRS Team Lead: Connor Gemerek Additional Staff: Torrey Duchessi, John Ulberg Description: The Executive commits to providing quarterly updates to the Legislature regarding Medicaid Managed Care rates. In the spirit of transparency, the Department, in conjunction with the Division of the Budget (DOB), will hold quarterly meetings with the chairpersons of the Senate and Assembly Health Committees, the Senate Finance Committee and the Assembly Ways and Means Committee. Staff from the offices of the chairpersons are welcome to participate in these monthly meetings in lieu of the elected official. The Department will also provide the actuarial memorandum which, pursuant to statute, is provided to managed care organizations 30 days in advance of submission to CMS. This document contains information regarding components of the premium (e.g. base amounts, trend percentages, category of service splits, etc.), add-on adjustments, quality pool amounts and various other Medicaid Managed Care rate development information. Finally, the Department will continue to provide the Legislature with all presentation materials disseminated at monthly managed care plan meetings. |  | Completed - January 2018
| 2017-05-17 | P | P | P | May Meeting with Legislature.
| 8/1/2017 9/30/2017 10/30/2017 11/30/2017 1/29/2017 | 8 | 8 | 8 | August Meeting with Legislature.
10204 |  |  |  |  | Project Name: Monthly Meetings with Legislature on the Medicaid Global Cap Division Lead: DFRS Team Lead: Mark Shutts Additional Staff: John Ulberg Description: The Executive commits to monthly meetings with the Legislature during the third Wednesday of every month to provide an update on actual spending to-date and potential changes to projections for the remainder of the State Fiscal Year (May 17, June 21, July 19, August 16, September 20, October 18, November15, December 20, January 17, February 21 and March 21). The agenda for such meetings shall be agreed upon by the Department and the Legislature. In addition, the Global Cap report will be expanded to include information on all non-Medicaid expenditures made out of Global Cap resources or any material changes on the program in the last month. |  | Completed - January 2018
| 2017-04-19 | P | P | P | FY 2017 GC Closeout
| 2017-05-17 | P | P | P | April 2017 Results
| 6/27/17 7/14/17 | P | P | P | May 2017 Results / FY 2018 Model
| 2017-07-19 | P | P | P | June 2017 Results Overview and Status of VAPAP/VBP-QIP Recipients and other Providers at Risk
| 2017-08-16 | P | P | P | June and July 2017 Results / FY 2018 Model
| 2017-09-20 | P | P | P | July and August 2017 Results
| 2017-10-18 | P | P | P | September 2017 Results August 2017 Results
| 2017-11-15 | P | P | P | October 2017 Results / FY 2018 Model September 2017 Results
| 2017-12-20 | 8 | 8 | 8 | November 2017 Results October 2017 Results
| 2017-01-24 | 8 | 8 | 8 | December 2017 Results / FY 2018 Model / Executive Budget Briefing (DOB) November 2017 Results / FY 2018 Model
| 2017-02-21 | 8 | 8 | 8 | January 2018 Results December 2017 Results / FY 2018 Model / Executive Budget Briefing (DOB)
| 2017-03-21 | 8 | 8 | 8 | January and February 2018 Results
10205 |  |  |  |  | Project Name: Wage Parity for CDPAP Assistants Division Lead: DFRS Team Lead: Laura Grassman Additional Staff: John Ulberg, Dan Carmody Description: Implement wage parity for CDPAP workers and verify inclusion in managed care rates | 9 | Effective Date: 7/1/2017 Completed December 2017
| 2017-06-14 | P | P | P | Send Program Guidance to FI's and Plans
| 2017-06-21 | P | P | P | Send further Guidance on the new 10/13/17 effective date
| 2017-06-22 | P | P | P | Minimum Wage related webinar to be held
| 6/30/17 7/30/17 | P | P | P | Discuss documenting additional funding already in rates for Plans-if needed
| 7/15/17 8/15/17 | P | P | P | Develop documentation for Plans if needed
| 2017-08-01 | P | P | P | Contract reivew surveys to plans
| 2017-09-01 | P | P | P | Contract reivew surveys to plans
| 2017-10-01 | P | P | P | Contract reivew surveys to plans
| 8/31/17 10/13/17 | P | P | P | Follow up on any questions received
10206 |  |  |  |  | Project Name: Reduce Hospital Quality Pool Division Lead: DFRS Team Lead: Monique Grimm Additional Staff: John Ulberg, Janet Baggetta Description: This proposal would reduce the funding associated with the Hospital Quality Pool. | -15 | Effective Date: 4/1/2017 Completed - September 2017
| 2017-06-30 | P | P | P | Reduce year 3 (2017-18) Hospital Quality Pool distribution by $30M Gross
| 2017-08-07 | P | P | P | Finalize reduced year 3 distribution using updated reporting compliance metrics
| 2017-08-07 | P | P | P | Update inpatient rates for Medicaid Managed Care effective 4/1/2017
| 2017-08-03 | P | P | P | Draft Provider/Health Plan Communications (Letters)
| 2017-08-07 | P | P | P | Release rates/communication to Hospitals
| 2017-08-09 | P | P | P | Release rates/communication to Health Plans
10207 |  |  |  |  | Project Name: Enhanced Safety Net Hospital Program Division Lead: DFRS Team Lead: Monique Grimm Additional Staff: John Ulberg, Janet Baggetta Description: This proposal provides funding to Safety Net providers meeting certain criteria. | 10 | Effective Date: 4/1/17
| 2017-05-26 | P | P | P | Create draft model for determining qualifying hospitals for Enhanced Safety Net Program
| 2017-07-26 | P | P | P | Create draft model for allocating funds to qualifying hospitals
| 2017-08-25 | P | P | P | Review draft models with hospital associations
| 9/8/17 9/29/17 | P | P | P | Finalize model for determining qualifying hospitals for Enhance Safety Net Program
| 9/15/17 10/13/17 11/14/17 12/20/17 2/28/18 3/30/18 | P | P | P | Finalize model for allocating funds to qualifying hospitals
| 9/19/17 10/17/17 11/17/17 12/22/17 3/2/18 4/2/18 | 8 | 8 | 8 | Finalize inpatient rates for Medicaid Managed Care effective 10/1/2017 1/1/2018 4/1/2018 (Hospital Rate Sheet & MC Publication/Fee Schedule)
| 5/31/18 8/31/18 10/31/18 12/31/18 | 8 | 8 | 8 | Division of the Budget Approval
| 11/30/18 1/30/19 | 8 | 8 | 8 | Centers for Medicare and Medicaid Approval for Lump Sum Payments
| 9/22/17 10/20/17 11/20/17 12/28/17 3/8/18 4/6/18 6/15/18 9/7/18 12/7/18 2/7/19 | 8 | 8 | 8 | Web development & Provider/Health Plan Communications (Letters) developed for review & approval
| 9/29/17 10/27/17 11/27/17 1/5/18 3/13/18 4/13/18 6/22/18 9/14/18 12/14/18 2/14/19 | 8 | 8 | 8 | Release rates/Communication to Hospitals
| 9/29/17 10/27/17 11/27/17 1/5/18 3/13/18 4/13/18 6/22/18 9/14/18 12/14/18 2/14/19 | 8 | 8 | 8 | Release rates/Communication to Health Plans/Payment Distribution
10208 |  |  |  |  | Project Name: Critical Access Hospitals Division Lead: DFRS Team Lead: Monique Grimm Additional Staff: Description: Provides additional funding to support Critical Access Hospitals. | 10 | Effective Date: 4/1/17
| 2017-07-12 | P | P | P | Create draft model for allocating State Only funds to Critical Access Hospitals
| 2017-08-18 | P | P | P | Finalize model for allocating State Only funds to Critical Access Hospitals
| 9/30/17 10/23/17 11/14/17 11/21/17 | P | P | P | Division of the Budget Approval
| 10/7/17 10/30/17 11/16/17 12/1/17 12/11/17 | P | P | P | Draft Provider Communication (Letter)
| 10/15/17 11/8/17 11/22/17 12/6/17 12/14/17 | P | P | P | Release Lump Sum State Only Payments to Hospitals
| 12/8/17 12/18/17 | P | P | P | Submit State Plan Amendment (SPA) to CMS for Federal Match
| 3/30/18 5/31/18 8/31/18 11/30/18 | 8 | 8 | 8 | CMS Approval of SPA
| 4/10/18 6/15/18 9/14/18 12/18/18 | 8 | 8 | 8 | Division of the Budget Approval (Federal Share)
| 4/13/18 6/18/18 9/17/18 12/21/18 | 8 | 8 | 8 | Draft Provider Communication (Letter - Federal Share)
| 4/18/18 6/29/18 9/29/18 12/28/18 | 8 | 8 | 8 | Release Lump Sum State Only Payments to Hospitals (Federal Share)
10209 |  |  |  |  | Project Name: SUNY DSH Division Lead: DFRS Team Lead: Kevin Wright Additional Staff: John Ulberg, Kevin Wright Description: Provides additional funding to SUNY to support the DSH costs. | 9.3 | Effective Date: 4/1/17 Completed June 2017
| 2017-06-22 | 8 | 8 | 8 | Remit SUNY DSH IGT payments up to the $318.6 (gross) $159.3M (State) cap limits. Factoring it remaining ICA and ICP payments.
| 2017-09-01 | ▲ | ▲ | ▲ | Deadline for SUNY to fund the balance of the non-Federal share of DSH IGT payment up to each hospitals facility specific DSH cap.
| 2017-09-15 | ▲ | ▲ | ▲ | Remit any unspent federal DSH funding to NYC H+H.
10210 |  |  |  |  | Project Name: Reduction in Mainstream Managed Care Quality Bonus Division Lead: DFRS Team Lead: Connor Gemerek Additional Staff: Torrey Duchessi, John Ulberg, Mike Dembrowsky Description: The Medicaid Managed Care Quality Incentive pool is currently valued at $315 million in gross annual funding. This proposal would reduce the value of the pool to $275 million gross annual funding. The Department is exploring operationalizing this reduction as an adjustment to the quality award for lower performing quality tiers. | -20 | Effective Date: 4/1/17 Completed August 2017
| 2017-05-23 | P | P | P | Draft April 17 rates to plans
| 2017-06-23 | P | P | P | April 17 rates sent to DOB
| 2017-06-23 | P | P | P | April 17 rates sent to CMS
| 2017-08-08 | P | P | P | April 17 rates approved by DOB.
| 2017-08-08 | P | P | P | April 17 rates approved by DOB.
| 2017-08-11 | P | P | P | April 17 rates loaded to the system. Assumes rates will be loaded once approval is secured from DOB.
10211 |  |  |  |  | Project Name: Reduction in Number of VBP Pilots Division Lead: DFRS Team Lead: Connor Gemerek Additional Staff: Torrey Duchessi, John Ulberg, Mike Dembrowsky Description: This proposal would reduce the incentive funding for the VBP Pilot Program from $25 million gross annually to $15 million gross annually. | -5 | Effective Date: 4/1/17 7/1/17 Completed - January 2018
| 7/31/2017 8/21/2017 9/4/2017 10/30/2017 11/30/2017 1/12/2018 | P | P | P | Draft July 17 October 17 rates to plans
| 9/1/2017 9/20/2017 10/9/2017 11/27/2017 12/27/2017 1/31/2018 | P | P | P | July 17 October 17 rates sent to DOB
| 9/1/2017 9/20/2017 10/9/2017 11/27/2017 12/27/2017 1/31/2018 | P | P | P | July 17 October 17 rates sent to CMS
| 10/16/2017 10/30/2017 12/4/2017 2/12/2018 | P | P | P | July 17 October 17 rates approved by DOB.
| 10/20/2017 12/4/2017 2/16/2018 | P | P | P | July 17 October 17 rates loaded to the system. Assumes rates will be loaded once approval is secured from DOB.
| 2018-02-07 | P | P | P | Draft April 18 rates to plans
| 2018-02-07 | P | P | P | April 18 rates sent to DOB
| 2018-02-07 | P | P | P | April 18 rates sent to CMS
| 2018-03-12 | P | P | P | April 18 rates approved by DOB.
| 2018-03-16 | P | P | P | April 18 rates loaded to the system. Assumes rates will be loaded once approval is secured from DOB.
10212 |  |  |  |  | Project Name: Medicaid Restimate / DSRIP Savings Division Lead: DFRS Team Lead: Connor Gemerek Additional Staff: Torrey Duchessi, John Ulberg, Mike Dembrowsky Description: Savings will be achieved through PPA/LANE Adjustment. | -25 | Effective Date: 4/1/17 Completed August 2017
| 2017-05-23 | P | P | P | Draft April 17 rates to plans
| 2017-06-23 | P | P | P | April 17 rates sent to DOB
| 2017-06-23 | P | P | P | April 17 rates sent to CMS
| 2017-08-08 | P | P | P | April 17 rates approved by DOB.
| 2017-08-08 | P | P | P | April 17 rates approved by DOB.
| 2017-08-11 | P | P | P | April 17 rates loaded to the system. Assumes rates will be loaded once approval is secured from DOB.
10213 |  |  |  |  | Project Name: Monroe County Special Payment Division Lead: DFRS Team Lead: Frank Czernicki Additional Staff: Jada Eberle, John Ulberg Description: Per enacted budget payment of $860,000 to St. Ann's Nursing home in Monroe County | 0.86 | Effective Date: 4/1/17 Completed August 2017
| 2017-04-03 | P | P | P | Receive final Enacted Budget scorecard / matrix
| 2017-04-05 | P | P | P | Determine which individual facility is to receive payment
| 2017-05-10 | P | P | P | Division Meeting to schedule payment
| 2017-05-10 | P | P | P | Determine rate effective date
| 2017-05-18 | P | P | P | Begin rate package
| 2017-05-18 | P | P | P | Determine applicability of federal share with DOB
| 2017-05-26 | P | P | P | Payment package in Bureau review
| 2017-06-02 | P | P | P | Payment Packaage in Division Review
| 2017-06-07 | P | P | P | Payment Package to Budget (Sent 6/9)
| 6/21/2017 7/1/17 | P | P | P | Package Approved by DOB
| 6/23/2017 7/06/17 | P | P | P | Payment to eMedNY Paid on cycle 2084 Check Release 8/23/17
10214 |  |  |  |  | Project Name: Generic Drugs Consumer Price Index (CPI) Division Lead: DFRS Team Lead: Donna Cater Additional Staff: Chris DeSorbo, John Ulberg Description: The Department will ensure the generic CPI penalty adjustment policy is implemented effectively and addresses the concerns of manufacturers who may be inappropriately impacted |  | Completed - February 2018
| 2017-02-28 | P | P | P | DOH rebate staff are reducing state penalties by the federal penalty, beginning 1/1/2017. Any other concerns are addressed as they received.
10215 |  |  |  |  | Project Name: Generic CPI Penalty Adjustment - 75% Division Lead: DFRS Team Lead: Donna Cater Additional Staff: Chris DeSorbo, John Ulberg Description: Generic drug manufacturers are required to pay additional rebates for year over year price increases greater than 75% of the State Maximum Acquisition Cost (SMAC). | -8.8 | Completed - February 2018 Effective Date: 4/1/17 10/1/17
| 6/1/2016 7/1/2016 8/15/16 | P | P | P | Develop Draft Methodology for Rebate Collections
| 6/1/2016 7/30/2016 9/15/16 10/7/16 10/24/16 | P | P | P | Engage Stakeholders
| 7/15/2016 8/15/2016 9/30/16 10/22/16 | P | P | P | Legal Review
| 8/1/2016 9/1/2016 10/15/16 11/1/16 11/15/16 | P | P | P | Finalize Methodology
| 8/30/2016 9/30/2016 11/15/16 12/1/16 12/31/16 3/15/17 4/1/17 5/15/17 5/30/17 7/15/17 | P | P | P | System Changes - Not making system changes.
| 10/1/2016 11/15/16 12/1/16 12/31/16 4/1/17 5/30/17 7/30/17 11/17/17 | P | P | P | Develop instructions for manufacturers on payment
| 12/31/2016 1/15/17 4/30/17 6/30/17 7/30/17 11/17/17 | P | P | P | Send out initial rebate invoices
| 12/31/2016 1/15/17 4/30/17 6/30/17 7/30/17 11/17/17 2/28/2018 | P | P | P | Operationalize invoice process
10216 |  |  |  |  | Project Name: Reduce Payments to Plans for Facilitated Enrollment Division Lead: DFRS Team Lead: Connor Gemerek Additional Staff: Torrey Duchessi, John Ulberg Description: This proposal would reduce Medicaid Managed Care Premium Payments to plans for facilitated enrollment by $20 million gross to reflect the decline in the uninsured rate. It would also ensure that those plans receiving the payments have active facilitated enrollers. | -10 | Effective Date: 4/1/17 Completed August 2017
| 2017-05-23 | P | P | P | Draft April 17 rates to plans
| 2017-06-23 | P | P | P | April 17 rates sent to DOB
| 2017-06-23 | P | P | P | April 17 rates sent to CMS
| 2017-08-08 | P | P | P | April 17 rates approved by DOB.
| 2017-08-08 | P | P | P | April 17 rates approved by DOB.
| 2017-08-11 | P | P | P | April 17 rates loaded to the system. Assumes rates will be loaded once approval is secured from DOB.

## Ph. 7 Long Term Care
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2017-2018 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
10301 |  |  |  |  | Project Name: Ban MLTC Marketing Division Lead: DLTC Team Lead: Kirk Dobson Additional Staff: Andrew Segal Description: This proposal instructs plans to cease marketing and advertising activities for the MLTC Partial Capitated product. The goal is to stabilize the sharp growth of MLTC enrollees through the cutting of marketing by the plans. | -3 | Effective Date: 4/1/17 Completed June 2017
Policy
| 2017-06-01 | P | P | P | Draft detailed MLTC marketing ban policy for distribution with the advice of DLA.
| 2017-06-15 | P | P | P | Send policy documents to MLTC trade associations for feedback
| 2017-06-30 | P | P | P | Send letters to MLTC Plans
Communicaiton
| 2017-06-30 | P | P | P | Alert MLTC Partial Capitation Plan Managers of changes and new policy
10302 |  |  |  |  | Project Name: Adjustment of Align End-of-Life Services for with Medicare Division Lead: DLTC Team Lead: Kathy Loerzel/Mark Tremblay Additional Staff: Kirk Dobson Description: Aims to align end-of-life/hospice services currently covered by Medicaid with Medicare, where applicable. Identify and correct erroneous Medicaid billing practices for Hospice services in cases where Medicare should be the primary payer | -4.4 | Effective Date: 6/1/17
| 2017-06-02 | P | P | P | Approve final draft language for MLTC plan (except PACE plans) and Hospice billing guidance (instead of letters).
| 6/9/2017 10/27/17 11/30/17 | P | P | P | Send letters to MLTC plans and notice all Hospice prorviders including free-standing hospice residences, as well as SNFs regarding changes in policy regrading Hospice billing.
| 2017-06-09 | P | P | P | Notice all Hospice providers including free standing hospice residences as well as SNFs regarding change in policy via DOH listservs (see previous item)
| 2017-06-09 | P | P | P | Issue requests to plans to obtain lists of Hospice enrollees
| 6/16/17 10/27/17 1/31/18 | 8 | 8 | 8 | Amend scope of benefits to prevent Skilled Nursing Facilties from billling FFS for Hospice nursing home enrollees - CSRA has agreed to amend the scope of benefits file which is scheduled for completetion by the date indicated.
| 6/30/17 6/30/18 | 8 | 8 | 8 | MLTC data collection complete
| 6/30/17 4/1/18 | 8 | 8 | 8 | Begin analyzing plan data relative to MDW claims data to determine Hospice billing practices and alignment between Medicare billing and Medicare eligbility for covered Hospice services
| 7/21/2017 3/31/18 9/30/18 | 8 | 8 | 8 | Confirm/update savings estimates utilizing plan/MDW data based on number of MLTC hospice enrollees, services utilization, and third party (Medicare) eligiblity/billing
| 7/28/2017 10/27/17 11/30/17 | P | P | P | Draft detailed, uniform Hospice billing guidance for all Hospice services for Hospice providers, MLTC plans, counties, and SNFs (see item two in workplan)
| 2018-06-30 | 8 | 8 | 8 | Update Hospice Manual and revise and reissue Hospice Q&A
| 11/17/2017 3/31/18 4/1/18 | 8 | 8 | 8 | Analyze first quarter Hospice data post implementaiton of new billing guidelines to estimate the level projected savings as well as identify opportunites to implement billing edits/restrictions to enforce compliance with new billing policies
10303 |  |  |  |  | Project Name: Implementation of a Plan Fining Mechanism for DLTC Division Lead: DLTC Team Lead: Kirk Dobson Additional Staff: Kori Kordato; Andrew Segal Description: Provides a mechanism for fining plans for systemic or habitual violations of implemented guidelines, contract provisions, and best practices guidelines where applicable. | -2 | Completed - May 2018 Effective Date: 12/1/17
Policy
| 2017-06-30 | P | P | P | Draft Fining Policy Document w/ OMIG
| 2017-07-15 | P | P | P | Finalize DLTC/OMIG roles (legal)
| 2017-07-15 | P | P | P | Finalize DLTC/OMIG roles (policy)
| 2017-07-15 | P | P | P | Determine UAS Policies
| 2017-07-15 | P | P | P | Determine Surveillance Policies
| 2017-07-15 | P | P | P | Determine Contracting Policies
Communicaiton
| 2017-04-15 | P | P | P | Draft detailed proposal to share with OMIG
| 6/15/2017 1/26/18 | 8 | 8 | 8 | Organize Call with OMIG to finalize Fining Procedure
| 7/30/2017 2/15/18 | 8 | 8 | 8 | Draft Internal and External Fining Guidance Document
| 8/15/2017 9/30/2017 12/1/17 2/20/2018 | 8 | 8 | 8 | Distribute Guidance to Internal and External Stakeholders
Regulatory/Legal
| 2017-07-10 | P | P | P | Submit Regulatory additions and changes to DLA for drafting
| 7/30/2017 9/15/17 | ▲ | ▲ | ▲ | Submit Regulatory Change/Additions Packages |  | New regulations may not be necessary; under review
| 8/30/2017 9/30/17 | ▲ | ▲ | ▲ | Regulations become Effecitve
Implementaiton
| 2017-09-15 | P | P | P | Surveillance and UAS recommendtations for Fining
10304 |  |  |  |  | Project Name: BIP Funds to Support FLSA Mandate Division Lead: DLTC Team Lead: Karen Meier Additional Staff: Dan Carmody Description: BIP funds will support the cost of implementing FLSA requirements to ensure continuity of service for individuals in need of LTC and to ensure that aides are paid fairly for personal and home health care. | -38.5 | Effective Date: 4/1/17 Completed June 2017
| 2017-02-28 | P | P | P | Obtain CMS Approval of Proposed Spending under BIP
| 2017-06-01 | 8 | 8 | 8 | Answer CMS Questions about Assuring Appropriate Fund Use
| 2016-11-01 | P | P | P | Develop an attestation process for plans and providers to assure that they are compliant with the FLSA mandate.
| 2017-07-01 | 8 | 8 | 8 | Work with OMIG and DOL to ensure that review and audit protocols are established that include the FLSA mandate components.
| 2017-09-30 | 8 | 8 | 8 | Monitor complaints of providers, consumers and providers related to continuity of care and other issues related to the FLSA mandate; continue to engage stakeholders in ensuring compliance.
| 2017-09-01 | 8 | 8 | 8 | Disburse funds through rates to managed care and managed long term care plans that provide, directly or through contract, personal and home health services and supports.
10305 |  |  |  |  | Project Name: BIP Funds to Support NY Connects Division Lead: DLTC Team Lead: Karen Meier Additional Staff: Jim DelBelso, Andrew Segal, NYSOFA Description: BIP funds will support the cost of operating the NY Connects NWD/SEP BIP deliverable for two additional quarters. | -5.3 | Effective Date: 4/1/17 Completed - April 2017
| 2015-10-01 | P | P | P | Determine Financial Plan Impact of NWD sustainability funding for 2017-2018 SFY ($18.1 million).
| 2015-03-01 | P | P | P | Receive extension of BIP spending period from CMS
| 2016-10-01 | P | P | P | Develop 2017-2018 SFY Budget with additional 2 quarters of BIP $
| 2016-10-01 | P | P | P | Financial plan commitment drops from $18.1 to $12.9 million
| 2017-04-09 | P | P | P | State budget adopted with $12.9 million for NY Connects; savings realized in an amount that exceeds expected ($5.2 million)
10306 |  |  |  |  | Project Name: NHTD/TBI carve out Division Lead: DLTC Team Lead: David Hoffman Additional Staff: Andrew Segal Description: The Executive agrees to continue the NHTD/TBI Medicaid Managed Care carve-out until January 1, 2019. |  | Merged with # 8401
10307 |  |  |  |  | Project Name: UAS Division Lead: DLTC Team Lead: Kirk Dobson Additional Staff: Andrew Segal Description: The Executive commits to analyzing and formulating recommendations regarding the Universal Assessment Tool (UAS) with the health care community. The Department will work with the Legislature to identify stakeholder groups to provide input. We will commit to regular meetings with members of the Legislature, stakeholders, Department representatives from both program and the UAS team, as well as representatives from the Department’s Office of Quality and Patient Safety who analyze data retrieved from the UAS. From these meetings, we will generate proposed improvements to the UAS tool. Upon request, the Department can provide the Legislature with updates on scheduled enhancements to the UAS tool. | 0 | Effective Date: 4/1/17 Completed - January 2018
Planning and Scheduling
| 8/1/2017 9/15/17 | P | P | P | First Quarterly Meeting |  | There are no recurring updates to the UAS tool. Rather DOB will schedule should further information be requested.
| 2017-12-01 | 8 | 8 | 8 | Second Quarterly Meeting
| 2018-03-01 | 8 | 8 | 8 | Third Quarterly Meeting
| 2018-07-02 | 8 | 8 | 8 | Fourth Quarterly Meeting
Meetings
| 8/1/2017 TBD by DOB | 8 | 8 | 8 | First Quarterly Meeting
| 2017-12-01 | 8 | 8 | 8 | Second Quarterly Meeting
| 2018-03-01 | 8 | 8 | 8 | Third Quarterly Meeting
| 2018-07-02 | 8 | 8 | 8 | Fourth Quarterly Meeting

## Ph. 7 Prog Development & Mgmt
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2017-2018 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
10401 |  |  |  |  | Project Name: Women’s Health Initiative – Infertility Treatment Division Lead: DPDM Team Lead: Melissa Kinnicutt Additional Staff: Beth Denniston, Emily Steinbach, Carol Lindley, Connie Donohue, Alda Osinaga, Greg Allen Description: Add coverage for infertility to Medicaid/FPBP benefits; In the event that federal financial participation is not available pursuant to paragraph (ee) of subdivision 2 of section 365-a of the social services law, the Department of Health will establish a Women’s Health and Prenatal Care Pilot program, utilizing such appropriated funds. Within appropriated amounts, the Department will make available funds necessary for the Pilot Program to provide medical assistance to women for certain infertility services and shall include the coverage of a set of services to ensure improved outcomes of women who are in the process of treatment with ovulation enhancing drugs, limited to the provision of such treatment, office visits, hysterosalpingogram services, pelvic ultrasounds, and blood testing; services will be limited to those necessary to monitor such treatment. The Department shall fund the Pilot Program within as many of the 50 zip codes in this State that have the highest incidence of multiples births in the preceding five years, as funds may permit. The Department shall make funds available for such Pilot Program as necessary to implement the program or up to $5 million dollars annually, whichever is less. The Pilot program shall commence in the event that the federal financial participation for such services in the Medicaid program is not available. | 5 | Effective Date: 4/1/17 7/1/17
| 6/9/2017 6/28/17 | P | P | P | Publish Federal Public Notice
| 2017-06-30 | P | P | P | Prepare draft SPAs for internal review
| 2017-07-18 | P | P | P | Share draft SPA/meet with Legislative stakeholders
| 8/15/2017 9/30/17 | P | P | P | Submit SPAs to CMS once legislative stakeholders agree with proposed language
| 10/15/201710/30/17 12/15/17 1/15/2018 2/15/2018 3/23/2018 | P | P | P | Obtain CMS approval for SPAs
| 10/15/201711/10/17 12/20/17 1/15/2018 2/15/2018 3/26/28 | P | P | P | Submit eMedNY Evolution Project Request
| 12/1/2017 1/5/18 1/15/2018 3/1/2018 4/1/2018 6/1/18 | P | P | P | Contingent on SPA approval/90% FMAP, pursue change in Medicaid regulations at 18 NYCRR 503
| 7/15/2018 8/15/18 8/22/18 | P | P | P | Publish updated Title 18 regulations – 60 day comment period begins
| 10/22/2018 11/15/18 | 8 | 8 | 8 | Updated Title 18 Regulations will be in effect (except if comments received cause substantial revision of the regulation(s))
| 12/1/2017 2/1/18 3/15/2018 4/15/2018 7/1/18 9/1/18 11/1/18 | 8 | 8 | 8 | Notify members and providers of new coverage
10402 |  |  |  |  | Project Name: Pasteurized Donor Human Milk (PDHM) Division Lead: DPDM Team Lead: Emily Steinbach Additional Staff: Alda Osinaga, Ron Bass, Beth Denniston, Connie Donohue Description: This proposal provides for use of pasteurized donor human milk (PDHM), with fortifiers as medically indicated, for inpatient use when medically necessary. Use of PDHM is based on a written medical order for infants who have a documented birth weight of less than 1500 grams, or are at high risk of developing necrotizing enterocolitis, or have other conditions as determined by the commissioner of health or his designee. | 0 | Effective Date: 7/1/17 Completed - July 2017
| 2017-06-13 | P | P | P | Evidence-based Benefit Review Advistory Committee Meeting |  | NY EBBRAC did not make a coverage recommendation, but reviewed the evidence surrounding the use of PDHM
| 2017-07-01 | P | P | P | Notify members and providers of new service
10403 |  |  |  |  | Project Name: School Based Health Centers carve out Division Lead: DPDM Team Lead: Jonathan Bick Additional Staff: Greg Allen, Connie Donohue Description: The Executive agrees to continue the SBHC Medicaid Managed Care carve-out until July 1, 2018. |  | Merged with 8401
| 2017-01-01 | P | P | P | State issued policy paper
| 2017-01-27 | P | P | P | FAQ's posted
| 2017-04-01 | P | P | P | Billing Guidance issued
| 2018-01-01 | 8 | 8 | 8 | Assess System Impact
| 2018-04-01 | 8 | 8 | 8 | Contract Amendment
| 2018-05-01 | 8 | 8 | 8 | Medicaid Update Article Issued
| 2018-05-01 | 8 | 8 | 8 | Update Scope of Benefits
| 2018-06-01 | 8 | 8 | 8 | CMS approval
| 2018-07-01 | 8 | 8 | 8 | Stakeholder feedback | These meetings are ongoing
| 2018-07-01 | 8 | 8 | 8 | Effective Date of Transition
10404 |  |  |  |  | Project Name: Reduce 911 "Frequent Flier" calls Division Lead: DPDM Team Lead: Mark Bertozzi Additional Staff: Robert Schmit, Josiah Blair, Liz Misa Description: Identify enrollees that have 10 or more emergency ambulance trips and reduce the total volume by 50%. | -4.25 | Effective Date: 10/1/17 Completed - August 2018
| 2017-05-25 | P | P | P | Meet with Salient and discuss parameters to identify our targeted frequent flier cohort for the period 10/2015 - 09/2016.
| 2017-06-14 | P | P | P | Identify primary diagnosis code, county of fiscal responsibility, and managed care plan associated with each enrollee.
| 6/28/2017 7/25/17 | P | P | P | Organize data to identify frequency of diagnosis codes, counties, and managed care plans. Identify outliers and cohorts that may be high utilizers
| 2017-07-12 | P | P | P | Meet with DOH Medical staff to determine what primary diagnosis codes are acceptable and which are not for emergency ambulance trips.
| 2017-07-26 | P | P | P | Remove inappropriate Separate end stage renal disease and dialysis enrollees from the main cohort list and identify cohort to focus on.
| 2017-08-03 | P | P | P | Gather enrollee, local DSS, and managed care plans contact information.
| 2017-08-23 | P | P | P | Divide the enrollees into groups by county and by managed care plans.
| 2017-09-13 | P | P | P | Draft and get approved 3 separate letters addressed to the enrollee, local DSS, and managed care plans.
| 2017-09-27 | P | P | P | Arranging mailing to enrollees, managed care plans, and local DSS's
| 10/2/17 11/3017 | P | P | P | Mailing complete.
| 10/25/17 12/15/17 | P | P | P | Report on status of mailings |  | 911 use for cohort will be monitored to assess usage/savings
| 2018-01-15 | P | P | P | Track returned mail and develop a follow up plan
| 2018-02-15 | P | P | P | Report on the current savings and estimated future savings
| 2018-03-15 | P | P | P | Report on the outreach efforts using HCS secure file transfer.
| 2018-05-22 | P | P | P | Report on current status of HCS and discuss next steps.
10405 |  |  |  |  | Project Name: Health Homes Restructuring and Reprogramming Outreach Division Lead: DPDM Team Lead: Peggy Elmer Additional Staff: Amy Clinton, Cynthia Buswell, Alyssa Altschul, Lana Earle, OASAS, OMH Description: Restructuring and reprogramming Health Home outreach and engagement | -10 | Effective Date: 4/1/17 Completed - May 2018
| 2017-05-30 | P | P | P | Submit Federal Public Notice for publication
| 2017-06-01 | P | P | P | Develop project budget
| 2017-06-01 | P | P | P | Finalize restructure and reprogram approaches
| 2017-07-26 | P | P | P | Submit revised Federal Public Notice for publication
| 6/15/2017 7/7/17 7/31/17 8/31/17 | P | P | P | Health Home SPA submitted to CMS
| 2017-06-30 | P | P | P | Updated MAPP/system
| 2017-10-04 | P | P | P | Informal discussion with CMS
| 2017-10-16 | P | P | P | NYS verbal response to Request for Additional Information
| 2017-11-20 | P | P | P | NYS written response to Request for Additional Information
| 9/1/2017 TBD | P | P | P | Approval of SPA by CMS
| 2017-09-30 | P | P | P | Implementation for outreach retroactive to 10/1/17 -
| 2018-05-01 | P | P | P | Implementation for revised rates
10406 |  |  |  |  | Project Name: Increase Penalty for Early Elective Deliveries Division Lead: DPDM Team Lead: Donna Urban Additional Staff: Joan Sicard, Greg Allen, Ron Bass Description: Increase Disallowance for Early Elective Deliveries less than 39 weeks without medical indication to 75% | -1.5 | Effective Date: 4/1/17 Completed June 2017
| 2017-05-31 | P | P | P | Provide appropriate eMedNY staff with notification of increase in reduction of payment from 50% to 75% for non-medically indicated obstetrical deliveries (EP not required as reduction percentages are in table format)
| 2017-05-31 | P | P | P | Inform Division of Health Plan Contractions and Oversight (Medicaid Managed Care) of increased reduction in payment for obstetrical claims
| 2017-05-31 | P | P | P | Communicate with systems re: change in reduction
| 2017-06-02 | P | P | P | Prepare draft Medicaid Update notifying providers of FFS and MMC implementation dates
| 2017-06-10 | P | P | P | Circulate draft Medicaid Update for review/editing
| 2017-06-30 | P | P | P | Finalize and publish Medicaid Update
10407 |  |  |  |  | Project Name: Continued Medicaid Coverage Review Division Lead: DPDM (Greg Allen, Ronald Bass) Team Lead: Kendra Muckle, Joan Sicard Additional Staff: Alda Osinaga, Doug Fish, Jonathan Curtin, Ron Bass, Connie Donohue, Emily Steinbach Description: This proposal would conduct a comprehensive examination of the current list of covered benefits and processes in the New York State Medicaid program and develop a list of savings proposals that will improve health care quality, lower costs and improve efficiency in the program. A list of savings proposals is under development. The Medicaid Evidence Based Benefit Review Advisory Committee would be engaged when such examination requires an evidence-based review. | -5 | Effective Date: 4/1/17 Completed - May 2018
| 7/1/17 12/31/17 | ▲ | 8 | 8 | Coverage of Topical Oxygen Wound Therapy - coverage determination pending.
| 2018-03-16 | P | 8 | 8 | Review and non-coverage decision for varicose vein treatment | $2.2 of 5 million
| 2018-03-16 | P | 8 | 8 | Co-insurance recoupment for non-covered services identified potential 2.3 million in overpayments. | $2.3 of 5 million
| 2018-03-16 | P | 8 | 8 | Changes to APG weights ($297,425 plus $491,958) | $789,383 of 5 million
| 2018-03-16 | P | 8 | 8 | Review of Upper Payment Limit and adjustment of lab fees will result in 7.4 million in savings going forward. | 3.7 million
Review Process
| 6/1/17 8/1/17 10/1/17 12/1/17 02/01/18 3/15/18 | P | 8 | 8 | Continue current process of identifying new procedure codes, services, and technologies (ongoing).
| 6/30/17 8/1/17 10/01/17 12/1/17 02/01/18 3/15/18 | P | 8 | 8 | Utilize existing groups (including OHIP medical directors) and processes to research these procedures, services and technologies. This internal review process will take into consideration other payer policies, expert recommendations/guidelines (ACOG, NCCN, USPSTF) and an estimated financial impact to the Program.
| 7/15/2017 09/01/17 11/01/17 12/1/17 02/01/18 3/15/18 | P | 8 | 8 | Existing groups (including OHIP medical directors) will determine if a more in depth evidence-based review (outside contractor) is needed (ongoing).
| 5/1/17 08/1/17 10/1/17 12/1/17 02/1/18 3/15/18 | P | 8 | 8 | The policy team (including medical directors) will select topics to present to the EBBRAC committee following internal/external reviews and/or the dossier process (ongoing throughout the year).
| 2/1/18 3/15/18 | P | 8 | 8 | Re-review previous MRT projects and coverage decisions to determine if policy updates and/or coding changes are needed. (ongoing review) |  | New Technology decisions re-review
| 7/1/17 10/1/17 01/1/18 3/1/18 | P | 8 | 8 | Request data quarterly outlining the largest spends within the Program, beginning 7/1/17; 10/1/17; 1/1/18; 3/1/18. |  | Data requested for 10/17- next request 1/18
| 7/15/17 09/15/17 11/15/17 01/15/18 3/1/18 | P | 8 | 8 | Conduct a brief internal review of the largest spends to identify any policy changes or guidance that may be needed surrounding identified technologies/services (quarterly).
System Changes
| 2017-07-01 | P | 8 | 8 | Set up a bi-monthly meeting to discuss policy-related system changes.
| 2017-07-01 | P | 8 | 8 | Set up bi-monthly meetings with the group to discuss any necessary system changes, beginning 7/1/17.
| 7/1/17 09/01/17 | P | 8 | 8 | Create a spreadsheet to track system changes.
| 9/15/2017 11/1/17 12/1/17 02/01/18 3/15/18 | P | 8 | 8 | Complete a draft of File Parameter Form and/or Evolution Project(EP) Form for projects to be implemented. (ongoing) |  | The File Maitenance team shared a new File Parameter Form and a new EP Form has been implemented. A form will be completed for each service/CPT where system changes are needed. System change meetings are on the calendar.
| 2018-02-01 | P | 8 | 8 | Share draft with appropriate staff for review and make revisions. |  | Beth -new file parameter sheet complete
| 10/15/17 12/1/17 02/01/18 3/15/18 | P | 8 | 8 | Submit file parameter changes and/or EP requests to appropriate staff.
Notifications
| 8/1/2017 10/1/17 12/1/17 02/01/18 3/15/18 | P | 8 | 8 | Meet with group to discuss policy guidance notifications including: postings to website for public comment, e-blasts and Medicaid Updates. (ongoing)
| 9/1/2017 11/1/2017 02/01/18 3/15/18 | P | 8 | 8 | Draft information for above communication and circulate for approval. Complete revisions and edits. (ongoing)
| 10/1/2017 02/01/18 3/15/18 | P | 8 | 8 | Submit approved Medicaid Update, e-blast or website posting for publication. (ongoing)
Outcomes
| 1/1/18 3/1/18 | P | 8 | 8 | Request data six months following a policy and/or system change to ensure that objectives are being met.
| 2017-08-01 | P | 8 | 8 | Form a group (including OHIP medical directors) to review outcome data.
| 2017-08-01 | P | 8 | 8 | Schedule bi-monthly meetings with this group to discuss outcomes of previous/planned initiatives and any changes that may be necessary.
10408 |  |  |  |  | Project Name: Enhanced Claim Editing for ESO Division Lead: DPDM Team Lead: Jassen Eide Additional Staff: Joan Sicard, Ron Bass, Alda Osinaga, Bill Bruno, Greg Allen Description: Enhance payment edits for undocumented immigrants who use emergency services only (ESO) and create claiming edits for the system to ensure that Medicaid payments are limited to emergency services which meet the federal regulatory definition. Specifically, system edits for Rehabilitation services, Alternate Level of Care services, Nursing Home Care & Home Care Services. Identify and change emergency service indicator of non-emergent procedure codes and diagnosis codes. | -2.5 | Effective Date: 4/1/17 Completed - May 2018
| 2016-06-01 | P | P | P | 7/2008 Medicaid Update reviewed for applicable settings not eligible to ESO population pursuant to Federal regulatory definition and coverage policy.
| 2016-07-01 | P | P | P | Compile list of rate codes for Evolution Project (EP) - initial codes identified and approved.
| 2016-07-15 | P | P | P | Draft EP to allow for additional rate codes as needed.
| 2016-08-01 | P | P | P | Circulate EP for approval.
| 2016-08-03 | P | P | P | Submit approved EP Request to Systems.
| 2016-10-05 | P | P | P | Create list of additional codes to review for appropriateness by rate setters/subject matter experts.
| 2016-11-04 | P | P | P | Meet with Finance & Rate Setting Unit to review additional applicable rate codes for EP - (reviewed additional rate codes, rate codes added to list, request sent to LTC to review rate codes/descriptions).
| 2016-12-20 | P | P | P | EP implemented effective 1/1/2017 - confirmed.
| 2016-12-29 | P | P | P | Obtain current nursing home rate codes - Received list of Long Term Care (LTC) rate codes - Schedule meeting to discuss rate codes/descriptions.
| 2017-01-27 | P | P | P | Meet with LTC unit to review rates codes and descriptions - Identified rate codes for EP.
| 2017-02-01 | P | P | P | Clarify nursing home billing procedure.
| 4/1/2017 5/1/17 6/1/17 | P | P | P | Finalize Rate Code List for EP implementation.
| 5/15/17 6/15/17 6/22/17 | P | P | P | Provide list of finalized rate codes to Systems for implemenation.
| 2017-06-28 | P | P | P | Confirmation received of finalized rate code list added to EP with 8/1/17 effective date
| 2017-06-30 | P | P | P | Identify non-emergent procedure codes and diagnosis codes. "Emergency Service" File parameter indicator changed to "n" effective 4/1/17 by File Reference Unit.
| 2017-07-01 | P | P | P | Prepare Medicaid Update Article outlining system edits with implementation date.
| 2017-07-01 | P | P | P | Request data on total claim amount paid for ESO recipients using only rate codes identified in EP for fiscal impact accuracy (State Savings).
| 2017-07-15 | P | P | P | Circulate Draft Medicaid Update Article.
| 2017-07-15 | P | P | P | Review data for accuracy - if necessary, adjust fiscal (State Savings).
| 2017-07-28 | P | P | P | Medicaid Update Article returned for revisions/ referneces
| 2017-08-08 | P | P | P | Re-Circulated Draft Medicaid Update Article
| 8/1/2017 9/1/2017 10/1/2017 11/1/2017 12/1/2017 2/1/18 3/1/18 4/1/18 5/1/18 | _ | 8 | 8 | Publish Medicaid Update Article.
| 2/1/18 6/1/18 | 8 | 8 | 8 | Run data to check for accuracy and effectiveness of EP (6 months from 1 year anniversary of effective date of EP).
10409 |  |  |  |  | Project Name: PCMH Enhanced Funding Reduction Division Lead: DPDM Team Lead: Mary Jane O'Brien Additional Staff: DPDM-Alda Osinaga, Ron Bass, Connie Donohue, Greg Allen; OQPS-Dana Schiffman, Carlton Wells Description: Effective July 1, 2017 eliminate payments for 2011 PCMH recognized providers. Payments for 2014 PCMH Level 2 providers will be reduced from $6 pmpm to $3 pmpm and payments for 2014 Level 3 providers will be reduced from $8 pmpm to $7.50 pmpm. | -10 | Effective Date: 4/1/17 7/1/17 Completed August 2017
| 2017-05-08 | P | P | P | Notify providers (April 2017 Medicaid Update; Provider Association call; DSRIP PPS listserv)
| 2017-05-16 | P | P | P | Finalize and submit system change requirements
| 6/30/2017 6/6/17 | P | P | P | Load rates on eMedNY
| 8/1/2017 9/1/17 | 8 | 8 | 8 | Include PMPM payment reduction language in 2017 Medicaid Managed Care contract amendment. |  | This information is not required for the MMC contract amendment
10410 |  |  |  |  | Project Name: Transition Medicaid Reimbursement Methodology From EAC to AAC Division Lead: DPDM Team Lead: Dan McNamara Monica Toohey Additional Staff: Carol Lindley, Mike Colabufo, Janet Zachary-Elkind Description: This proposal aligns NY State Medicaid with the CMS Covered Outpatient Drug Rule, which requires that States move to a cost based pharmacy reimbursement methodology for Fee-For-Service (FFS) pharmacy program. | 11 | Effective Date: 4/1/17
| 2017-04-01 | P | P | P | Enacted Budget For Pharmacy Reimbursement
| 2017-04-01 | P | P | P | Submit System Projects (5 total projects dependent on each other)
| 6/1/17 5/9/17 | P | P | P | Draft and Submit SPA for Internal/Executive Approval
| 2017-06-30 | P | P | P | Executive Approval of SPA
| 2017-06-30 | P | P | P | Submit SPA To CMS
Track System Projects/Complete Design
| 2017-07-01 | P | P | P | EP2156: NADAC Pricing and Methodology
| 2017-07-01 | P | P | P | EP2158: OTC/COD Indicator MERGED With Project 5, EP2155
| 2017-07-01 | P | P | P | EP2157: 340B Pharmacy Ceiling Price
| 2017-07-01 | P | P | P | EP2159: Short Cycle Billing
| 2017-07-01 | P | P | P | EP2155: Drug Termination Date
System Testing
| 7/1/2017 8/15/2017 11/9/2017 | P | P | P | EP2156: NADAC Pricing and Methodology
| 7/1/2017 8/15/2017 | P | P | P | EP2158: OTC/COD Indicator MERGED With Project 5 |  | MERGED With EP2155
| 7/1/2017 8/15/2017 11/9/2017 | P | P | P | EP2157: 340B Pharmacy Ceiling Price
| 7/1/2017 8/15/2017 11/9/2017 | P | P | P | EP2159: Short Cycle Billing
| 7/1/2017 8/15/2017 11/9/2017 | P | P | P | EP2155: Drug Termination Date
| 8/1/2017 11/30/17 3/1/2018 7/1/18 1/1/19 | 8 | 8 | 8 | State issues policy guidance on repricing Pharmacy claims retro to 04/01/2017
| 2017-08-01 | P | P | P | Provider Communication
| 2017-09-01 | P | P | P | CMS Approval of SPA | Verbal Approval Not posted on web yet
| 9/1/2017 11/9/17 | P | P | P | Implement/Go Live New Pharmacy Reimbursement
| 2017-09-15 | P | P | P | Assure NYMISS Alignment and Readiness
| 10/1/201711/30/17 3/1/2018 7/1/18 1/1/19 | 8 | 8 | 8 | Reprice retro claims
| 10/1/201711/30/17 3/1/2018 7/1/18 1/1/19 | 8 | 8 | 8 | Monitor/Ongoing
10411 |  |  |  |  | Project Name: Change Copayment for Brand Drugs Division Lead: DPDM Team Lead: Carol Lindley Additional Staff: Bonny DeCastro, Monica Toohey, Janet Zachary-Elkind, Justin Seastrum Description: Change copayments for brand name drugs (other than BLTG drugs) to $2.50 | 0 | Effective Date: 7/23/18 Budget Neutral
ADMINISTRATIVE
| 2017-04-20 | P | P | P | Obtain enabling legislation
| 2017-05-03 | P | P | P | Draft State Plan Amendment
| 2017-05-03 | P | P | P | Submit State Plan Amendment for Internal Review |  | 5/18/17 - with DOB
| 2017-06-12 | P | P | P | Submit State Plan Amendment to CMS
| 8/11/2017 10/16/17 12/31/2017 03/31/2018 | _ | _ | _ | State Plan Approval |  | Per CMS, SPA approval is being held until State takes specific actions in submitting a waiver of comparability re: copay (MMC members do not pay a copay for medical services, only pharmacy.) Waiver packet submitted to CMS 3/20/2018. CMS will discuss internally at what part of the Waiver review process the copay SPA can be approved.
NOTIFICATIONS
| 2017-05-12 | P | P | P | Determine if notification letter is required to beneficiaries |  | Per DLA, we must notice both FFS and MCO.
| 2017-05-30 | P | P | P | Determine strategy and process for noticing. Prferred sources unable to complete tasks; will need to issue an IFB
| 2017-06-30 | P | P | P | Develop IFB
| 9/15/2017 10/16/17 12/31/17 1/31/2018 | P | P | P | Receive IFB and Beneficiary Letter Approvals |  | Approval received on March 14th.
| 11/14/2017 1/15/18 2/9/18 5/1/2018 5/31/18 | P | P | P | Issue IFB |  | Issued March 24.
| 11/22/2017 2/26/18 7/1/2018 7/26/18 8/24/18 | P | P | P | Evaluate Bids
| 1/16/2018 3/12/18 8/1/18 10/15/18 11/15/2018 | 8 | 8 | 8 | Award Recommendation/Selection |  | Waiting for BOC to send comments on VAP.
| 6/12/2018 8/12/2018 11/1/2018 12/01/2018 2/1/2019 | 8 | 8 | 8 | Contract Approval
| 5/30/17 7/10/17 | P | P | P | Initiate coordination efforts with Medicaid mainstream managed care plans
| 2017-05-30 | P | P | P | Draft beneficiary coverage letter
| 2017-06-05 | P | P | P | Submit beneficiary coverage letter to DLA for approval |  | DLA approval received with IFB Approvals as noted above on March 14th.
| 7/14/2017 6/1/2018 12/1/2018 2/15/2019 | 8 | 8 | 8 | Submit Medicaid Update article to alert prescribers/pharmacies
| 2017-07-14 | P | P | P | Approved beneficiary notification translated. A one-page language assistance availability notice will be included with each letter, with a phrase regarding where to call for assistance in understanding the Notice (Medicaid Helpline - Maximus) written in English and 7 additional languages.
| 7/21/18 8/15/18 1/2/19 | 8 | 8 | 8 | Initiate printing and mailing of beneficary notification
| 7/21/17 6/15/18 8/15/18 1/2/19 | 8 | 8 | 8 | Provide Medicaid Helpline staff training information
| 8/4/17 6/29/18 8/29/18 1/16/19 | 8 | 8 | 8 | Develop GIS for LDSS
| 8/4/17 6/29/18 8/29/18 1/16/19 | 8 | 8 | 8 | Determine changes needed for eMedny website and provider manuals
| 8/4/17 6/29/18 8/29/18 1/16/19 | 8 | 8 | 8 | Determine changes needed for DOH/pharmacy website
EVOLUTION
| 2017-05-24 | P | P | P | Determine FFS System Modifications Required
| 2017-05-31 | P | P | P | Initiate Evolution Project |  | No EP needed
| 6/7/17 7/2/18 9/3/18 1/16/19 | 8 | 8 | 8 | Submit Evolution Project Transmittal Letter
| 2017-08-09 | 8 | 8 | 8 | Test for systems |  | No testing required.
| 9/1/17 7/23/18 9/24/18 1/23/19 | 8 | 8 | 8 | Implement Evolution Project Change in Co-Pay
10412 |  |  |  |  | Project Name: Enhanced Program Integrity for Opioids/Controlled Substances Division Lead: Janet Zachary-Elkind Team Lead: Tracy Berger Additional Staff: John Naioti, Monica Toohey, Kelly Kimball (OMIG), Steve Feuerstein, Walter Gibson (UB), Kendra Griffin (HID) Description: This proposal will build on the State’s effort to combat the opioid crisis by: - enabling the Commissioner of Health to terminate or suspend provider’s Medicaid enrollment where there is a preponderance of evidence of inappropriate or overprescribing of opioids to Medicaid members; and - aligning refill-too-soon edits with New York State Controlled Substance regulation by decreasing the amount of controlled substance medication a patient can have on hand (from 10 days to 7 days), consistent with NY State Controlled Substance Law. | -0.19628 | Effective Date: 7/1/17
PROGRAM DEVELOPMENT
| 2017-04-14 | P | P | P | Submit systems project to adjust calims editing to allow a refill of a controlled substance to occur no greater than a cumulative 7 days early over a 90 day period |  | Monica Toohey
NOTIFICATIONS
| 2017-04-01 | P | P | P | Send opioid guideline educational letter to high opioid prescribers. |  | Monica Toohey
| 2017-06-15 | P | P | P | Develop and distribute Medicaid Update and comunications to inform stakeholders about the tightened early fill time frame for controlled substances. |  | Toohey/Berger
IMPLEMENTATION
| 7/1/2017 9/1/2017 10/1/2017 02/22/2018 | P | P | P | Implement claims editing to allow a refill of a controlled substance to occur no greater than a cumulative 7 days early over a 90 day period | * project submitted waiting on programing -Implementation set for 2/22/18
| 2017-07-13 | P | P | P | Meet with OMIG to discuss project
| 7/1/2017 7/15/2017 7/27/2017 8/15/2017 | P | P | P | Obtain and evaluate MED report and >7day supply prescriber list from UB (monthly) (quarterly) |  | Tracy Berger
| 7/1/2017 7/15/2017 7/27/2017 8/15/2017 | P | P | P | Obtain and evaluate opioid PA frequency by provider report from MMA share with OMIG as indicated. (monthly) (quarterly) |  | Tracy Berger
| 2017-07-26 | P | P | P | Meet with HID to discuss case review and top opioid prescriber list
| 7/1/2017 7/15/2017 7/27/2017 8/5/2017 | P | P | P | Utilizing retro-DUR identify high opioid prescribers using ICER criteria and send to UB for review. (Monthly) |  | John Naioti
| 2017-09-15 | P | P | P | Meet with UB and OMIG to discuss UB Case reports
| 7/1/2017 7/15/2017 7/27/2017 8/2017 9/15/2017 | P | P | P | Evaluate UB case review and share with OMIG as indicated (Monthly) |  | Berger/Naioti
| 8/1/2017 9/15/2017 10/15/2017 | P | P | P | Obtain and evaluate high opioid prescriber list from HID UB (quarterly)- |  | Berger/Naioti
| 8/1/2017 10/01/2017 | P | P | P | Work with OMIG to determine status of identified prescribers (Monthly) |  | Berger/Naioti
[5 empty] | POST IMPLEMENTATION |  | John Naioti
| 7/1/2017 8/1/2017 9/15/2017 10/1/2017 11/01/2017 | P | P | P | • Review high prescriber report -% opioid claims by prescriber (UB) • Evaluate MED report from UB • Evaluate >7day supply prescriber list from UB • Evaluate PA frequency data (MMA) • Monitor opioid utilization via ICER (HID/UB) Share reports with OMIG as indicated (Quarterly) |  | Berger/Naioti
| 10/15/2017 11/20/2017 12/15/2017 | P | P | P | Work with OMIG to determine status of identified prescribers (Monthly) |  | Berger/Naioti
| 2/15/2018 3/15/2018 | P | P | P | Review 4Q17 Reports • high prescriber report -% opioid claims by prescriber (UB) • Evaluate MED report (UB) • Evaluate >7day supply prescriber list (UB) • Evaluate PA frequency data (MMA) • Monitor opioid utilization via ICER (HID/UB) Share reports with OMIG as indicated (Quarterly) |  | Berger/Naioti
| 2018-03-31 | P | P | P | Send 2 targeted letters 1- high volume opioid prescribers 2-High dose opioid prescribers |  | Berger
| 3/15/2018 4/15/2018 6/30/18 | P | P | P | Work with OMIG to determine status of identified prescribers (Monthly) |  | Berger/Naioti
| 6/30/2018 7/30/2018 8/15/2018 | P | P | P | Work with Michelle Griguts, DDS to send targeted letter to high volume opioid prescribing dentists and oral surgerons
| 2018-09-05 | P | P | P | Send High volume and high dose prescriber lists to MPEP via Barb Rogler, UB fo reducational consideration
| 3/31/2018 10/01/2018 12/1/2018 | 8 | 8 | 8 | Summary of FY 2017 |  | Berger/Naioti
| 6/15/2018 7/5/2018 | P | P | P | Review 1Q18 Reports Share reports with OMIG as indicated (Quarterly) |  | Berger/Naioti
| 2018-07-15 | P | P | P | Work with OMIG to determine status of identified prescribers (Monthly) |  | Berger/Naioti
| 2019-04-15 | 8 | 8 | 8 | Summary of FY 2018 |  | Berger/Naioti
| 2019-04-15 | 8 | 8 | 8 | Summary and Close out of Project
10413 |  |  |  |  | Project Name: Conduct Comprehensive Clinical Editing Division Lead: DPDM Team Lead: Monica Toohey Additional Staff: Tracy Berger, Janet Zachary-Elkind Description: Expands point-of-sale pharmacy claims editing to medical claims, to ensure appropriate utilization. | -0.35 | Effective Date: 4/1/17
PROGRAM DEVELOPMENT
| 2017-04-01 | P | P | P | Identify targeted drug(s) & supplies for clinical drug edits
| 2017-04-27 | P | P | P | Begin working with Health Information Designs to develop clinical editing (phased in approach)- 1st edit to implement 7/1/17
| 2017-05-19 | P | P | P | Review with Magellan Medicaid Administration the PA criteria
| 6/7/2017 7/6/17 | P | P | P | Review language for the call center PA process & PA website document
| 6/15/2017 7/13/17 | P | P | P | Review & test phase 1
| 2017-07-20 | P | P | P | Phase 1 edit to implement
| 2018-03-18 | P | P | P | Draft Medicaid Update
| 2018-04-05 | P | P | P | Review & test Phase 2
| 2018-04-05 | P | P | P | Review with Magellan Medicaid Administration the PA criteria & review language for the call center PA process & PA website document
| 8/3/2017 9/14/17 1/6/18 2/8/18 3/6/18 4/19/18 | P | P | P | Phase II edit to implement
| 9/20/2018 9/28/2018 | P | P | P | Phase III edit to implement
| 8/3/2017 9/14/17 1/6/18 2/8/18 3/6/18 | 8 | 8 | 8 | Determine next edit to implement & how to approach (Phase II)
IMPLEMENTATION
| 7/1/2017 7/20/17 | P | P | P | Phase 1 go-live
POST IMPLEMENTATION
| 7/1/2017 7/20/17 | P | P | P | Monitor drug utilization and claims data (Monthly)
| 2018-05-18 | P | P | P | Monitor drug utilization and claims data (Monthly) Phase 2
| 2019-01-15 | 8 | 8 | 8 | Monitor drug utilization and claims data Phase 3

## Compete Plans
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2017-2018 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
[5 empty] | Project Name: DOH Global Cap Admin Division Lead: DEPS Team Lead: Jacqueline McGovern Additional Staff: Geza Hrazdina Description: This proposal would reduce the funding associated with the OHIP State operations budget in order to achieve necessary savings in SFY 17-18. | -8 | No WP Needed
[5 empty] | Project Name: Reduce Supportive Housing Division Lead: DLTC Team Lead: Denard Cummings Additional Staff: Liz Misa, Andrew Segal Description: This proposal would reduce the Medicaid Redesign Team (MRT) Supportive Housing Program by $20 million. In order to achieve savings, this proposal would delay the development of any new programs and restrict growth of existing housing programs to their current levels. | -20 | No WP Needed
[5 empty] | Project Name: Reduce VAPAP/VBP-QIP Division Lead: OPCHSM Team Lead: Additional Staff: D. Sheppard Description: This proposal would reduce funding for VAPAP/VBP-QIP. | -15 | No WP Needed
[5 empty] | Project Name: Essential Plan Cost Sharing requirements Division Lead: DEMI Team Lead: Additional Staff: Judy Arnold Description: The Executive agrees to maintain the current level of Essential Plan cost sharing requirements from enrollees for State Fiscal Year 2018 that were applicable the previous year. |  | No WP Needed
[5 empty] | Project Name: Medicare Part B and Part D Increases Division Lead: DFRS Team Lead: Additional Staff: John Ulberg Description: This proposal would pay for increased Medicare Part B and Part D costs. Medicare Part B costs are expected to increase by 10% and Medicare Part D clawback costs are expected to increase by 11.93% in CY 2017. | 175.4 | No WP Needed
[5 empty] | Project Name: ACA Overclaim Repayment Division Lead: DFRS Team Lead: Additional Staff: John Ulberg Description: This proposal extends the repayment to CMS from 2 to 3 years. | 59 | No WP Needed
[5 empty] | Project Name: Mental Hygiene Stabilization Fund Division Lead: DFRS Team Lead: Additional Staff: John Ulberg Description: | -267 | No WP Needed
[5 empty] | Project Name: Reduce MLTCP Quality Bonus Division Lead: DFRS Team Lead: Laura Grassman Additional Staff: John Ulberg, Dan Carmody Description: This proposal is to reduce the total current Quality funding projection of $150 million awarded to Partial Capitation, PACE and MAP managed long term care (MLTC) programs to $120 million. The Department is exploring operationalizing this reduction as an adjustment to the quality award for lower performing quality tiers. | -15 | No WP Needed
[5 empty] | Project Name: Emergency Department Rate Reductions Division Lead: DFRS Team Lead: Additional Staff: John Ulberg Description: The Department will not reduce Medicaid payment rates for certain conditions being treated in a hospital emergency room, as had been proposed by the Executive. The negotiated budget provides Medicaid funding for this purpose. |  | No WP Needed
[5 empty] | Project Name: VBP Implementation/Targeted Provider Rate Increase Division Lead: DFRS Team Lead: Additional Staff: John Ulberg, Greg Allen Description: | 0 | Effective Date: 4/1/17 No WP Needed
[5 empty] | Project Name: Women's Health and Prenatal Care Pilot Division Lead: DPDM Team Lead: Melissa Kinnicutt Additional Staff: Greg Allen, Connie Donohue Description: In the event that federal financial participation is not available pursuant to paragraph (ee) of subdivision 2 of section 365-a of the social services law, the Department of Health will establish a Women’s Health and Prenatal Care Pilot program, utilizing such appropriated funds. Within appropriated amounts, the Department will make available funds necessary for the Pilot Program to provide medical assistance to women for certain infertility services and shall include the coverage of a set of services to ensure improved outcomes of women who are in the process of treatment with ovulation enhancing drugs, limited to the provision of such treatment, office visits, hysterosalpingogram services, pelvic ultrasounds, and blood testing; services will be limited to those necessary to monitor such treatment. The Department shall fund the Pilot Program within as many of the 50 zip codes in this State that have the highest incidence of multiples births in the preceding five years, as funds may permit. The Department shall make funds available for such Pilot Program as necessary to implement the program or up to $5 million dollars annually, whichever is less. The Pilot program shall commence in the event that the federal financial participation for such services in the Medicaid program is not available. |  | Merged with 10401; No WP Needed
[5 empty] | Project Name: Adult Day Health Care Transportation Division Lead: DPDM Team Lead: Mark Bertozzi Additional Staff: Greg Allen, Andrew Segal Description: The Executive will refrain from taking administrative actions intended to carve out the provision of Medicaid transportation from the ADHC programs reimbursed to manage their own transportation to Fee For Service under the administration of the State's transportation manager during State Fiscal Year 2018. |  | No WP Needed
[5 empty] | Project Name: Transportation Manager Savings Division Lead: DPDM Team Lead: Mark Bertozzi Additional Staff: Greg Allen, Liz Misa Description: Savings will achieved from the competitive re-procurement of the NYC Medicaid Transportation Management contract at a reduced price. | -8 | Completed: April 2017 No WP Needed

## Boo Yah
Boo-Yah!