## MRT Proposals Project Workplan
MRT Proposals Project Management Plan
Short Title: | Rate Reform
Long Title: | Provider Rate Reform
Organization: | DHCAA
Lead: | Jim Johnston
Strategic Alignment:
Description: | Reform Provider Rates to achieve DHCAA goals. Provider value-driven health care within the framework of addressing the Medicaid budget challenge. Reduce utilization of discretionary, low-value health care services and increase access to necessary, high-value health care.
Outcome Measures: | >Budget savings (approx. $600 million AF). >Provide more efficient health care. >Improve member health care outcomes.
Assumptions & Notes: | 1) Design, Development and Testing Processes Can Begin Immediately Following HP Receipt of Detailed Requirements from the State. 2) For items where requirements are not completed and HP has not yet estimated Design, Development, and Implementation, UAT is estimated for approximately 4 weeks prior to implementation date. All UAT Dates indicate the estimated earliest "start" date for UAT. 3) Implementation dates are targeted dates to achieve the savings target amount; if implementation date changes, savings target will likely need to be revised.
Milestones: | Date | Schedule | Budget | Risk | Description | State Savings 2011-12 ($millions) | Change Indicator | Change Description | Information for Team Leads | Information for Team Leads | Information for Team Leads
Key: |  |  |  |  | P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
MRT# 5 |  |  |  |  | Project Name: Reduce and Control Utilization of Certified Home Health Agency Services Division Lead: DHCF Team Lead: Charles Tobey Add'l Staff: Tim Casey Description: To control utilization and reduce costs, the proposal will transition long-term CHHA patients to Managed Long Term Care. | -100
PER-PATIENT SPENDING LIMITS:
| 2011-03-15 | P | P | P | Request updated CHHA paid claims data for base year (CY 2009)
| 2011-03-22 | P | P | P | Determine if preliminary caps will be implemented by adjusting provider rates or provider payments.
| 2011-03-30 | P | P | P | Calculate Provider Caps and interim rate/payment adjustments.
| 2011-04-01 | P | P | P | Work with BHOFA staff to prepare necessary State Plan Amendment materials.
| 2011-04-01 | P | P | P | Determine if regulations are needed for Provider Caps - if so, work with legal staff to prepare regs. and determine public notice requirements.
| 2011-04-11 | P | P | P | 10 days after legislation approved: Send Dear Administrator Letter to providers regarding caps (if/when budget approved).
| 2011-04-15 | P | P | P | Work with DOH Division of Systems and eMedNY staff to determine systems requirements.
| 2011-04-19 | P | P | P | Submit State Plan Amendment 11-50 to BHOFA for processing to CMS.
| 2011-04-29 | P | P | P | Contact DOH Managed Care staff to discuss potential issues involving accelerated movement of LT patients from CHHAs to MLTC.
| 2011-05-15 | P | P | P | Distribute additional data used in calculation of caps to providers via HCS website.
| 2011-05-25 | P | P | P | Meet with Division of Systems and Medicaid Financial Management to discusss recoupment issues/strategy.
| 2011-07-15 | 8 | 8 | 8 | When CMS approval is received, implement payment reductions on eMedNY.
| 2011-10-01 | 8 | 8 | 8 | Perform preliminary reconciliation for 4/1/11-6/30/11 and inform providers of results.
| 2012-01-01 | 8 | 8 | 8 | Preliminary reconciliation for 4/1/11-9/30/11.
| 2012-04-01 | 8 | 8 | 8 | Preliminary reconciliation for 4/1/11-12/31/11.
| 2012-07-01 | 8 | 8 | 8 | Preliminary reconciliation for 4/1/11-3/31/12.
| 2012-10-01 | 8 | 8 | 8 | Final reconciliation for 4/1/11-3/31/12 - calculate actual savings vs. target.
EPISODIC PAYMENT SYSTEM:
| 2011-05-15 | P | P | P | Work with BHOFA staff to prepare necessary State Plan Amendment materials.
| 2011-06-01 | 8 | 8 | 8 | Determine if regulations are needed for Provider Caps - if so, work with legal staff to prepare regs. and determine public notice requirements.
| 2011-06-01 | 8 | 8 | 8 | Submit State Plan Amendment.
| 2011-07-01 | 8 | 8 | 8 | Determine systems requirements.
| 2011-07-01 | 8 | 8 | 8 | Meet with industry representatives to plan for testing and provider software requirements.
| 2011-08-01 | 8 | 8 | 8 | Design, configuration, testing
| 2011-10-01 | 8 | 8 | 8 | Finzalize base price, CMI etc. from base year data (2009).
| 2012-03-01 | 8 | 8 | 8 | Transmit episodic rates and other required data to eMedNY.
| 2012-04-01 | 8 | 8 | 8 | Implement episodic system.
| 2012-01-01 | 8 | 8 | 8 | Evaluate data from first six months of episodic system - estimate savings.
| 2012-07-01 | 8 | 8 | 8 | Evaluate date from full year of new system - compare savings to target.
MRT# 6 |  |  |  |  | Project Name: Reduce Medicaid Managed Care and Family Health Plus Profit (from 3% to 1%) Division Lead: DMC Team Lead: Paul Souliske Add'l Staff: James DeMatteo Description: Reduce the profit component included in the plan rates from 3% to 1% for the Medicaid and Family Health Plus Managed Care Programs. | -94
Revise Part 98-1.11(b) & (e)
| 2011-03-11 | P | P | P | Submitted regulatory Concept Paper to Regulatory Affairs Unit (RAU)
| 2011-03-16 | P | P | P | Present Concept Paper to Regulatory Affairs Committee
| 2011-04-22 | P | P | P | Prepare Regulatory package and submits to RAU
| 2011-04-29 | P | P | P | RAU Submits Reg Package to DLA for approval |  |  |  |  | Maintenance
| 5/20/2011 6/8/11 | 8 | 8 | 8 | RAU seeks Commissioner's approval and files rule with Dept of State |  |  |  | On hold: Discussions between Gov's office and SID
| 5/31/2011 6/22/11 | 8 | 8 | 8 | Dept of State publishes Notice of Emergency Adoption in NYS Register
Calculate Revised Premium Rates
| 2011-08-01 | 8 | 8 | 8 | Implement all changes to rates effective 4/1/11 (marketing, trend reduction, surplus reduction, inpatient changes, etc) & add pharmacy to 10/1/11 rates
| 2011-08-15 | 8 | 8 | 8 | Submit Rates to DOB for approval
| 2011-09-12 | 8 | 8 | 8 | DOB Approval
| 2011-09-19 | 8 | 8 | 8 | Mercer rate certification letter
| 2011-09-26 | 8 | 8 | 8 | Submit to CMS for approval
| 2011-10-24 | 8 | 8 | 8 | Mail/Post rates after CMS approval and all needed changes have been made to model contract and 1115 waiver (see MRT 1458)
MRT# 10 |  |  |  |  | Project Name: Eliminate Marketing Costs From Medicaid Managed Care and Family Health Plus Premiums Division Lead: DMC Team Lead: Adella Lamb Additional Staff: James DeMatteo Description: Eliminate the marketing component from the Medicaid and Family Health Plus Rates | -22.5
Calculate Revised Premium Rates (note completion of premium rate changes will reflect impact of multiple MRTs)
| 2011-03-16 | P | P | P | meet with trade associations todiscuss marketing carve-out
| 2011-04-01 | P | P | P | calculate marketing carve-out component from rate
| 2011-08-01 | 8 | 8 | 8 | Implement all changes to rates effective 4/1/11 (marketing, trend reduction, surplus reduction, inpatient changes, etc)
| 2011-08-15 | 8 | 8 | 8 | Submit Rates to DOB for approval
| 2011-09-12 | 8 | 8 | 8 | DOB Approval
| 2011-09-19 | 8 | 8 | 8 | Mercer rate certification letter |  |  |  |  | Maintenance
| 2011-09-26 | 8 | 8 | 8 | Submit to CMS for approval
| 2011-10-24 | 8 | 8 | 8 | Mail/Post rates after CMS approval and all needed changes have been made to model contract and 1115 waiver (see MRT 1458)
Revise Model Contract
| 4/1/2011 6-1-11 | 8 | 8 | 8 | Send marketing notice to plans and counties
| 4/1/2011 6-1-11 | 8 | 8 | 8 | Prior approval of contract to CMS
| 6/1/2011 7-1-11 | 8 | 8 | 8 | Section 11 and Appendix D revisions of model contract approved by by OSC
MRT #11 |  |  |  |  | Project Name: Bundle Pharmacy into Medicaid Managed Care Division Lead: DFPP Team Lead: Kim Leonard Additional Staff: Susan Barth, Adella Lamb, Jennifer Dean Description: Move the NYS Medicaid Pharmacy program under the management of Medicaid managed Care to leverage additional clinical and fiscal benefits | -50
ADMINISTRATIVE
| 2011-04-01 | P | P | P | Obtain enabling legislation |  |  |  | Completed
| 2011-03-10 | P | P | P | Determine Federal Public Notice needs |  |  |  | Not required per CMS
| 2011-03-10 | P | P | P | Amend 1115 Waiver for MMC |  |  |  | CMS has informed us that an amendment to the 1115 waiver does not have to be made
| 2011-03-10 | P | P | P | Amend 1115 Waiver for Family Health Plus |  |  |  | CMS has informed us that an amendment to the 1115 waiver does not have to be made
EVOLUTION
| 2011-03-28 | P | P | P | Submit evolution project |  |  |  | System requirements: edit to direct claims to MMC/FHP plans, submission of pharmacy claim data to MMC/FHP plans, process for recipiet of MMC/FHP pharmacy encounter claims, ability to pay E-Prescribing incentive to prescribers/pharmacies, eligibility information.
| 2011-05-15 | P | P | P | Submit system change request to eliminate CBIC cards for FHP beneficiaries |  |  |  | Discontinue cards for case type 24 and use card code X
| 2011-06-15 | 8 | 8 | 8 | Coordinate pharmacy claim data exchange with MMC/FHP plans |  |  |  | *Claim data transfer to allow DUR, transisition - plans receive weekly pharmacy data
| 2011-08-19 | 8 | 8 | 8 | Establish process for pharmacy encounter data submission to fiscal agent |  |  |  | Contract changing to require weekly feeds
| 2011-10-01 | 8 | 8 | 8 | Implement EP1605 Bundle Pharmacy into Medicaid Managed Care |  |  |  | FRD meeting held 4/12/11
| 2011-10-01 | 8 | 8 | 8 | Process for payment of electronic prescribing incentive |  |  |  | NCPDP RX Origin Code incldued in data exchange file layout
PROGRAM DEVELOPMENT
| 2011-04-20 | P | P | P | Begin ongoing MMC Operational Issues Conference Calls |  |  |  | Briefed health plans
| 2011-05-02 | P | P | P | Determine scope of benefits for MMC |  |  |  | Discussion to include the following: family planning (concern with Catholic based plans), hearing aid batteries, enteral nutrition, over the counter products (including emergency contraception), prenatal vitamins, insulin and diabetic supplies, and clotting factor products
| 2011-05-02 | P | P | P | Determine scope of benefits for FHP |  |  |  | Discussion to include the following: family planning (concern with Catholic based plans), hearing aid batteries, enteral nutrition, over the counter products (including emergency contraception), prenatal vitamins, insulin and diabetic supplies, and clotting factor products
| 2011-05-13 | P | P | P | Identify transition issues |  |  |  | *Special populations,-hemophilia
| 2011-05-20 | P | P | P | Establish transition policy and guidance |  |  |  | Comments due 4/27 for Draft document
| 2011-05-27 | P | P | P | MMC/FHP transition procedures/policies and timeline issued to plans
| 2011-06-01 | P | P | P | Notification to Medicaid Prescriber Education Program |  |  |  | PEP outreach to MC medical directors. Supplied with listing of plans & medical directors. Plan for outreach in development
| 2011-07-01 | P | P | P | MMC/FHP ID card issuance |  |  |  | *Plans will determine need for cards. Contract requires the use of CIN on all cards issued after 10/1/2004
| 2011-07-01 | 8 | 8 | 8 | Assess necessary cost report changes
| 2011-07-06 | 8 | 8 | 8 | Require transition policy/identification of issues from MMC/FHP plans
| 2011-07-06 | 8 | 8 | 8 | State to evaluate transition plan for coverage and access
| 2011-07-06 | 8 | 8 | 8 | MMC/FHP evaluation of pharmacy data file by MMC/FHP plans to ensure transition |  |  |  | Plans should identify/propose solutions (target prescribers, patient outreach, etc)
| 2011-07-27 | 8 | 8 | 8 | State review/approval of transition plan completed
| 2011-08-12 | 8 | 8 | 8 | Evaluate plan contractual requirements |  |  |  | Mail order, third party liability, short cycle dispensing, medicare cross over billing, etc.
| 2011-09-02 | 8 | 8 | 8 | Develop Emergency process for at counter issues
| 2011-09-02 | 8 | 8 | 8 | Provide pharmacy providers with MC/FHP billing information |  |  |  | *Guidance will include BIN and PCN#s for billing MC plans
| 2011-10-01 | 8 | 8 | 8 | Implement cost report changes
CONTRACT
| 2011-06-10 | 8 | 8 | 8 | Notification of contract changes to MMC plans
| 2011-06-10 | 8 | 8 | 8 | Notification of contract changes to FHP plans
| 2011-08-01 | 8 | 8 | 8 | Recalculate MMC & FHP rates to include pharmacy benefit. See MRT #6 for complete schedule. |  |  |  | *Deadline is subject to change based on other items impacting the rates (i.e. inpatient rates).
| 2011-08-05 | 8 | 8 | 8 | Amend MMC contracts to include pharmacy benefit
| 2011-08-05 | 8 | 8 | 8 | Amend FHP contracts to include pharmacy benefit
| 2011-10-01 | 8 | 8 | 8 | Implement cost report changes
ELIGIBLITY
| 2011-08-05 | P | P | P | Establish an eligiblity feed to MMC plans
| 2011-08-05 | P | P | P | Establish an eligiblity feed to FHP plans
| 2011-09-02 | 8 | 8 | 8 | Determine eligible MMC population (including guarantee MMC)
| 2011-09-02 | 8 | 8 | 8 | Determine eligible FHP population (including guarantee FHP)
NOTIFICATIONS
| 2011-04-08 | P | P | P | Determine if "reduction of benefits" letter is required to beneficiaries |  |  |  | REQUIRED
| 2011-05-15 | P | P | P | Develop modifications for beneficiary coverage letter
| 2011-06-06 | 8 | 8 | 8 | Participate in FE Conference Call
| 2011-07-01 | 8 | 8 | 8 | Develop beneficiary notification |  |  |  | In progress
| 2011-07-01 | 8 | 8 | 8 | Participate in MTAG conference call with LDSS
| 2011-07-08 | 8 | 8 | 8 | Submit Medicaid Update article to alert prescribers/pharmacies
| 2011-07-08 | 8 | 8 | 8 | Develop poster/notification for MNY update
| 2011-07-22 | 8 | 8 | 8 | Approved beneficiary notification translated
| 2011-08-05 | 8 | 8 | 8 | Develop GIS for LDSS
| 2011-08-05 | 8 | 8 | 8 | Notification to Facilitated enrollers
| 2011-08-05 | 8 | 8 | 8 | Notify SUNY FE trainers of program changes
| 2011-08-05 | 8 | 8 | 8 | Notification to other state programs
| 2011-08-12 | 8 | 8 | 8 | Determine changes needed for MMC/FHP website
| 2011-08-12 | 8 | 8 | 8 | Determine changes needed for eMedny website and provider manuals
| 2011-08-12 | 8 | 8 | 8 | Determine changes needed for DOH/pharmacy website
| 2011-08-12 | 8 | 8 | 8 | Determine changes for MMC brochures, materials, etc…
| 2011-08-12 | 8 | 8 | 8 | Determine changes for FHP brochures, materials, etc…
| 2011-09-02 | 8 | 8 | 8 | Mail beneficary notification
REBATE COLLECTION
| 2011-04-15 | P | P | P | Establish rebate workgroup to include DFPP, CSC, MC staff
| 2011-08-05 | 8 | 8 | 8 | Guidance to plans regarding forumulary development and management
| 2011-08-05 | 8 | 8 | 8 | Establish process for OBRA rebate program administration
| 2011-08-05 | 8 | 8 | 8 | Determine process for rebate collection
| 2011-08-05 | 8 | 8 | 8 | Identify MMC/FHP data encounter contacts needed for data issues
| 2011-08-26 | 8 | 8 | 8 | Process for MMC/FHP plans to provide drug data
| 2011-08-26 | 8 | 8 | 8 | Data extract process
| 2011-09-09 | 8 | 8 | 8 | Process to create and mail invoices
| 2011-09-09 | 8 | 8 | 8 | Process for dispute resolution
| 2011-09-16 | 8 | 8 | 8 | Notification to drug manufacturers
| Ongoing | 8 | 8 | 8 | Identify financial management/oversight/reporting issues
MRT #13 |  |  |  |  | Project Name: Preschool/School Supportive Health Services (SSHSP) Cost Study Division Lead: DFPP Team Lead: Constance Donohue Description: Increase federal Medicaid funding by determining actual costs incurred by school districts and counties in providing SSHSP services including transportation | -50 | Constance Donohue (cld03) 6-9512
| 2011-01-11 | P | P | P | Draft Article VII language
| 2011-02-28 | P | P | P | Transmit final Article VII language to DOB
| 2011-03-15 | P | P | P | Begin drafting solicitation documents
| 2011-03-30 | P | P | P | Public Notice date |  |  |  | Time line would be affected if competitive bid is required
| 2011-04-01 | P | P | P | Authorizing legislation passed
| 2011-05-10 | P | P | P | Submit B-1184
| 2011-05-16 | 8 | 8 | 8 | Initiate clearance process
| 5/6/2011 5-20-11 6-7-11 | 8 | 8 | 8 | Post solicitation documents on DOH website |  | Time line would be affected if competitive bid is required
| 5/13/2011 5/27/11 6-14-11 | 8 | 8 | 8 | Bidders' questions due
| 5/13/2011 6-1-11 | 8 | 8 | 8 | Targeted SPA submission date
| 5/20/2011 6-3-11 6-21-11 | 8 | 8 | 8 | DOH responds to bidders' questions
| 6/6/2011 6-20-11 7-8-11 | 8 | 8 | 8 | Proposals due (30 days)
| 6/27/2011 7-15-11 | 8 | 8 | 8 | DOH completes review/evaluation of proposals
| 7/1/2011 7-22-11 | 8 | 8 | 8 | DOH internal approval/contractor; sign contract
| 7/2/2011 7-25-11 | 8 | 8 | 8 | Meet with contractor/contractor work begins
| 7/8/2011 8-1-11 | 8 | 8 | 8 | Submit (transportation) study design to CMS for review per SPA #09-61
| 7/15/2011 8-1-11 | 8 | 8 | 8 | Conduct cost study (contractor; coordinate with State Education Department)
| 8/22/2011 8-29-11 | 8 | 8 | 8 | Evaluate findings, develop updated SSHSP rates as appropriate
| 9/1/2011 9-10-11 | 8 | 8 | 8 | Submit updated proposed rates to CMS
| 2011-09-15 | 8 | 8 | 8 | Update rates in eMedNY
| 2011-09-15 | 8 | 8 | 8 | Notify SSHSP providers of new payment rates
| 2011-09-30 | 8 | 8 | 8 | SPA approved
| 2011-10-01 | 8 | 8 | 8 | Implement new payment rates
MRT# 14 |  |  |  |  | Project Name: Restructure Reimbursement for Proprietary Nursing Homes Division Lead: DHCF Team Lead: Cynthia Treis Description: Effective April 1, 2011 eliminate all equity payments from the capital component of Nursing Home rates | 32.1 |  |  |  | Maintenance
| 2011-04-01 | P | P | P | Set up designated Capital Rate set for 2011 Rates effective April 1, 2011
| 2011-05-13 | P | P | P | On or before this date receive feedback from Industry about potential alternatives
| 2011-06-01 | 8 | 8 | 8 | Submit SPA for CMS approval (SPA #11-49) NOTE: No Regs Required - this action requires resolution from the Industry about finding other resources/options to mitigate or eliminate the impact of this proposal - Industry due date is April 25, 2011 |  |  |  | BHFOA Contact Sarah Atkinson
| 7/1/111 | 8 | 8 | 8 | Revise rates to reflect industry feedback / final decisions
| 2011-07-15 | 8 | 8 | 8 | Prepare DOB Schedule and DOB Memo
| 2011-07-15 | 8 | 8 | 8 | Prepare Draft Dear Admin letter to NHs advising them of rate change
| 2011-07-15 | 8 | 8 | 8 | Upon CMS approval of SPA Submit DOB Schedule and DOB Memo for J.Ulberg, J. Helgerson, and DOB Approval
| 2011-08-01 | 8 | 8 | 8 | Upon CMS approval Send Rate Schedule to EMEDNY
| 2011-08-01 | 8 | 8 | 8 | Mail DAL letter to NHs notifying of rate change
MRT #15 |  |  |  |  | Project Name: Consolidate all Pharmacy FFS Proposals into a Comprehensive Reform Package Division Lead: Divison of Financial Planning & Policy (DFPP) Team Lead: Mary Carroll Description: Consolidates all pharmacy fee-for-service proposals into one reform package which includes several initiatives that optimize rebate opportunities, reduce waste, rationalize coverage and reimbursement, or remove statutory limits that drive cost. | -59.1
| 2011-04-01 | P | P | P | Proposal 15-A (see below)
| 2011-04-01 | P | P | P | Proposal 15-B (see below)
| 2011-08-01 | ▲ | ▲ | ▲ | Proposal 15-C (see below) |  |  |  |  | Maintenance
| 2011-05-01 | P | P | P | Proposal 15-E (see below)
| 2011-10-01 | 8 | 8 | 8 | Proposal 15-F (see below)
| 2011-10-01 | 8 | 8 | 8 | Proposal 15-G (see below)
| 2011-10-01 | 8 | 8 | 8 | Proposal 15-H (see below)
| 2011-10-01 | 8 | 8 | 8 | Proposal 15-I (see below)
| 2011-11-01 | 8 | 8 | 8 | Proposal 15-J (see below)
| 2011-12-01 | 8 | 8 | 8 | Proposal 15-K (see below)
| 2012-01-01 | 8 | 8 | 8 | Proposal 15-L (see below)
MRT# 15C |  |  |  |  | Project Name: Reduce Pharmacy Reimbursement & Dispensing Fees Division Lead: DFPP Team Lead: Mary Carroll Description: Reduction in pharmacy ingredient cost and dispensing fee reimbursement amounts to align with levels achieved in other State Medicaid Programs and commercial payers. | -30.2
| 2011-04-01 | P | P | P | Obtain enabling legislation to reduce reimbursement & fees. |  |  |  | Executive language accepted.
| 2011-04-01 | P | P | P | Obtain legislation to eliminate HIV Specialty Pharmacy designation and associated higher drug reimbursement. |  |  |  | Executive language accepted.
| 2011-04-15 | P | P | P | Draft State Plan Amendment (SPA) (Program impact statement & State Plan Review Summary) |  |  |  | Complete.
| 2011-04-25 | P | P | P | Workgroup to determine strategy and timing for rate reduction |  |  |  | Staff from DFPP/DOB/DOIT
| 2011-05-01 | P | P | P | Determine staffing needs. |  |  |  | No additional staffing requirements.
| 2011-05-01 | P | P | P | Meet with regulated parties (PSSNY, chains) |  |  |  | Discussion with PSSNY & NACDS 4/12- f/u to be scheduled week of 5/2
| 2011-05-01 | P | P | P | Submit final SPA package |  |  |  | With State Plan Coordinator
| 2011-05-15 | P | P | P | Establish Average Acquisition Cost (AAC) workgroup
| 2011-07-01 | 8 | 8 | 8 | Revise reimbursement methodology in claims system |  |  |  | To be done internally by DFPP staff
| 2011-07-01 | 8 | 8 | 8 | Revise dispensing fees in claims system |  |  |  | To be done internally by DFPP staff
| 2011-04-15 | P | P | P | Meet with staff from ADAP re: HIV Specialty Pharmacy. |  |  |  | Notification/discussion with C Rivera
| 6/1/2011 6-15-11 | 8 | 8 | 8 | Notify stakeholders through Medicaid Update article and Provider letters
| 6/1/2011 6-15-11 | 8 | 8 | 8 | Update DOH website "Pricing Methodology"
| 2011-07-01 | ▲ | ▲ | ▲ | Obtain SPA approval
| 2011-07-01 | ▲ | ▲ | ▲ | Implement |  |  |  | Savings are based on 4/1/11 implementation. Staff have developed a plan that will achieve the savings based on a 4/1 date.
| 2011-07-01 | 8 | 8 | 8 | Establish potential process for retroactive pricing adjustment to achieve savings estimate, if decision is made to retroactively apply reductions |  |  |  | SPA submission prior to 6/30/11 will be retro to first day of submission quarter (4/1).
| 2011-09-01 | 8 | 8 | 8 | Determine final payment for HIV pharmacy and notify FMG to make payment. |  |  |  | collect data from current HIV pharmacy and compute payment.
| 2011-10-01 | 8 | 8 | 8 | Implement AAC reimbursement methodology
MRT# 15F |  |  |  |  | Project Name: Implement a Voluntary Mail Order Program Division Lead: DFPP Team Lead: Mary Carroll Description: Create a mail order pharmacy benefit for maintenance drugs, to take advantage of higher discounts. | -5
| 2011-04-15 | P | P | P | Determine need for regulatory changes. [Any willing provider] |  |  |  | Complete
| 2011-05-01 | P | P | P | Identify staffing needs
| 2011-05-01 | P | P | P | Develop reimbursement rates for VMO pharmacies BRAND: AWP-20% or WAC - 4% (dispensing fee $3.50) GENERIC: The lower of AWP-25%, Federal Upper Limit (FUL), State Maximum Allowable Cost (SMAC), usual and customary, or Average Acquisition Cost (dispensing fee $1.00) |  |  |  | Brand-AWP-20% (3.50 dispensing). Generic- retail price (2.00 dispensing)
| 2011-05-31 | P | P | P | State Plan Amendment (per CMS "any willing, qualified provider") |  |  |  | With State Plan Coordinator
| 5/15/2011 6-1-2011 | P | P | P | Submit regulatory package |  |  |  | In executive clearance process
| 5/15/2011 6-1-2011 | 8 | 8 | 8 | Develop credentialing criteria and provider agreements |  |  |  | Work with enrollment
| 2011-06-01 | 8 | 8 | 8 | Make change to DOH policy
| 2011-06-01 | P | P | P | Identify systems impact. System enhancements will be required to ensure that VMO pharmacies are identified and paid at appropriate rate. |  |  |  | EP 1606 submitted
| 2011-08-01 | 8 | 8 | 8 | Work with DLA to notify legislature of reimbursement rate for VMO
| 2011-10-01 | 8 | 8 | 8 | Notify stakeholders via Medicaid Update article, e-blasts, etc.
| 2011-10-01 | 8 | 8 | 8 | Implement systems enhancements and appropriate reimbursement rates |  |  |  | working with DOIT
MRT# 15G |  |  |  |  | Project Name: Eliminate Part D Drug Wrap in Medicaid Division Lead: DFPP Team Lead: Mary Carroll Description: Eliminate Medicaid coverage and reimbursement of drugs that are available to Medicaid/Medicare dual eligible beneficiaries through their Medicare Part D plans. | -2.8
| 2011-04-01 | P | P | P | Obtain enabling legislation. |  |  |  | Executive language accepted.
| 2011-04-01 | P | P | P | Determine system impact. Modification to Medicare edit to eliminate bypass. |  |  |  | EP 1604 submitted, bundled with 15i.
| 2011-04-01 | P | P | P | Identify staffing needs. |  |  |  | To be completed by existing staff.
| 2011-09-01 | 8 | 8 | 8 | Develop beneficiary "Reduction in Benefit Notice" and schedule mailing |  |  |  | Drafted. Needs approval by DLA. Would like to send in coordinated notifications with other MRTs
| 2011-09-01 | 8 | 8 | 8 | Notify stakeholders via Medicaid Update article, e-blasts, etc.
| 2011-09-01 | 8 | 8 | 8 | Develop GIS for local districts |  |  |  | Will be sent by DCLDR
| 2011-09-01 | 8 | 8 | 8 | Communicate with stakeholders (SOAF,HIICAP,MRC,PSSNY,MSSNY,OMRDD, OMH, GNYHA, etc)
| 2011-09-01 | 8 | 8 | 8 | Develop and provide information materials for DOH provider and beneficiary call centers
| 2011-10-01 | 8 | 8 | 8 | Implement system and program changes |  |  |  | work with DOS
MRT# 15H |  |  |  |  | Project Name: Prior Authorization for Exempt Drug Classes Division Lead: DFPP Team Lead: Mary Carroll Description: Allow prior authorization under the Preferred Drug Program (PDP) for the following drug classes: anti-depressants, atypical anti-psychotics, anti-retrovirals and immunosuppressants. | -6.4
| 2011-04-01 | P | P | P | Obtain enabling legislation. |  |  |  | Executive language accepted.
| 2011-04-01 | P | P | P | Determine system impact. |  |  |  | Change in PA code can be done by DFPP staff
| 2011-05-01 | P | P | P | Create workgroup to identify savings opportunities, strategy and P&TC timeline.
| 2011-06-01 | P | P | P | Notify stakeholders via Medicaid Update article, e-blasts, etc. |  |  |  | To be done in conjunction with P&TC notices for June 16th P&TC meeting
| 2011-07-01 | 8 | 8 | 8 | Develop operational procedures for prior authorization that will minimize impact.
| 2011-08-15 | 8 | 8 | 8 | Revise PDL removing PA prohibition language from class and re-post.
| 2011-09-01 | 8 | 8 | 8 | Implement system changes to allow grandfathering for patients stabalized on non-preferred and to lengthen the time a PA is valid for to 1 year.
MRT# 15I |  |  |  |  | Project Name: Implement Preferred Drug Program prior authorization requirements based on effective date Division Lead: DFPP Team Lead: Mary Carroll Description: Accelerate the collection of rebates through immediate enforcement of a drug's non-preferred status. | -0.39
| 2011-04-01 | P | P | P | Identify sytems impact. Will require change to enforce PA requirements based on effective date of PA code rather than date written. Work with DOS. |  |  |  | EP 1604 submitted- bundled with 15g.
| 2011-09-01 | 8 | 8 | 8 | Notify stakeholders (prescribers, pharmacies, manufacturers) via Medicaid Update article, e-blasts, etc.
| 2011-10-01 | 8 | 8 | 8 | Implement system changes to correctly enforce PA requirements based on effective date of PA code.
| 2011-10-01 | 8 | 8 | 8 | Develop method to track savings. |  |  |  | Work with current PBM.
MRT# 15J |  |  |  |  | Project Name: Reimbursement Changes for Clotting Factor Products Division Lead: DFPP Team Lead: Mary Carroll Description: Change the reimbursement methodology for clotting factor products to pay at the lesser of acquisition cost or the Medicaid established state maximum allowable cost (SMAC). | 0
| 2011-05-01 | P | P | P | Develop specialized pricing and appeals process. |  |  |  | Will use "lower of" acquisition cost or SMAC (currently provided by the Hemophilia consortium)
| 2011-05-01 | P | P | P | Identify systems impact. Will require change to identify clotting factor and reimburse using appropriate methodology. Will need to develop acquisition cost field and pricing calculation. Work with DOS. |  |  |  | EP 1610 submitted 3/28/11.
| 2011-05-01 | P | P | P | Identify staffing needs |  |  |  | No additional staff.
| 2011-10-01 | 8 | 8 | 8 | Communicate with stakeholders (beneficiaries with hemophilia, prescribers and pharmacy providers)
| 2011-11-01 | 8 | 8 | 8 | Implement system/reimbursement changes |  |  |  | Work with DOS
MRT# 15K |  |  |  |  | Project Name: Limit opioids to a four prescription fill limit every thirty days. Division Lead: DFPP Team Lead: Mary Carroll Description: Limit opioid prescriptions to a four prescriptions fill limit every thirty days for Medicaid beneficiaries. | -0.2
| 2011-04-01 | P | P | P | Obtain enabling legislation. |  |  |  | Executive language accepted.
| 2011-04-01 | P | P | P | Identify systems impact. Consider up front clinical editing system.
| 2011-04-01 | P | P | P | Identify staffing needs |  |  |  | Appeals pharmacist is in place under current PBM contract. Additional State staff requirements under review.
| 2011-06-01 | P | P | P | Develop authorization procedures for exceptions
| 2011-06-01 | P | P | P | Develop Fair Hearing process |  |  |  | Process set in statute
| 2011-09-01 | 8 | 8 | 8 | Notify stakeholders (prescribers, pharmacies, manufacturers) via Medicaid Update article, e-blasts, etc.
| 2011-10-01 | 8 | 8 | 8 | Implement system edit
MRT# 15L |  |  |  |  | Project Name: Proper disposal of unused meds and waste reduction through short cycle dispensing and re-dispensing Division Lead: DFPP Team Lead: Mary Carroll Description: Ensure the appropriate disposal and/or return of unused medications and require long term care (LTC) pharmacies to dispense in quantities less than 30 days | -0.8
| 2011-05-01 | P | P | P | Identify systems impact. Requires changes to allow "partial fill, " capture NCPDP short cycle billing fields, edit to require short cycle for LTC and apply appropriate dispensing fees. Will also need editing to enforce short cycle dispensing. EP have to included NCPDP fields once they are identified by established workgroups. System will be modeled after Part D 2012 project. |  |  |  | EP 1608 submitted 3/28/11.
| 2011-05-01 | P | P | P | Identify staffing needs
| 2011-06-01 | P | P | P | Determine need for regulatory changes related to returned meds
| 2011-07-01 | P | P | P | Review and identify impact of federal ACA guidelines |  |  |  | Final Rule published 4/15/11
| 2011-07-01 | 8 | 8 | 8 | Collaborate with OMIG regarding MRT#154 "return to stock"
| 2011-10-01 | 8 | 8 | 8 | Notify stakeholders |  |  |  | work with OLTC.
| 2011-11-01 | 8 | 8 | 8 | Communicate procedural changes to providers through Medicaid Update, e-blasts, etc.
| 2011-12-01 | 8 | 8 | 8 | Update provider manuals for pharmacy and LTC
| 2012-01-01 | 8 | 8 | 8 | Implement
MRT# 17 |  |  |  |  | Project Name: Reduce fee-for-service dental payment on select procedures Division Lead: DFPP Team Lead: Alan Maughan Description: Fee-for-service dental payments should be reduced to match rates paid by managed care providers on high volume dental procedures. | -27.7
| 2011-03-21 | P | P | P | Identify average Manage Care payment for dental procedures billed in NYS Medicaid in CY 2009
| 2011-05-14 | P | P | P | Notify NYSDA, NYSADCs, and Oral Health Coalition of need for final comments by 5-16-11 - no additional comments were received.
| 5/1/2011 5-16-11 | P | P | P | Finalize reduced dental fee schedule and provide to DPRUM and provider associations
| 2011-05-18 | P | P | P | Load fees into eMedNY (retro to 5/15/11)
| 5/1/11 5/19/11 | P | P | P | Implement effective 5/15/11
| 5/15/2011 5/27/2011 | 8 | 8 | 8 | Notify providers via Medicaid Update and eMedNY Provider Communications
| 2011-06-15 | 8 | 8 | 8 | Reprocess affected claims back to 5/1/11
MRT# 21 |  |  |  |  | Project Name: Streamline the Processing of Nursing Home Rate Appeals Division Lead: DHCF Team Lead: Steve Simmons Description: Streamline the processing of nursing home rate appeals by prioritizing and amending processing timeframes, authorizing negotiated settlements, and temporarily capping the annual dollar amount of appeals authorized to be processed | -35 |  |  |  | Maintenance
| Ongoing | P | P | P | Continue to update tracking mechanism to monitor appeal expenditures for compliance with $80M cap
| Ongoing | P | P | P | Establish a list of "priority appeals" (budget to cost based appeals, remaining old 1983 rebasings, large capital projects etc.) that are not negotiated settlement candidates
| Ongoing | P | P | P | Update criteria to identify financially challenged/unstable facilities (update for 2010 cost report when available - around October)
| 2011-03-17 | P | P | P | Distribute draft appeals settlement agreement with OMIG. OMIG will review and respond on or before April 13, 2011 quarterly meeting.
| 2011-05-01 | P | P | P | Identify next 25 homes to begin the negotiated settlement process with (Department is in the process of doing a pilot test settlement for two homes)
| 5/15/11 6-1-11 | 8 | 8 | 8 | Finalize "negotiated settlement" document language with both DOH counsel and OMIG, Meet with DAL counsel on 5/3
| 5/15/11 6-1-11 | 8 | 8 | 8 | Expand number of staff working on the "settlement team"
| 2011-05-24 | P | P | P | Begin to contact the homes on the list of 25 to discuss negotiated settlement process, identify agreed to list of open appeals etc.
| 2011-06-01 | 8 | 8 | 8 | Expand list to 50 homes
| 2011-06-08 | 8 | 8 | 8 | Send a letter to the 50 homes seeking letter of interest, their list of outstanding appeals (within 15 days of receipt), and within 40 days estimates of the value of each outstanding appeal
| 2011-06-08 | 8 | 8 | 8 | Finalize negotiated settlement agreement with OMIG
| 2012-03-01 | 8 | 8 | 8 | Draft Regulation to amend processing timeframes for appeals
MRT # 24 |  |  |  |  | Project Name: Payment for Enteral Formula with Medical Necessity Criteria Division Lead: DPRUM Team Lead: Jonathan Bick Description: Provide coverage of enteral formula to individuals who cannot obtain nutrition through any other means | -14.7
Legislative Change
| 2011-04-01 | P | P | P | Legislation enacted
Federal Public Notice
| 2011-03-09 | P | P | P | Draft to DHCF
| 2011-03-30 | P | P | P | Published
State Plan Ammendment
| 2011-03-25 | P | P | P | Draft to DHCF
| 2011-04-01 | 8 | 8 | 8 | Effective
| 2011-06-30 | 8 | 8 | 8 | Last approval date
Regulation Change
| 2011-03-16 | P | P | P | Identify and discuss with legal
| 2011-03-21 | P | P | P | Draft to legal
| 2011-05-01 | P | P | P | Emergency Rule Adopted |  |  |  | Will be published in 4/27/11 State Register, effective 5/1/11
Staff Training
| 2011-04-15 | P | P | P | Prior Approval procedures
| 2011-04-15 | P | P | P | Pended claims procedures
| 2011-04-15 | P | P | P | Provider Inquiries
| 2011-04-15 | P | P | P | CSC Call Center
System Changes
| 2011-03-18 | P | P | P | Identify procedure file changes required |  |  |  | No procedure file changes needed - will be handled in PA system changes.
| 2011-04-01 | P | P | P | PA Routing |  |  |  | EP submitted for systematic routing, will be done manually until EP implementation
Prior Authorization System Changes
| 2011-01-31 | P | P | P | Identify changes required
| 2011-02-07 | P | P | P | Estimate from contractor
| 2011-03-21 | P | P | P | Secure funding
| 2011-04-15 | P | P | P | Develop and test changes
| 2011-05-02 | P | P | P | Implement changes
Provider Notification
| 2011-03-21 | P | P | P | Develop langauge for coverage criteria and notification
| 2011-03-25 | P | P | P | Notify provider associations
| 2011-04-15 | P | P | P | Pharmacy and DME emedny.org communication
| 2011-04-15 | P | P | P | eMedNY Listserv, DME and Pharmacy email
| 2011-04-01 | P | P | P | Provider Manual - Fee Schedule update
| 2011-04-27 | P | P | P | Provider Manual - Procedure Section update
MRT# 25 |  |  |  |  | Project Name: Remove Physician Component from Ambulatory Patient Group (APG) Base Rates Division Lead: DFPP Team Lead: Alan Maughan Description: Remove physician related reimbursement from hospital ambulatory patient groups (APGs) payment/rate structure. | -14.25
| 2011-06-01 | 8 | 8 | 8 | CMS approval of additional APG investment
| 2011-06-08 | 8 | 8 | 8 | Upon CMS approvale of additional APG investment, identify and remove physician component from APG calculation and calculate new base rates
| 2011-06-15 | 8 | 8 | 8 | Notify providers associations and providers of new base rates
| 2011-06-15 | 8 | 8 | 8 | Submit package to DOB
| 2011-07-06 | 8 | 8 | 8 | DOB approves rate package
| 2011-08-15 | 8 | 8 | 8 | Implement (load rates into eMedNY-retroactive to 4/1/11) July-August 2011
MRT# 26 |  |  |  |  | Project Name: Utilization Controls on Behavioral Health Clinics Division Lead: DFPP Team Lead: Alan Maughan Description: Under this proposal, mental hygiene clinic rates would be subject to either provider specific or patient specific utilization standards or thresholds. | -13.3
| 2011-03-12 | P | P | P | Receive draft proposals from Mental Hygeine Agencies
| 2011-03-14 | P | P | P | Begin drafting required EP, SPA, Regulation changes (responsibility of Mental Hygiene Agencies), and Federal Public Notice
| 2011-03-15 | P | P | P | Submit Public Notice
| 2011-03-29 | 8 | 8 | 8 | Submit final EP to eMedNY (EP would only apply to patient speciifc thresholds)
| 2011-05-15 | 8 | 8 | 8 | Notify providers via Medicaid Update and eMedNY Provider Communications
| 2011-05-16 | P | P | P | Submit SPA
| 2011-05-30 | 8 | 8 | 8 | Finalize proposals from Mental Hygeine Agencies
| 5/15/2011 6/1/11 | 8 | 8 | 8 | Calculate standards or thresholds (responsibility of Mental Hygiene Agencies)
| 5/1/2011 6-1-11 | 8 | 8 | 8 | Submit Regualtion
| 5/15/2011 6-15-11 | 8 | 8 | 8 | EP or rate adjustments completed and submitted to DOS for systems work
| 6/1/2011 6-15-11 | 8 | 8 | 8 | Implement retroactive to 4/1/11 (pending SPA approval)
MRT# 29 |  |  |  |  | Project Name: Reduce Transportation Costs through Regional Management Recommended Targeted Fee Actions Division Lead: DFPP Team Lead: Mark Bertozzi Add. Staff: Tim Perry-Coon Description: Achieve savings by State procurement of regional transportation management | -30.5
Medicaid Transportation Management Initiative below:
| 2010-11-19 | P | P | P | Hudson Valley Transportation Management Procurement - posted on website
| 2011-04-15 | P | P | P | Selection of Hudson Valley management contractor
| 2011-04-30 | P | P | P | Negotiate Hudson Valley Contractor Bid
| 2011-05-03 | P | P | P | Hudson Valley Contractor Award
| 2011-05-20 | P | P | P | Hudson Valley Contractor submits required Work Plan
| 2011-05-25 | 8 | 8 | 8 | DOH Approves Hudson Valley Contractor Work Plan
| 2011-06-01 | 8 | 8 | 8 | Begin Implementation of Hudson Valley management contract
| 2011-07-01 | 8 | 8 | 8 | Carve out transportation from managed care - Hudson Valley
| 2011-04-15 | P | P | P | NYC Transportation Management Procurement - posted on website |  |  |  |  | Maintenance
| 2011-07-29 | 8 | 8 | 8 | Selection of NYC management contractor
| 2011-08-12 | 8 | 8 | 8 | Negotiate NYC Contractor Bid
| 2011-08-19 | 8 | 8 | 8 | NYC Contractor Award
| 2011-09-02 | 8 | 8 | 8 | NYC Contractor submits required Work Plan
| 2011-09-09 | 8 | 8 | 8 | DOH Approves NYC Contractor Work Plan
| 2011-09-16 | 8 | 8 | 8 | Begin Implementation of NYC management contract
| 2011-10-01 | 8 | 8 | 8 | Carve out transportation from managed care - NYC
| 2011-10-03 | 8 | 8 | 8 | Rest-of-State Transportation Management County Participation
| 2011-10-07 | 8 | 8 | 8 | Determine Rest-of-State method of procurement (new FAS? / other method?)
| 2011-11-15 | 8 | 8 | 8 | Implement Rest-of-State procurement
| 2011-12-01 | 8 | 8 | 8 | Carve out transportation from managed care - Rest-of-State
Medicaid Transportation fee changes below:
| 2011-05-15 | P | P | P | Medicaid Update to Reduce ambulette dialysis fee to ADHC fee drafted
| 2011-06-01 | 8 | 8 | 8 | Reduce ambulette dialysis fee to Adult Day Home Care (ADHC) fee
| 2011-04-01 | P | P | P | Freeze transportation fees at the 4/1/11 level, with limited exceptions
| 2011-12-01 | 8 | 8 | 8 | Hudson Valley , ROS managers development of group rides to major medical centers
| 2011-04-29 | P | P | P | Approval of action plan to redirecting "frequent flyer" 911 users of ambulance transportation to the appropriate transportation mode.
| 2011-06-01 | P | P | P | Implement redirecting "frequent flyer" 911 users of ambulance transportation to the appropriate transportation mode. |  |  |  | Estimated at $5 M annually for 860 enrollees with 30 + trips in 2010
MRT # 30 |  |  |  |  | Project Name: Prescription Footwear Payment and Coverage Division Lead: DPRUM Team Lead: Jonathan Bick Description: Update the Medicaid footwear benefit coverage and payment methodology, reducing over utilization and administrative burden | -7.17
Legislative Change
| 2011-04-01 | P | P | P | Legislation enacted
[5 empty] | Federal Public Notice |  |  |  |  | Maintenance
| 2011-03-09 | P | P | P | Draft to DHCF
| 2011-03-30 | P | P | P | Published
State Plan Ammendment
| 2011-03-25 | P | P | P | Draft to DHCF
| 2011-04-01 | 8 | 8 | 8 | Effective
| 2011-06-30 | 8 | 8 | 8 | Last approval date
Regulation Change
| 2011-03-16 | P | P | P | Identify and discuss with legal
| 2011-03-21 | P | P | P | Draft to legal
| 2011-04-01 | P | P | P | Emergency Rule Adopted |  |  |  | Will be published in 4/27/11 State Register, benefit limit effective 4/1/11, MRA effective 5/1/11
Staff Training
| 2011-03-25 | P | P | P | Update Prior Approval procedures
| 2011-03-25 | P | P | P | Update pended claims procedures
| 2011-03-25 | P | P | P | Provider Inquiries
| 2011-03-25 | P | P | P | CSC Call Center
System Changes
| 2011-03-18 | P | P | P | Identify procedure file changes required
| 2011-03-31 | P | P | P | Update procedure file with benefit paramters
| 2011-04-30 | P | P | P | Update procedure file with new pricing methodology effective 5/1/11
| 2011-04-01 | P | P | P | PA Routing
Provider Notification
| 2011-03-21 | P | P | P | Develop langauge for coverage criteria and notification
| 2011-03-25 | P | P | P | Notify provider associations
| 2011-04-01 | P | P | P | Pharmacy and DME emedny.org communication
| 2011-04-01 | P | P | P | eMedNY Listserv, DME and Pharmacy email
| 2011-04-01 | P | P | P | Provider Manual - Fee Schedule update
| 2011-04-27 | P | P | P | Provider Manual - Procedure Section update
| 2011-04-20 | P | P | P | Solicit MRA input from associations
| 2011-05-01 | P | P | P | Implement new MRA's
MRT #34 |  |  |  |  | Project Name: Establish Utilization Limits for Physical Therapy, Occupational Therapy, and Speech Therapy Division Lead: DFPP Team Lead: Constance Donohue; Additional Staff: Mike Dembrosky Description: Establish utilization limits for physical therapy, occupational therapy, speech therapy (speech-language pathology) for practitioners and clinics. | -2.47
| 2011-01-11 | P | P | P | Draft Article VII language
| 2011-03-09 | P | P | P | Draft Federal public notice
| 2011-03-30 | P | P | P | Federal Public Notice
| 2011-04-01 | P | P | P | Prepare State Plan Amendment
| 2011-04-01 | P | P | P | Targeted SPA submission date
| 2011-04-01 | P | P | P | Authorizing language passed
| 2011-04-15 | P | P | P | Initiate preparation of Evolution Project Request (EPR) to effect systems (eMedNY) changes
| 2011-04-30 | P | P | P | Meet with provider representative groups (e.g., NYSSLHA, NYSOTA, NYSPTA) |  |  |  | Met with JH
| 2011-05-04 | P | P | P | Meet with NYSSLHA representatives
| 2011-05-05 | P | P | P | Contact Medicaid Matters to schedule meeting |  |  |  | Contacted L Kassel, Meeting TBA
| 5/7/2011 6/10//11 | 8 | 8 | 8 | Respond to any requests for additional information |  |  |  | Informal follow up questions received from CMS 5/24/11
| 2011-07-31 | 8 | 8 | 8 | Update provider manuals
| 2011-09-01 | 8 | 8 | 8 | Post updated provider information/prepare Medicaid Update
| 2011-10-01 | 8 | 8 | 8 | Implement changes
MRT #37 |  |  |  |  | Project Name: Eliminate Case Mix Adj for AIDS Nursing Svcs in CHHA and LTHHCP Programs Division Lead: DHCF Team Lead: Tim Casey with Charles Tobey Description: Eliminate separate rate adjustment for AIDS Nursing Services provided under the CHHA and LTHHCP Programs | -2.01
| 2011-04-15 | P | P | P | Process annual 2011 "standard" (non-AIDS) Nursing per visit rates for LTHHCP's. Prepare DOB package.
| 2011-04-19 | P | P | P | Submit State Plan Amendment 11-53 to BHOFA for processing to CMS. |  |  |  | BHFOA Contact Sarah Atkinson
| 2011-05-19 | P | P | P | Request BCSD project to modify CHHA/ LTHHCP rate development systems - MMIS transmittal changes to transmit "standard" nursing rates to eMEDNY on AIDS Nursing rate codes
| 2011-06-01 | 8 | 8 | 8 | Process annual 2011 "standard" (non-AIDS) Nursing per visit rates forCHHA's.Prepare DOB package.
| 2011-11-01 | 8 | 8 | 8 | After CMS approval received, Submit Rates for DOH and DOB approvals
| 2011-12-15 | 8 | 8 | 8 | After DOB approval, Transmit "standard" 2011 nursing rates for each provider to eMedNY for loading to the AIDS nursing rate codes retro to statutory eff date of 4/1/11, and post rates and DAL letters to HPN
| 2012-03-01 | 8 | 8 | 8 | Request BCSD project to modify CHHA/ LTHHCP 2011 cost report software to consolidate AIDS and non- AIDS nursing cost for future rate development.
| 2012-09-01 | 8 | 8 | 8 | Request DataMart extract from eMedNY system to track savings target
MRT # 42 |  |  |  |  | Project Name: Stocking coverage Division Lead: DPRUM Team Lead: Jonathan Bick Description: Limit Medicaid coverage for compression stockings to the Medicare criteria and include coverage during pregancy | -0.93 | 2.13 | 2.13
Legislative Change
| 2011-04-01 | P | P | P | Legislation enacted
Federal Public Notice
| 2011-03-09 | P | P | P | Draft to DHCF
| 2011-03-30 | P | P | P | Published
State Plan Ammendment
| 2011-03-25 | P | P | P | Draft to DHCF
| 2011-04-01 | 8 | 8 | 8 | Effective
| 2011-06-30 | 8 | 8 | 8 | Last approval date
Regulation Change
| 2011-03-16 | P | P | P | Identify and discuss with legal
| 2011-03-21 | P | P | P | Draft to legal
| 2011-04-01 | P | P | P | Emergency Rule Adopted |  |  |  | Will be published in 4/27/11 State Register, effective 4/1/11
Staff Training
| 2011-03-25 | P | P | P | Prior Approval procedures
| 2011-03-25 | P | P | P | Provider Inquiries
| 2011-03-25 | P | P | P | CSC Call Center
System Changes
| 2011-03-18 | P | P | P | Identify procedure file changes required
| 2011-03-31 | P | P | P | Update procedure file
| 2011-04-01 | P | P | P | PA Routing
Provider Notification
| 2011-03-21 | P | P | P | Develop langauge for coverage criteria and notification
| 2011-03-25 | P | P | P | Notify provider associations
| 2011-04-01 | P | P | P | Pharmacy and DME emedny.org communication
| 2011-04-01 | P | P | P | eMedNY Listserv, DME and Pharmacy email
| 2011-04-01 | P | P | P | Provider Manual - Fee Schedule update
| 2011-04-27 | P | P | P | Provider Manual - Procedure Section update
MRT# 49 |  |  |  |  | Project Name: Reimburse Art 28 clinics for HIV counseling/testing using APGs Division Lead: DFPP Team Lead: Alan Maughan Description: Medicaid will incorporate payment to Article 28 clinics for HIV counseling and testing services into the Ambulatory Patient Group (APG) payment structure. | -0.2
| 2011-04-11 | P | P | P | Calcute applicable APG rate setting figures and update APG software
| 2011-06-01 | 8 | 8 | 8 | Notify providers via Medicaid Update and eMedNY Provider Communications
| 2011-06-10 | 8 | 8 | 8 | Calculate new FQHC rates and impacts
| 2011-07-01 | 8 | 8 | 8 | Implement in APGs 7/1/11 as discussed with providers and provider assocaitions, no savings possible until Jan 1, 2012
| 2011-08-01 | 8 | 8 | 8 | Notify FQHCs of rate changes
| 2011-10-01 | 8 | 8 | 8 | Implementing new rates for FQHCs
MRT# 54 |  |  |  |  | Project Name: Adjust 340B Drug payment in 340B-eligible clinics via Ambulatory Patient Groups (APGs) Division Lead: DFPP Team Lead: Alan Maughan Description: Adjust payment downward under APGs for 340B Drugs in 340B-eligible clinics comparable to the savings inherent in the 340 B drug benefit program. | -0.25
| 2011-04-12 | P | P | P | Notify Hospital Associations
| 2011-04-19 | P | P | P | Notify providers via eMedNY Provider Communications
| 2011-07-01 | 8 | 8 | 8 | Implement-all systems work already completed as of 3/15/11
MRT #61 |  |  |  |  | Project Name: Home Care Worker Parity Division Lead: OLTC - DHCBS Team Lead: Mary Ann Anglin Additional Staff: Sue Barth, Tim Casey Description: Require living wage for home care workers | 0
| 2011-04-15 | P | P | P | DOH to review and modify if necessary CHHA and MLTC cost report to include wage information necessary to monitor compliance with parity requirement for applicable providers
| 2011-04-15 | P | P | P | OLTC to review and modify if necessary LHCSA statistical report to include wage information necessary to monitor compliance with parity requirment for applicable providers
| 2011-04-22 | P | P | P | Research initiated on local districts with Living Wages re: existing contracting and attestation process
| 2011-05-02 | P | P | P | Convene internal meetings to determine content of guidance to implement parity requirement
| 2011-05-03 | P | P | P | Initate design of attestation form
| 2011-05-15 | P | P | P | Consult with the Department of Labor on developing forms for providers to certify compliance with the parity requirement
| 5/16/2011 6/6/11 | 8 | 8 | 8 | Prepare and share draft attestation form with DLA (internally) |  |  |  |  | Maintenance
| 2011-05-27 | 8 | 8 | 8 | Meet with workgroup to share draft of transition form
| 6/1/2011 6/15/11 | 8 | 8 | 8 | Identify providers that employ home health aides in living wage areas as defined persuant to Art VII language
| 2011-07-01 | 8 | 8 | 8 | Draft forms for provider certification, attestation and reporting related to the parity requirement
| 2011-07-01 | 8 | 8 | 8 | DOH to develop mechanism to determine living wage in respective relevant areas
| 2011-08-01 | 8 | 8 | 8 | Draft a DAL to be issued to impacted providers
| 12/1/2011, 12/1/12, 12/1/13 | 8 | 8 | 8 | DOH to issue official notice of minimum rates of home care aid compensation for each applicable area on December 1 of each year
| annually | 8 | 8 | 8 | DOH to monitor provider compliance via submitted cost reports or other mechanisms
MRT #67 |  |  |  |  | Project Name: Assist Safety Net Providers Division Lead: OHSM Team Lead: Lora Lefebvre Description: Provide a package of assistance to safety providers | 0
| 2011-04-01 | P | P | P | Identify DOH workgroup members needed
| 2011-04-01 | P | P | P | Determine which specific interventions are available after Budget passes: HEAL allocation, Temp operator authority, Anti Trust oversight, workforce retraining funds; nursing home temporary closure rate , capital restructuring
| 2011-04-08 | P | P | P | Convene internal DOH workgroup to develop initiative requirements and process:
| 2011-04-15 | P | P | P | Identify stakeholders to consult - GNYHA, HANYS, Iroquois, NYSHFA, NYAHSA
| 2011-05-06 | P | P | P | Convene meetings for stakeholder input
| 5/20/2011 6-3-11 | 8 | 8 | 8 | Develop defintion of eligible safety provider
| 5/20/2011 6-3-11 | 8 | 8 | 8 | Identify criteria and requirements for provider application to Department
| 2011-06-15 | 8 | 8 | 8 | Determine whether to develop recommendation for consideration by the Public Health and Health Planning Council to establish a Planning entity to assist in application assessment
| 2011-06-15 | 8 | 8 | 8 | Establish Planning entity with PHHPC to assist Department
| 2011-06-15 | 8 | 8 | 8 | Identify DoH process for evaluation of applications and determination of what assistance/intervention will be provided
| 2011-06-15 | 8 | 8 | 8 | Identify DoH resources both data and analysts to review applications
| 2011-06-15 | 8 | 8 | 8 | Identify DoH resources to implement DoH agreed upon interventions
| 2011-06-01 | 8 | 8 | 8 | Develop regs for Nursing Home closure rate establishment
| 2011-06-30 | 8 | 8 | 8 | OHIP to establish MA rates for hospitals-- to assist closures and APG rate enhancement for voluntary inpatient bed reductions
MRT # 68 |  |  |  |  | Project Name: Repatriation of Out-of-State Nursing Home Residents Division Lead: OLTC Team Lead: Jacqueline Pappalardi Add'l Staff: Lydia Kosinski, Charlotte Mason, Teresa Scilipote, Cathleen Bobrick,Valerie Deetz Description: This proposal would identify spending on out-of-state placements and seek to repatriate those individuals within three years. | 0
| 2011-04-01 | P | P | P | Engage internal and external stakeholders to support the repatriation efforts.
| 2011-05-01 | P | P | P | Develop a comprehensive workplan for repatriation of out-of-state nursing home residents. Based on assessment of recipient needs and available/necessary resources, the workplan will include a timeline outlining the action steps and milestones.
| 2011-06-30 | P | P | P | Convene workgroup comprised of staff from the Department of Health, Office of Mental Health and the Office of People with Developmental Disabilities to develop an accurate roster of NYS Medicaid recipients residing in out-of-state nursing homes.
| 2011-08-30 | 8 | 8 | 8 | Calculate potential costs of repatriating recipients and creating additional resources, as needed, to return these individuals to NYS, and identify barriers to achieving repatriation goals.
| 2012-01-01 | 8 | 8 | 8 | Internal workgroup will develop an electronic tracking system correlated with the eMedny program to track placement of Medicaid recipients within the long term care system.
| 2012-04-01 | 8 | 8 | 8 | Develop an incentive plan for NYS long term care providers to facilitate the appropriate placement of residents within NYS.
MRT # 69 |  |  |  |  | Project Name: Uniform Assessment Tool (UAT) for LTC Division Lead: Carla Williams Team Lead: K. John Russell Description: Deliver electronic uniform assessment tool for long term care recipients | 1.85
Development and Testing of Uniform Assessment System
| 2011-04-01 | P | P | P | Department of Health (DOH) submission of GCOM Software contract to Attorney General (AG) for approval.
| 4/11/2011 4/8/11 | P | P | P | AG approval of contract with GCOM Software
| 4/11/2011 4/8/11 | P | P | P | DOH submission of GCOM Software contract to Office of State Comptroller (OSC) for approval (pending AG approval).
| 4/11/2011 4/14/11 4/21/11 | P | P | P | Release announcement of OLTC plans and intentions regarding uniform assessment in NYS.
| 4/1/2011 4/8/11 4/15/11 | P | P | P | Department of Budget (DOB) approval of expenditure (B-1184) for NYSTEC to conduct independent verification & validation (IV&V) of delivered solution from GCOM.
| 4/11/2011 4/29/11 5/11/11 | P | P | P | DOH submission of NYSTEC contract to OSC for approval.
| 5/15/11 4/26/11 | P | P | P | OSC approval of contract with GCOM Software, Inc.
| 5/15/2011 5/24/2011 | P | P | P | OSC approval of contract with NYSTEC
| 2011-05-16 | P | P | P | Technology Project Kick-Off -- pending GCOM and NYSTEC contract approvals by AG and OSC: Project kick-off initiates the software development project with technology vendors at the table. |  |  |  | Formal meeting set for 6/3. | Maintenance
| 2011-06-10 | 8 | 8 | 8 | Computer Readiness Survey to LDSS and Service Providers |  |  |  | Computer readiness survey will inform beta/pilot participation discussion/decision.
| 6/6/2011 6/24/2011 | 8 | 8 | 8 | Identify Beta/Pilot participants
| 2011-07-20 | 8 | 8 | 8 | Completion of Project Iteration #1 Project Planning
| 2011-10-03 | 8 | 8 | 8 | Completion of Project Iteration #2 Technical Architecture
| 2011-12-15 | 8 | 8 | 8 | Completion of Project Iteration #3 interRAI formats and supplements
| 2012-03-13 | 8 | 8 | 8 | Completion of Project Iteration #4 LOC, CAPS, Training, System Performance
| 2012-05-18 | 8 | 8 | 8 | Completion of Project Iteration #5: Beta Test
| 2012-06-15 | 8 | 8 | 8 | Completion of Final Candidate Cycle and System Acceptance
| 2012-08-31 | 8 | 8 | 8 | Completion of Live Pilot
Statewide Implementation and Training for Uniform Assessment
| 2012 | 8 | 8 | 8 | State-wide Implementation Planning - DOH staff started
Development and Testing of Expanded UAT Capabilities (program determination, service planning, case management)
|  | 8 | 8 | 8 | TBD: Project Scope Expansion Analysis and Design for Program Determination, Service Planning, and Case Management
|  | 8 | 8 | 8 | TBD: Iteration(s) for Project Expansion
Statewide Implementation and Training for Program Determination, Service Planning, Case Management
|  | 8 | 8 | 8 | State-wide Implementation Planning
MRT # 70 |  |  |  |  | Project Name: Multi-payer Statewide Patient Centered Medical Home Division Lead: Medical Director/DQE Team Lead: Foster Gesten; Additional Staff: Jackey Matson; Ralph Bielefeldt, Gabrielle Armenia Description: Expand the current Statewide Patient Centered Medical Home Program (PCMH) to more payers. | 8.5
Coordination with Internal Divisions
| 2011-03-11 | P | P | P | CHPLUS INCORPORATION AND PMPM FOR FFS - Meet with CHPlus staff to discuss incorporation of CHPlus. Additional meetings as necessary. |  |  |  | Plans will be required to submit CHPlus PCP rosters. Per member per month payment done outside of capitation payment.
| 2011-03-14 | P | P | P | Determine need for regulation |  |  |  | No
| 2011-04-13 | P | P | P | DUALS-Reach out to relevent DOH staff also involved with duals to begin discussions on coordinating dual initiatives. |  |  |  | Meeting sheduled for 5/13/11.
| 5/1/2011 9/2011 | 8 | 8 | 8 | MULTI-PAYER DEMO: Meet with DMC to discuss plan outreach, rate development, MMCOR reporting |  |  |  | Establish on going meetnigs if necessary. Long-term.
| 5/1/2011 9/2011 | 8 | 8 | 8 | MULTI-PAYER DEMO: Meet with DLA to ensure anti-trust protection. |  |  |  | Met with the group. Focus is on mergers.
| 2011-05-01 | P | P | P | CHPLUS INCORPORATION AND PMPM FOR FFS- Develop overall project design: establish general parameters for provider participation and eligible services; identify internal and external stakeholders; establish payment models: risk adjusted global payments and FFS MH payments; identify systems (EP) needs. |  |  |  | Ongoing
| 2011-05-15 | P | P | P | In conjunction with MRT Proposal #217 create advisory group to the Commissioner consisting of payor and provider participants and stakeholders. Advisory group will focus on both primary care objectives and patient centered medical homes. |  |  |  | Met with Karen and another meeting is scheduled to discuss combining work plans.
| 2011-05-02 | P | P | P | MULTI-PAYER DEMO: Assist DFPP with FAS. |  |  |  | Ongoing
Public Notice
| 2011-03-09 | P | P | P | Draft Public Notice
| 2011-03-29 | P | P | P | Public Notice Issued
State Plan Ammendment
| 2011-03-22 | P | P | P | Draft State Plan Amendment for items: 3) testing new models of payment and 8) changing FFS payment methods. Split SPA for community-based physicians, DTCs, FQHCs and OPDs;
| 2011-04-15 | P | P | P | Submit SPA to CMS |  |  |  | Meeting scheduled with DHCF and DFPP staff to discuss fiscal
| 2011-07-01 | 8 | 8 | 8 | Answer RAIs in a timely manner
| 2011-04-22 | P | P | P | CHPlus - Draft State Plan Amendment
| 2011-05-06 | P | P | P | CHPlus -Submit SPA to CMS
Incorporation of CHPlus into ADK and SW
| 2011-03-01 | P | P | P | CHPlus - Meet with Health Plans and their Associations to discuss proposal
| 2011-03-08 | P | P | P | CHPlus - Begin policy/draft requirements development
| 2011-03-31 | P | P | P | CHPlus- Complete policy/task requirements
| 2011-04-29 | P | P | P | CHPlus - Draft change specifications to MMCOR for cost reporting
| 2011-08-15 | 8 | 8 | 8 | CHPlus - Request updated information on current CHPlus enrollees in medical homes
| 2011-08-01 | 8 | 8 | 8 | CHPlus - Issue ADM informing plans of the project and supporting policies and requirements
| 2011-08-01 | 8 | 8 | 8 | CHPlus Draft changes to Plan Manual and contracts
| 2011-09-01 | 8 | 8 | 8 | CHPlus - Receive CMS SPA approval (required for implementation)
| 2011-09-01 | 8 | 8 | 8 | CHPlus - Compute additional payment and modify pmpm rates effective 10/1/2011
| 2011-10-01 | 8 | 8 | 8 | CHPlus - Implement (effective 10/1/11)(Contingent upon implementation of programmatic requirements in CHPlus)
PMPM For FFS SW and ADK
| 2011-05-15 | P | P | P | Begin to develop, programming and testing of attribution methodology. |  |  |  | ADK attribution methodology applied to non-dual FFS recipients resulting in 24K individuals attributed to a MH provider. Meeting scheduled.
| 2011-06-01 | 8 | 8 | 8 | Submit Evolution Request for FFS PMPM MH payments |  |  |  | Spoke to Mark Malone. Might need to move up date.
| 2011-08-01 | 8 | 8 | 8 | Oversee Evolution Request: Set up and attend meetings as necessary with DOIT and CSC. Review FRD. CSC testing. |  |  |  | Continual monitoring to ensure payments are accurate.
| 2012-01-01 | 8 | 8 | 8 | Implement eMedNY Systems Change - retroactive to 10/1/11 ? |  |  |  | Retroactive may not be necessary if get specs. In. Still need
| 2011-09-01 | 8 | 8 | 8 | Draft Medicaid Update Article for 10/1/11 edition.
Level 3 New Payment Methodologies
| 2011-06-15 | 8 | 8 | 8 | Begin to develop and test risk adjustment payment methodologies
| 2011-06-15 | 8 | 8 | 8 | Begin to establish any necessary data feed from providers or participants
| 2011-08-01 | 8 | 8 | 8 | Modify health plan contracts ??
| 2011-08-01 | 8 | 8 | 8 | Implement changes to MMCOR ??
New Multi-payer Demonstration
| 2011-09-01 |  |  |  | Identify region and possible payers
| 5/15/2011 9/1/2011 | 8 | 8 | 8 | Implementation - Begin to identify DOH (Medicaid/ CHPlus/OHIT/DLA)/SID/GOER/Civil Service workgroup participants. |  |  |  | Establish monthly meetings and conference calls. Establish payor and provider expections with regard to certification, timeframes and payment. (Draft Guidelines for participation.) Advise on implementation of EHR and a multi-payer datawarehouse(?) in order to implement performance measures and P4P. Develop attribution methodology. Advise on risk adjustment.
Evaluation of: SW MH, Multi-payer Demo; New Level Payment Methods
| 2012-01-01 | 8 | 8 | 8 | Develop an evaluation Plan; Contract with an independent evaluator (?) |  |  |  | Note: Baseline QARR and CAHPS rates available for current SW MH.
MRT #82 |  |  |  |  | Project Name: Reduce reimbursement for Hospital Acquired Conditions and Potentially Preventable Negative Outcomes (PPNOs) Division Lead: DHCF Team Lead: Charles Fontenot Additional Staff: Dr. Foster Gesten; Mark Shutts Description: Reduce or deny payment to hospitals for patient conditions acquired while admitted to a hospital | -2
Research and development
HACs | 2011-02-17 | P | P | P | Begin review of Federal policy/draft requirements (CMS HAC Proposed Rule) |  |  |  | Retrieved proposed rule from CMS website initial; analysis of requirements
| 2011-03-11 | P | P | P | Research current Serious Advese Events conditions in relation to HAC conditions |  |  |  | Analyzing how the SAE policy coresponds to the HAC policy
| 2011-03-11 | P | P | P | Research side-by-side comparison of HACs/PPCs/PSIs for veracity and effectiveness as quality indicators and cost containers |  |  |  | Research and review each quality indicator looking for similarities, overlap, and condition specificity that will ensure the fullest measure of quality and safety for patients
| 2011-03-14 | P | P | P | Research and analyze POA requirements for HAC implementation and expansion |  |  |  | Determined status of current POA compliance and effectiveness as relates to current SAE program; appears CMS understands the difficulty in the application of POA as an indicator for HACs and seem to be following NYSs lead on self-reporting and claim review as indicated in the HAC proposed rule; tentative plan for HAC indication is the redaction of the condition via ICD-9 code
| 2011-04-01 | P | P | P | Complete policy definition
| 2011-04-01 | P | P | P | Determine eMedNY systems impacts/requirements
| 2011-04-01 | P | P | P | Design eMedNY systems configuration
| 5/6/2011 5/27/11 | P | P | P | Complete eMedNY system requirements
| 2011-06-01 | 8 | 8 | 8 | Delivery of software from 3M to CSC
| 2011-06-15 | 8 | 8 | 8 | Test eMedNY systems configuration
Communication
| 3/4/2011 3/10/2011 4/21/11 4/28/11 | P | P | P | Internal policy discussions |  |  |  | Discussions focus on current state of SAE program, HAC requirements and strength of PPC concept as an alternative to achieve greater quality, safety, and cost effectiveness
| 3/4/11 4/1/11 | P | P | P | Communications with 3M for APR-DRG grouper changes |  |  |  | Conference call with 3M to explore what APR-DRG grouper changes may be needed to comply with HAC requirement
| 2011-03-11 | P | P | P | Discussions with associations about Present On Admission Indicator compliance (claims data quality issue) |  |  |  | Conference call:Talked about the POA as an indicator for HACs and why some hospitals are have issues on accurate reporting of indicator; associations claim they were unaware of the substantial number of hospitals w/reporting issues
| 2011-03-11 | P | P | P | Communications with HANYS and GNYHA |  |  |  | Conference call with associations to explore the HAC requirement and whether PPCs would be a better alternative; associations split on PPC effectiveness, claiming that following Medicare's lead with AHRQ indicators would be less burdensome on hospitals
| 2011-03-17 | P | P | P | Meeting with 3M and Treo Solutions to discuss comparisons of quality indicators |  |  |  | Data analysis provided reflecting the strengths and weaknesses of the various quality indicators and associated cost effectiveness
| 3/4/11 3/18/11 4/1/11 | P | P | P | Communications with eMedNY to determine systems impacts/requirements |  |  |  | Spoke with Mark(Malone) regarding the implementation of HACS to be effective July 1, 2011. He indicated that if the only change being made was to effectuate a new grouper that suppresses the HAC in grouper assignment, CSC would need the software application no later than June 1. However, we need to discuss the types of output fields that will be incorporated into the grouper since there will be requirements placed on us to identify the type and number of HACS being suppressed.
| 2011-03-18 | P | P | P | Communications with 3M for APR-DRG grouper changes needed to comply with 7/1/11 HAC implementation date and 10/1/11 APR-DRG revison update |  |  |  | In order to meet the needs for July 1, the APR DRG grouper itself will not be returning any HAC information. It will be assumed that the discharged APR DRG will be HAC adjusted based on the data that is passed through it. . However, you will be receiving a separate HAC component that will output HAC related information. I am waiting to hear back from the engineers so that I can provide you with the input and output info that you are requesting for yourself and CSC. For October, the APR DRG grouper will be modified to provide an actual HAC adjusted discharge DRG along with the unadjusted discharge DRG and HAC related output. There are two phases that will need to be addressed, the immediate needs for July and the more involved changes for October.
| 2011-04-01 | P | P | P | Meeting with 3M and eMedNY/CSC to discuss APR-DRG grouper software changes to facilitate 7/1 implementation of HACs |  |  |  | Conference call discussing work requirements and hardware and software strategies to ensure timely compliance with HAC directive on 7/1 and larger issues for APR-DRG grouper updates for 10/1
| 4/4/11 4/11/11 | P | P | P | Communication with Foster Gesten on Serious Adverse Events program implications
| 2011-04-12 | P | P | P | Communicate with Department legal office for statute guidance on HAC program
| 4/15/11 4/29/11 5/6/11 | P | P | P | Meeting with 3M and eMedNY/CSC to discuss APR-DRG grouper software changes to facilitate 7/1 implementation of HACs
Administrative
| 2011-03-08 | P | P | P | Draft Federal Public Notice |  |  |  | Drafted and submitted information describing HAC and PPC program for inclusion to Medicaid Redisgn Team Federal Public Notice
| 2011-03-15 | P | P | P | Review current Serious Adverse Events State Plan Amendment |  |  |  | Reviewed SPA content and determine what changes need to be made for implementing new policy
| 2011-03-30 | P | P | P | Public Notice Issued
| 2011-04-07 | P | P | P | Draft and submit clarifying Federal Public Notice
| 2011-04-27 | P | P | P | Clarifying Federal Public Notice Issued
| 2011-04-01 | P | P | P | Draft State Plan Amendment
| 3/21/11 3/30/11 4/1/11 4/5/11 | P | P | P | Design/Draft/Submit evolution project for eMedNY systems changes
| 2011-04-15 | P | P | P | State Plan Amendment Completed
| 2011-05-23 | P | P | P | Approved Evolution Project FRD
| 2011-05-24 | P | P | P | Completed draft HAC/PPNO regulations
| 2011-06-10 | 8 | 8 | 8 | Recalculate Savings Against Savings Estimate Target
| 2011-06-15 | 8 | 8 | 8 | Submit HAC/PPNO regulation package
| 2011-06-15 | 8 | 8 | 8 | State Plan Amendment submitted to CMS
| 2011-07-01 | 8 | 8 | 8 | HAC Implementation
Research and development
PPNOs | 2011-02-15 | P | P | P | Intenal policy discussions |  |  |  | Discussions focus on current state of SAE program, HAC requirements and strength of PPC concept as an alternative to achieve greater quality, safety, and cost effectiveness
| 2011-03-01 | P | P | P | Begin policy/draft requirements development
| 2011-03-08 | P | P | P | Review literature from other States |  |  |  | Researched PPC experience from other states
| 2011-05-01 | P | P | P | Preliminary analysis of Potentially Preventable Complications (PPC) and Potentially Preventable Readmission (PPR) rates using 2009 paid claims data and 3M software. |  |  |  | Data will be provided by the Bureau of Program Quality Information and Evaluation
| 2011-06-01 | 8 | 8 | 8 | Determine eMedNY systems impacts/requirements
| 2011-06-30 | 8 | 8 | 8 | Metric for tracking savings
Communication
| 2011-04-20 | P | P | P | Meet with Hospital Associations (HANYS and GNYHA) to discuss options to meet savings target |  |  |  | Conference call with associations to explore the HAC requirement and whether PPCs would be a better alternative; associations split on PPC effectiveness, claiming that following Medicare's lead with AHRQ indicators would be less burdensome on hospitals but provide less in the name of quality and cost effectiveness
Administrative
| 2011-03-08 | P | P | P | Draft Federal Public Notice
| 2011-03-30 | P | P | P | Public Notice Issued
| 2011-04-07 | P | P | P | Draft and submit clarifying Federal Public Notice
| 2011-04-27 | P | P | P | Clarifying Federal Public Notice Issued
| 2011-06-01 | 8 | 8 | 8 | Draft State Plan Amendment
| 2011-07-01 | 8 | 8 | 8 | State Plan Amendment Completed
| 2011-07-01 | 8 | 8 | 8 | PPNOs implemented
MRT # 83 |  |  |  |  | Project Name: Expand SBIRT Division Lead: Greg Allen Team Lead: Priscilla Smith Description: Expand SBIRT (Screening, Brief Intervention and Treatment) for alcohol/drug use to allow services in additional settings (hospital ER, clinic and office settings) | (-0.85) | (-0.85) | (-0.85)
| 2011-03-18 | P | P | P | Draft Article 7 language |  | Included in Article 7 Bill
| 2011-04-01 | P | P | P | Obtain legislative approval
| 2011-04-08 | P | P | P | Determine need for EP to add rate codes, set reimbursement amounts and program edits |  | EP not required
| 2011-04-11 | P | P | P | Initiate analysis of impact on MC capitation rates |  | DMC will determine whether rate is changed
| 2011-05-03 | P | P | P | Hold meeting to discuss rates for payment in office settings (APGs already in place for ER/clinic settings)
| 2011-05-14 | P | P | P | Submit draft provider qualifications, billing and and coverage guidance to OASAS |  |  |  | 5/18: Guidance under review by MMC
| 2011-06-01 | 8 | 8 | 8 | Finalize provider qualifications, billing and coverage guidance
| 2011-06-02 | P | P | P | Inititate updates to practioner fee schedules
| 2011-06-15 | 8 | 8 | 8 | Finalize practioner fee schedules
| 2011-08-08 | 8 | 8 | 8 | Publish Medicaid Update and updates to Provider Manuals
| 2011-09-01 | 8 | 8 | 8 | Implement expansion
MRT # 89 |  |  |  |  | Project Name: Health Homes for High Cost, High Need Enrollees Division Lead: DFPP Team Lead: Denise Spor, Add'l Staff: Vallencia Lloyd, Patrick Roohan, Linda Jones, Lauren Tobias Description: Provide care coordination to high cost/need enrollees to reduce cost & hsp admissions, ER visits & admits to SNF | -33.2
Health Home Implementation Phase 1
| 2011-01-11 | P | P | P | Draft Article 7 language
| 2011-03-31 | P | P | P | Submit FPN
| 2011-04-01 | ü | ü | ü | Obtain State legislative authority |  |  |  | HH language in Art. 7
| 2011-04-13 | ü | ü | ü | Meet with NYCHRA, NYCDOHMH, NYC Dept. of Homeless Services, OASAS, and OMH on homelessness and health homes
| 2011-04-14 | ü | ü | ü | Develop central interested parties list to facilitate program updates, solicit suggestions and feedback
| 2011-04-14 | ü | ü | ü | Meet with OMH to discuss approaches for coordinating and integrating programs/services for beneficiaries with mental health illness |  |  |  | additional meetings planned
| 2011-04-20 | ü | ü | ü | Identify workgroup teams and team leaders to address key issues including data, reporting, qualifty measures, HIT, enrollment, etc. |  |  |  | Subgroups will be needed to work on activities related to the patient selection and enrollment, reporting, data exchange, measurement features of health homes, etc.
| 2011-04-20 | ü | ü | ü | Discuss payment methodology & reimbursement for health homes Phase 1 internally
| 2011-04-22 | ü | ü | ü | Explore development of interagency team for health home development & implementation
| 2011-04-22 | ü | ü | ü | Initiate development and design of DOH Health Home website to share program information
| 2011-04-22 | ü | ü | ü | Initiate development of Phase 1 Health Home Program to include CIDP and non-TCM patient populations
| 2011-04-22 | ü | ü | ü | Initiate development of payment methodology and reimbursement amounts for Phase 1 programs
| 2011-04-22 | ü | ü | ü | Initiate identification and development of data requirements for Phase 1
| 2011-04-22 | ü | ü | ü | Initiate identification and development of Phase 1 population selection criteria
| 2011-04-22 | ü | ü | ü | Initiate development of evaluation methodology for Phase 1
| 2011-04-27 | ü | ü | ü | Discuss SPA preprint internally
| 2011-04-29 | ü | ü | ü | Initiate identification and development of federal and State reporting requirements for Phase 1
| 2011-05-03 | ü | ü | ü | Discuss SPA pre-print requirements for quality measures and development of HIT requirements for health homes
| 2011-05-03 | ü | ü | ü | Meet with OPWDD to discuss approaches for coordinating and integrating programs/services for beneficiaries with intellectual/developmental disabilities
| 2011-05-05 | ü | ü | ü | Discuss SPA preprint with TREO
| 2011-05-06 | ü | ü | ü | Initiate discussion on duals
| 2011-05-06 | ü | ü | ü | Meet with OASAS to discuss approaches for coordinating and integrating programs/services for beneficiaries with substance abuse
| 2011-05-06 |  |  |  | Initiate development of a mechanism to accept referrals for a health home from hospitals and other providers
| 2011-05-09 | ü | ü | ü | Meeting with DOH, OMH, OASAS, OPWDD and select providers on development of Health Home Provider Qualifications
| 2011-05-13 | ü | ü | ü | Finalize Health Home website design to share information
| 5/13/2011 5/20/11 |  |  |  | Initiate the development of a process for enrollee auto assignment based on Phase 1 selection criteria
| 2011-05-20 | ü | ü | ü | Finalize a core set of general requirements that applies to all health home providers |  |  |  | Provider qualifications drafted that focus on serving enrollees with behavioral health and/or chronic medical conditions
| 2011-05-23 |  |  |  | Implementation of Health Home website to share information
| 2011-05-25 |  |  |  | Initiate discussion with CMS (Center for Medicare & Medicaid Intervention, Federal Coordinated Health Care Office) on inclusion of dual eligible in HH
| 2011-05-25 | ü | ü | ü | Initiate discussion with CMS on HH model for enrollees with behavorial health and/or chronic medical conditions
| 2011-05-25 | ü | ü | ü | Initiate identification of system needs related to claims editing and payment for Phase 1
| 2011-05-26 | ü | ü | ü | Initiate development of Phase 1 SPA submission
| 2011-06-01 |  |  |  | Finalize set of Phase 1 HH provider specific enrollment and operational requirements
| 2011-06-01 | ü | ü | ü | Finalize draft of payment options and circulate to HCF, MC, DQE for comment
| 2011-06-01 | 8 | 8 | 8 | Finalize Phase 1 population selection criteria
| 2011-06-01 |  |  |  | Finalize process for enrollee auto assignment based on Phase 1 selection criteria
| 2011-06-01 |  |  |  | Finalize draft evaluation methodology for Phase 1
| 5/25/2011 6/2/11 | 8 | 8 | 8 | Initiate discussion with CMS (Center for Medicare & Medicaid Intervention, Federal Coordinated Health Care Office) on inclusion of dual eligible in HH
| 5/23/2011 6/3/11 | 8 | 8 | 8 | Implementation of Health Home website to share information
| 6/1/2011 6/8/11 | 8 | 8 | 8 | Finalize draft evaluation methodology for Phase 1
| 2011-06-10 | 8 | 8 | 8 | Continued discussion with CMS on SPA submission for enrollees with behavioral health and or/chronic medical conditions and to discuss hospital referrals of recipients to health homes requirement
| 2011-06-10 | 8 | 8 | 8 | Discussion with GNYHA and HANYS to discuss procedures for hospital referrals of recipients to health homes
| 2011-06-10 | 8 | 8 | 8 | Finalize initial HIT requirements for health homes
| 2011-06-10 | 8 | 8 | 8 | Finalize system needs related to claims editing and payment for Phase 1
| 2011-06-10 | 8 | 8 | 8 | Finalize federal and State reporting requirements for Phase 1
| 2011-06-10 | 8 | 8 | 8 | Finalize plan to incorporate the dual eligibles in health homes
| 2011-06-10 | 8 | 8 | 8 | Finalize data requirements for Phase 1
| 2011-06-15 | 8 | 8 | 8 | Consult with SAMHSA prior to Phase 1 SPA submission
| 6/1/2011 6/15/11 | 8 | 8 | 8 | Finalize set of Phase 1 HH provider specific enrollment and operational requirements
| 6/1/2011 6/15/11 | 8 | 8 | 8 | Finalize payment methodology and reimbursement amounts for Phase 1 programs
| 6/8/2011 6/20/11 | 8 | 8 | 8 | Finalize development of a mechanism to accept referrals for a health home from hospitals and other providers
| 2011-06-20 | 8 | 8 | 8 | Receive SAMHSA approval for submission of Phase 1 SPA
| 2011-06-24 | 8 | 8 | 8 | Finalize strategies for submission of subsequent TCM conversion to HH SPAs (AI, OMH, OWPDD, OASAS)
| 2011-06-30 | 8 | 8 | 8 | Submit Phase 1 SPA
| 2011-07-01 | 8 | 8 | 8 | Finalize HH enrollee notification letter for Phase 1
| 2011-07-18 | 8 | 8 | 8 | Notify Phase 1 HH potential providers that applications are being accepted by DOH and coordinate notification with sister agencies and associations to facilitate notification to potential providers, members, and interested parties.
| 2011-08-01 | 8 | 8 | 8 | Begin provider enrollment of health home entities for Phase 1
| 2011-08-15 | 8 | 8 | 8 | Receive SPA approval for Phase 1
| 2011-08-19 | 8 | 8 | 8 | Begin enrollment of Medicaid enrollees into Phase 1 HH
| 2011-08-19 | 8 | 8 | 8 | Complete development of program manuals and guidance materials for Phase 1 HH
| 5/13/2011 5/20/11 9/8/11 | 8 | 8 | 8 | Initiate the development of a process for enrollee auto assignment based on Phase 1 selection criteria
| 2011-10-01 | 8 | 8 | 8 | Implement Phase 1 program
| 2014-01-01 | 8 | 8 | 8 | Survey and interim report due to CMS
Health Home Implementation Phase 2
| 2011-06-01 | ü | ü | ü | Initiate development of Phase 2 SPA for TCM conversion to HH (AI, OMH, OWPDD, OASAS) including transition plans, population criteria selection, federal and State reporting requirements, payment methodology and reimbursement amounts, system needs, data needs, evaluation method, and enrollee auto-assignment.
| 2011-06-13 | 8 | 8 | 8 | Initiate discussion with CMS regarding Phase 2 Health Home SPA submission
| 2011-07-05 | 8 | 8 | 8 | Finalize payment methodology and reimbursement amounts for Phase 2 programs
| 2011-07-05 | 8 | 8 | 8 | Consult with SAMHSA prior to Phase 2 SPA submission
| 2011-07-05 | 8 | 8 | 8 | Finalize system needs related to claims editing and payment for Phase 2
| 2011-07-15 | 8 | 8 | 8 | Finalize federal and State reporting requirements for Phase 2
| 2011-07-15 | 8 | 8 | 8 | Finalize Phase 2 data requirements
| 2011-07-15 | 8 | 8 | 8 | Finalize Phase 2 population selection criteria
| 2011-07-15 | 8 | 8 | 8 | Finalize process for enrollee auto assignment based on Phase 2 selection criteria
| 2011-07-22 | 8 | 8 | 8 | Finalize evaluation methodology for Phase 2
| 2011-07-22 | 8 | 8 | 8 | Finalize Phase 2 population selection criteria
| 2011-07-22 | 8 | 8 | 8 | Finalize process for enrollee auto assignment based on Phase 2 selection criteria
| 2011-07-29 | 8 | 8 | 8 | Finalize draft evaluation methodology for Phase 2
| 2011-07-29 | 8 | 8 | 8 | Receive SAMHSA approval for submission of Phase 2 SPA
| 2011-08-12 | 8 | 8 | 8 | Submit freedom of choice waiver for mandatory enrollment in health homes
| 2011-08-26 | 8 | 8 | 8 | Submit Phase 2 SPA for TCM conversion to HH (AI, OMH, OWPDD, OASAS)
| 2011-09-09 | 8 | 8 | 8 | Finalize HH enrollee notification letter for Phase 2
| 6/1/2011 9/30/11 | 8 | 8 | 8 | Finalize process for enrollee auto assignment based on Phase 1 selection criteria
| 2011-10-01 | 8 | 8 | 8 | Receive SPA approval for Phase 2 SPA
| 2012-01-30 | 8 | 8 | 8 | Implement Phase 2 program
| 2014-01-01 | 8 | 8 | 8 | Survey and interim report due to CMS
Vendor contract for HH/PCMH implementation assistance
| 2011-04-13 | ü | ü | ü | Initiate development of a vendor contract to utilize a vendor for assistance with program implementation, management and operations activities.
| 2011-05-05 | ü | ü | ü | Submission of BB1184 |  |  |  | BB1184 approved
| 5/6/2011 5-16-11 5-20-11 | ü | ü | ü | Complete development of a vendor contract to utilize a vendor for assistance with program implementation, management and operations activities.
| 5/17/2011 5-22-11 | ü | ü | ü | Initiate clearance process of solicitation document
| 5/13/2011 5-27-11 6-3-11 | 8 | 8 | 8 | Post vendor contract for HH/PCMH implementation assistance for 30 days
| 5/20/2011 6-3-11 6-10-11 | 8 | 8 | 8 | Bidder's questions received on vendor HH/PCMH implementation assistance contract
| 5/27/2011 6-10-11 6-17-11 | 8 | 8 | 8 | DOH response to HH/PCMH implementation assistance bidder questions
| 6/13/2011 6-27-11 7-3-11 | 8 | 8 | 8 | Bid proposals due for vendor contract for HH/PCMH implementation assistance
| 6/21/2011 7-11-11 7-18-11 | 8 | 8 | 8 | Complete evaluation and selection of vendor contract for HH/PCMH implementation assistance
| 6/29/2011 7-22-11 7-29-11 | 8 | 8 | 8 | Complete DOH internal approval and sign contract for vendor contract for HH/PCMH implementation assistance
| 7/5/2011 8-1-11 8-8-11 | 8 | 8 | 8 | Vendor for HH/PCMH implementation assistance begins work
Colocation of Services
| 2011-05-04 | ü | ü | ü | Meet with OHSM, OMH, OASAS, and OPWDD to identify areas for streamlining licensing requirements for colocation and discuss future roles and responsibilities.
| 2011-06-01 |  |  |  | Develop interagency MOU outlining roles and responsibilities of agencies in colocating services.
| 2011-06-06 |  |  |  | Finalize initial development of a single set of license requirements for multiagency co-located services
| 2011-06-16 | 8 | 8 | 8 | Continue discussion on colocation issues with agencies
| 2011-06-16 | 8 | 8 | 8 | Reach agreement on a single multi-agency patient consent form for health home use
| 2011-06-30 | 8 | 8 | 8 | Continue discussion on colocation issues with agencies
| 6/6/2011 7/15/11 | 8 | 8 | 8 | Finalize initial development of a single set of license requirements for multiagency co-located services
| 6/1/2011 8/4/11 | 8 | 8 | 8 | Develop interagency MOU outlining roles and responsibilities of agencies in colocating services.
| 8/1/2011 9/1/11 | 8 | 8 | 8 | Complete interagency colocation MOU outlining roles and responsibilities of agencies in colocating services.
| 8/8/2011 10/1/11 | 8 | 8 | 8 | Initiate implementation activities related to co-locating services as identified in the MOU.
MRT #90 |  |  |  |  | Project Name: Mandatory Enrollment in MLTC/ Plans / Health Home Conversion Division Lead: DMC Team Lead: Linda Gowdy Additional Staff: Susan Barth, Mary Ann Anglin, Paul Uppal Description: Transition Medicaid Recipients age 21 and older in need of community-based long term care services into MLTC plans, and convert MLTC plans to Health Homes. Phase 1 to begin to remove LDSS from enrollment process; target implementation 9/1/11. Phase 2 to begin Mandatory enrollment 4/2012 in NYC, including transition of current users of community based long term care services. Target for transition is 5/2015. Expansion Upstate will roll out as capacity is achieved. | -8.33
| 2011-03-24 | P | P | P | Meeting with MLTC Plans. Dialogue on proposal.
| 5/30/2011 6/8/11 | 8 | 8 | 8 | Establish Membership of Workgroup
| 2011-11-01 | 8 | 8 | 8 | Workgroup report submitted to Department
CONVERT MLTC TO HEALTH HOME
| 5/1/2011 6-30-11 | 8 | 8 | 8 | Establish Health Home Standards. Determine if plan operations need modification.
| 5/13/2011 5-26-11 | 8 | 8 | 8 | Submit draft State Plan Amendment to CMS. |  |  |  | Based on workplan #89
| 5/20/2011 6-1-11 | 8 | 8 | 8 | Incorporate necessary Health Home MLTC plan contract changes with Phase 1 amendment
| 6/1/2011 6-15-11 | 8 | 8 | 8 | Identify any systems / claiming issues
| 8/1/2011 8-15-11 | 8 | 8 | 8 | Response to CMS Questions, State Plan Approval |  |  |  | Based on workplan #89
| October 2011 - March 2013 | 8 | 8 | 8 | Enhanced federal share
PHASE ONE - ELIMINATE LDSS
| 2011-04-01 | P | P | P | Issue Revised Service Area Expansion Application
| 2011-04-29 | P | P | P | Draft amendment to MTLC contract to adress changes to LDSS and benefit package changes into internal review
| 2011-04-30 | P | P | P | Anticipate receipt of Service Area Expansion applications for review
| 2011-05-11 | P | P | P | Discuss MLTC and proposed changes with MCARP
| 4/22/2011 5-26-11 6-14-11 | 8 | 8 | 8 | Issue revised Certificate of Authority application and application to add another line of business for a plan with a COA |  |  |  | Pending meeting with OLTC
| 5/20/2011 6/20/11 | 8 | 8 | 8 | MLTC contract amendments sent to CMS for approval
| 6/1/2011 7-1-11 | 8 | 8 | 8 | MLTC contract amendment approved by CMS. Sent to plans
| 6/11 - ongoing | 8 | 8 | 8 | Anticipate receipt of first new MLTC COA applications Review and processing of new MLTC COA Applications
| 7/1/2011 8-1-11 | 8 | 8 | 8 | Contract amendments complete DOH clearance and sent to OSC
| 2011-07-15 | 8 | 8 | 8 | Training of Enrollment Broker and other entities who may assist with education/enrollment
| 2011-08-01 | 8 | 8 | 8 | Revised MLTC plan materials finalized including handbooks, member notices, marketing materials
| 2011-08-15 | 8 | 8 | 8 | Finalize parameters and processes for post enrollment review with contractor.
| 2011-09-01 | 8 | 8 | 8 | Commence enrollment activities without LDSS for 10/1/11 enrollments
PHASE TWO - MANDATORY MLTC ENROLLMENT
| 2011-04-22 | P | P | P | Submit 1115 Waiver amendment to CMS
| 2011-04-30 | P | P | P | Begin system modifications for auto-assignment algorithm
| 2011-05-01 | P | P | P | Begin discussions with Actuary re: rate development for 4/12 rate cycle
| 2011-05-11 | P | P | P | Discuss MLTC and proposed changes with MCARP
| 2011-06-01 | 8 | 8 | 8 | Provide staff assistance to MRT workgroup regarding development of guidelines for other care coordination models
| 2011-08-01 | 8 | 8 | 8 | Waiver approved by CMS
| 2011-10-01 | 8 | 8 | 8 | Draft MLTC contract amendment changes for mandatory enrollment
| 2011-10-01 | 8 | 8 | 8 | Begin to establish process to ensure MLTC home care network providers meet certification criteria
| 2011-11-01 | 8 | 8 | 8 | MLTC contract amendments sent to CMS for approval
| 2011-11-15 | 8 | 8 | 8 | Posting of care coordination model guidance on DOH website
| 2011-12-01 | 8 | 8 | 8 | MLTC contract amendments approved by CMS. Sent to plans
| 2011-12-01 | 8 | 8 | 8 | Completion of rates
| 2012-01-06 | 8 | 8 | 8 | Contract amendments complete DOH clearance, to include network certification. Sent to OSC.
| 2012-01-31 | 8 | 8 | 8 | Educational materials developed for use with current and new personal care users
| 2012-02-28 | 8 | 8 | 8 | Training of Enrollment Broker and other entities who may assist with education/enrollment
| 2012-02-01 | 8 | 8 | 8 | OCS approves contract amendments
| 2012-02-28 | 8 | 8 | 8 | Notices go out to first group of personal care users about need to select a plan within the next 30 days
| 2012-03-01 | 8 | 8 | 8 | New applicants for personal care are directed to MLTC for services to commence 4/1/12
| 2012-03-31 | 8 | 8 | 8 | Current users who have not selected a plan are auto-assigned. MLTC plan notified of current service plan and home care provider
| 2012-04-01 | 8 | 8 | 8 | First group of new users begin service in MLTC plan
| 2012-04-01 | 8 | 8 | 8 | First group of auto-assigned members begin MLTC enrollment
| 2015-05-01 | 8 | 8 | 8 | Complete transition of personal care users into MLTC
MRT #93 |  |  |  |  | Project Name: Establish behavioral health organizations (BHOs) to manage carved-out behavioral health services Division Lead: DFPP Team Lead: Bob Myers (OMH) Add'l staff: Priscilla Smith, Lauren Tobias, Cynthia Buswell, Jackie Allaman, Mark Tremblay Description: Use BHOs to manage behavioral health services that are provided outside of managed care. OASAS lead: Rob Kent 485-2312 | -5
| 2011-03-31 | P | P | P | Submit FPN
| 2011-04-01 | P | P | P | Obtain State legislative authority |  |  |  | Included in Article 7 bill
| 2011-04-11 | P | P | P | DOH/OMH/OASAS meeting scheduled to determine roles and responsibillities
| 2011-05-12 | P | P | P | Meet with stakeholders
| 2011-05-16 | P | P | P | Meet with stakeholders
| 2011-05-13 | P | P | P | Determine BHO program requirements including relationship to health homes |  |  |  | Ongoing and in progress
| 2011-05-27 | P | P | P | Determine eMedNY system requirements |  |  |  | Ongoing and in progress
| 2011-05-27 | 8 | 8 | 8 | Determine BHO payment methodology
| 2011-06-03 | 8 | 8 | 8 | Develop interagency MOU identifying each agencies roles and responsibilities in administering and managing the BHO initiative
| 2011-06-10 | 8 | 8 | 8 | Develop BHO contract award criteria including min. network, financial, information systems
| 2011-06-24 | 8 | 8 | 8 | Post contract requirements on web
| 2011-06-24 | 8 | 8 | 8 | Solicit bids
| 2011-08-05 | 8 | 8 | 8 | Review bids
| 2011-08-19 | 8 | 8 | 8 | Select vendors
| 2011-08-26 | 8 | 8 | 8 | Execute contracts with BHOs
| 2011-09-15 | 8 | 8 | 8 | Complete readiness reviews
| 2011-10-01 | 8 | 8 | 8 | Implement eMedNy system edits
| 2011-10-01 | 8 | 8 | 8 | Implement program
| 2013-04-01 | 8 | 8 | 8 | Determine capacity and financial ability of NYC Special Needs Plans (SNPs) to be designated as regional BHO
MRT #101 |  |  |  |  | Project Name: Develop Initiatives to Integrate and Manage Care for Dual Eligibles Division Lead: DMC Team Lead: Linda Gowdy Description: Develop approaches for serving dual eligibles | 0
| 4/1/2011 4/18/11 | P | P | P | Anticipate receiving planning contract from CMS for planning activities
| 3/30/2011 5-30-11 | 8 | 8 | 8 | Receive Medicare data from CMS |  |  |  | Waiting on CMS
| 4/1/11 5-30-11 - 10/31/12 | 8 | 8 | 8 | Conduct data analysis of Medicare and Medicaid data on dual eligibles
| 6/1/2011 6-17-11 | 8 | 8 | 8 | Select vendor for actuarial work
| 6/1/2011 6-17-11 | 8 | 8 | 8 | Select vendor for analytic work
| 6/1/2011 6-17-11 | 8 | 8 | 8 | Select vendor for assistance with stakeholder meetings
| 2011-07-01 | 8 | 8 | 8 | Recruit, hire and train staff
| 8/11-9/11 | 8 | 8 | 8 | Conven e stakeholder and informational meetings
| 11/11-12/11 | 8 | 8 | 8 | Prepare demonstration recommendations
| 12/11-2/12 | 8 | 8 | 8 | Develop reimbursement methodology
| 2012-01-01 | 8 | 8 | 8 | Propose legislation for demonstration
| 2012-04-01 | 8 | 8 | 8 | Submit demonstration proposal to CMS
| 4/12-10/12 | 8 | 8 | 8 | Negotiate as needed with CMS on demonstration
| 2012-10-01 | 8 | 8 | 8 | Begin implementation of dual demonstration(s)
MRT # 102 |  |  |  |  | Project Name: Centralize Responsibility for Medicaid Trauma & Estate Recovery Process Division Lead: OMIG Portfolio Manager: Katherine Napoli / Alicia Whitlingum Project Lead: Jeff Flora Description: Statewide responsibility for making Medicaid recoveries from the estates of deceased recipients, in personal injury actions and in legally responsible relative refusal cases. | -39
Derive Methodology for Savings
| 2011-04-29 | P | P | P | Develop methodology
| 2011-05-06 | P | P | P | Complete Budget Savings Form
| 2011-05-20 | P | P | P | Approval by BBFM
| 2011-04-28 | P | P | P | Update MRS in FACTS
| 2011-05-27 | P | P | P | Derive Methodology for Savings Completed
Outreach activities
| 2011-06-02 | 8 | 8 | 8 | Submit to NYPWA Presentation Description
| 2011-07-31 | 8 | 8 | 8 | Conduct presentation at NYPWA in July
| 2011-07-01 | 8 | 8 | 8 | Review Rockefeller study
| 2011-05-24 | P | P | P | OMIG Finalize Local Commissioners Memorandum (LCM)
| 2011-05-24 | P | P | P | Submit to OHIP for distribution
| 2011-05-26 | P | P | P | M-Tag Meeting
Implementation
Voluntary (in process)
| 2011-04-25 | P | P | P | Identify interested counties
| 2011-06-01 | 8 | 8 | 8 | Implement with first interested counties
| 2011-06-01 | 8 | 8 | 8 | Start reporting recoveries
Legislation Enactment
| 2011-03-14 | P | P | P | Identify state statutes • Social Services Law §§104, 104-b, 369 • Administrative Directive 02 OMM/ADM - 3
| 2011-05-31 | 8 | 8 | 8 | Review and obtain clarification on statutory authority for OMIG to collect Public Assistance recoveries.
Concept Legislation
| 2011-12-30 | 8 | 8 | 8 | If necessary, expand OMIG enabling Statute regarding to include Public Assistance.
| 2011-12-30 | 8 | 8 | 8 | Amend Social Services Law §§104, 104-b, 369 language. Purpose is to provide statutory authority at State level to perform estate and casualty recovery of public assistance and medical care.
| 2011-12-30 | 8 | 8 | 8 | Develop consistent State authority policy language required within 02 OMM/ADM - 3
| 2011-12-30 | 8 | 8 | 8 | Create new legislation under SSL §369 -req notice of estate and casualty filings be given to the State by attorneys, workers' compensation, liability & no-fault carriers. May include penalty language consistent with Medicare, Medicaid, Medicaid, and SCHIP.
| 2011-12-30 | 8 | 8 | 8 | Create new leg allowing State to hold PIA (Personal Incident Account) funds as the probate jurisdiction administering the estate. Purpose of legislation is to avoid payment of fees and commissions to the PA for appointment to handle all PIA funds.
| 2011-12-30 | 8 | 8 | 8 | Social Services Law §369(6) - Expand definition of "estate" to include non-probate assets (MRT#132). Purpose of law is to increase available assets for recovery
| 2011-12-30 | 8 | 8 | 8 | Propose Legislation changes
| 2012-04-02 | 8 | 8 | 8 | Obtain approval of legislation changes
| 2012-04-02 | 8 | 8 | 8 | Implement Legislative changes
Improve Medicaid Lien Recovery
| 2012-12-31 | 8 | 8 | 8 | Establish database system of claimants
| 2012-12-31 | 8 | 8 | 8 | Establish mechanism for recovery of funds
MRT # 103 |  |  |  |  | Project Name: Reduce Inappropriate Use of Certain Services Division Lead: DHCF Team Lead: Ann Heilmann Add'l Staff: Laura Grassmann Description: This proposal would institute financial disincentives to reduce inappropriate use of cesarean deliveries. | -12.1
ADMINISTRATIVE
| 2011-03-25 | P | P | P | Full policy definition to clarify services and actions: -Initial denial of c-section claims / quality incentives on others
| 2011-03-30 | P | P | P | Federal Public Notice publication
| 2011-04-01 | P | P | P | Regulations |  |  |  | Emergency reg filed 4/6
| 2011-04-01 | P | P | P | Draft State Plan Amendment to CMS |  |  |  | In DOH Review - Draft to CMS 4/15/11
| 2011-05-30 | 8 | 8 | 8 | Revise Federal Public Notice publication
| 2011-06-15 | 8 | 8 | 8 | Revise Regulations
| 2011-06-15 | 8 | 8 | 8 | Revise Draft State Plan Amendment and send to CMS
| 2011-06-15 | 8 | 8 | 8 | Assessment of public comment from obgyn doctor regarding email dated 4/20/11 (Karla)
RESEARCH AND DEVELOPMENT
| 2011-03-25 | P | P | P | Discuss with 3M an appropriate DRG and severity level assignment for the initial claim default payment
| 2011-04-15 | P | P | P | Discuss clinical standards for 'medically necessary' cases with Department Medical Directors |  |  |  | Email sent 4/6/11 - Meeting w/ Dr Gesten, Terry, John, Phil, Pat R. etc on 4/12 to discuss
| 2011-04-12 | P | P | P | Meet with Department Medical Director and Division of Quality and Evaluation to discuss alternatives to using an appeal process: standard payment for all deliveries |  |  |  | Met on 4/12. Possible use of blended weights for all deliveries to achieve savings upfront
| 2011-04-20 | P | P | P | Meet with IPRO and OHSM to begin appeal process discussions. |  |  |  | Met with IPRO on 4/7 and developed initial plan and steps to take
| 2011-04-28 | P | P | P | Analyze option to adjust SIW's as an alternative to appeals |  |  |  | Discussing analysis at 4/29/11 meeting
| 2011-04-28 | P | P | P | Meet with IPRO, DPR and DOIT to discuss details on appeal process/systems issues |  |  |  | Meeting scheduled for 4/28/11
| 2011-04-29 | P | P | P | Meet with DQE and Medical Director to discuss all available implementation options |  |  |  | Meeting scheduled for 4/29/11
| 2011-05-05 | P | P | P | Key decision to be made whether or not to include Managed Care
| 5/5/2011 5/30/11 | 8 | 8 | 8 | Meet with IPRO and Medical Directors to discuss clinical details for appeals |  |  |  | On hold
SYSTEM ISSUES
| 2011-03-21 | P | P | P | Discuss timeframe / steps for systems requirements with Division of Information Technology |  |  |  | Discussed a temporary means to implement due to time issues
| 4/30/2011 5-30-11 | 8 | 8 | 8 | Submit evolution project for eMedNY program changes - on hold |  |  |  | Working on details with DOIT and IPRO
| 5/15/2011 5-30-11 | 8 | 8 | 8 | Retroactive appeals need to be considered - on hold |  |  |  | Made DOIT aware of this issue
COMMUNICATION WITH STAKEHOLDERS
| 2011-05-17 | P | P | P | Meet with Associations to discuss impact on providers - conference call held to discuss alternative options, agreement reached |  |  |  | GNY offered input on how cases should be handled
| 5/15/2011 6-15-11 | 8 | 8 | 8 | Develop a Q & A Document - on hold
| 2011-05-30 | 8 | 8 | 8 | Notify Providers through the Medicaid Update
| 2011-05-30 | 8 | 8 | 8 | Work with Provider Relations to develop communication strategy
|  | 8 | 8 | 8 | SAVINGS METRIC
| 2011-05-01 | 8 | 8 | 8 | Identify a process to identify savings including effect on appeals and develop a metric for calculating and tracking savings
ADDITIONAL QUALITY INITIATIVES
| 2011-05-30 | 8 | 8 | 8 | Begin discussions with the Division of Quality and Evaluation to identify additional cost saving services (including CABG & PCI procedures)
| 2011-05-30 | 8 | 8 | 8 | Meet with Department Medical Directors and Division of Quality and Evaluation to discuss options for quality incentives
| 2011-05-30 | 8 | 8 | 8 | Identify measures to be put into place to improve quailty and reduce utilization
| 2011-05-30 | 8 | 8 | 8 | Identify a means to relay the quality measures to providers
| 2011-05-30 | 8 | 8 | 8 | Implement plan to inform providers of quality measures
MRT # 109 |  |  |  |  | Project Name: Requires Hospitals and Nursing Homes to provide Patient Centered Palliative Care Division Lead: OHSM - DPSQ Team Lead: Anna D. Colello, Esq., additional staff Karen Lipson Description: To inform patients about palliative care and pain management options in hospitals, nursing homes, home care, special needs assisted living residences and enhanced assisted living residences pursuant to PHL 2997-d | 0
| 2011-03-15 | P | P | P | Task 1 - Develop project management plan (the plan will include stakeholders within the department, provider associations and appropriate palliative care council members who have expertise in this area.
| 2011-03-15 | P | P | P | Task 2 - Review tools developed for the implementation of Palliative Care Information Act which can be used to inform all providers. |  |  |  | Review is underway.
| 2011-03-21 | P | P | P | Task 3 - Schedule meeting with Department staff in the hospital, nursing home, home care and assisted living programs. (Mary Ellen Hennessy/Ruth Leslie/Jackie Pappalardi/Val Deetz/Mary Ann Anglin/Becky Fuller-Gray and Mary Hart) To discuss: (a) the development of standards for compliance with PHL 2997-d (b) the development of guidance tools based on these standards which can be used by surveillance staff to monitor compliance (c) the development of a dissemination plan for this information using such department communication formats such as "Dear Administrator" letters (d) the processes that already exist in each of these settings to provide health information to the patient/resident/consumers for whom they care.
| 2011-04-11 | P | P | P | Task 4 -2nd call with DOH program staff
| 2011-04-25 | P | P | P | Task 5 - Meet with Hospital Associations (HANYS-Kathy Ciccone/Mary Therriault and Greater New York-Lorraine Ryan) on 4/25/11 to review requirement and seek input as to what systems exist in hospitals and nursing homes to convey patient information: (a) how would they identify appropriate patients to receive the information (b) how would they document the information was given (c) what information (resources found on DOH website, Palliative Care page) |  |  |  | Meetings to take place week of 4/18/11
| 2011-04-25 | P | P | P | Task 6 - Meet with Nursing Home Associations (NYASA-Elliot Frost, NYSHFA-Nancy Leveille and HANYS-Deb LeBarron) Discuss same questions as above.
| 2011-04-25 | P | P | P | Task 7 - Meet with Home Care and Assisted Living Associations (HCA-Andrew Koski, HCP-Margaret Gorman/Christina Miller-Foster and ESAAL-Lisa Newcomb). Discuss same questions as above.
| 2011-04-27 | P | P | P | Task 8 - Palliative Care Council meeting already scheduled. This topic could be added to agenda to seek input from experts on the council in hospitals, nursing homes and home care. Discuss same questions as above.
| 2011-05-10 | P | P | P | Task 9 - Met with Hospice and Palliative Care Association. Discussed services available in each county and collaborations which can be developed among providers in community.
| 2011-05-31 | 8 | 8 | 8 | Task 10 - Meet with Dr. Diane Meier to discuss how the Center to Advance Palliative Care can assist in being a resource to entities required by PHL 2997-d to facilitate access to palliative care services.
| 2011-06-27 | 8 | 8 | 8 | Task 11 - Meeting with Central Office program staff in Hospitals, Nursing Homes, Home Care, Assisted Living to develop investigative tool to review compliance with law by providers
| 2011-07-11 | 8 | 8 | 8 | Task 12 - 2nd meeting with provider association staff to review expectations for compliance. Develop Frequently Asked Questions.
| 2011-09-10 | 8 | 8 | 8 | Task 13 - Develop Dear Administrator letter setting forth the requirements, which includes how information will be provided, how DOH programs will monitor compliance and what resources are available.
| 2011-09-14 | 8 | 8 | 8 | Task 14 - Train DOH regional surveillance staff who will be investigating complaints relative to violations of this law.
| 2011-09-27 | 8 | 8 | 8 | Task 15- Law effective
MRT # 116 |  |  |  |  | Project Name: Accelerate IPRO Review of Medically Managed Detox Division Lead: Greg Allen Team Lead: Priscilla Smith Description: Refocus Island Peer Review Organization (IPRO) reviews of medically managed withdrawal cases from those based on DRG rates to those using the new rate codes | -1.1
| 2011-03-25 | P | P | P | Discuss scope of project with OASAS staff
| 2011-05-02 | P | P | P | Contact DOH IPRO coordinator to determine options for refocused review models, given scope of current contract
| 2011-05-06 | P | P | P | Consult with OASAS staff to determine optimal model for refocused reviews
| 2011-05-06 | P | P | P | Contact IPRO to discuss timeline for implementation of new review methodology
| 2011-05-16 | P | P | P | Determine whether contract amendment is required |  |  |  | No contract amendment required
| 2011-06-27 | 8 | 8 | 8 | Finalize (with OASAS and IPRO) protocol and tools for refocused IPRO reviews
| 2011-10-01 | 8 | 8 | 8 | Effective implementation date
MRT # 129 |  |  |  |  | Project Name: Minimize Anti-Trust Exposure by Supervising Integration of Providers Division Lead: Team Lead: Karen Lipson Description: Implement regulatory framework to provide active supervision and confer anti-trust immunity on providers that are merging, consolidating, integrating operations.
| 2011-04-01 | P | P | P | Enactment of legislation
| 2011-04-30 | P | P | P | Assemble internal work group
| 2011-05-02 | P | P | P | Consult with NYS attorney general's office
| 2011-06-30 | 8 | 8 | 8 | Draft regulations |  |  |  |  | Maintenance
| 2011-07-15 | 8 | 8 | 8 | Consult with stakeholders
| 2011-07-15 | 8 | 8 | 8 | Secure Governor's Counsel's Office approval
| 2011-07-21 | 8 | 8 | 8 | Present draft regulations to PHHPC committee for discussion
| 2011-08-04 | 8 | 8 | 8 | Present draft regulations to PHHPC for discussion
| 2011-09-07 | 8 | 8 | 8 | Publish in State Register for 45-day comment period
| 2011-12-08 | 8 | 8 | 8 | Present to PHHPC Codes Committee and Council for adoption.
| 2011-12-28 | 8 | 8 | 8 | Publish Notice of adoption in State Register
| 2011-12-31 | 8 | 8 | 8 | Develop application and policy guidance, train staff
MRT #131 |  |  |  |  | Project Name: Reform Medical Malpractice and Patient Safety Division Lead: OHSM Team Lead: Lora Lefebvre Description: Create a neurologically impaired inant medical indemnity fund and establish a cap on non-economic damages in medical malpractice cases in addition to exploring other alternatives. | -88
[5 empty] | Project Name: Medical Malpractice Reform Division Lead: Insurance /Health Team Lead: Sapna Maloor/Lora Lefebvre Description: Medical Indemnity Fund |  |  |  | Lora Lefebvre, DFR: Kate Powers
| 2011-04-30 | P | P | P | Identify and start scheduling meetings with stakeholders (GNYHA, HANYS,Mediciad Matters, ACOG, MSSNY, UCP,March of Dimes, Med Mal insurers, other insurers, Office of Court Adminsration, Bar Association)
| 2011-04-30 | P | P | P | Conduct internal state stakeholder meetings (DoH- Early Intervention, OLTC Waiver program; OPWDD, ACCES, Tax Department, Education Department
| 2011-05-01 | P | P | P | Start selection process for a fund administrator |  |  |  | DFS
| 2011-05-01 | P | P | P | Initiate development of regulations relating to: claims process and form development, definition of medically necessary costs (refer to Medicaid and Medicaid waiver projects); dispute resolution/appeal process; Medicaid lien identification; expense certification to Tax & Finance |  |  |  | Need to identify Department and Insurance Department resources to write regulations | Maintenance
| 2011-05-15 | P | P | P | Begin website development (Fund Administrator or Departments)
| 2011-05-30 | P | P | P | Begin to identify consumer advisory committee members/schedule meetings; add to fund administrator responsibliites
| 2011-06-01 | 8 | 8 | 8 | Identify actuarial resources |  |  |  | DFS
| 2011-06-01 | 8 | 8 | 8 | Intiate notification of consumers, providers of service and insurers about Indemnity Fund |  |  |  | DOI/DoH/Fund Administrator
| 2011-06-15 | 8 | 8 | 8 | Choose fund administrator |  |  |  | DFS
| 2011-06-15 | 8 | 8 | 8 | Establish current year's actuarial estimate for fund |  |  |  | DFS
| 2011-07-01 | 8 | 8 | 8 | Establish fund with Tax & Finance
| 5/15/2011 5/22/11 8-1-11 | 8 | 8 | 8 | Explicit directions on HCRA transfer to Fund |  |  |  | Roland Guilz
| 2011-08-01 | 8 | 8 | 8 | Complete program regulations/submit for emergency approval
| 2011-09-30 | 8 | 8 | 8 | Regulation approval
[5 empty] | Hospital Quality Initiative - develop the Hospital Safety Insititute |  |  |  | Lora Lefebvre, John Morley
| 2011-05-15 | P | P | P | Meet with stakeholders (GNYHA, HANYS, MSSNY, ACOG,Art Levin)
| 2011-05-30 | 8 | 8 | 8 | Recommend stakeholders to Commissioner
| 2011-06-30 | 8 | 8 | 8 | Hold organizing meeting to identify ob safety programs
| 2011-08-30 | 8 | 8 | 8 | Develop a multi-year plan on programs to intiate with provider community
| 2011-09-30 | 8 | 8 | 8 | Indentify first year projects and resources
| 2011-10-15 | 8 | 8 | 8 | Convene stakeholders group to develop program and discuss implementation
Project Name: Improved Medicaid Lien Recovery Division Lead: OMIG Team Lead: Add'l Staff: Description: Incentive lien recovery with counties
| 2011-05-01 | P | P | P | Determine whether OMIG is lead
Hospital Quality Fee collection
| 2011-03-31 | P | P | P | Discuss how to incorporate into the current Health Facility Cash Assessment Program (HFCAP) for hospitals. Collections have to be reported and deposited separately. |  |  |  | We will need a separate reporting mechanism to handle the existing assessment plus the new assessment.
| 2011-03-31 | P | P | P | Schedule conference call with Pool Administrator to discuss program |  |  |  | Pool Adminsitrator is anticipating information from the Dept and ready to implement.
| 2011-05-02 | P | P | P | Create Hospital list |  |  |  | Consistent with HFCAP program | Maintenance
| 2011-05-20 | P | P | P | Design electronic report |  |  |  | Need Pool Administrator's input and programming. Need to combine into existing report.
| 2011-05-20 | P | P | P | Develop reporting due date schedule |  |  |  | Same as existing HFCAP
| 2011-05-20 | P | P | P | Create instructions for report |  |  |  | Similar to existing HFCAP report, but need to explicitly define obstetrical (OB) patient care service revenues.
| 2011-05-31 | 8 | 8 | 8 | Notify Providers of Hospital Quality Contributions assessment using letters\website. |  |  |  | There is some question about whether newborn services should be included with obstetrical services and what actions need to occur to ensure all intended services are assessed.
| 2011-05-31 | 8 | 8 | 8 | Test electronic report |  |  |  | Time consuming. Need to wait until items above are completed.
| 2011-05-31 | 8 | 8 | 8 | Post all appropriate materials to DOH website |  |  |  | Soon after providers are notified.
| 2011-06-06 | 8 | 8 | 8 | Incorporate into existing HFCAP database but account for reporting and payments separately |  |  |  | Billing and accounting for payments will be separate from HFCAP report. Need to test billing/recoupment process
| 2011-06-15 | 8 | 8 | 8 | Confirm accounts for transferring funds/e-mail notification |  |  |  | Coordinate with Bureau of Accounts Management, OSC and Division of Budget as needed
| 2011-07-15 | 8 | 8 | 8 | Develop required reports for budgeting purposes for collections/transfers etc. |  |  |  | Similar to HFCAP reports.
| 2011-07-15 | 8 | 8 | 8 | Write FAQs for website |  |  |  | Similar to HFCAP FAQs, but with obstetrical and possibly newborn services
| 2011-07-15 | 8 | 8 | 8 | Develop Cost Estimates based on ICR data for billing |  |  |  | Similar to HFCAP reports.
| 2011-12-01 | 8 | 8 | 8 | Evalutate if the current HQC rate (1.6%) is adquate to collect the $30M tartget. |  |  |  | After three months of collections, a determination will need to be made as to whether the rate needs to be increased or other actions should be taken. The December report month (due 1/17/12) would be the first month to be adjusted.
| ongoing, beginning December 2011 | 8 | 8 | 8 | Bill Delinquent Hospitals Quarterly - the initial billing cycle will likely have issues requiring immediate attention and will likely result in a significant increase in phone calls from the hospitals. |  |  |  | A decision to generate separate bills for the existing HFCAP and the Obstetrical Services component will need to be addressed. A thorough and complete review of all hospitals will be required to ensure accuracy.
| ongoing, beginning January 2012 | 8 | 8 | 8 | Send Delinquent Hospitals billings to MA for Recoupment |  |  |  | Allocation of recoupment dollars to HFCAP account and HCRA resources account is a new requirement and will have to be handled properly.
| ongoing | 8 | 8 | 8 | Answer provider phone calls |  |  |  | Call volume may be heavy upon initial notification and initial billing.
| ongoing | 8 | 8 | 8 | Reconcile to make sure outstanding balance in Medicaid matches outstanding balance on database |  |  |  | This is ongoing, important maintenance.
MRT#132 |  |  |  |  | Project Name: Expand the Definition of Estate Division Lead: DCE Team Lead: Wendy Butz Description: Expand definition of "estate" to include assets that bypass probate in order to recover more assets from the estate of a deceased Medicaid recipient. Estate recoveries are pursued from the estate of deceased Medicaid recipients who were permanently institutionalized and from the estate of deceased Medicaid recipients over age 55. Expand the definition of estate to allow recovery against non-probate assets (assets that fall outside of the estate, e.g. joint bank accounts, life estate interest) | -1.1
Policy and Procedure
| 2011-04-15 | P | P | P | Complete review of policy issues
| 5/16/2011 5-20-11 | P | P | P | Submit draft ADM for clearance
| 6/1/2011 6/17/11 | 8 | 8 | 8 | Issue ADM
State Plan Amendment
| 2011-04-22 | P | P | P | Submit draft SPA to DHCF for submission to CMS for informal review
Regulation Amendment
| 6/1/2011 6/17/11 | 8 | 8 | 8 | Submit emergency regulation change |  |  |  | Date pushed back due to comments received from Bar Association. Staff will work with local DA's and OMIG, and will have a projected start date of 6/1/11
Estate Recovery Reporting
| 2011-03-31 | P | P | P | Complete review of quarterly reports for estate recoveries
| 5/30/2011 6/10/11 | 8 | 8 | 8 | Submit proposed changes to estate recovery reporting - quarterly report identifies amounts recovered from non-probate assets in order to track savings.
MRT #133 |  |  |  |  | Project Name: Administrative Renewal for Aged, Blind, and Disabled and Medicare Savings Program (MSP) Participants Division Lead: DCE Team Lead: Wendy Butz Description: Allow aged, blind and disabled with fixed incomes to be automatically renewed based on cost of living increases. | -0.2
Policy and Procedure
| 2011-04-30 | P | P | P | Complete review of policy issues
| 2011-07-01 | 8 | 8 | 8 | Submit draft ADM for clearance
| 2011-10-01 | 8 | 8 | 8 | Issue ADM - effective 1/01/2012
Systems Updates
| 2011-04-01 | P | P | P | Submit System Change Request
| 2011-04-15 | P | P | P | Finalize system change requirements
| 5/17/2011 6-10-11 | 8 | 8 | 8 | Finalize System Action Request
CNS
| 2011-05-17 | P | P | P | Submit new CNS renewal notices
| 2011-08-22 | 8 | 8 | 8 | Development/coding changes
| 2011-10-07 | 8 | 8 | 8 | Unit testing
| 2011-10-12 | 8 | 8 | 8 | User Acceptance
WMS
| 2011-08-22 | 8 | 8 | 8 | Development/coding changes
| 2011-10-07 | 8 | 8 | 8 | Unit testing
| 2011-10-12 | 8 | 8 | 8 | User Acceptance
|  | 8 | 8 | 8 | MBL
| 2011-08-22 | 8 | 8 | 8 | Development/coding changes
| 2011-10-07 | 8 | 8 | 8 | Unit testing
| 2011-10-12 | 8 | 8 | 8 | User Acceptance
Local District Interfaces
| 2011-04-25 | P | P | P | Define changes to existing renewal interfaces (i.e. EDITS, MRT, CHEM)
| 2011-08-22 | 8 | 8 | 8 | Development/coding changes
| 2011-10-07 | 8 | 8 | 8 | Unit testing
| 2011-10-12 | 8 | 8 | 8 | User Acceptance
| November, 2011 (as part of Mass Re-Budgeting) | 8 | 8 | 8 | Migrate system changes (October 17 2011 .. 11.3 migration)
| 2012-01-01 | 8 | 8 | 8 | Implementation
MRT# 134 |  |  |  |  | Project Name: Audit of Cost Reports submitted by hospitals; replacing CPA certifications Division Lead: DHCF Team Lead: Jane Casale Description: Contract with independent certified public accounting firms licensed in NYS to conduct annual field and desk audits of the Institutional Cost Reports | -0.75
| 2011-03-30 | P | P | P | Federal Public Notice
| 2011-04-01 | P | P | P | SPA submission date |  |  |  | To CMS 4/15/11
| 2011-04-01 | P | P | P | Draft regulation to collect audit fees for review by Administration
| 2011-04-04 | P | P | P | Briefing the industry on the tentative Audit plan
| 2011-04-08 | P | P | P | Draft FAS (Funding Availability Solicitation) RFP for review by OHIP administration |  |  |  | Draft submitted to J.Zeccolo in OHIP contracting; revisions are being made based on his recommendations.
| 05/23/11 5/1/2011 | 8 | 8 | 8 | RFP FAS submitted for DOH review (Including Form 2333 and EDC Form) |  |  |  | Form 2333 and EDC are completed. FAS final revisions being made to submit for DOH review.
| 05/23/11 5/1/2011 | 8 | 8 | 8 | Deliver fee schedule for billing and collection. Post to DOH Website. |  |  |  | Fee schedule has been reviewed and discussed with Associations. Expect to post to DOH website next week.
| 06/01/11 5/1/2011 | 8 | 8 | 8 | Attachment A approval (Dependent upon budget approval) |  |  |  | In DOH review. Signed by J. Helgerson 4/22/11. Presently in Bureau of Accounts Management. DOB advised that we would be looking for quick turnaround upon receipt.
| 6/20/11 5/31/2011 | 8 | 8 | 8 | Due Date of Cost Report |  |  |  | The ICR has a revised due date of 6/20/11 to give providers more time to file accurately due to numerous software changes.
| 2011-07-01 | 8 | 8 | 8 | Release of FAS to designated list. Release of RFP through Contract Reporter |  |  |  | In a meeting with OHIP Contracting on 5/11/11, it was agreed that the 7/1/11 date is on target.
| 2011-07-10 | 8 | 8 | 8 | Written questions due from bidders |  |  |  |  | Maintenance
| 2011-07-21 | 8 | 8 | 8 | Response to written questions from the Department to the bidders
| 2011-08-01 | 8 | 8 | 8 | Proposal due from bidders to the Department
| 2011-09-01 | 8 | 8 | 8 | Negotiation of contract terms after award
| 2011-09-15 | 8 | 8 | 8 | Finalization of Audit Plan - Present to industry
| 2011-11-01 | 8 | 8 | 8 | Commencing of Audit (ICR 2010)
MRT#137 |  |  |  |  | Project Name: Disregard Retirement Assets Such as 401K Plans for MBI-WPD Division Lead: DCE Team Lead: Wendy Butz Description: Raise the resource standard and disregard retirement accounts for the MBI-WPD program as an incentive to participation in the program. | 0.5
Policy and Procedure
| 2011-04-30 | P | P | P | Complete review of policy issues
| 2011-07-01 | 8 | 8 | 8 | Submit draft ADM for clearance
| 2011-09-01 | 8 | 8 | 8 | Issue ADM
State Plan
| 2011-05-13 | P | P | P | Submit draft SPA to DHCF for submission to CMS for informal review
Systems Updates
| 2011-04-01 | P | P | P | Submit System Change Request
| 2011-04-25 | P | P | P | Finalize system change requirements
| 2011-05-01 | P | P | P | Finalize System Action Request
MBL
| 2011-08-22 | 8 | 8 | 8 | Development/coding changes
| 2011-10-07 | 8 | 8 | 8 | Unit testing
| 2011-10-12 | 8 | 8 | 8 | User Acceptance
CEM/WMS
| 2011-08-22 | 8 | 8 | 8 | Development/coding changes
| 2011-10-07 | 8 | 8 | 8 | Unit testing
| 2011-10-12 | 8 | 8 | 8 | User Acceptance
CNS
| 2011-04-11 | P | P | P | Finalize and submit CNS notices
| 2011-08-22 | 8 | 8 | 8 | Development/coding changes
| 2011-10-07 | 8 | 8 | 8 | Unit testing
| 2011-10-12 | 8 | 8 | 8 | User Acceptance
| 2011-10-17 | 8 | 8 | 8 | Migrate system changes
Website
| 2011-08-01 | 8 | 8 | 8 | Submit revisions for MBI-WPD website, including Toolkit, for DOH clearance
| 2011-09-30 | 8 | 8 | 8 | Post revisions to MBI-WPD website
| 2011-10-22 | 8 | 8 | 8 | Implementation
MRT# 139 |  |  |  |  | Project Name: Implement the new waiver for LTHHCP Division Lead: OLTC - DHCBS Team Lead: Lydia Kosinski Add'l Staff: Doreen Sharp, Tim Casey Description: To implement the new enhancements of the LTHHCP waiver, initiating the opportunities for increased Medicaid cost-savings and performance. | 0
| 2011-05-01 | P | P | P | Issue Implementation guidance to LDSS (ADM) and LTHHCP (DAL) agencies
| 2011-05-18 | P | P | P | Conference call with local districts for questions related to issued guidance
| 6/15/2011 7-1-11 | 8 | 8 | 8 | Rates officially established for new waiver services, contingent on issuance of final rates
| 2011-07-15 | 8 | 8 | 8 | Draft Medicaid Update article with claiming instructions for LTHHCP providers related to new/expanded services
| 7/15/2011 8/15/11 | 8 | 8 | 8 | External review and comment of of the revised LTHHCP provider manual by selected local districts and LTHHCP providers
| 2011-08-15 | 8 | 8 | 8 | Rates for new services available in eMedNY to allow claims processing
| 2011-08-15 | 8 | 8 | 8 | Implement new/expanded services
| 2012-01-01 | 8 | 8 | 8 | issue Revised LTHHCP Reference manual
MRT #141 |  |  |  |  | Project Name: Accelerate State Assumption of Medicaid Program Division Lead: DMC Team Lead: Jennifer Dean Additional Staff: Linda Gowdy Description: Accelerate State Assumption of Medicaid program authorization for Managed Long Term Care; State takeover of Medicaid managed care contracting process statewide | 0
Part A:Take over Medicaid Managed Care Contracts from NYC
| 2011-03-01 | P | P | P | Review NYC Specific sections of the MMC contract for input into statewide contract
| 2011-03-15 | P | P | P | Meet with NYC and plan associations to discuss changes proposed
| 2011-04-01 | P | P | P | Review NYC Specific sections of the SNP contract for input into statewide contract
| 2011-04-15 | P | P | P | Draft dual eligible Medicaid managed care contract language for Medicaid Advantage Plans NYC service areas included with the effective date of 1/1/11.
| 2011-04-20 | P | P | P | Dual eligible Medicaid Managed care contract language for Medicaid Advantage to CMS for approval
| 5/10/2011 5-30-11 6-6-11 | 8 | 8 | 8 | MMC statewide contract amendment including service area language effective 8-1-2011 drafted
| 5/10/2011 5-30-11 6-10-11 | 8 | 8 | 8 | Draft mainstream managed care contract termination for MCOs with NYC contracts effective 6/30/11 7-31-11
| 2011-06-01 | 8 | 8 | 8 | SNP state contract approved by CMS. SNP state contract sent to OSC for approval.
| 6/1/2011 6-8-11 | 8 | 8 | 8 | Dual eligible Medicaid Managed care contract language for Medicaid Advantage approved by CMS - sent to plans
| 2011-06-15 | 8 | 8 | 8 | MMC/NYC contract terminations and MMC amendments to CMS for approval
| 2011-06-30 | 8 | 8 | 8 | MMC/NYC contract terminations and MMC contract amendment approved by CMS. Sent to plans and returned
| 5/25/2011 6-30-11 | 8 | 8 | 8 | Draft SNP managed care state contract changes for consolidation into 7/1/11 8-1-11 combined MMC/FHP/SNP state contract for plans that are MMC and SNP
| 2011-07-01 | 8 | 8 | 8 | Dual eligible Medicaid Managed care contract language for Medicaid Advantage approved by CMS - returned by plans
| 2011-06-10 | 8 | 8 | 8 | New state SNP contracts for SNP only to CMS for approval
MRT # 144 |  |  |  |  | Project Name: Eliminate Duplicative Behavioral Health Hosp Surveys Division Lead: OHSM - with OMH and OASAS Team Lead: Jayne Van Bramer (OMH) Additional Staff: Chuck Monson (OASAS), Ruth Leslie (DOH) Description: The granting of "deemed status" in lieu of state licensing surveys to hospitals accredited by The Joint Commission or other nationally accrediting body assessing NYS specific concerns. | 0
| 3/31/2011 | P | P | P | Discussions among DOH, OASAS and OMH to fully appreciate the nature of the different deemed status agreements/plans with The Joint Commission (TJC).
| 3/31/2011 | P | P | P | Continue discussions with TJC regarding readiness to begin deemed OMH surveys including the potential role of OMH in training behavioral health surveyors in the OMH addendum.
| 3/31/2011 | P | P | P | Review with TJC the scope of psychiatric inpatient services in NYS. Prepare list with # units per hospital, # of beds and population type of units to inform decision on additional surveyor day(s) to conduct the behavioral health addendum.
| 3/31/2011 | P | P | P | Commence conversations with TJC regarding the use of a deemed status arrangement to satisfy OASAS certification requirements for hospital-based medically managed withdrawal (1st priority) and inpatient rehabilitation (2nd priority).
| 3/31/2011 | P | P | P | Initiate discussions with Det Norske Veritas (DNV) and American Osteopathic Association’s Healthcare Facilities Accreditation Program (AOA) regarding the use of a deemed status arrangement to satisfy OMH and OASAS licensing requirements.
| 4/30/2011 | P | P | P | After careful review of the DOH Collaborative Agreement, develop a Collaborative Agreement between NYS OMH and TJC which describes the responsibilities of each party.
| 4/30/2011 | P | P | P | Identify required regulatory changes to implement deemed status arrangement.
| 4/30/2011 | P | P | P | Develop regulatory language (text of rule) to amend applicable Parts in Title 14 NYCRR.
| 4/30/2011 | P | P | P | Review and if necessary revise the surveyor addendum to ensure it reflects the most recent TJC standards and OMH NYS rules and regulations.
| 4/30/2011 | P | P | P | Conduct a comparison of standards utilized by AOA against the OMH licensing tool.
| 5/31/2011 | P | P | P | Update hospital associations re readiness to begin deemed surveys. Identify additional issues, barriers, and solutions.
| 5/31/2011 | P | P | P | Develop an addendum to AOA survey, if needed, to include high risk and/or New York State OMH specific items.
| 5/31/2011 | P | P | P | Conduct a comparison of standards utilized by DNV against the OMH licensing tool.
| 6/30/2011 | 8 | 8 | 8 | Compare TJC Survey Standards against OASAS Program Regulations -- medically managed withdrawal and inpatient rehabilitation.
| 6-30-2011 | P | P | P | Develop and sign collaborative agreement/memorandum of understanding between the Joint Commission and NYS Office of Mental Health.
| 6/30/2011 | 8 | 8 | 8 | Determine if rule change should be filed as a Notice of Proposed Rulemaking or Emergency Rulemaking.
| 6/30/2011 | 8 | 8 | 8 | Secure Governor’s Office approval to file an emergency rule (per Executive Order 17), if applicable.
| 6/30/2011 | P | P | P | Prepare accompanying regulatory paperwork.
| 6/30/2011 | P | P | P | Circulate rule with completed regulatory filing paperwork internally for approval.
| 6/30/2011 | P | P | P | Submit Notice of Proposed Rulemaking to Governor’s Office for approval.
| 6/30/2011 | P | P | P | Determine which OMH providers will be eligible to apply to TJC for deemed status. Share information with TJC.
| 6/30/2011 | P | P | P | Work with TJC to develop interim procedure for hospitals to opt-in or opt-out of deemed status survey process, including consent to share report with OMH. Develop process for OMH to be notified of hospital decision.
| 6/30/2011 | 8 | 8 | 8 | Develop an addendum to DNV survey, if needed, to include high risk and/or New York State OMH specific items.
| 7/31/2011 | 8 | 8 | 8 | Distribute Dear Provider letter to inform hospitals of OMH deemed status procedures.
| 7/31/2011 | 8 | 8 | 8 | Brief Mental Health Services Council on the proposed rule and conduct vote.
| 7/31/2011 | 8 | 8 | 8 | Coordinate with DOH to achieve OMH participation in validation surveys in hospitals with licensed psychiatric units; Develop protocol to validate survey of NYS/OMH addendum.
| 7/31/2011 | 8 | 8 | 8 | Continue to conduct surveys and issue licenses to non-accredited hospitals and those opting out of deemed survey.
| 8/31/2011 | 8 | 8 | 8 | Upon receipt of successful TJC reports, issue 3 year OMH licenses.
| 8/31/2011 | 8 | 8 | 8 | Meet with Standards Compliance and Field staff to identify quality of care and safety issues and the areas where OASAS has specific regulations not covered by TJC. Develop potential list of areas to be included in an addendum to TJC Survey Standards.
| 8/31/2011 | 8 | 8 | 8 | Submit proposed rule to Department of State for publication in the NYS Register.
| 8/31/2011 | 8 | 8 | 8 | Develop parameters and protocols for rapidly deploying OMH staff to conduct on site for cause surveys.
| 9/30/2011 | 8 | 8 | 8 | Discussions between OASAS and TJC leadership to develop a list of New York State specific concerns to be included in a TJC chemical dependence addendum.
| 9/30/2011 | 8 | 8 | 8 | Meet with hospital associations' membership to review opportunities, options, procedures and protocols for deemed surveys.
| 10/31/2011 | 8 | 8 | 8 | Discussions between OASAS and TJC leadership to agree on steps and timetable for implementation.
| 10/31/2011 | 8 | 8 | 8 | Assess Public Comment if received, and prepare assessment paperwork. Submit 101-A letters to appropriate legislative leaders.
| 10/31/2011 | 8 | 8 | 8 | Update OMH website to inform public of deemed status arrangement.
| 10/31/2011 | 8 | 8 | 8 | Add accrediting body information to OMH Provider Directory for hospitals.
| 11/30/2011 | 8 | 8 | 8 | Circulate Notice of Adoption, including assessment of public comments internally for approval.
| 11/30/2011 | 8 | 8 | 8 | Submit the Notice of Adoption to DOS for publication in State Register and mail 101-A letters to appropriate legislative leaders.
| 12/31/2011 | 8 | 8 | 8 | Work with AOA and with the hospital associations to conduct pilot surveys.
| 1/31/2012 | 8 | 8 | 8 | Review results of AOA pilot surveys, modify protocols as needed.
| 1/31/2012 | 8 | 8 | 8 | Work with DNV and with the hospital associations to conduct pilot surveys.
| 1/31/2011 | 8 | 8 | 8 | Identify providers eligible to participate in a deemed status agreement with AOA and develop a schedule of certification due dates.
| 1/31/2012 | 8 | 8 | 8 | Work with AOA to develop procedure for hospitals to opt-in or opt-out of deemed status survey process, including consent to share report with OMH. Develop process for OMH to be notified of hospital decision.
| 1/31/2012 | 8 | 8 | 8 | Issue OMH 3 year license, upon receipt of successful American Osteopathic Association’s Healthcare Facilities Accreditation Program (AOA) Survey report.
| 1/31/2012 | 8 | 8 | 8 | Identify providers eligible to participate in a deemed status agreement with DNV and develop a schedule of certification due dates.
| 2/28/2012 | 8 | 8 | 8 | Review results of DNV pilot surveys, modify protocols as needed.
| 2/28/2012 | 8 | 8 | 8 | Issue OMH 3 year license, upon receipt of successful American Osteopathic Association’s Healthcare Facilities Accreditation Program (AOA) Survey report.
| 3/31/2012 | 8 | 8 | 8 | Identify providers eligible to participate in a deemed status agreement with DNV and develop a schedule of certification due dates.
| 3/31/2012 | 8 | 8 | 8 | Work with DNV to develop procedure for hospitals to opt-in or opt-out of deemed status survey process, including consent to share report with OMH. Develop process for OMH to be notified of hospital decision.
| 3/31/2012 | 8 | 8 | 8 | Issue OMH 3 year license, upon receipt of successful DNV's The National Integrated Accreditation for Healthcare Organizations (NIAHO) Survfey Report.
MRT #147 |  |  |  |  | Project Name: Eliminate or Modify Unnecessary Regulations Division Lead: OHSM Team Lead: Karen Lipson Description: There are a number of suggested initiatives that require both statutory and regulatory actions to reduce burdens on hospitals and other health care facilities and expand access to capital. | 0
Develop a Uniform Incident Reporting System for Nursing Homes
| 2011-03-01 | P | P | P | Create Project Proposal and Business Design Document
| 2011-04-01 | P | P | P | Present Proposal to Internal Stakeholders
| 2011-05-02 | P | P | P | Develop Prototype of Incident Form
| 7/1/2011 9/1/11 | 8 | 8 | 8 | Design and Test Electronic Form via the Health Commerce System (HCS), and Receive Form Approval |  |  |  |  | Maintenance
| 7/1/2011 9-15-11 | 8 | 8 | 8 | Develop, Receive Executive Clearance, and Send Dear Administrator Letter to Nursing Home Administrators
| 8/1/2011 10-1-11 | 8 | 8 | 8 | Develop Policies and Procedures to Receive Electronic Incident Form and Train Staff
| 8/15/2011 10-15-11 | 8 | 8 | 8 | Implement Electronic Incident Form for Nursing Homes
NYPORTS reform implementation
| 2011-03-10 | P | P | P | Establish workgroup
| 2011-03-10 | P | P | P | Set meeting calendar dates
| 2011-03-18 | P | P | P | Review NQF reporting structures
| 2011-03-18 | P | P | P | Develop cross-walk to current NYPORTS
| 2011-03-18 | P | P | P | Assign draft codes to those NQF unique fileds
| 2011-04-22 | P | P | P | Meet with executive staff to discuss implementation plan
| 2011-04-30 | P | P | P | Convene stakeholders
| 2011-05-30 | 8 | 8 | 8 | Draft revised regulations
| 2011-05-30 | 8 | 8 | 8 | Revise reporting manual
| 2011-05-30 | P | P | P | Plan educaton and training schedule
| 2011-05-30 | P | P | P | Development of training materials
| 2011-06-30 | 8 | 8 | 8 | Development of policy/ procedures
| 2011-06-30 | 8 | 8 | 8 | Conduct trainings for DOH staff and regulated providers
| 2011-06-30 | 8 | 8 | 8 | Finalize regulations
| 2011-06-30 | 8 | 8 | 8 | Circulate regulations to Stakeholders for comment
| 2011-07-05 | 8 | 8 | 8 | Modified reporting approach implemented
| 2011-07-15 | 8 | 8 | 8 | Secure Governor's Office approvall of regulations
| 2011-07-21 | 8 | 8 | 8 | Present proposed regulations to PHHPC Committee for discussion
| 2011-08-04 | 8 | 8 | 8 | Present regulations at PHHPC
| 2011-08-15 | 8 | 8 | 8 | Revise regulations, if necessary
| 2011-08-31 | 8 | 8 | 8 | Publish regulations in State Register
| 2011-10-15 | 8 | 8 | 8 | 45-day comment period
| 2011-12-08 | 8 | 8 | 8 | Assuming no revisions, present regulations to PHHPC Codes Committee for recommendation and to full Council for adoption. |  |  |  |  | Maintenance
| 2011-12-28 | 8 | 8 | 8 | Publish Notice of Adoption in State Regiser
| 2012-01-30 | 8 | 8 | 8 | Disseminate information via HPN to hospitals regarding revised adverse event reporting regulations
Allow home health aide training programs to have a single qualified supervisor RN for multiple training programs
| 2011-04-10 | P | P | P | Draft policy guidance in the Home Health Aide Guidelines for Home Health Training Programs
| 6/1/2011 6-15-11 7-1-11 | 8 | 8 | 8 | Draft Dear Administrator Letters informing home health aide training programs of the revised guidance on RN supervision
| 6/1/2011 6-15-11 7-1-11 | 8 | 8 | 8 | Draft modifications to surveillance and monitoring tools
| 6/15/2011 7-15-11 | 8 | 8 | 8 | Seek feedback from stakeholders and interested parties re: content and clarity of draft documents including State Education Department.
| 6/15/2011 6-30-11 | 8 | 8 | 8 | Post DAL's to the HPN to home care agencies and training programs
| 6/15/2011 7-15-11 | 8 | 8 | 8 | Revise surveillance training to surveyors and disseminate revised materials to regional offices
| 2011-07-15 | 8 | 8 | 8 | Work with stakeholder organizations to develop FAQ document(s) to respond to questions, if needed.
Eliminate the requirement for a physician to be on the Quality Improvement (QI) Committee of Licensed Home Care Services Agencies (LHCSAs)
| 2011-04-15 | P | P | P | Draft revised licensed home care regulation 766.9 (k)(1)
| 5/1/2011 6-10-11 | 8 | 8 | 8 | Prepare notice ot state register for publication of regulations
| 5/30/2011 6-30-11 | 8 | 8 | 8 | Secure Governor's Counsel's Office approval of revised regulations.
| 2011-07-21 | 8 | 8 | 8 | Present regulations to PHHPC Committee for discussion
| 2011-08-04 | 8 | 8 | 8 | Present ro PHHPC for discussion
| 2011-08-01 | 8 | 8 | 8 | Develop and draft revised surveillance protocols and inform surveyors of new protocols
| 2011-08-15 | 8 | 8 | 8 | Revise regulations, if necessary
| 2011-08-31 | 8 | 8 | 8 | Publish proposed regulations in State Register
| 2011-10-15 | 8 | 8 | 8 | 45-day comment period
| 2011-10-15 | 8 | 8 | 8 | Prepare response to public comments
| 2011-12-08 | 8 | 8 | 8 | Present regulations to PHHPC Codes Committee for recommendation and to full Council for adoption.
| 2011-12-28 | 8 | 8 | 8 | Publish Notice of Adoption in State Register
| 2011-12-28 | 8 | 8 | 8 | Draft DAL informing LHCSA of revised requirement and effective date
| 2012-01-15 | 8 | 8 | 8 | Post DAL's to the HCS informing providers of the revised regulation policy and procedure
Authorize Observation Units as Adjunct to Emergency Departments and Create Medicaid Rate
| 2011-04-01 | P | P | P | Finalize development of Medicaid rate for observation units
| 2011-04-20 | P | P | P | Present regulations to DOH Regulatory Advisory Committee
| 2011-04-30 | P | P | P | Circulate regulations to Stakeholders for comment
| 2011-05-04 | P | P | P | Finalize draft Observation Unit operating regulations
| 2011-05-31 | P | P | P | Publish Medicaid Update article on observation unit rate for waiver units
| 2011-05-31 | P | P | P | Launch Medicaid rate for existing observation units
| 5/31/2011 6-30-11 | 8 | 8 | 8 | Secure Governor's Counsel's approval of draft regs
| 6/30/2011 7-15-11 | 8 | 8 | 8 | Publish proposed regulations in State Register
| 2011-10-15 | 8 | 8 | 8 | 45-day comment period
| 2011-12-08 | 8 | 8 | 8 | Present regulations to PHHPC Codes Committee for recommendation and to full Council for adoption.
| 2011-12-28 | 8 | 8 | 8 | Publish Medicaid Update article regarding availability of rate for new observation units
| 2011-12-28 | 8 | 8 | 8 | Publish Notice of Adoption in State Regiser
| 2011-12-31 | 8 | 8 | 8 | Train staff
| 2011-12-31 | 8 | 8 | 8 | Disseminate information via HPN to hospitals regarding new operating standards for observation units and availability of Medicaid reimbursement.
Facilitate Access to Capital Financing through Obligated Groups, Including Multi-State Obligated Groups
| 2011-04-01 | P | P | P | Identify DOH workgroup members needed
| 2011-04-08 | P | P | P | Convene internal DOH workgroup to discuss and begin developing initiative requirements
| 2011-05-30 | 8 | 8 | 8 | Begin drafting of needed policy guidance and regulation(s), as needed
| 7/21/11 | 8 | 8 | 8 | Introduction of potential policy change to the Public Health and Health Planning Council Establishment and Project Review Committee
| 2011-08-04 | 8 | 8 | 8 | Present policy change to PHHPC
| 2011-08-15 | 8 | 8 | 8 | Revise policy guidance and regulations in response to PHHPC discussion.
| 2011-08-15 | 8 | 8 | 8 | Submit draft policy document and possible regulatory language for executive review
| 2011-09-13 | 8 | 8 | 8 | Executive sign-off of draft policy/regulation
| 2011-09-28 | 8 | 8 | 8 | Publish proposed regulation, if needed, in the State Register for 45 day public notice
| 2011-11-17 | 8 | 8 | 8 | Public Health and Health Planning Council Codes Committee review of proposed regulation for adoption
| 2011-12-08 | 8 | 8 | 8 | Public Health and Health Planning Council review of proposed regulation for adoption
| 2011-12-28 | 8 | 8 | 8 | Publish Notice of Adoption in State Register
| 2012-01-01 | 8 | 8 | 8 | Implementation of policy change and needed regulation changes
MRT#150 |  |  |  |  | Project Name: Develop an Automated Exchange/Medicaid Eligibility System Division Lead: Systems/DCE Team Lead: Judy Arnold/Tom Donovan Description: Execute Contract to Begin Development | 0
| 2011-04-01 | P | P | P | Statute enacted to permit mini-procurement for Early Innovator
| 5/15/2011 5/24/11 | 8 | 8 | 8 | Post Requirements on Web
| 4/30/2011 6/30/11 | 8 | 8 | 8 | Submit APD to CMS for Medicaid funding
| 2011-06-30 | 8 | 8 | 8 | Submit Contract to OSC
| 2011-08-30 | 8 | 8 | 8 | Execute Contract
MRT 153 |  |  |  |  | Project Name: Develop Innovative Telemedicine Applications by Reducing Regulatory Barriers and Providing Payment Incentives Division Lead: DFPP Team Lead: Joan Sicard Add'l Staff: Ronald Bass Description: Promote and enhance coverage of telemedicine by providing payment incentives and reducing coverage barriers | -0.23
| 2011-05-01 | P | P | P | Research other State Medicaid programs' policy and coverage guidelines for telemedicine (including credentialing arrangements, etc.)
| 5/1/2011 05/09/11 | P | P | P | Research Medicare's telemedicine policy including, but not limited to, credentialing arrangements, professional accountability/malpractice implications and coverage guidelines |  |  |  | New Medicare regs are pending. Final regs were to be published March 25, but have not yet been issued.
| 2011-06-15 | 8 | 8 | 8 | Meet with key stakeholders and organizations to gather information and identify advantages and barriers to implementation of telemedicine, telehealth, teleradiology and telepsych. |  |  |  |  | Maintenance
| 2011-06-15 | 8 | 8 | 8 | Determine, with staff from the Office of Technology and Dept of Legal Affairs, security issues related to health information exchange, patient confidentiality, etc.
| 2011-07-15 | 8 | 8 | 8 | Establish payment criteria and develop reimbursement amounts
| 2011-07-15 | 8 | 8 | 8 | Facilitate coverage with Medicaid Managed Care plans
| 2011-07-30 | 8 | 8 | 8 | Initiate regulatory process (concept paper, complete regulatory package, DLA review, publish proposed rule in State Register, public comment period, respond to public comments, finalize regulation)
| 2011-08-15 | 8 | 8 | 8 | Develop payment protocol and reimbursment methodology
| 2011-09-01 | 8 | 8 | 8 | Prepare a Medicaid Update article outlining telemedicine policy, coverage and billing guidelines
| 2011-09-15 | 8 | 8 | 8 | Update provider manuals and guidance documents
| 2011-09-30 | 8 | 8 | 8 | Regulation filed as final.
| 2011-09-30 | 8 | 8 | 8 | Educate Helpline and CSC staff to ensure that accurate policy information is communicated when responding to telemedicine inquiries
| 2011-10-01 | 8 | 8 | 8 | Implement policy
MRT # 154 |  |  |  |  | Project Name: Enhance and Improve the State's Medicaid Program Integrity Efforts. Division Lead: OMIG Portfolio Manager: Alicia Whitlingum |  |  |  | (62.00) - total
| MRT 154 - 2 |  |  |  | Exception and Conflict Report- Mandate Home Health Care Providers to provide OMIG with Exception and Conflict Report Data Project Lead: Tom Meyer Description: Mandate that all Certified Home Health Agencies (HHA) and Personal Care (PC) providers statewide utilize SANData or equivalent product as the point of service verification vendor, and provide Exception and Conflict Report data to the OMIG, which includes the identity of individual providers. Currently, such vendor data and reports are used by New York City (NYC) to verify actual services provided; length of visits; provider credentials; location of services provided; and schedule visits. | -45
Strategy and Plan to Educate Home Health Providers
| 2011-05-13 | P | P | P | Develop Strategy to Educate Home Health Providers on OMIG's plans for Controls and Monitoring
| 2011-05-25 | P | P | P | Conduct Webinar
| 2011-06-20 | 8 | 8 | 8 | Send Letters to Affected Providers
| 2011-08-05 | 8 | 8 | 8 | Visit Providers
| 2011-05-27 | 8 | 8 | 8 | Start tracking behavior
| 2011-05-25 | P | P | P | Begin Executing Education Plan Activities
| 2011-05-27 | 8 | 8 | 8 | Develop Review Plan for Suspicious Home Health Providers who use Vendors
| 2011-05-27 | 8 | 8 | 8 | Develop list of providers, using vendors, that reflect suspicious claiming behavior
| 5/30/11 | 8 | 8 | 8 | Begin Execute Review Plan for each provider as staffing plan allows
| 5/16/11 | P | P | P | Begin developing and implementing cost savings methodologies for education and review activities as applicable
Legislation
| 3/18/11 | P | P | P | Legislation proposed
| 4/1/11 | P | P | P | Legislation approval consistent with Budget enactment
Scope Clarification - Approach
| 2011-03-07 | P | P | P | Deputy meeting to set general project direction
High Level Program Development
| 4/8/11 | P | P | P | Identify leads and create workgroup stakeholders (DMI, Audit, Target, Admin, Compliance, County Demo, LTC)
| 5/6/2011 5/13/11 5/18/11 | 8 | 8 | 8 | Continue effort to get one or more LTC Designees |  |  |  | Mary Ann Anglin assigned from LTC
| 3/30/11 | P | P | P | Identify qualified vendors
| 2011-04-26 | P | P | P | Hold kickoff meeting with full representation of stakeholders
| 2011-05-12 | 8 | 8 | 8 | Identify requirements and roles of stakeholder groups
| 2011-05-13 | 8 | 8 | 8 | Identify data feeds destination (FACTS or Warehouse on eMedNY)
| 2011-05-23 | 8 | 8 | 8 | Develop detail project outline (rules and regulations, internal roles and processes, objectives, system/data requirements, timeframes)
| 2011-05-24 | 8 | 8 | 8 | External meeting to finalize scope and obtain buyin (necessary if LTC joins group?)
Develop Detailed Program Requirements
Regulatory Changes Reg.
| 2011-05-25 | 8 | 8 | 8 | Research current NYC Regulation
| 2011-06-21 | 8 | 8 | 8 | Draft concept paper and prepare package to Legal
| 2011-06-28 | 8 | 8 | 8 | Legal Review
| 2011-09-27 | 8 | 8 | 8 | GORR review and approval
| 2011-09-27 | 8 | 8 | 8 | Outreach meetings
| 2011-10-11 | 8 | 8 | 8 | Submit Proposal to DOS
| 2011-12-13 | 8 | 8 | 8 | Comment period
| 2011-12-20 | 8 | 8 | 8 | Draft public commentary assessment
| 2012-01-03 | 8 | 8 | 8 | Adoption of regulatory change (assume no provisions are needed)
Program Development by Stakeholder
| 2011-05-25 | 8 | 8 | 8 | Define OMIG Person/Organization Responsible for Overal Program Oversight
| 2011-06-28 | 8 | 8 | 8 | Develop detailed requirements and processes for DMI
| 2011-06-28 | 8 | 8 | 8 | Develop detailed requirements and processes for DTBA
| 2011-06-28 | 8 | 8 | 8 | Develop detailed requirements and processes for Compliance
| 2011-06-28 | 8 | 8 | 8 | Develop detailed requirements and processes for County Demo
| 2011-06-28 | 8 | 8 | 8 | Develop detailed requirements and processes for Audit
| 2011-06-28 | 8 | 8 | 8 | Develop detailed requirements and processes for LTC
Develop and Perform Reachout Functions
| 8/5/11 | 8 | 8 | 8 | Administrative Directives
| 8/5/11 | 8 | 8 | 8 | Medicaid Updates
| 8/5/11 | 8 | 8 | 8 | Webinar
| 8/5/11 | 8 | 8 | 8 | Policy Manual Updates
| 8/5/11 | 8 | 8 | 8 | Meeting with Trade Associations
Derive Methodology for the savings
| 7/18/11 | 8 | 8 | 8 | Develop methodology
| 8/1/11 | 8 | 8 | 8 | Approval by BBFM
| 8/15/11 | 8 | 8 | 8 | Internal Controls for initial review (audit of methodology)
| 8/15/11 4/28/11 | P | P | P | Update MRS Functionality in FACTS
Operational Details
| 2011-12-19 | 8 | 8 | 8 | Work with Providers and Vendors to begin program
Measure Savings - $45 M
| 2011-12-19 | 8 | 8 | 8 | Measure Cash Savings
| 2011-12-19 | 8 | 8 | 8 | Update MRS monthly in FACTS (cost avoidance)
| 2011-12-19 | 8 | 8 | 8 | Divisions Submit MRTSavings to BBFM
| 2011-12-19 | 8 | 8 | 8 | Perform Program Monitoring & Targeting
| 2011-12-19 | 8 | 8 | 8 | Begin Phase II - IT Tasks with Vendors
| MRT 154 - 3 | ▲ | ▲ | ▲ | Pharmacy Signature- Require Identification and Signature for Home Delivery and for Receipt of Prescriptions at Pharmacies Project Lead: Sharon Conway Description: Require all pharmacies to: reclaim from LTC facilities any unused drugs/supplies that were originally dispensed to Medicaid enrollees, restock and reuse returned unused drugs/supplies where permitted, require records for the credit, reuse, and destruction of returned unused drugs/supplies. | -0.24 |  |  | Impacted by pharmacies moving into manage care. Have not obtained a finalized rollout plan from DOH Valencia Lloyd.
| 2011-04-21 | P | P | P | Reach out to DOH OHIP for history of signature and opinion on proposal
| 2011-04-22 | P | P | P | Meet with OMIG legal staff to explain/discuss proposal
| 4/29/2011 5/13/11 | P | P | P | OHIP legal staff to consult with DOH OHIP counsel Jane McCloskey
| 2011-05-20 | P | P | P | OHIP Policy / Legal Schedule meeting w. Stakeholders to determine validality
Derive methodology for the savings
| 4/15/2011 4/22/11 | P | P | P | Develop methodology
| 2011-04-22 17:00 | P | P | P | Complete Budget Savings Form
| 5/6/2011 4/26/11 | P | P | P | Approval by BBFM
| 2011-05-20 | P | P | P | Internal Controls for initial review (audit of methodology)
| 5/27/2011 4/28/2011 | P | P | P | Update MRS in FACTS
Emergency Regulatory Change
| 2011-06-10 | 8 | 8 | 8 | Conduct emergency rule adoption process
| 2011-07-29 | 8 | 8 | 8 | Emergency Rule Adopted
Formally Adopt Regulation
| 2011-05-20 | P | P | P | Draft Programmatic Regulatory Language 18NYCRR505.3
| 2011-05-20 | P | P | P | Draft concept paper and prepare package to Legal
| 2011-06-03 | 8 | 8 | 8 | Legal Review
| 2011-07-22 17:00 | 8 | 8 | 8 | GO review and approval
| 2011-07-22 17:00 | 8 | 8 | 8 | Outreach meetings
| 2011-08-05 17:00 | 8 | 8 | 8 | Submit Proposal to DOS
| 2011-10-07 17:00 | 8 | 8 | 8 | Comment period
| 2011-10-14 17:00 | 8 | 8 | 8 | Draft public commentary assessment
| 2011-10-28 17:00 | 8 | 8 | 8 | Adoption of regulatory change (assume no provisions are needed)
| 2011-11-01 17:00 | 8 | 8 | 8 | Publish to Register
| 2011-11-02 17:00 | 8 | 8 | 8 | Regulation approved
Revise Audit Protocols & Findings
| 2012-01-25 | 8 | 8 | 8 | Implement protocol for audit periods consistent with effective date of regulation
| 2011-07-22 | 8 | 8 | 8 | Consult w. County demo
Notify Providers
| 2011-07-27 | 8 | 8 | 8 | Develop and distribute notification letter to all enrolled pharmacies
| 2011-09-07 | 8 | 8 | 8 | Develop and publish Medicaid Update article
| 2011-12-14 | 8 | 8 | 8 | Notification to PSSNY
Preparing provider for the change
| 5/20/201 4/22/11 | P | P | P | Explore the idea of using CardSwipe as method for obtaining signatures (if so, this should be part of the reg)
| 2011-12-14 | 8 | 8 | 8 | Provide template signature log
| 2011-12-14 | 8 | 8 | 8 | Provide template notice for signage within the pharmacy
| 2012-03-07 | 8 | 8 | 8 | Implement change with Pharmacies
Measure Savings $.6M
| 2012-07-12 | 8 | 8 | 8 | Measure cash savings (Audit findings)
| 2012-03-08 | 8 | 8 | 8 | Update MRS monthly in FACTS (cost avoidance)
| 2012-03-08 | 8 | 8 | 8 | Submit to BBFM
| MRT 154 - 4 | ▲ | ▲ | ▲ | Pharmacy Restock- Require Pharmacies to Restock and Re-Dispense Returned Medications Project Lead: Sharon Conway Project Description: Require pharmacies to restock and re-dispense returned medications from nursing homes, and maintain destruction records for drugs that cannot be re-dispensed. Currently, such providers “may” restock and re-dispense such medications (Medicaid Update article). While nursing homes return such medications to pharmacies, it is unclear how these providers process such returns. This proposal would conform State processes relative to the restocking of medications to Federal Deficit Reduction Act of 2005 requirements. | -0.6 |  |  | Impacted by pharmacies moving into manage care. Have not obtained a finalized rollout plan from DOH Valencia Lloyd.
Determine interrelationship with MRT 15L
| 2011-03-31 17:00 | P | P | P | Schedule conference call with OHIP Policy Staff to discuss duplicative actions in 154-4 and 15L
| 2011-04-12 17:00 | P | P | P | Agreement with DOH OHIP to work collaboratively on 154-4 and 15L
| 2011-04-22 | P | P | P | Collaboration meeting with DOH OHIP to discuss agency roles in implementation.
| 2011-06-01 | 8 | 8 | 8 | Decision needed regarding merging with 15 L
| 2011-06-10 | 8 | 8 | 8 | Revise current work plan/cost savings to reflect above decision
Derive methodology for the savings
| 2011-04-07 17:00 | P | P | P | Schedule meeting DMA DTBA on Pharmacy void tracking
| 4/15/2011 4/22/11 | P | P | P | Develop methodology
| 2011-04-22 17:00 | P | P | P | Complete Budget Savings Form
| 5/6/2011 4/26/11 | P | P | P | Approval by BBFM
| 2011-05-20 | P | P | P | Internal Controls for initial review (audit of methodology)
| 5/27/2011 4/28/2011 | P | P | P | Update MRS in FACTS
Emergency Regulatory Change
| 2011-06-10 | 8 | 8 | 8 | Conduct emergency rule adoption process
| 2011-07-29 | 8 | 8 | 8 | Emergency Rule Adopted
Formally Adopt Regulation 505.3
| 2011-05-20 | 8 | 8 | 8 | Draft Programmatic Regulatory Language 18NYCRR505.3
| 2011-05-20 | 8 | 8 | 8 | Draft concept paper and prepare package to Legal
| 2011-06-03 | 8 | 8 | 8 | Legal Review
| 2011-07-22 17:00 | 8 | 8 | 8 | GO review and approval
| 2011-07-22 17:00 | 8 | 8 | 8 | Outreach meetings
| 2011-08-05 17:00 | 8 | 8 | 8 | Submit Proposal to Department of State
| 2011-10-07 17:00 | 8 | 8 | 8 | Comment period
| 2011-10-14 17:00 | 8 | 8 | 8 | Draft public commentary assessment
| 2011-11-04 17:00 | 8 | 8 | 8 | Adoption of regulatory change (assume no provisions are needed)
| 2011-11-01 17:00 | 8 | 8 | 8 | Publish to Register-Regulation Effective Date
Revise Audit Protocols & Findings
| 2011-11-02 17:00 | 8 | 8 | 8 | Implement protocol for audit periods consistent with effective date of regulation
| 2011-11-02 17:00 | 8 | 8 | 8 | Coordinate with County Demo
Notify Providers
| 2011-09-02 17:00 | 8 | 8 | 8 | Develop and distribute notification letter to all enrolled pharmacies
| 2011-09-05 17:00 | 8 | 8 | 8 | Develop and publish Medicaid Update article
| 2011-09-02 17:00 | 8 | 8 | 8 | Notification to PSSNY
Measure Savings $1.5M
| 2011-11-03 17:00 | 8 | 8 | 8 | Measure cash savings (Adjustments/Voids)
| 2011-11-04 17:00 | 8 | 8 | 8 | Update MRS monthly in FACTS (cost avoidance)
| 2011-11-07 17:00 | 8 | 8 | 8 | Submit to BBFM
| MRT 154 - 5 |  |  |  | Access DOH BNE - Allow Access to the Department of Health (DOH) Bureau of Narcotics Enforcement (BNE), New York State Prescription Information Database Project Lead: Angelo Ruperto Project Description: Allow the OMIG access to DOH BNE data, which provides information on the cash purchase of controlled substances, to improve OMIG’s RRP targeting capabilities. Currently RRP targeting is limited to Medicaid payment data only.
Derive methodology for the savings
| 5/20/11 5/13/11 4/29/11 | P | P | P | Complete Budget Savings Form
| 5/2711 | 8 | 8 | 8 | Approval by BBFM
| 6/4//11 | 8 | 8 | 8 | Internal Controls for initial review (audit of methodology)
| 6/17/11 4/28/11 | P | P | P | Update MRS in FACTS
| 12/22/11 6/30/11 | 8 | 8 | 8 | Enact Legislation DOH Departmental #45 05-11
Formally Adopt Regulation
| 6/17/11 | 8 | 8 | 8 | OMIG Staff/DOH Discussions ongoing
System access
| 12/23/11 9/9/11 | 8 | 8 | 8 | Obtain access to DOH BNE system data
| 1/3/2012 10/17/11 | 8 | 8 | 8 | Determine rrp candidate restrictions
| 2/3/2012 10/17/11 | 8 | 8 | 8 | SMRT Review required
| 3/2/2012 10/17/11 | 8 | 8 | 8 | Determine referral to law enforcement
Measure Savings .1M
| 4/2/2012 11/18/11 | 8 | 8 | 8 | Update MRS monthly in FACTS (cost avoidance)
| 4/2/2012 11/18/11 | 8 | 8 | 8 | Submit to BBFM
| MRT 154 - 6 |  |  |  | Expand RRP - Expand the Restricted Recipient Program Project Lead: Sam Spitzberg Project Description: Define triggers that create mandatory restriction for recipients without existing full clinical reviews; automatically authorize recipient restriction for recipients who possess multiple (two or more) Medicaid identification cards and use or attempt to use such cards as well as present a forged or altered prescription; authorize recipient restriction for managed care enrollees for pharmacy/dental/other restriction categories; and extend the initial restriction period from 24 to 36 months, and extend the second, third and any additional restriction periods. | -2.2
| 2011-04-08 | P | P | P | Assigned staff members to assist drafting regulatory supporting documents as described by Erin M. from Counsel’s Office.
| 2011-04-08 | P | P | P | Provided copy of draft/rough regulation to DOH OOMC to explain how RRP works. DOH is moving ahead with teaching MCOs how to identify Medicaid recipients that ought to be restricted.
| 2011-04-08 | P | P | P | Reviewed NYC HRA and NYS DSS MOU from 1991 indicating that DSS would handle implementation for all NYC Restriction cases. HRA was supposed to provide payment to NYS for four state staff (two grade 18, two grade 6). Vicky Parry advised that no payments have been received from NYC HRA. MOU can be canceled by NYS with 90 days notice.
| 2011-04-08 | P | P | P | Received guidance from MIG to proceed with RRP Expansion project after advising him about the conflicts between mandatory managed care and eliminating the pharmacy carve out. RRP saves $150MM annually. The other MRT proposals that will wipe out the RRP FFS program expect to save significantly less money.
Determine Impact of MRT # 11 on MRT 154-4
| 2011-05-18 | P | P | P | Start determining impact of MCO, Pharmacy Carve Out on RRP Initiative
| 2011-06-10 | 8 | 8 | 8 | Revise work plan to reflect changes to RRP as a result of MRT #11 - Pharmacy Bundle into Medicaid Manage Care
| TBD | P | P | P | Obtain dates from OMC when MCO/Rx Carve Out Occuring by Population
Derive methodology for the savings
| 2011-05-20 | 8 | 8 | 8 | Develop methodology
| 2011-05-24 | 8 | 8 | 8 | Complete Budget Savings Form
| 2011-06-01 | 8 | 8 | 8 | Approval by BBFM
| 2011-07-15 | 8 | 8 | 8 | Internal Controls for initial review (audit of methodology)
| 7/15/2011 4/28/2011 | P | P | P | Update MRS in FACTS
Revise Methodology for the Savings
| TBD | 8 | 8 | 8 | Revise & Submit Budget Savings Form to BBFM
| TBD | 8 | 8 | 8 | Obtain Approval by BBFM
| TBD | 8 | 8 | 8 | Internal Controls Review Completed
| 2011-04-22 | P | P | P | Add cost avoidance category to MRS in FACTS
Add RRP Language to Manage Care Contract
| 2011-05-25 | 8 | 8 | 8 | Draft managed care contract language that includes timeframes for the lengths of restrictions and MCO responsibilities
| 2011-05-25 | P | P | P | Compile list of those recipients currently in the RRP
| 2011-05-25 | 8 | 8 | 8 | Compile criteria used to identify restricted recipients (utilization thresholds, medical appropriateness, list of abusive practices, JSURS criteria);
| 2011-06-03 | 8 | 8 | 8 | Develop narrative analysis when identifying/reporting criminal activity
| 2011-05-25 | 8 | 8 | 8 | Submit package to OHIP
| TBD | 8 | 8 | 8 | RRP Payment Edits need to be changed to identify those in MC and determine if edit should be invoked
| TBD | 8 | 8 | 8 | Test RRP Payment Edits
| TBD | 8 | 8 | 8 | Streamline RRP Administrative Processes (Restrict Remaining FFS Population + Recommend Restrictions to MCO)
Emergency Regulatory Change
| 2011-10-15 | 8 | 8 | 8 | Conduct emergency rule adoption process
| 2012-04-15 | 8 | 8 | 8 | Emergency Rule Adopted
Formally Adopt Regulation
| 2011-05-15 | 8 | 8 | 8 | Draft concept paper and prepare package to Legal
| 2011-05-15 | 8 | 8 | 8 | Submit to OMIG Legal
| 2011-06-15 | 8 | 8 | 8 | Legal Review
| 2011-07-15 | 8 | 8 | 8 | GO review and approval
| 2011-07-15 | 8 | 8 | 8 | Outreach meetings
| 7/22/11 | 8 | 8 | 8 | Submit Proposal to DOS
| 9/23/11 | 8 | 8 | 8 | Comment period
| 9/30/11 | 8 | 8 | 8 | Draft public commentary assessment
| 2011-12-01 | 8 | 8 | 8 | Adoption of regulatory change (assume no provisions are needed)
Implementation
| 2011-06-01 | 8 | 8 | 8 | Determine impact of MCO, Pharmacy Carve Out on RRP Initiative
| 2011-06-01 | 8 | 8 | 8 | Obtain dates from OMC when MCO/Rx Carve Out Occuring
| 2011-06-01 | 8 | 8 | 8 | Obtain guidance on how MCOs will incorporate 1.5M lives
| 2011-07-01 | 8 | 8 | 8 | Create Edits within the RRP system to identify people to restrict
| 2012-04-15 | 8 | 8 | 8 | Conduct additional targeting based on the modified Reg
| 2012-04-15 | 8 | 8 | 8 | Streamline SMRT Process
| 2012-04-15 | 8 | 8 | 8 | Automatically restrict Recipient consistent w. regulation change (7 criteria)
| 2012-04-15 | 8 | 8 | 8 | Relate to BNE cash payments
| 2012-04-15 | 8 | 8 | 8 | Authorize restriction of Manage Care Carved out Services
| 2012-04-15 | 8 | 8 | 8 | Extend restriction periods
|  | 8 | 8 | 8 | LDSS Outreach (ongoing)
| 2011-07-15 | 8 | 8 | 8 | Counties/Local Districts
| 2011-07-15 | 8 | 8 | 8 | Beneficiary organizations
| 2011-07-15 | 8 | 8 | 8 | Physicians / Pharmacy
Measure Savings
| 2011-05-15 | 8 | 8 | 8 | Measure cash savings (Audit findings)
| 2011-06-01 | 8 | 8 | 8 | Update MRS monthly in FACTS (cost avoidance)
| 2011-06-01 | 8 | 8 | 8 | Submit to BBFM
| MRT 154 - 7 | T | T | T | Card Swipe Pharmacy- Mandate Participation in the Cardswipe Program for Pharmacies Billing in Excess of $1M in 2010 Who Have Not Submitted A Compliance Certification Project Lead: Sheila Emminger Project Description: Require all pharmacies billing Medicaid in excess of $1M who have not filed a Compliance Certificate with the Bureau of Compliance to participate in the OMIG Cardswipe Program (landline) with a Vx570 terminal supplied by the department. | -3.99 |  |  |  | Maintenance
Derive methodology for the savings
| 2011-03-29 17:00 | P | P | P | Develop methodology
| 5/19/2011 6/3/11 | 8 | 8 | 8 | Confirm DOB approval of funding for contract ammendment for terminals
| 2011-05-19 | P | P | P | Compile expenditure and projected savings data for the 98 pharmacies billing Medicaid in excess of $1M that have not filed a Compliance Certificate
| 2011-05-19 | P | P | P | Compile expenditure and projected savings data for the 149 pharmacies billing Medicaid in excess of $1M that have filed a Compliance Certificate
| 2011-05-19 | 8 | 8 | 8 | For both populations, work with Mike Waring (DMI) to obtain AG clearance for the 84 (14 + 70) providers currently under AG review
| 5/19/2011 05/17/11 | P | P | P | Arrange a meeting for week of 5/23/2011 to discuss results of above data analysis. Invitees: J.Sheehan; T. Meyer; V.Parry; M. Hennessey; M. Babcock; L. Pink; S. Emminger; A. Whitlingham
| 2011-05-20 | P | P | P | At 5/19/2011 meeting, discuss with M. Hennessey any feedback received from pharmacy advocates/industry and the need for outreach
| 2011-05-20 | P | P | P | Obtain Mr. Sheehan's decision on population - will we include those pharmacies billing Medicaid in excess of $1M that have filed a Compliance Certificate
| 2011-05-27 | 8 | 8 | 8 | Work with Kathy Napoli to craft the "welcome to the program" letter that will be sent to the 247 providers
| 4/15/2011 4/22/2011 5/20/2011 5/27/2011 | 8 | 8 | 8 | Complete Budget Savings Form
| 4/22/2011 4/26/11 5/23/2011 5/31/2011 | 8 | 8 | 8 | Submit Budget Savings Form to BBFM
| 4/18/2011 4/29/11 5/27/2011 6/3/2011 | 8 | 8 | 8 | Approval by BBFM
| 5/2/2011 5/9/11 06/03/2011 6/10/2011 | 8 | 8 | 8 | Internal Controls for initial review (Audit of methodology)
| 5/19/2011 4/28/11 05/11/2011 | P | P | P | Add new cost avoidance category to MRS in FACTS
| 2011-07-01 17:00 | 8 | 8 | 8 | Address data storage capacity in FACTS
| 2011-12-28 17:00 | 8 | 8 | 8 | Produce and Report Monthly cost avoidance
Rollout/Adding All Pharmacies Billing Over $1M - No Compliance Certification
| 4/1/2011 5/20/2011 | 8 | 8 | 8 | Develop a deployment plan based on Pharmacies Billing Over $1M that have not completed a Compliance Certification
| 6/1/11 6-3-11 | T | T | T | Obtain Funding for POS Terminals
| 5/2/2012 6/15/2011 | 8 | 8 | 8 | Begin Contacting providers to explain the program (ongoing)
| 5/2/2012 6/15/2011 | 8 | 8 | 8 | Begin opening and tracking cases in FACTS (ongoing)
| 5/2/2012 6/15/2011 | 8 | 8 | 8 | Begin process to establish start date for using terminal and send letter (target mailing) - ongoing
| 5/2/2012 6/15/2011 | 8 | 8 | 8 | Provide support to providers establishing terminal use (ongoing)
| 2011-07-30 | T | T | T | Monitor Impact of DOH's 5010 rollout on terminal deployment
| 2011-07-30 | 8 | 8 | 8 | Adjust deployment schedules as needed
Monitor and Control Rollout
| 5/2/2012 6/15/2011 | 8 | 8 | 8 | Deal with providers that refuse participation - ongoing process
| 5/2/2012 6/15/2011 | 8 | 8 | 8 | Perform Focus review and/or site visit - ongoing process
| 5/2/2012 6/15/2011 | 8 | 8 | 8 | Send Letter from the MIG - as needed
| 5/2/2012 6/15/2011 | 8 | 8 | 8 | Place on edit 1141 - if needed
Education and outreach
| 10/7/2011 8/15/2011 | 8 | 8 | 8 | Begin Site visits - ongoing
| 10/7/2011 8/15/2011 | 8 | 8 | 8 | Begin Outreach to Local Districts- ongoing
| 2011-08-26 17:00 | 8 | 8 | 8 | Arrange Webinars
| 9/5/2012 9/15/2011 |  |  |  | Monitor Compliance
| 9/5/2012 9/15/2011 | 8 | 8 | 8 | Begin Monthly Monitoring 3 months after first deployment - ongoing
| 9/5/2012 9/15/2011 | 8 | 8 | 8 | Begin process to Establish swipe percentage - ongoing
| 9/5/2012 9/15/2011 | 8 | 8 | 8 | Quarterly Preparation of Mail merger - ongoing
| 9/5/2012 9/15/2011 | 8 | 8 | 8 | Begin process to document in FACTS - ongoing
| 9/5/2012 9/15/2011 | 8 | 8 | 8 | Ongoing process to assist providers with swipe percentage issues
| 9/5/2012 9/15/2011 | 8 | 8 | 8 | Ongoing process to produce statistical reports on card swipe program as required
| 9/5/2012 9/15/2011 |  |  |  | Measure Savings $13M
| 9/5/2012 9/15/2011 | 8 | 8 | 8 | Measure cash savings (Audit findings) cost avoidance
| 9/5/2012 9/15/2011 | 8 | 8 | 8 | Update MRS monthly in FACTS (cost avoidance)
| 9/5/2012 9/15/2011 | 8 | 8 | 8 | Submit to BBFM (Monthly)
| 2012-03-07 17:00 | T | T | T | Monitor implementation dates and assess impact of MRT-11/EPR #1605 - Bundle Pharmacy fee-for-service into Medicaid Managed Care
| 2012-03-07 17:00 | 8 | 8 | 8 | Monitor Bill (6555) to require palm scanning/Biometric monitoring
| MRT 154 - 8 |  |  |  | Project Name: Duplicate Claims- Medicare Coordination of Benefits with Provider Submitted Duplicate Claims Project Lead: Julie DeRubertis, Cathy McCulskey Project Description: Review claims approved and paid by Medicare for dual eligible recipients, which are also submitted to Medicaid for payment, and refine existing edit logic (#02112) to prevent such duplication. Existing edit logic is not always adequate to identify such duplication, which results in the payment of same claims by both Medicare and Medicaid. Potential duplicate claims will be reviewed and recoveries made when appropriate. Finding/recovery validation will help further refine the current edit logic criteria to appropriately reflect Medicare participation prior to authorizing Medicaid payments. | -10
Edit Change 02113
| 2011-04-15 17:00 | P | P | P | Edit Calculation 02113
Derive methodology for the savings
| 2011-04-01 17:00 | P | P | P | Develop methodology
| 4/20/2011 4/29/11 | P | P | P | Complete Budget Savings Form
| 5/6/2011 5/3/2011 | P | P | P | Approval by BBFM
| 2011-05-16 17:00 | P | P | P | Internal Controls for initial review (audit of methodology)
| 2011-05-17 | P | P | P | Update MRS in FACTS
Change to Payment Process for All Crossover Claims
Implement Edit
| 2011-04-11 17:00 | P | P | P | Request Edit Logic Change
| 4/25/2011 4/20/2011 | P | P | P | Obtain DOH Policy approval of Evolution Request
| 5/20/2011 5/30/11 | 8 | 8 | 8 | Prioritize as e-MedNY Evolution
| 2011-07-22 17:00 | 8 | 8 | 8 | Functional Requirements Document Developed
| 2011-05-30 17:00 | 8 | 8 | 8 | Technical evaluation of system
| 2011-06-01 17:00 | 8 | 8 | 8 | Obtain project implementation date
| 2011-06-01 17:00 | 8 | 8 | 8 | Schedule of Edit Runs by OHIP and Systems
| 2011-06-06 17:00 | 8 | 8 | 8 | Testing
| 2011-08-02 17:00 | 8 | 8 | 8 | Project Implementation
| 2011-11-01 17:00 | 8 | 8 | 8 | New Data warehouse Training
| 2011-10-03 17:00 | 8 | 8 | 8 | User Acceptance Testing
| 2011-10-31 17:00 | 8 | 8 | 8 | Rollout system changes to e-Med NY
Derive methodology for the savings
| 4/15/2011 4/29/11 | P | P | P | Develop methodology
| 5/2/2011 4/29/11 | P | P | P | Complete Budget Savings Form
| 5/16/2011 5/3/2011 | P | P | P | Approval by BBFM
| 2011-05-30 17:00 | P | P | P | Internal Controls for initial review (audit of methodology)
| 2011-05-17 | P | P | P | Update MRS in FACTS
Obtain recoveries (Checks, Voids, and Withholds)
| 2011-06-15 | P | P | P | Medicaid update article |  |  |  | Article submitted to Erin Bonano on 4/28/11, OMIG coordinator.
| 2011-12-30 17:00 | P | P | P | Obtain staffing
| 2011-12-23 17:00 | 8 | 8 | 8 | Track recoveries
| 2011-12-23 17:00 | 8 | 8 | 8 | Run Recoveries against J. Flora files |  |  |  | Submitted claims to J. Flora 5/5/11 to identify duplicate recovery efforts.
| 2011-12-23 17:00 | 8 | 8 | 8 | Conduct system match of Medicare crossover claims (4 way match)
| 2011-12-23 17:00 | 8 | 8 | 8 | Send out letters to providers
| 2011-05-27 | 8 | 8 | 8 | Calculate Medicaid savings to support Edit and submit to BBFM
| 2011-05-27 | 8 | 8 | 8 | Share with Medicaid director (Jason Helgerson)
System Match
Medicaid Crossover
| 2011-12-26 17:00 | 8 | 8 | 8 | Identify system matches (12/31/10) |  |  |  | Claims for recovery have been identified 5/5/11 and sent to Kevin Ryan and Jeff Flora for removal of duplicate recovery efforts.
| 2011-10-03 17:00 | 8 | 8 | 8 | Send provider notice
| 2011-12-23 17:00 | 8 | 8 | 8 | Recover savings
| 2012-12-31 17:00 | 8 | 8 | 8 | Repeat as needed (until edits are implemented)
Derive methodology for the savings
| 4/1/2011 4/29/11 | P | P | P | Develop methodology
| 5/2/2011 4/29/11 | P | P | P | Complete Budget Savings Form
| 5/16/2011 5/3/2011 | P | P | P | Approval by BBFM
| 2011-05-31 17:00 | P | P | P | Internal Controls for initial review (audit of methodology)
| 2011-05-17 | P | P | P | Update MRS in FACTS
Update Enrollments for ownership changes & Mergers (Entity ID)
| 2011-06-30 | 8 | 8 | 8 | Meet with OHIP enrollment
| 2011-12-31 | 8 | 8 | 8 | Coordinate and rectify NPI and Entity IDs |  |  |  | Ongoing process to determine additional NPI's which should have same entity ID.
| 2011-06-15 | P | P | P | Medicaid update article submitted |  |  |  | Article submitted to Erin Bonano on 4/28/11, OMIG coordinator.
| 2011-12-30 17:00 | 8 | 8 | 8 | Recovery of funds (VOIDS)
Measure Savings
| 2011-12-30 17:00 | 8 | 8 | 8 | Track recoveries
| 2011-12-30 17:00 | 8 | 8 | 8 | Update MRS monthly in FACTS Savings (cost avoidance) $10M
MRT # 164 |  |  |  |  | Project Name: Align Medicare Part B clinic coinsurance with Medicaid coverage and rates Division Lead: DFPP Team Lead: Ron Bass Description: Ensure that Medicare B payment does not exceed Medicaid allowed amount | -8.55
| 2011-03-31 | P | P | P | Draft Federal Public Notice
| 2011-03-31 | P | P | P | Draft revisions to State Plan
| 2011-04-15 | P | P | P | Determine policy changes
| 2011-04-15 | P | P | P | Initiate regulatory process (concept paper, complete regulatory package, DLA review, publish proposed rule in State Register, public comment period, respond to public comments, finalize regulation)
| 2011-04-15 | P | P | P | Initiate eMedNY system changes (develop Evolution Project Request to update/develop edit(s))
| 2011-04-22 | P | P | P | Submit State Plan Amendment
| 2011-05-18 | 8 | 8 | 8 | Regulatory Reform Committee Meeting
| 2011-08-01 | 8 | 8 | 8 | Receive SPA approval
| 2011-08-01 | 8 | 8 | 8 | Regulation filed as final.
| 2011-08-15 | 8 | 8 | 8 | Provider notification via Medicaid Update
| 2011-09-15 | 8 | 8 | 8 | Train staff (including DOH staff, CSC staff, Helpline staff) to respond to provider and enrollee inquiries
| 2011-09-15 | 8 | 8 | 8 | Complete system changes.
| 2011-10-01 | 8 | 8 | 8 | Implementation of new policies and associated system changes.
MRT # 191 |  |  |  |  | Project Name: Decrease the Incidence and Improve Treatment of Pressure Ulcers Division Lead: OLTC Team Lead: Jackie Pappalardi Add'l Staff: Mary Ellen Hennessy,Ruth Leslie,Valerie Deetz, Jonaca Martin Description: This proposal provides financial support for the development of regional collaboratives to improve communications in care transitions across the healthcare continuum and for the development of measurement systems to show the reduction of pressure ulcers. | 0.35
| 2010-06-01 | P | P | P | Convene Stakeholders across health care settings to develop a plan to reduce the incidence and improve the treatment of pressure ulcers.
| 2010-07-15 | P | P | P | Develop regional collaboratives for the reduction of pressure ulcers through improving communications and sharing evidenced based resources to build care transitions across health care settings.
| 2010-08-15 | P | P | P | Send a letter of introduction to the Gold Stamp:Reduction of Pressure Ulcer Initiative to providers across health care settings.
| 10/04/2010-02/28/2011 | P | P | P | Communicate plan to providers and industry stateholders through Webinars, informational brochures and regional conferences.
| 2011-07-01 | 8 | 8 | 8 | Complete all aspects of the funding process.
| 2011-09-01 | 8 | 8 | 8 | Engage regional health care leaders to commit staff time and resources to work together in regional collaboratives.
| 2011-10-01 | 8 | 8 | 8 | Provide funding and technical support for the facilitation of new regional coalitions and the development of a tool to measure the reduction of pressure ulcers.
| 2011-12-15 | 8 | 8 | 8 | Implement the Evaluation Plan to measure performance.
MRT# 196 |  |  |  |  | Project Name: Supportive Housing Division Lead: OLTC Team Lead: Mark Kissinger Description: Create a supportive housing interagency work group with a goal of a proposal submitted to the MRT by October 1, 2011. The goal of the workgroup is to create between 5000 and 10,000 housing opportunities for persons at risk of nursing home or other institutional placements. This will be a $75M increase starting with SFY 12-13. | 0
| 05/01-08/11 | 8 | 8 | 8 | Conduct research on prior state efforts at supportive housing.
| 6/1/2011 7-1-11 | 8 | 8 | 8 | Establish the interagency supportive housing workgroup.
| 7/1/2011 8-1-11 | 8 | 8 | 8 | First meeting of the workgroup.
| 07/11-09/01/11 | 8 | 8 | 8 | Meeting internally and with external stakeholders on options.
| 9/1/2011 10/1/11 | 8 | 8 | 8 | Finalize the 2012-13 Budget Proposal
| 10/01-12/31/11 | 8 | 8 | 8 | Meet with Executive Chamber and the Division of Budget on the proposal.
MRT #200 |  |  |  |  | Project Name: Change in scope of practice for mid-level providers to promote efficeiency and lower Medicaid costs Division Lead: OLTC Team Lead: Mary Ann Anglin Add'l Staff: Jackie Pappalardi, Rebecca Gray, Mary Hart Description: Expand the scope of practice for RNs, LPNs, and home health aides to improve access to services and decrease associated costs in delivering services | 0
Part A - Permit Nurses/patient s(under their scope of practice exemption) to orient/direct HHAs and PC wokers to provide nursing care as is currently allowed in the consumer directed personal assistant program;
| 2011-04-15 | P | P | P | Convene internal meetings to determine next steps for revising scope of practice
| 2011-05-15 | P | P | P | Identify stakeholders with representatives of State Education Department; New York State Nurses Association and other interested stakeholders; identify areas in statutes, regulations and policies that would require change and formulate recommendations on scope of practice
| 6/1/2011 7/1/11 | 8 | 8 | 8 | Set schedule and outcomes for workgroup
| 6/15/2011 7-15-11 | 8 | 8 | 8 | Convene first workgroup meeting
| 2011-10-01 | 8 | 8 | 8 | Workgroup to present report with recommendations on revisions to scope of practice
Part B - Allow Nurse Practioners to sign Medical Evaluations for ACF/AL.
| 2011-06-01 | P | P | P | Draft regulatory changes to title 18 for internal review
| 2011-06-01 | P | P | P | Draft statuatory language for internal review
|  | 8 | 8 | 8 | Publish regulations in state register
|  | 8 | 8 | 8 | Respond to public comment
| 2012-01-01 | 8 | 8 | 8 | Promulgate regulations
| 2012-04-01 | 8 | 8 | 8 | Issue final DAL
Part C Eliminate restrictions on nursing practices in ACFs.
| 2011-04-28 | P | P | P | Discussed the concept of nursing in ACFs with the Division of Legal Affairs
| 2011-05-11 | P | P | P | Meeting scheduled with State Education Department representatives to discuss medications in ACFs
| 5/20/2011 6/20/11 | 8 | 8 | 8 | DAL to draft cncept paper proposal re: ACF limited LHCSAs
| 6/15/2011 7-1-11 | 8 | 8 | 8 | Complete review of ACF Regulations and identify necessary amendments
Part D Allow LPNs to complete assessments in LTC settings
| 2011-04-15 | P | P | P | Convene internal meetings to determine next steps for revising scope of practice
| 2011-05-15 | P | P | P | Identify stakeholders with representatives of State Education Department; New York State Nurses Association and other interested stakeholders; identify areas in statutes, regulations and policies that would require change and formulate recommendations on scope of practice
| 6/1/2011 7-1-11 | 8 | 8 | 8 | Set schedule and outcomes for workgroup
| 6/15/2011 7-15-11 | 8 | 8 | 8 | Convene first workgroup meeting
| 2011-10-01 | 8 | 8 | 8 | Workgroup to present report with recommendations on revisions to scope of practice
Part E Extend the use of medication aides into nursing homes
| 5/1/2011 7-1-11 | 8 | 8 | 8 | Establish work group with representatives of State Education Department; New York State Nurses Association and other interested stakeholders
| 5/15/2011 7-15-11 | 8 | 8 | 8 | Identify areas in statutes, regulations and policies that would require change
| 5/15/2011 7-15-11 | 8 | 8 | 8 | Develop agenda and timeline for meetings with SED and industry on proposed changes
| 9/1/2011 10-1-11 | 8 | 8 | 8 | Draft changes to SED statute after workgroup discussions and consensus is reached
Part F Expand the scope of practice of home health aides to include the administration of pre-poured medications to both self-directing and non-self directing individuals
| 2011-04-15 | P | P | P | Convene internal meetings to determine next steps for revising scope of practice
| 2011-05-15 | P | P | P | Identify stakeholders with representatives of State Education Department; New York State Nurses Association and other interested stakeholders; identify areas in statutes, regulations and policies that would require change and formulate recommendations on scope of practice
| 6/1/2011 7-1-11 | 8 | 8 | 8 | Set schedule and outcomes for workgroup
| 6/15/2011 7-15-11 | 8 | 8 | 8 | Convene first workgroup meeting
| 2011-10-01 | 8 | 8 | 8 | Workgroup to present report with recommendations on revisions to scope of practice |  |  |  |  | Maintenance
MRT #209 |  |  |  |  | Project Name: Expand Hospice Division Lead: OLTC Team Lead: Mary Ann Anglin Add'l Staff: Rebecca Fuller Gray Description: This proposal will expand hospice: Expand concurrent hopsice and curative care to Medicaid adults; Expand definition of terminal illness to 12 months; Integrate hospice into medical home and ACO projects | 0
| 2011-03-25 | P | P | P | Request data to determine the number of dual eligibles, i.e. Medicare and Medicaid over age 18 that access hospice benefits; to determine the current length of stay for hospice; determine the number of Medicaid only individuals that access hospice
| 2011-05-05 | P | P | P | Request DLA to review the proposal in terms of Social Security Act issues
| 2011-05-15 | P | P | P | Contact the CMS Central Office to clarify rules regarding election of hospice benefit and the continuation of curative treatment in adults
| 2011-05-24 | P | P | P | Discuss components of the proposal with the Hospice and Palliative Care Association of NYS
| TBD | 8 | 8 | 8 | Encourage NYS hospices to apply to participate in CMS's 15 three-year demonstration projects to evaluate impact of concurrent hospice and curative care for adults when available. Demonstration in design phase and presently not funded. Anticipated project date not known.
| 6/1/2011 8-1-11 | 8 | 8 | 8 | Conduct research on the medical home model of care delivery in NYS and specifically as it relates to the Affordable Care Act and end of life care. Health care reform legislation authorizes the Department of Health and Human Services (HHS) to test medical homes among other new care-delivery models. Supporters hope patient-centered medical homes will help refocus the U.S. health care system on the benefits of primary care.
| 6/1/2011 8-1-11 | 8 | 8 | 8 | Conduct research on the ACO and its success in NYS and applicability to hospice in particular. The accountable care organization has been a model for health care reform, yet its success has been limited to a handful of health care systems across the country. The accountable care organization model has recently taken on far greater significance since being introduced as one of Medicare’s pilot programs in the Senate’s health reform bill.
| 2011-07-01 | T | T | T | Evaluate research to determine how to implement the expansion of the definition of terminal illness to 12 months if possible |  |  |  | Per our research and CMS determination, expanding terminal definition does not qualify for FFP.
| 2011-08-01 | 8 | 8 | 8 | Draft Federal Notice for SPA change if necessary
| 2011-08-01 | 8 | 8 | 8 | Draft revised hospice regulations
| 2011-09-01 | 8 | 8 | 8 | Prepare notice to state register for publication of regulations
| 2011-10-01 | 8 | 8 | 8 | Prepare response to public comments
| 2011-11-01 | 8 | 8 | 8 | Revise billing methodolgy and payment rules for implementation
| 2011-11-15 | 8 | 8 | 8 | Draft state plan amendment
| 2011-12-15 | 8 | 8 | 8 | Submit state plan amendment
| 2012-01-01 | 8 | 8 | 8 | Implement expanded hospice benefit in NYS
MRT #217 |  |  |  |  | Project Name: Create an Office for Development of Patient-Centered Primary Care Initiatives Division Lead: Primary Care Team Lead: Karen Westervelt Description: Create a dedicated Office of Primary Care | 0
| 2011-04-29 | P | P | P | Meet with external stakeholders to discuss and obtain feedback re: initial proposed office framework
| 4/1/2011 5/1/2011 | P | P | P | Convene internal DOH workgroup to discuss and develop initial proposed office frame-work/structure
| 2011-06-15 | 8 | 8 | 8 | Draft plan based on feedback. Circulate to internal workgroup for comments.
| 4-15-11 6/30/2011 | 8 | 8 | 8 | Reconvene internal workgroup to discuss legal and implementation issues-redraft plan.
| 5/1/2011 7-15-11 | 8 | 8 | 8 | Prepare initial office creation plan-circulate and obtain clearances.
| 5/15/2011 7-30-11 | 8 | 8 | 8 | Meet with external stakeholders. |  |  |  |  | Maintenance
| 5/15/2011 7-30-11 | 8 | 8 | 8 | In conjunction with MRT Proposal #70, create advisory group to the Commissioner consisting of payor and provider participants and stakeholders. Advisory group will focus on both primary care objectives and patient centered medical homes.
| 6/15//2011 8-1-11 | 8 | 8 | 8 | Rework plan based on stakeholder input.
| 6/30/2011 8-15-11 | 8 | 8 | 8 | Finalize plan and obtain clearances.
| 7/1/2011 8-25-11 | 8 | 8 | 8 | Implement plan.
| 7/2/2011 8-17-11 | 8 | 8 | 8 | Prepare statewide primary care needs assessment to help facilitate expansion of primary care.
| 7/3/2011 8-31-11 | 8 | 8 | 8 | Finalize needs assessment.
| 7/4/2011 9-1-11 | 8 | 8 | 8 | Develop statewide primary care growth strategy to plan for expansion of patient-centered medical home settings and 2014 Affordable Care Act reforms.
MRT # 243 |  |  |  |  | Project Name: Accountable Care Organizations Division Lead: DHCF Team Lead: Ann Heilmann Add'l Staff: Caitlin Connor Description: Ensure that every Medicaid member is enrolled in Care Coordination for improving quality of care, efficiencient delivery of services, while generating cost savings. | 0
ADMINISTRATIVE
| 2011-05-06 | P | P | P | Internal discussion on DOH comments on proposed federal ACO rule.
| 2011-06-06 | 8 | 8 | 8 | Comments due
| 2011-09-28 | 8 | 8 | 8 | Federal Public Notice publication
| 2011-09-30 | 8 | 8 | 8 | Regulations (required by enacted statute) |  |  |  | Must have Regs for: ACO certification criteria; quality standards; reporting requirements.
| 2011-12-31 | 8 | 8 | 8 | Waiver Application to CMS |  |  |  | May need waiver of SSA 1915 requirements for statewideness; freedom of choice.
| 2011-12-31 | 8 | 8 | 8 | State Plan Amendment to CMS
RESEARCH AND DEVELOPMENT
| 2011-04-14 | P | P | P | Review and summarize enacted state statute
| 2011-04-14 | P | P | P | Review proposed federal rule on Medicare based ACOs/ Summarize for Jason H.
| 2011-04-15 | P | P | P | Provide ACO Briefing Paper for Commissioner
| 2011-03-18 | P | P | P | Contact HANYS and Greater NY for feedback on proposal
| 2011-03-18 | P | P | P | Conference call with Bronx Project (Montefiore) on their interest, ideas, and concerns
| 2011-04-30 | P | P | P | Research ACOs prototypes: Buffalo area informal ACO, Rural Health Network
| 2011-04-30 | 8 | 8 | 8 | Review Kaiser Foundation reports for ACO information
| 2011-05-17 | P | P | P | Begin ongoing discussions with HANYS and Greater NY for hospital interest
| 2011-05-31 | P | P | P | Research ACOs in other states - Colorado, Massachusetts, North Carolina, Vermont, California Kaiser Network; summarize by state |  |  |  | See document On The Road to Better Value: State Role in Promoting ACOs (National Academy for State Health Policy) from K.L.
| 2011-06-30 | 8 | 8 | 8 | Contact associations for primary care providers, including physician's groups, for interest in participating
| 2011-06-30 | 8 | 8 | 8 | Research implications of Risk to providers/ Reserve requirements
| 2011-09-30 | 8 | 8 | 8 | Develop ACO cerification criteria |  |  |  | required by statute; to be defined through regulation
| 2011-09-30 | 8 | 8 | 8 | Develop quality standards |  |  |  | required by statute; to be defined through regulation
| 2011-09-30 | 8 | 8 | 8 | Develop reporting requirements |  |  |  | required by statute; to be defined through regulation
| 2011-12-31 | 8 | 8 | 8 | Develop accountability standards
LEGAL ISSUES
| 2011-04-30 | P | P | P | Contact legal staff to clarify any legal issues: anti trust implications, legal structure needed for ACO billing on behalf of all participating providers
| 2011-04-30 | P | P | P | Contact legal staff to clarify any legal issues related to patient rights and responsibilities
INTERNAL DISCUSSIONS
| 2011-05-30 | 8 | 8 | 8 | Advantages / Disadvantages to entering into a three year agreement with CMS to implement ACOs.
| 2011-05-30 | 8 | 8 | 8 | Determine whether to pursue federal health care reform ACO programs/demonstrations or establish independent New York Medicaid ACOs.
| 2011-05-30 | 8 | 8 | 8 | Discussions regarding who is the ACO leader: hospital, physician, medical home
| 2011-06-30 | 8 | 8 | 8 | Identify target population: fee for service and/or managed care; geographic region
| 2011-05-30 | 8 | 8 | 8 | Determination on pros and cons of mandatory or voluntary participation on part of providers and enrollees
| 2011-05-30 | 8 | 8 | 8 | Discussions on limiting program to a specific geographic area
| 2011-06-30 | 8 | 8 | 8 | Identify services: 'all' or do we exclude mental hygiene and LTC
| 2011-06-30 | 8 | 8 | 8 | Discuss with Division of Policy and Planning and department medical directors the relationship of ACOs to Medical Homes and Health Homes
| 2011-06-30 | 8 | 8 | 8 | Contact managed care to identify and discuss possible partial capitation issues
COMMUNICATION WITH STAKEHOLDERS
| 2011-12-31 | 8 | 8 | 8 | Article for the Medicaid Update once more details are available
| 2011-12-31 | 8 | 8 | 8 | Q and As for Department WEB site
QUALITY MEASURES
| 2011-12-31 | 8 | 8 | 8 | Research National Committee for Quality Assurance Standard
| 2011-12-31 | 8 | 8 | 8 | Work with Division of Quality and Evaluation to establish quality and cost measurement tools as well as a system for tracking savings
| 2011-12-31 | 8 | 8 | 8 | Meet with department medical directors on ideas for quality improvements while promoting efficiencies
| 2011-12-31 | 8 | 8 | 8 | Appropriate data base for all payer quality measures (SPARCS)
EMEDNY SYSTEM ISSUES
| 2011-12-31 | 8 | 8 | 8 | Meet with Division of Information Technology to determine how to distribute and track payments to a central organization rather than individual providers
| 2011-12-31 | 8 | 8 | 8 | Develop and Submit Evolution Project if required
PAYMENT / REIMBURSEMENT
| 2011-12-31 | 8 | 8 | 8 | Work with Division of Health Care Financing reimbursement staff on possible rate setting issues related to hospital inpatient
| 2011-12-31 | 8 | 8 | 8 | Work with Division of Health Policy and Planning staff on possible rate setting issues related to physicians and APG outpatient
FOLLOW UP
| 2011-12-31 | 8 | 8 | 8 | Develop survey tool for participating providers to track quality of care and efficiencies
MRT# 889 |  |  |  |  | Project Name: Redesign NYS Bed Hold Policy for Nursing Homes Division Lead: OLTC Team Lead: Jacqueline Pappalardi Additional Staff: John Ulberg, Robert Loftus, Linda Gowdy Description: Redesign the nursing home bed hold policy for all Medicaid recipients over 21 to recalibrate Medicaid benefits and reimbursement rates, and to meet the Medicaid savings target as proposed. | 0
| 2011-03-10 | P | P | P | Meet with Internal Stakeholders to review options to implement proposal.
| 2011-03-11 | P | P | P | Submit Federal Public Notice for MRT 889
| 2011-05-13 | P | P | P | Draft and submit SPA.
| 2011-07-15 | 8 | 8 | 8 | Identify regulatory and systems requirements necessary to implement the recommendations of the proposal |  |  |  |  | Maintenance
| 2011-08-15 | 8 | 8 | 8 | Submit draft policy recommendations to Department Executives.
| 2011-09-01 | 8 | 8 | 8 | Repeal existing nursing home Reserved Bed Day Payment regulations.
| 2011-10-01 | 8 | 8 | 8 | Communicate policy requirements to Stakeholders through a Dear Administrator Letter and Dear CEO letter. Post Questions and Answers and provider communication to the public website.
| 2012-01-01 | 8 | 8 | 8 | Effective date of legislation
#990 |  |  |  |  | Project Name: Explore the Establishment of Reimbursement Rates to Support Efforts to Address Health Disparities Division Lead: Division of Financial Planning and Policy (DFPP); Greg Allen, Director Team Lead: Ron Bass Add'l staff: Donna Haskin Description: Explore enhanced reimbursement rates for culturally competent care | 0
| 5/15/2011 5/1/2011 | P | P | P | Discuss initiative with the Office of Public Health to determine activities necessary to support culturally competent care that address health disparities |  |  |  | Meetings with OPH and CCH on 5/5, 5/9. Ron Bass, DFPP, will be contacting CMS and DOB regarding FMAP and reporting considerations.
| 5/15/2011 5/1/2011 | P | P | P | Identify availability of information on cultural competency and training opportunities for health care providers
| 5/29/2011 5/15/2011 | 8 | 8 | 8 | Meet with stakeholders
| 5/15/2011 6/15/11 | 8 | 8 | 8 | Identify costs associated with incorporating cultural competency in health care settings
| 6/1/2011 6/29/11 | 8 | 8 | 8 | Determine feasibility of providing enhanced reimbursement and, if feasible, the amount of enhancing reimbursement for culturally competent care
| 6/30/2011 7/29/11 | 8 | 8 | 8 | Based on feasibility of enhanced reimbursement, determine policy and monitoring protocols related to enhanced reimbursement for culturally competent care.
| 7/5/2011 8/15/11 | 8 | 8 | 8 | If enhancing reimbursement, determine payment methodology
| 9/15/2011 9/1/2011 | 8 | 8 | 8 | Notify providers of available enhancement and billing guidance.
| 2011-09-15 | 8 | 8 | 8 | Complete system changes.
| 10/15/2011 10/1/2011 | 8 | 8 | 8 | Implement enhancement.
MRT#1032 |  |  |  |  | Project Name: Establish a Housing Disregard as Incentive to Join Managed Long Term care (MLTC) Division Lead: Coverage and Enrollment Team Lead: Wendy Butz Description: Provide nursing home residents who are discharged back to the community with a housing disregard if they join a MLTC plan. | 0
Policy and Procedure
| 2011-07-30 | 8 | 8 | 8 | Complete review of policy issues
| 2011-12-01 | 8 | 8 | 8 | Submit draft ADM for clearance
| 2012-03-01 | 8 | 8 | 8 | Issue ADM - effective 04/02/2012
1115 Waiver
| 2011-07-30 | 8 | 8 | 8 | Submit draft Waiver to CMS for informal review
| 2011-07-31 | 8 | 8 | 8 | Submit draft Waiver for DOH clearance
| 2011-10-31 | 8 | 8 | 8 | Finalize and submit Waiver to HCRA
| 2012-03-01 | 8 | 8 | 8 | Submission of Waiver to CMS
Systems Updates
| 2011-04-01 | P | P | P | Submit System Change Request
| 2011-08-05 | 8 | 8 | 8 | Finalize system change requirements
| 2011-08-30 | 8 | 8 | 8 | Finalize System Action Request
CNS
| 2012-04-27 | 8 | 8 | 8 | Development/coding changes
| 2012-06-08 | 8 | 8 | 8 | Unit testing
| 2012-06-15 | 8 | 8 | 8 | User Acceptance
MBL
| 2012-04-27 | 8 | 8 | 8 | Development/coding changes
| 2012-06-08 | 8 | 8 | 8 | Unit testing
| 2012-06-15 | 8 | 8 | 8 | User Acceptance
WMS
| 2012-04-27 | 8 | 8 | 8 | Development/coding changes
| 2012-06-08 | 8 | 8 | 8 | Unit testing
| 2012-06-15 | 8 | 8 | 8 | User Acceptance
| 06/2012 (12.2 Migration) | 8 | 8 | 8 | Migrate system changes
| 2012-06-20 | 8 | 8 | 8 | Implementation
MRT #1058 |  |  |  |  | Project Name: Maximize Peer Services Division Lead: DFPP Team Lead: Jacqueline Allaman Description: Explore Medicaid Reimbursement for peer services such as care and recovery coaches | 0
| 2011-03-31 | P | P | P | Submit FPN |  |  |  | Included in health home FPN
| 2011-04-20 | P | P | P | Begin research regarding use of peers in health programs including mental health and substance abuse programs, programs for people with developmental disabilities, and long term care programs.
| 2011-05-03 | P | P | P | Meet with OMH, OPWDD, OASAS, OLTC regarding use of peers
| 2011-05-20 | P | P | P | Meet with stakeholders to discuss ideas, suggestions, etc.
| 2011-07-08 | 8 | 8 | 8 | Meet with stakeholders to share research findings and discuss recommendations
| 2011-08-01 | 8 | 8 | 8 | Develop draft report and place in internal clearance |  |  |  |  | Maintenance
| 2011-08-08 | 8 | 8 | 8 | Complete internal clearance and send to stakeholders for comments
| 2011-08-22 | 8 | 8 | 8 | Receive comments from stakeholders on draft report
| 2011-08-26 | 8 | 8 | 8 | Revise report
| 2011-09-09 | 8 | 8 | 8 | Meet with stakeholders to discuss final edits
| 2011-09-16 | 8 | 8 | 8 | Complete report and place in final internal clearance for approval
| 2011-09-16 | 8 | 8 | 8 | Determine next steps based on report findings
| 2011-10-03 | 8 | 8 | 8 | Announce report regarding the use of peers within Medicaid reimbursable programs
MRT#1116 |  |  |  |  | Project Name: Apply 60 Month Look Back Period to Non-Institutional Long Term Care Division Lead: Coverage and Enrollment Team Lead: Wendy Butz Description: Apply 60 month look back period for transfer of assets to non-institutional long term care applicants with spousal impovershment protections. | 0
Policy and Procedure
| 2011-05-30 | 8 | 8 | 8 | Complete review of policy issues
| 2011-10-01 | 8 | 8 | 8 | Submit draft ADM for clearance
| 2012-03-01 | 8 | 8 | 8 | Issue ADM
CMS
| 2011-03-14 | P | P | P | Preliminary discussion with CMS
| 5/15/2011 6-10-11 | 8 | 8 | 8 | Follow up discussions with CMS
1115 Waiver/SPA
| 2012-03-01 | 8 | 8 | 8 | Submit any changes required based on CMS direction
Systems Updates
| 2011-04-01 | P | P | P | Submit System Change Request
| 6/3/2011 6/17/11 | 8 | 8 | 8 | Finalize system change requirements
| 6/10/2011 6/17/11 | 8 | 8 | 8 | Finalize System Action Request
CNS
| 2011-06-10 | 8 | 8 | 8 | Submit CNS notice changes
| 2012-02-04 | 8 | 8 | 8 | Development/coding changes
| 2012-03-17 | 8 | 8 | 8 | Unit testing
| 2012-03-25 | 8 | 8 | 8 | User Acceptance
eMedNY
| 2011-06-01 | 8 | 8 | 8 | Complete review of coverage codes for changes
| 6/1/2011 6/17/11 | 8 | 8 | 8 | Submit Evolution Project Request - provider meassages/coverage codes if applicable
Medicaid Update Article
| 2012-01-01 | 8 | 8 | 8 | Submit article
| 2012-04-01 | 8 | 8 | 8 | Implementation
MRT# 1172 |  |  |  |  | Project Name: Nursing Home Sprinkler Loan Pool Division Lead: DHCF Team Lead: Lana I. Earle Description: Assist NHs with Developing Financing Mechanism to Satisfy Federal Sprinkler Mandate, Effective August 13, 2013 | 0 |  |  |  | Maintenance
| 2011-04-21 | P | P | P | Follow up meeting on conference calls and discussions held in Mid March with DASNY, NYAHSA and DOH to determine the potential financing vehicles/structures available to NHs to meet Federal Mandate
| 2011-05-15 | P | P | P | Exchange information with Industry Associations identifying sprinkler needs and costs by facility and sponsor, continue to determine if there are lenders willing to finance NH sprinklers, and/or if there are sprinkler vendors interested in large pooled financings
| 5/25/2011 6-2-11 | 8 | 8 | 8 | Internal meeting to discuss next steps.
MRT #1427 |  |  |  |  | Project Name: CDPAP and Managed Care Division Lead: OLTC/DHCBS Team Lead: Linda Gowdy Description: Include of Consumer Directed Services in Managed Long Term Care Benefit (A) & Promulgate CDPAP regulations (B)
Part A CDPAP in MLTC
| 2011-03-15 | P | P | P | OHIP to review implementing regulations to determine if change is required
| 4/15/2011 10-15-11 | 8 | 8 | 8 | OHIP to draft regulatory changes, if necessary
| 5/1/2011 11/1/2011 | 8 | 8 | 8 | OHIP to develop assessment and authorization process for MC plans
| 5/1/2011 11/1/2011 | 8 | 8 | 8 | OHIP to review and make changes to existing MC contracts as necessary
| 6/1/2011 12/1/2011 | 8 | 8 | 8 | Develop contracting procedure for MA plans and Fiscal Intermediaries
Part B Promulgate CDPAP Regulations
| 2010-09-01 | P | P | P | Develop CDPAP regulations
| 2010-09-29 | P | P | P | Publish draft regulations
| 2010-11-15 | P | P | P | Public comments submitted
| 2011-01-20 | P | P | P | Proposed revisions forwarded for consideration
| 2011-03-21 | P | P | P | Review draft regulations for potential changes based on inclusion of benefit in MC
| 2011-03-23 | P | P | P | Make regulatory changes and forward to GORR for publication
| 2011-04-01 | P | P | P | Promulgate final reg
MRT# 1434 |  |  |  |  | Project Name: Convert a portion of Family Planning grants to Medicaid rate reimbursement Division Lead: DFFP Team Lead: Alan Maughan Description: Convert a portion of Family Planning grants to 90% federally funded Medicaid rates. | -7
| 2011-03-14 | P | P | P | Begin drafting required SPA, Regulation changes, and Federal Public Notice
| 2011-03-15 | P | P | P | Submit Public Notice
| 2011-04-13 | P | P | P | Notify providers via Medicaid Update and eMedNY Provider Communications
| 2011-03-25 | P | P | P | Submit SPA - SPA no longer required
| 2011-05-01 | P | P | P | Submit regulation changes - Regulation no longer required |  |  |  |  | Maintenance
| 5/23/2011 5/30/11 | 8 | 8 | 8 | Notify providers of the updated implementation methodology
| 5/25/2011 5/30/11 | 8 | 8 | 8 | Receive schedule for contract updates from the Division of Family Health
| 2011-07-01 | 8 | 8 | 8 | Implement Prospectively
| 2011-07-01 | 8 | 8 | 8 | Implement retroactive to 4/1/11 (pending SPA approval)
| 2011-08-15 | 8 | 8 | 8 | Reprocess affected claims back to 4/1/11 - July-August 2011
MRT #1451 |  |  |  |  | Project Name: Establish Various MRT Workgroups Division Lead: Team Lead: Jason Helgerson Description: Establish various workgroups to focus discussion on major reform issues. Workgroups will include: Payment Reform, Basic Benefit Review, Program Streamlining and State/Local Responsibility, Supportive Housing, Managed Long Term Care Implemenation and Waiver Redesign, Behavioral Health Reform, Workforce Flexibility and Change of Scope Practice, Medical Malpractice and Health Disparities | 0
| 2011-03-21 | P | P | P | Solicit participation of MRT members through email
| 2011-04-08 | P | P | P | Determine State lead for each of the nine subcommittees
| 2011-04-18 | P | P | P | Distribute draft subcommittee charges to DOH leads
| 2011-04-22 | P | P | P | Meet with State subcommittee leads to determine process for engaging outside stakeholders & calendar of meetings
| 2011-05-05 | P | P | P | Deadline for MRT members to identify subcommittees they would like to participate in
| 2011-05-25 | P | P | P | Kickoff meeting with internal staff on initial three workgroups: Behavioral health reform, MLTC, Program Streamlining and State/Local
| 2011-06-15 | 8 | 8 | 8 | DOH subcommittee leads to present Jason Helgerson with list of outside stakeholders to participate in subcommittee, determined in consultation with subcommittee chairs
| 2011-06-15 | 8 | 8 | 8 | Biweekly meetings with Jason Helgerson and State subcommittee leads to commence.
| 2011-06-25 | 8 | 8 | 8 | First subcommittee meeting. Subcommittees will meet a minimum of 2-3 times between June and October. |  |  |  |  | Maintenance
| 2011-07-01 | 8 | 8 | 8 | Plan submitted to Jason Helgerson on areas subcommittee will focus on, upcoming meeting dates and locations
| 2011-10-01 | 8 | 8 | 8 | Draft recommendations from each subcommittee presented to MRT
| 2011-11-01 | 8 | 8 | 8 | Final recommendations from each subcommittee presented to MRT
MRT # 1458 |  |  |  |  | Project Name: Care Management Population & Benefit Expansion, Access to Services, and Consumer Rights Division Lead: DMC Team Lead: Jennifer Dean Additional Staff: Linda Gowdy Description: Omnibus Medicaid Managed Care initiatives, eliminates many exempt/excluded populations, expands the benefit package, promotes access to services, and ensures consumer rights | -10.1
| Att. 1 |  |  |  | Attachment 1 - Expand Managed care Enrollment for non-dual eligibles and modify mainstream benefit package
Rates
| 4/30/2011 6/30/11 | 8 | 8 | 8 | Develop rates for benefit package change (personal care)
| 2011-08-01 | 8 | 8 | 8 | Implement all changes to rates effective 4/1/11 (marketing, trend reduction, surplus reduction, inpatient changes, etc)
| 2011-08-15 | 8 | 8 | 8 | Submit Rates to DOB for approval
| 2011-09-12 | 8 | 8 | 8 | DOB Approval
| 2011-09-19 | 8 | 8 | 8 | Mercer rate certification letter
| 2011-09-26 | 8 | 8 | 8 | Submit to CMS for approval
| 2011-10-24 | 8 | 8 | 8 | Mail/Post rates after CMS approval and all needed changes have been made to model contract and 1115 waiver
| 2011-12-16 | 8 | 8 | 8 | Submit Rates to DOB for approval
| 2012-01-13 | 8 | 8 | 8 | DOB Approval
| 2012-01-20 | 8 | 8 | 8 | Mercer rate certification letter
| 2012-01-27 | 8 | 8 | 8 | Submit to CMS for approval
| 2012-02-24 | 8 | 8 | 8 | Mail/Post rates after CMS approval and all needed changes have been made to model contract and 1115 waiver
DMC Implementation
| 2011-03-11 | P | P | P | Draft accompanying legislation for review
| 2011-03-14 | P | P | P | Assess systems impact internally and discussed with EB/EC systems staff |  |  |  |  | Maintenance
| 2011-03-20 | P | P | P | Draft accompanying waiver changes for proposal to CMS
| 2011-03-21 | P | P | P | Internal meeting regarding personal care benefit change / MCO contracting issues
| 2011-03-24 | P | P | P | Meet with Health Plan Associations to discuss proposal impact
| 2011-04-11 | P | P | P | Meet with enrollment broker to discuss proposal impact
| 2011-04-13 | P | P | P | Conference Call with LDSS to discuss changes
| 2011-04-20 | P | P | P | CMS waiver changes sent to CMS
| 2011-04-20 | P | P | P | Tribal notice sent
| 2011-04-21 | P | P | P | Begin weekly meetings with systems staff
| 2011-04-25 | P | P | P | Finalize recipient restriction policy for enforcing restrictions on carved out services
| 2011-04-27 | P | P | P | MMC Contract to CMS for approval
| 2011-04-27 | P | P | P | Public Notice Issued for waiver amendment
| 2011-04-30 | P | P | P | Notify MCO's of personal care contracting requirements
| 2011-04-30 | P | P | P | Deliver systems change SA /EP to WMS/eMedNY for implementation
| 2011-04-30 | P | P | P | Meet with Enrollment Broker Contractor to review changes made and training needs for call center and outreach staff
| 2011-05-04 | P | P | P | Meet with managed care plans regarding personal care benefit transition and restricting recipients within MMC
| 2011-05-11 | P | P | P | MMCARP meeting review of changes
| 5/10/2011 5-30-11 6-6-11 | 8 | 8 | 8 | Draft MMC statewide contract amendment including new benefit package language effective 7-1-2011 8-1-2011
| 5/30/2011 6-6-11 | 8 | 8 | 8 | Review and approve MCO subcontracts for personal care benefit
| 5/25/2011 6-15-11 | 8 | 8 | 8 | Notify current managed care recipients of personal care of benefit change
| 2011-06-15 | 8 | 8 | 8 | Identify excluded/exempt populations in FFS (for Rates)
| 2011-06-20 | 8 | 8 | 8 | MMC Contract to OSC for approval
| 2011-12-01 | 8 | 8 | 8 | Implement all other rate adjustments effective 10/1/11 (benefit package changes, excluded/exempt populations, inpatient changes, etc) -
| 2011-08-01 | 8 | 8 | 8 | Train local social services districts and EB/EC staff on populations being added
| 2011-09-01 | 8 | 8 | 8 | Distribute new materials to LDSS/other stakeholders
| 2011-09-01 | 8 | 8 | 8 | Training completed for Fair Hearings staff
| 2011-09-01 | 8 | 8 | 8 | Medicaid Update article released
| 2011-09-01 | 8 | 8 | 8 | Waiver negotiations complete
| 2011-09-01 | 8 | 8 | 8 | Complete rate work with Mercer and DQ&E
| 2011-09-01 | 8 | 8 | 8 | Complete budget neutrality repotting requirements
| 2011-09-15 | 8 | 8 | 8 | Outreach completed for providers, plans, advocacy groups, etc.
| 2011-10-01 | 8 | 8 | 8 | Implementation
| Att. 2 |  |  |  | Attachment 2 - Access to Benefits and Consumer Protections
| 2011-03-24 | P | P | P | Meet with Health Plan Associations to discuss proposal impact
| 2011-04-15 | P | P | P | Review MCO benefits denial model notices for changes
| 2011-04-30 | P | P | P | Review model managed care handbooks for information regarding benefits coverage
| 2011-05-11 | P | P | P | MMCARP meeting review of changes
| 4/30/2011 5/25/2011 6-1-11 | 8 | 8 | 8 | Distribute new model language to plans for benefits denial notices
| 5/20/2011 6-3-11 | 8 | 8 | 8 | Distribute to plans amended handbook language for eratta sheets
| 5/30/2011 7-1-11 | 8 | 8 | 8 | Develop training modules for plans to review covered benefits and expanded consumer information necessary for new chronic populations to navigate system
| 2011-07-01 | 8 | 8 | 8 | Implementation of updated notices
| 2011-09-15 | 8 | 8 | 8 | Outreach completed for providers, plans, advocacy groups, etc.
| Att. 3 |  |  |  | Attachment 3 - Streamline Managed care Eligibility Process
| 2011-03-11 | P | P | P | Draft accompanying legislation for review
| 2011-03-14 | P | P | P | Assess systems impact internally and discussed with EB/EC systems staff
| 2011-03-20 | P | P | P | Draft accompanying waiver changes for proposal to CMS
| 2011-03-21 | P | P | P | Internal meeting with OHIP eligibility and FE oversight staff regarding choice period
| 2011-03-24 | P | P | P | Meet with Health Plan Associations to discuss proposal impact
| 2011-04-04 | P | P | P | Develop managed care contract change
| 2011-04-08 | P | P | P | Meet with systems staff to ensure timing of changes.
| 2011-04-20 | P | P | P | Review available informational materials for necessary changes
| 2011-04-27 | P | P | P | Public Notice Issued for waiver amendment
| 2011-04-30 | P | P | P | Meet with Enrollment Broker Contractor to review changes made and training needs for call center and outreach staff
| 2011-05-05 | P | P | P | Draft/approve changes to program materials for printing (brochures, enrollment forms,etc)
| 2011-05-06 | P | P | P | Finalize system change requirements
| 2011-05-11 | P | P | P | MMCARP meeting review of changes
| 2011-05-13 | P | P | P | Deliver systems change EP to eMedNY for implementation |  |  |  |  | Maintenance
| 2011-05-13 | P | P | P | System specifications submitted to WMS (SA)
| 2011-08-01 | 8 | 8 | 8 | Train local social services districts and EB/EC staff on chioce period changes
| 2011-08-17 | 8 | 8 | 8 | Test WMS Systems changes
| 2011-09-01 | 8 | 8 | 8 | Distribute new materials to LDSS/other stakeholders
| 2011-09-01 | 8 | 8 | 8 | Training completed for Fair Hearings staff
| 2011-09-01 | 8 | 8 | 8 | Medicaid Update article released
| 2011-09-01 | 8 | 8 | 8 | Waiver negotiations complete
| 2011-09-15 | 8 | 8 | 8 | Outreach completed for providers, plans, advocacy groups, etc.
| 2011-09-20 | 8 | 8 | 8 | Training completed for Fair Hearings staff
| 2011-10-01 | 8 | 8 | 8 | Implementation
MRT #1462 |  |  |  |  | Project Name: Long Term Care Insurance Proposals Division Lead: OLTC Team Lead: Mary Ann Anglin Add'l Staff: Dave Hoffman Description: Various strategies to promote use of private LTC insurance | 0
Part A- Create Additional Plan Option for the Partnership for LTC
| 2011-04-25 | P | P | P | Confirm passage of budget language/ Draft 2-4-100 Proposal
| 2011-05-10 | P | P | P | Solicit comment and seek approval of the PLTC E -Board
| 6/1/2011 7-1-11 | 8 | 8 | 8 | Draft State Plan Amendment
| 7-1-11 8-1-11 | 8 | 8 | 8 | Submit State Plan Amendment
| 2011-09-01 | 8 | 8 | 8 | Collaborate with SID for implementation
| 2011-12-01 | 8 | 8 | 8 | Inform insurers and the public of new option
Part B Strategies to incent purchase of LTC insurance
| 2011-07-01 | 8 | 8 | 8 | Review Federal Tax Law to assess implication for use of IRA/401k and other tools without penalty
| 2011-08-01 | 8 | 8 | 8 | Develop Program Bill for 500 person demo of pre-tax LTC savings accounts
| 2011-11-01 | 8 | 8 | 8 | Review legal implication of Use of Accelerated death benefit
| 2011-12-01 | 8 | 8 | 8 | Investigate possible use of reverse mortgage to pay for LTC insurance
Part C Creation of LTC Insurance Marketing Fund and Campaign
| 2011-05-15 | P | P | P | Review Marketing Fund Proposal with E-Board
| 2011-06-01 | 8 | 8 | 8 | Draft Marketing Fund Proposal
| 2011-08-01 | 8 | 8 | 8 | Present Proposal to E-Board for feedback
| 2011-08-01 | 8 | 8 | 8 | Convene E-Board Marketing Sub-Committee
| 2011-09-01 | 8 | 8 | 8 | Solicit commitment from insurers
| 2011-10-01 | 8 | 8 | 8 | Convene LTC Insurance Marketing Partners
| 2011-12-01 | 8 | 8 | 8 | Contract for campaign development
MRT# 4647 |  |  |  |  | Project Name: Expand MATS Division Lead: DFPP Team Lead: Rob Kent (OASAS) Add'l Staff: Deirdre Astin (DOH) Description: Explore expanding and transitioning MATS into health home. | 0
| 2011-03-31 | P | P | P | Submit FPN
| 2011-05-06 | P | P | P | OASAS meeting with DOH, NYCDOH/MH, and MATS providers to discuss expansion plans and integration of MATS case management into health homes
| 2011-05-09 | P | P | P | Initiate MATS transition planning to Health Homes including population selection and assignment, payment, systems, reporting, data, enrollment, and evaluation requirements
| 2011-06-01 | 8 | 8 | 8 | Initiate development of SPA for MATS conversion to Health Home |  |  |  |  | Maintenance
| 2011-07-05 | 8 | 8 | 8 | Finalize payment methodology and reimbursement amounts for MATS
| 2011-07-05 | 8 | 8 | 8 | Finalize system needs related to claims editing and payment
| 2011-07-05 | 8 | 8 | 8 | Consult with SAMHSA prior to SPA submission
| 2011-07-15 | 8 | 8 | 8 | Finalize federal and State reporting requirements
| 2011-07-15 | 8 | 8 | 8 | Finalize data requirements
| 2011-07-15 | 8 | 8 | 8 | Finalize population selection criteria
| 2011-07-15 | 8 | 8 | 8 | Finalize enrollee auto assignment based on MATS/HH selection criteria
| 2011-07-29 | 8 | 8 | 8 | Finalize draft evaluation methodology
| 2011-07-29 | 8 | 8 | 8 | Receive SAMHSA approval
| 2011-08-26 | 8 | 8 | 8 | Submit SPA
| 2011-09-09 | 8 | 8 | 8 | Finalize Health Home enrollee notification letter
| 2011-10-01 | 8 | 8 | 8 | Receive SPA approval
| 2012-01-30 | 8 | 8 | 8 | Implement program
MRT #4648 |  |  |  |  | Project Name: Family Planning Benefit Program (FPBP) as a State Plan Service Division Lead: DCE Team Lead: Kathleen Johnson Description: Transition FPBP from 1115 Waiver to State Plan | 0
PART 1
Transition FPBP from 1115 Waiver to State Plan
Policy and Procedure
| 2011-06-01 | P | P | P | Complete preliminary review of policy issues
| 2012-03-01 | 8 | 8 | 8 | Submit draft Administrative Directive (ADM) for clearance
| 2012-04-01 | 8 | 8 | 8 | Take necessary steps to discontinue FPBP in 1115 Waiver
| 2012-06-01 | 8 | 8 | 8 | Issue ADM
State Plan
| 2011-05-05 | P | P | P | Submit draft SPA 11-40 for DOH clearance
| 2011-05-13 | P | P | P | Finalize and submit SPA 11-40 to HCRA Operations and Financial Analysis
System Updates
MBL/WMS/HEART
| 2011-04-11 | P | P | P | Submit System Change Request Form
| 2011-06-01 | P | P | P | Finalize system change requirements
| 2011-06-15 | P | P | P | Finalize System Action Request
| 2012-04-27 | 8 | 8 | 8 | Development/coding changes
| 2012-06-08 | 8 | 8 | 8 | Unit testing
| 2012-06-15 | 8 | 8 | 8 | User Acceptance
eMedNY
| 2011-04-25 | P | P | P | Submit emedNY evolution project
| 2012-02-01 | 8 | 8 | 8 | Finalize eMedNY evolution project
PART 2
Presumptive Eligibility for FPBP
Policy and Procedure
| 2011-06-01 | P | P | P | Complete preliminary review of policy issues
| 7/1/2011 12/1/2011 | 8 | 8 | 8 | Develop and submit Regulations
| 2012-01-01 | 8 | 8 | 8 | Revise online training for FPBP providers and training for LDSS staff
| 2012-01-01 | 8 | 8 | 8 | Modify Memorandum of Understanding with FPBP providers and for clearance
| 2012-02-01 | 8 | 8 | 8 | Submit draft letter to FPBP providers for clearance
| 2012-04-01 | 8 | 8 | 8 | Develop PE screening form for providers/Revise FPBP appllication
| 2012-04-01 | 8 | 8 | 8 | Submit draft Administrative Directive (ADM) for clearance
| 2012-04-01 | 8 | 8 | 8 | Mail letters and MOU to FPBP providers
| 2012-06-01 | 8 | 8 | 8 | Issue ADM
State Plan
| 2011-05-05 | P | P | P | Submit draft SPA 11-40 for DOH clearance
| 2011-05-13 | P | P | P | Finalize and submit SPA 11-40 to HCRA Operations and Financial Analysis
Website
| 2012-06-01 | 8 | 8 | 8 | Post information about presumptive eligiblitiy for Family Planning services
System Updates
MBL/WMS/HEART
| 2011-04-11 | P | P | P | Submit System Change Request Form
| 2011-06-01 | 8 | 8 | 8 | Finalize system change requirements
| 2011-06-15 | 8 | 8 | 8 | Finalize System Action Request
| 2012-04-27 | 8 | 8 | 8 | Development/coding changes
| 2012-06-08 | 8 | 8 | 8 | Unit testing
| 2012-06-15 | 8 | 8 | 8 | User Acceptance
| 2012-06-18 | 8 | 8 | 8 | Migrate system change
CNS
| 2012-01-01 | 8 | 8 | 8 | Finalize and submit CNS notices
| 2012-04-27 | 8 | 8 | 8 | Development/coding changes
| 2012-06-08 | 8 | 8 | 8 | Unit testing
| 2012-06-15 | 8 | 8 | 8 | User Acceptance
PART 3
Automate Enrollment of Post-Partum women into Family Planning Benefit Program or Family Planning Extension Program
Policy and Procedure
| 2011-06-01 | P | P | P | Complete preliminary review of policy issues
| 2012-04-01 | 8 | 8 | 8 | Submit draft ADM for clearance
| 2012-06-01 | 8 | 8 | 8 | Issue ADM
| 2012-04-01 | 8 | 8 | 8 | Coordinate with Bureau of Maternal and Child Health to draft and clear Medicaid Update article for Family Planning Providers
| 2012-04-01 | 8 | 8 | 8 | Coordinate with Bureau of Maternal and Child Health to draft letter to Family Planning providers
| 2012-06-01 | 8 | 8 | 8 | Issue Medicaid Update article for Familiy Planning Providers
| 2012-06-01 | 8 | 8 | 8 | Mail letter to FPBP providers
System Updates
MBL/WMS/HEART
| 2011-04-11 | P | P | P | Submit System Change Request Form
| 2011-06-01 | 8 | 8 | 8 | Finalize system change requirements
| 2011-06-15 | 8 | 8 | 8 | Finalize System Action Request
| 2012-04-27 | 8 | 8 | 8 | Development/coding changes
| 2012-06-08 | 8 | 8 | 8 | Unit testing
| 2012-06-15 | 8 | 8 | 8 | User Acceptance
| 2012-06-18 | 8 | 8 | 8 | Migrate system change
eMedNY
| 2011-04-25 | P | P | P | Submit emedNY evolution project
| 2012-02-01 | 8 | 8 | 8 | Finalize eMedNY evolution project
CNS
| 2012-01-01 | 8 | 8 | 8 | Finalize and submit CNS notices
| 2012-04-27 | 8 | 8 | 8 | Development/coding changes
| 2012-06-08 | 8 | 8 | 8 | Unit testing
| 2012-06-15 | 8 | 8 | 8 | User Acceptance
| 2012-07-01 | 8 | 8 | 8 | Implementation (12.2)
MRT # 4651-A |  |  |  |  | Project Name: Global Spending Cap Division Lead: John Ulberg Team Lead: Stephanie Fargnoli Add'l Staff: Megan Ryan; Mark Shutts and Shaneeva Norbi Description: Periodically monitors Medicaid spending and implements Savings Allocation Plans (if needed), which are designed to bring projected spending in line with a cap (aka Global Spending Cap) of approximately 4% growth per year.
| 2011-03-30 | P | P | P | Issue a Federal Public Notice
| 2011-03-30 | P | P | P | Consulted within the Department and with the Division of Budget (DOB) to develop a model that will track Medicaid expenditures by industry sector (i.e., inpatient outpatient, freestanding clinic, nursing homes, etc) that make up and coincide with the approximately $15 billion State spending cap.
| 2011-04-01 | P | P | P | Map data warehouse extraction using MARS detcat codes to the same sectors agreed upon with DOB to gain confidence that monthly extractions are appropriately being input into the model.
| 2011-04-01 | P | P | P | Model monthly cash flow for online (claims) expenditures using historical experience (2009-10) adjusted for known anomalies (ie. Retroactive rate packages) within each sector.
| 2011-04-05 | P | P | P | Test receipt of data from data warehouse and the input/output of the established model.
| 2011-04-11 | P | P | P | Model monthly cash flow for offline expenditures in consultation with DOB's internal cash flow attributed to each sector. |  |  |  |  | Maintenance
| 2011-04-15 | P | P | P | Model monthly cash flow for each MRT proposal by industry sector.
| 2011-04-15 | P | P | P | Combine monthly cash flows for online, offline and MRT proposals into one model.
| 2011-04-19 | P | P | P | Brief DOH Executive Staff on cap reporting documents.
| 2011-04-22 | P | P | P | Review and get agreement upon a format for reporting monthly. Discussion will include the format of the cash flow and any accompanying charts.
| 2011-04-22 | P | P | P | Discuss and get agreement on any additional/supplemental reports to be posted.
| 2011-05-05 | P | P | P | Brief the Hospital Associations regarding data sources and calculations used in the development of the Medicaid global spending cap cash flow. |  |  |  | Shared all data files with HANYS and GNY on 5/06/11
| 2011-05-16 | P | P | P | Receive April's data feed (online and offline) and and input into the model.
| 2011-05-23 | P | P | P | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 5/16/2011 5/26/11 | P | P | P | Brief Legislative staffs on cap reporting documents.
| 5/27/2011 5/31/11 | 8 | 8 | 8 | Post reports to the website.
| 2011-06-16 | 8 | 8 | 8 | Receive May's data feed (online and offline) and and input into the model. |  |  |  |  | Maintenance
| 2011-06-24 | 8 | 8 | 8 | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 2011-06-30 | 8 | 8 | 8 | Post reports to the website.
| 2011-07-15 | 8 | 8 | 8 | Receive June's data feed (online and offline) and and input into the model.
| 2011-07-22 | 8 | 8 | 8 | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 2011-07-29 | 8 | 8 | 8 | Post reports to the website.
| 2011-08-15 | 8 | 8 | 8 | Receive July's data feed (online and offline) and and input into the model.
| 2011-08-22 | 8 | 8 | 8 | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 2011-08-31 | 8 | 8 | 8 | Post reports to the website.
| 2011-09-16 | 8 | 8 | 8 | Receive August's data feed (online and offline) and and input into the model. |  |  |  |  | Maintenance
| 2011-09-23 | 8 | 8 | 8 | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 2011-09-30 | 8 | 8 | 8 | Post reports to the website.
| 2011-10-15 | 8 | 8 | 8 | Receive September's data feed (online and offline) and and input into the model.
| 2011-10-22 | 8 | 8 | 8 | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 2011-10-31 | 8 | 8 | 8 | Post reports to the website.
| 2011-11-16 | 8 | 8 | 8 | Receive October's data feed (online and offline) and and input into the model.
| 2011-11-23 | 8 | 8 | 8 | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 2011-11-30 | 8 | 8 | 8 | Post reports to the website.
| 2011-12-16 | 8 | 8 | 8 | Receive November's data feed (online and offline) and and input into the model. |  |  |  |  | Maintenance
| 2011-12-23 | 8 | 8 | 8 | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 2011-12-30 | 8 | 8 | 8 | Post reports to the website.
| 2012-01-16 | 8 | 8 | 8 | Receive December's data feed (online and offline) and and input into the model.
| 2012-01-23 | 8 | 8 | 8 | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 2012-01-31 | 8 | 8 | 8 | Post reports to the website.
| 2012-02-15 | 8 | 8 | 8 | Receive January's data feed (online and offline) and and input into the model.
| 2012-02-22 | 8 | 8 | 8 | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 2012-02-29 | 8 | 8 | 8 | Post reports to the website.
| 2012-03-16 | 8 | 8 | 8 | Receive February's data feed (online and offline) and and input into the model.
| 2012-03-23 | 8 | 8 | 8 | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 2012-03-30 | 8 | 8 | 8 | Post reports to the website.
| 2012-04-16 | 8 | 8 | 8 | Receive March's data feed (online and offline) and and input into the model.
| 2012-04-23 | 8 | 8 | 8 | Complete Q&A of the model output and the data feed and complete a variance analysis.
| 2012-04-30 | 8 | 8 | 8 | Post reports to the website.
|  | 8 | 8 | 8 | SFY 12-13 Monthly reporting will fall on the same monthly schedule as 2011-12.
MRT # 4651-B |  |  |  |  | Project Name: 2% Across the Board Reductions Division Lead: John Ulberg Team Lead: Stephanie Fargnoli Add'l Staff: Shaneeva Norbi Description: This proposal implements a 2% Across the Board Reductions to most Medicaid payments | -345
General process for Implementation
| 2011-03-30 | P | P | P | Publish the Federal Public Notice based on the Executive Budget language.
| 2011-04-27 | P | P | P | Publish a clarifying Federal Public Notice based on the Enacted Budget and negotiated alternatives by sector.
| 5/17/2011 5-31-11 | P | P | P | Finalize list of included/excluded services for purposes of the State Plan Amendment |  |  |  | This information is needed to complete the State Plan Amendment
| 2011-04-21 | P | P | P | Submit a draft of the Hospital Inpatient State Plan Amendment to CMS for the across the board actions
| 2011-06-03 | 8 | 8 | 8 | Submit a draft of the Outpatient Services State Plan Amendment to CMS for the across the board actions and if needed any plans for alternatives identified by the sectors (several sectors are included in this state plan amendment please see list below)
| 5/21/2011 6-8-11 | 8 | 8 | 8 | Develop language for provider letter and Medicaid update
| 5/27/2011 6-13-11 | 8 | 8 | 8 | Notify provider communities through email blasts; dear administrator letters; and/or the Medicaid Update
| 6/1/2011 6-20-11 | 8 | 8 | 8 | Complete an Evolution Project Request for changes that will be made to the system to effectuate the inclusions/exclusions to the across the board reduction. |  |  |  | The Division on Planning and Policy is the lead for the Evolution Project.
Path of participation by Sector (alternative proposal accepted or rejected)
Work plan is expected to be significantly expanded as discussions continue
Inpatient
|  | P | P | P | Industry did not propose an alternative to the across the board, therefore 2% reduction applies.
| 2011-04-21 | P | P | P | Submit SPA as a draft to CMS ( Hospital Inpatient)
Hospital Based Outpatient
|  | P | P | P | Industry did not propose an alternative to the across the board, therefore 2% reduction applies.
| 2011-06-03 | 8 | 8 | 8 | Submit SPA as a draft to CMS (Outpatient Services)
Freestanding Clinic
|  | P | P | P | Alternative proposal accepted to generate commensurate savings through an reduction to the unpaid APG investment.
|  | 8 | 8 | 8 | Amend SPA amendment if needed |  |  |  | The Division on Planning and Policy
Nursing Home
| 2011-03-31 | P | P | P | Alternative proposal accepted to generate commensurate savings through an increase of the cash assessment accepted.
| 2011-03-31 | P | P | P | Complete provider impact
| 2011-03-31 | P | P | P | DOB approval
| 2011-04-15 | P | P | P | Discuss and finalize set up of system change with the Office of Pool Administrator (OPA)
| 2011-04-18 | P | P | P | OPA system updated to accept new reports with increased cash assessment
| 2011-04-28 | P | P | P | Notify provider communities through dear administrator letter
| 2011-05-16 | P | P | P | First receipt of increase
Personal Care
|  | P | P | P | Industry did not propose an alternative to the across the board, therefore 2% reduction applies.
| 2011-06-03 | 8 | 8 | 8 | Submit SPA as a draft to CMS (Outpatient Services)
Home Health
|  | P | P | P | CHHA- Industry proposal rejected, therefore 2% reduction applies
| 2011-06-03 | 8 | 8 | 8 | Submit SPA as a draft to CMS (Outpatient Services)
|  | 8 | 8 | 8 | LTHHCP- Discussions still in progress
Home Nursing
|  | P | P | P | Industry did not propose an alternative to the across the board, therefore 2% reduction applies.
| 2011-06-03 | 8 | 8 | 8 | Submit SPA as a draft to CMS (Outpatient Services)
[5 empty] | Assisted Living Programs |  |  |  | DRS/OLTC- Warner
|  | P | P | P | Alternative proposal accepted to generate commensurate savings through a reduction of the state only funding of 'EQUAL'.
|  | 8 | 8 | 8 | Official letter from industry
|  | 8 | 8 | 8 | Complete impact by provider
|  | 8 | 8 | 8 | Discuss and finalize set up of system change
Managed Long Term Care
|  | P | P | P | Alternative proposal accepted to generate commensurate savings through reducing premium levels
Managed Care/ FHP
|  | P | P | P | Alternative proposal accepted to generate commensurate savings through reducing premium levels
Pharmacy
|  | P | P | P | Interactions amongst existing proposals and other pharmacy programs will generate commensurate savings, resulting in 1% or less in ATB cuts.
|  | 8 | 8 | 8 | Submit a draft State Plan Amendment to CMS for alternatives as needed
Physicians
|  | P | P | P | Office place of service - Alternative proposal accepted to generate commensurate savings for office based physicians through an reduction in radiology fees.
|  | 8 | 8 | 8 | Submit a draft State Plan Amendment to CMS for alternatives as needed
|  | P | P | P | All other places of service- Industry did not propose an alternative to the across the board, therefore 2% reduction applies.
| 2011-06-03 | 8 | 8 | 8 | Submit SPA as a draft to CMS (Outpatient Services)
Other Services (Dental, Eye/X-ray, etc.)
|  | P | P | P | Industry did not propose an alternative to the across the board, therefore 2% reduction applies.
| 2011-06-03 | 8 | 8 | 8 | Submit SPA as a draft to CMS (Outpatient Services)
MRT#4652 |  |  |  |  | Project Name: Reform Personal Care Services Program in NYC Division Lead: OLTC/DHCBS Team Lead: Mary Ann Anglin Add'l Staff: Margaret O. Willard and Linda Gowdy Description: | -113.81
State Plan Amendment & Regulatory Process
| 2011-03-17 | P | P | P | Review SPA, Statute and regulations related to the PCSP |  |  |  |  | Maintenance
| 2011-04-01 | P | P | P | Make appropriate changes as needed to SPA, Statute and/or Regulations with DLA direction. Follow existing process for changes. |  |  |  | No SPA required.
| 2011-04-19 | P | P | P | Change in regulation 18 NYCRR 505.14 and 505.28 initiated
| 2011-05-02 | P | P | P | Preliminary review of draft regulations by DLA
| 5/20/2011 6-17-11 | 8 | 8 | 8 | Necessary changes made to draft regulations based on DLA recommendations
| 5/13/2011 5/23/11 6-22-11 | 8 | 8 | 8 | Internal administrative review initiated after DLA preliminary review completed
| 5/25/2011 7-6-11 | 8 | 8 | 8 | Internal review completed, package advanced to Executive Chamber Publication in State Register
| 6/8/2011 7-20-11 | 8 | 8 | 8 | Publication in State Register
GIS/Fair Hearings
| 2011-04-28 | P | P | P | Draft of GIS limiting Level 1 services
| 2011-04-28 | P | P | P | GIS enters Internal Clearance Process
| 2011-04-13 | P | P | P | Conference between DOH and OTDA re: Fair Hearing rights
| 2011-04-28 | P | P | P | Draft of FH reduction notice to be prepared
| 2011-05-02 | P | P | P | Create FH notice as ana attachment to GIS
| 5/20/2011 6-4-11 | 8 | 8 | 8 | GIS completed internal clearance process
| 5/13/2011 5/24/11 6-4-11 | 8 | 8 | 8 | Distribution of GIS to Local Districts
Collaboration with HRA and HHC
| 2011-05-06 | P | P | P | Conference call with HRA staff to discuss CCO model
| 2011-05-09 | P | P | P | Formulate questions to be used by HRA in discussions with HHC
| 2011-05-12 | P | P | P | Initiate internal clearance of OLTC questions for HRAs use
| 5/19/2011 6-10-11 | 8 | 8 | 8 | Share questions and concerns with HRA for consideration and response
| 2011-06-15 | 8 | 8 | 8 | Collaborate with HRA and HHC in establishing criteria for a care coordination model for high needs PCS recipients.
| 4/15/2011 5-31-11 6-15-11 | 8 | 8 | 8 | Collaborate with HRA and Health and Hospitals Corporation in establishing criteria for a Care Coordination Model for high needs PCS recepients
| 4/1/2011 6-6-11 6-15-11 | 8 | 8 | 8 | Collaborate with HRA in developing and approving the process for moving low need CHHA cases to the PCSP
| 2011-09-01 | 8 | 8 | 8 | Develop and issue policy directives/standards for local districts
| 2011-09-01 | 8 | 8 | 8 | Provide ongoing training and monitoring of the PCSP as required
MRT #4153 |  |  |  |  | Project Name: Expanded Pharmacy Reimbursement Controls Division Lead: DOIT Team Lead: Mark Malone Add'l Staff: Steve Helmin, Mary Carroll, Kim Leonard Description: Implement contract to enhance controls on drug utilization. | -2.3
Administrative
| 2011-07-01 | 8 | 8 | 8 | Obtain approval for contract modification
| 2011-06-01 | ▲ | ▲ | ▲ | CSC agreement to work at risk
| 2011-07-01 | ▲ | ▲ | ▲ | HID agreement to work at risk
Systems
| 2011-05-05 | P | P | P | Reinstate EP 0719/HID project
| 2011-05-05 | P | P | P | Identify interfaces with all contractors
| 2011-06-01 | 8 | 8 | 8 | Requirements Definition: Functional Requirements Document |  | HID's involvement with requirements definition will not begin until 7/1/11
| 2011-09-01 | 8 | 8 | 8 | System Detailed Design: Program Design Document
| 2011-11-15 | 8 | 8 | 8 | Coding and Unit Test: Develop source code and systems documentation.
| 2012-01-09 | 8 | 8 | 8 | Systems Integration Test: Proposed test cases to be exercised during SIT
| 2012-01-16 | 8 | 8 | 8 | State approval of SIT
| 2012-02-06 | 8 | 8 | 8 | Regression, Performance and User Acceptance Testing
| 2012-02-23 | 8 | 8 | 8 | Implement EP0719 with enhanced clinical upfront editing function.
Program/Clinical
| 2011-05-01 | P | P | P | Identify clinical program requirements and timelines
| 2012-02-23 | 8 | 8 | 8 | Implement DURB frequency/quantity/duration recommendations
| 2012-02-23 | 8 | 8 | 8 | Implement MRT 15H: PA for Previously Exempt Classes |  | savings attached to proposal 15
| 2012-02-23 | 8 | 8 | 8 | Implement PA length of 12 months
| 2012-02-23 | 8 | 8 | 8 | Implement MRT 15K: Limit Opioids to 4 scripts every 30 days |  | savings attached to proposal 15
| 2012-02-23 | 8 | 8 | 8 | Implement PDL drugs and clinical criteria
| 2012-02-23 | 8 | 8 | 8 | Implement step-therapy
| 2012-02-23 | 8 | 8 | 8 | Implement CDRP clinical criteria
MRT # 4655 |  |  |  |  | Project Name: Expand Downstate FQHC Region Division Lead: DOH / DHCF Team Lead: Janet Baggetta Add'l Staff: Phyllis Casale, Rick Nair Description: Expand the downstate region to increase reimbursment to certain Federally Qualified Health Centers (FQHC) that serve residents of this region. | 2.4 |  |  | Includes MMC wrap 2.1
| 2011-04-27 | P | P | P | Submit FPN.
| 2011-04-15 | P | P | P | Determine if regulations are needed. |  |  |  | No FQHC regulations
| 2011-04-18 | P | P | P | Work with BHOFA staff to prepare necessary State Plan Amendment materials.
| 2011-04-20 | P | P | P | Submit State Plan Amendment 11-59. |  |  |  | Draft submitted
| 2011-04-29 | P | P | P | Calculate revised FQHC Rate Sheets
| 2011-05-05 | P | P | P | Receive Medicaid Managed Care impact for Budget Package for wrap payment
| 5/5/2011 5/20/2011 | P | P | P | Finalize Budget Package with revised FQHC/wrap Rates. Submit for Executive approval.
| 5/5/2011 5/20/11 | 8 | 8 | 8 | Submit Draft Budget package/rates to DoB for initial review
| 5/26/2011 7/1/2011 | 8 | 8 | 8 | Receive Budget Package Executive approval
| 2011-07-20 | 8 | 8 | 8 | Receive CMS Approval
| 2011-07-21 | 8 | 8 | 8 | Submit Final Budget package/rates to DOB for approval
| 2011-07-28 | 8 | 8 | 8 | Receive DOB Approval
| 2011-07-29 | 8 | 8 | 8 | Transmit revised FQHC rates and other required data to eMedNY.
Formulas:
Date = [Date, row above]+7
Date = [Date, row above]

## Completed
Milestones: | Date | Schedule | Budget | Risk | Description | Savings Target ($millions)
MRT# 15A |  |  |  |  | Project Name: Enhance NYS Leverage for Supplemental Rebates Division Lead: DFPP Team Lead: Mary Carroll Description: Allow the Commissioner of Health more flexibility to add drugs/classes to the PDP and in negotiating with manufacturers. | -0.83
| 2011-04-01 | P | P | P | Obtain statute modification to allow the Commissioner more flexibility when directly with drug manufacturers (PHL Article 2-A) section 272 11 (b).
| 2011-04-01 | P | P | P | Obtain enabling legislation allowing Commissioner to add drugs/drug classes to the PDP as preferred until the P&TC may conduct a review. Revised language allows for a class with one drug.
| 2011-04-01 | P | P | P | Identify potential drugs/classes
| 2011-04-01 | P | P | P | Determine staffing needs
| 2011-04-01 | P | P | P | Determine system impact.
| 2011-04-15 | P | P | P | When inititiating SDC process, notify direct contract manufacturers of legislative changes that allow DOH to non-prefer selected drugs of specific manufacturers in the absence of successful negotiations.
| 2011-05-02 | P | P | P | Revise PDL and post on PDP website.
| 2011-05-02 | P | P | P | Implement
MRT# 15B |  |  |  |  | Project Name: Tighten the Early Refill Process Division Lead: DFPP Team Lead: Mary Carroll Description: Tighten up requirements for obtaining authorization to fill a prescription when it is denied because it has been “refilled too soon.” | -0.6
| 2011-04-01 | P | P | P | Draft revised policy for early fill
| 2011-04-01 | P | P | P | Obtain legal approval of proposed policy
| 2011-04-01 | P | P | P | Develop prior authorization procedures for exceptions
| 2011-04-01 | P | P | P | Determine system impact.
| 2011-04-01 | P | P | P | Implement EP 1555
| 2011-04-01 | P | P | P | Determine staffing needs
| 2011-04-01 | P | P | P | Develop and send e-blasts and DUR letters to providers (DUR letters will be mailed 3/18, Medicaid Update article will be published in March, e-blasts will be sent 3/18)
| 2011-04-01 | P | P | P | Develop Medicaid Update articles and publish
| 2011-04-01 | P | P | P | Communicate with stakeholders (PSSNY,MSSNY, OMIG)
| 2011-04-01 | P | P | P | Implement new process with soft edit
| 2011-06-01 | P | P | P | Turn off "04" claims edit override for hard edit.
MRT# 15E |  |  |  |  | Project Name: Rebuild NY Preferred Drug List Division Lead: DFPP Team Lead: Mary Carroll Description: Change the way the preferred drug list is developed, in order to increase savings. | -11.9
| 2011-04-01 | P | P | P | Obtain enabling legislation. Language permitting the Commissioner to designate a member of the department to act on his/her behalf intentionally omitted, as was language calling for the elimination of "prescriber prevails"
| 2011-04-01 | P | P | P | Identify systems impact
| 2011-04-01 | P | P | P | Identify staffing needs.
| 2011-04-01 | P | P | P | Create workgroup to develop strategy to achieve estimated savings.
| 2011-04-02 | P | P | P | Identify State staff designated to chair P&TC
| 2011-04-15 | P | P | P | Develop process for making recommendations to P&TC
| 2011-05-01 | P | P | P | Communicate new procedures to stakeholders
| 2011-05-01 | P | P | P | Implement administrative changes
| 2011-05-01 | P | P | P | Engage Magellan in discussion to increase State's involvement in NMPI bid process
| 2011-05-01 | P | P | P | Implement administrative changes
| 2011-05-01 | P | P | P | Engage Magellan in discussion to increase State's involvement in NMPI bid process
MRT# 31 |  |  |  |  | Project Name: Eliminate worker recruitment and retention Division Lead: DHCF Team Lead: Joseph Sohn Add'l Staff: Description: Eliminate worker recruitment and retention add-on from Medicaid rates of eligible Diagnostic and Treatment Centers (D&TCs) effective 4/1/11. | -6.5
|  | P | P | P | Section 2807(17)(a)(x) under Article 28 of the Public Health Law ended WRR add-on on March 31, 2011. If new periods are not added in the law, WRR add-on will be removed from applicable Medicaid rates effective 4/1/11. No FPN or SPA approval is required.
| 2009-12-23 | P | P | P | Based on decision made by the Department, send a transmittal to remove WRR add-on effective 1/1/2010, while waiting for CMS approval that implements a new WRR allocation methodology for the period 7/1/07 - 3/31/11.
| 2011-03-03 | P | P | P | Process a Budget package that adjusts WRR add-on retraoctively for the period 7/1/07-12/31/10 and add a new WRR add-on for the period 1/1/10 -3/31/11. This budget package will reconcile WRR payments based on the new allocation method causing payouts and takebakcs among D&TCs. The Package delivered to the Division of the Budget for their approval on 3/11/2011.
| 2011-04-13 | P | P | P | Remove WRR add-on from the applicable Medicaid rates effective 4/1/11 when preparing a rate transmittal for the WRR Budget package. Savings will be achieved going forward due to elimination of WRR add-on effective 4/1/11, not by the Budget package.
| 2011-04-26 | P | P | P | Rates went to production on 4/26/11 and will be activated on 4/27/11 in cycle 1759.
MRT # 55 |  |  |  |  | Project Name: Increase coverage of tobacco cessation counseling Division Lead: Greg Allen Team Lead: Donna Haskin Additional staff: Adella Lamb, Mike Dembrosky Description: Smoking cessation counseling services will be available to any Medicaid enrollee. | 0.31
| 2011-01-11 | P | P | P | Draft Article 7 language
| 2011-01-13 | P | P | P | Determine if SPA is needed
| 2011-03-31 | P | P | P | Submit Federal Public Notice
| 2011-03-11 | P | P | P | Determine if regulations are needed
| 2011-03-18 | P | P | P | Determine any additional program requirements
| 2011-03-18 | P | P | P | Assess managed care impact
| 2011-04-01 | P | P | P | Obtain legislative authority to provide smoking cessation counseling.
| 2011-04-01 | P | P | P | Expansion implemented.
| 2011-04-08 | P | P | P | Determine system requirements- edits and modifiers can be completed without an EP.
| 2011-04-08 | P | P | P | Initiate payment discussion that will allow FQHCs to bill for SCC outside of their PPS rate.
| 2011-04-21 | P | P | P | Draft policy/billing guidance for Medicaid Update- for May publication.
| 2011-05-01 | P | P | P | Notify stakeholders (American Lung Assn and National Cancer Society) of program expansion
| 2011-05-13 | P | P | P | Finalize payment policy and rates that will allow FQHCs to bill for SCC outside of their PPS rate.
| 2011-05-15 | P | P | P | Notify FQHCs of policy and rate codes for SCC.
| 2011-06-01 | P | P | P | Implement payment policy and rates that will allow FQHCs to bill for SCC outside of their PPS rate.
MRT# 60 |  |  |  |  | Project Name: Delink Workers Compensation and No Fault (WCNF) Rates from Medicaid Division Lead: DOH / DHCF Team Lead: Janet Baggetta Description: WCNF rates can be delinked from the Medicaid Fee-for-Service inpatient rates and not receive the benefits of the Medicaid reimbursement cuts enacted in Medicaid.
| 2011-03-03 | P | P | P | Statute Amended - Part of MRT Article VII. Does not need Federal Public Notice or State Plan Amendment.
| 2010-04-01 | P | P | P | Implement programming in Medicaid FFS rate sheet to separate WCNF -- Since the delink of the rates began 4/1/2010, this programming was implemented at that time.
| 2011-04-20 | P | P | P | Publish Rates effective 4/1/2011 without Medicaid reductions: letter to the Workers Compensation Board required to complete publication -- The January 1, 2011 WCNF rates have been calculated including the 2011 Trend Factor and without the reduction for Potentially Preventable Readmissions. Since there are no changes to the rate method and the 1/1/2011 rates already reflect the 1% 2011 trend, the 4/1/2011 rates do not require any rate changes to the 1/1/2011 rate already calculated.
MRT # 4155 |  |  |  |  | Project Name: Eliminate Long Term Care Assessment Center Funding Division Lead: Team Lead: Add'l Staff: Description: Eliminate Long Term Care Assessment Center funding. | -6
| 2011-04-01 | P | P | P | LTC Assessment Center Funding Removed from the Budget

## Merged
Milestones: | Date | Schedule | Budget | Risk | Description | Savings Target ($millions)
Proposal Name - List MRT Proposal that is being merged with this proposal >> Decription of why this decision was made and list the date/who requested it be merged
MRT1 #1021 |  |  |  |  | Project Name: Facilitating Co-Located physical health, behavioral health and developmental disability services Division Lead: DFPP Team Lead: Denise Spor Description: To streamline process & eliminate barriers and to determine a single set of rules for facilities seeking to co-locate services | 0
Merged with #89 Health Homes; approved by Jason Helgerson 4/6/11.
MRT#1029 |  |  |  |  | Project Name: Administrative Renewal for Aged, Blind, and Disabled and Medicare Savings Program (MSP) Participants Division Lead: DCE Team Lead: Wendy Butz Description: Allow aged, blind and disabled with fixed incomes to be automatically renewed based on cost of living increases. | -0.1
Merged with #133; approved by Jason Helgerson 4/6/11.

## Cancelled
MRT Proposal: |  | Description | Savings Target ($millions)
PROPOSALS NOT INCLUDED IN ENACTED BUDGET:
MRT # 15-D |  | Project Name: Increase the Number of Immunizations that a Pharmacist May Administer Division Lead: DFPP Team Lead: Mary Carroll Description: This proposal will allow pharmacists to administer all vaccines recommended by the CDC for patients ages 11 and above. | -30.2
MRT#18 |  | Project Name: Eliminate Spousal Refusal Division Lead: DCE Team Lead: Wendy Butz Description: Eliminate the loophole that allows legally responsible relatives to refuse to financially support their applying spouse, or child to obtain Medicaid. | -28.3
MRT # 41 |  | Project Name: New York State Public Health Service Corps Division Lead: Primary Care Team Lead: Karen Westervelt Additional Staff: Caleb Wistar/Barry Gray Description: Implement the New York State Public Health Service Corps | 1
MRT# 104 |  | Project Name: Medicaid Co-payment Changes Division Lead: DFPP Team Lead: Akbar Khan (MA) Add'l staff: Ron Bass (MA), Ralph Bielefeldt (CHP), Sue Barth (FHP) Description: Ensure Consumer Protection and Promote Personal Responsibility | -7.5
MRT# 121 |  | Project Name: Public Nursing Homes Corporation Division Lead: Team Lead: Valerie Deetz Add'l Staff: Mark Kissinger, Laura Sprague, Jackie Pappalardi Description: This proposal would establish a State authority/public benefit corporation that counties with nursing homes would have the option to join. | 0
MRT # 147 |  | Certain initiatives from MRT # 145 were rejected: Reinstate Industrial Development Agency (IDA) Financing Temporary suspension of NCQPA by Article 28 facilities Death and Felony Crime Reporting
MRT# 264 |  | Project Name: Apply a surcharge to Physician Office Based Surgery and Radiology Services Division Lead: DHCF Team Lead: Anthony Naglieri Add'l Staff: Phyllis Stanton, Michelle Levesque Description: Implement a broad based and uniform surcharge on surgery and radiology services provided by phyisicians in office-based settings, including non-licensed urgent care centers, utilizing CPT codes. | -57.8