## EP Gantt Chart (old) (hidden)
Exact Date | time axis 2015-10-01 to 2020-05-01
DSRIP DY1 begins (as of April 2015) | April 2015 - April 2016 | bar: 2015-10-01 to 2016-03-01
DOH finalizes EIP per member per month (PMPM) rates and sends to CMS/DOB for review | October 14th 2015 | bar: 2015-10-01
All PPS/MCO pairings complete Phase 1 of the Equity Program Contracts (EIP) | December 15th 2015 – February 1st 2016 | bar: 2015-12-01 to 2016-01-01
DOH begins monthly disbursement of EIP payments to MCOs (first payment retroactive to April 2015) | January 5th 2016 | bar: 2016-01-01
DY1 Q3 Quarterly Report due | January 31st 2016 | bar: 2016-01-01
MCOs make DY1 Q3 quarterly EIP payments to PPSs (this first payment retroactive to April 2015) | February 1st 2016 – February 28th 2016 | bar: 2016-02-01
All PPS/MCO pairings complete Phase 2 of the Equity Program Contracts (EPP) | February 15th 2016 – March 15th 2016 | bar: 2016-02-01 to 2016-03-01
DOH finalizes EPP per member per month (PMPM) rates and sends to CMS/DOB for review | March 21st 2016 | bar: 2016-03-01
DSRIP DY2 begins | April 2016 - April 2017 | bar: 2016-04-01 to 2017-03-01
DOH begins monthly disbursement of EPP payments to MCOs (first payment retroactive to April 2015) | April 15th 2016 | bar: 2016-04-01
MCOs make first annual EPP payments to PPSs | April 1st 2016 – April 30th 2016 | bar: 2016-04-01
DY1 Q4 Quarterly Report due | April 30th 2016 | bar: 2016-04-01
MCOs make DY1 Q4 quarterly EIP payments to PPSs | May 1st 2016 – May 31st 2016 | bar: 2016-05-01
DY2 Q1 Quarterly Report due | July 30th 2016 | bar: 2016-07-01
MCOs make DY2 Q1 quarterly EIP payments to PPSs | August 1st 2016 – August 30th 2016 | bar: 2016-08-01
DY2 Q2 Quarterly Report due | October 31st 2016 | bar: 2016-10-01
MCOs make DY2 Q2 quarterly EIP payments to PPSs | November 1st 2016 – November 30th 2016 | bar: 2016-11-01
DY2 Q3 Quarterly Report due | January 31st 2017 | bar: 2017-01-01
MCOs make DY2 Q3 quarterly EIP payments to PPSs | February 1st 2017 – February 28th 2017 | bar: 2017-02-01
DSRIP DY3 begins | April 2017 - April 2018 | bar: 2017-04-01 to 2018-03-01
MCOs make second annual EPP payments to PPSs | April 1st 2017 – April 30th 2017 | bar: 2017-04-01
DY2 Q4 Quarterly Report due | April 30th 2017 | bar: 2017-04-01
MCOs make DY2 Q4 quarterly EIP payments to PPSs | May 1st 2017 – May 31st 2017 | bar: 2017-05-01
DY3 Q1 Quarterly Report due | July 30th 2017 | bar: 2017-07-01
MCOs make DY3 Q1 quarterly EIP payments to PPSs | August 1st 2017 – August 30th 2017 | bar: 2017-08-01
DY3 Q2 Quarterly Report due | October 31st 2017 | bar: 2017-10-01
MCOs make DY3 Q2 quarterly EIP payments to PPSs | November 1st 2017 – November 30th 2017 | bar: 2017-11-01
DY3 Q3 Quarterly Report due | January 31st 2018 | bar: 2018-01-01
MCOs make DY3 Q3 quarterly EIP payments to PPSs | February 1st 2018 – February 28th 2018 | bar: 2018-02-01
DSRIP DY4 begins | April 2018 - April 2019 | bar: 2018-04-01 to 2019-03-01
MCOs make third annual EPP payments to PPSs | April 1st 2018 – April 30th 2018 | bar: 2018-04-01
DY3 Q4 Quarterly Report due | April 30th 2018 | bar: 2018-04-01
MCOs make DY3 Q4 quarterly EIP payments to PPSs | May 1st 2018 – May 31st 2018 | bar: 2018-05-01
DY4 Q1 Quarterly Report due | July 30th 2018 | bar: 2018-07-01
MCOs make DY4 Q1 quarterly EIP payments to PPSs | August 1st 2018 – August 30th 2018 | bar: 2018-08-01
DY4 Q2 Quarterly Report due | October 31st 2018 | bar: 2018-10-01
MCOs make DY4 Q2 quarterly EIP payments to PPSs | November 1st 2018 – November 30th 2018 | bar: 2018-11-01
DY4 Q3 Quarterly Report due | January 31st 2019 | bar: 2019-01-01
MCOs make DY4 Q3 quarterly EIP payments to PPSs | February 1st 2019 – February 28th 2019 | bar: 2019-02-01
DSRIP DY5 begins | April 2019 - April 2020 | bar: 2019-04-01 to 2020-03-01
MCOs make fourth annual EPP payments to PPSs | April 1st 2019 – April 30th 2019 | bar: 2019-04-01
DY4 Q4 Quarterly Report due | April 30th 2019 | bar: 2019-04-01
MCOs make DY4 Q4 quarterly EIP payments to PPSs | May 1st 2019 – May 31st 2019 | bar: 2019-05-01
DY5 Q1 Quarterly Report due | July 30th 2019 | bar: 2019-07-01
MCOs make DY5 Q1 quarterly EIP payments to PPSs | August 1st 2019 – August 30th 2019 | bar: 2019-08-01
DY5 Q2 Quarterly Report due | October 31st 2019 | bar: 2019-10-01
MCOs make DY5 Q2 quarterly EIP payments to PPSs | November 1st 2019 – November 30th 2019 | bar: 2019-11-01
DY5 Q3 Quarterly Report due | January 31st 2020 | bar: 2020-01-01
MCOs make DY5 Q3 quarterly EIP payments to PPSs | February 1st 2020 – February 28th 2020 | bar: 2020-02-01
DSRIP Program ends | April 1st 2020 | bar: 2020-04-01 to 2020-05-01
MCOs make fifth annual EPP payments to PPSs | April 1st 2020 – April 30th 2020 | bar: 2020-04-01
DY5 Q4 Quarterly Report due | April 30th 2020 + | bar: 2020-04-01
MCOs make DY5 Q4 quarterly EIP payments to PPSs | May 1st 2020 – May 31st 2020 | bar: 2020-05-01

## EPP Measurement-Pay Timeline (hidden)
EPP Measurement vs. Payment Timeline
|  | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
Scenario 1: EPP Annual Reporting; Annual Payment
| DSRIP Demonstration Year | October: DSRIP DY1 (2015); April: DSRIP DY2 (2016); April: DSRIP DY3 (2017), DY4 (2018), & DY5 (2019); April: DY6 (2020, Post-DSRIP); April: DY7 (2021, Post-DSRIP)
| All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | January: EIP and EPP contracts complete; February: Updates to (EIP) Contracts; February: Updates to (EIP) Contracts (Years 3 & 4 only)
| All MCOs submit Equity Program Governance Document to DOH | January: EP Governance Document complete; February: Updates to EP Governance Document; February: Updates to EP Governance Document (Years 3 & 4 only)
| DOH begins monthly disbursement of EP payments to MCOs (EIP first payment retroactive to April 2015) | January: Monthly EIP Payments to MCOs begin; April: Monthly EPP Payments to MCOs begin; March: Last Monthly EIP Payment to MCOs; March: Last Monthly EPP Payment to MCOs
| DSRIP Quarterly Reporting in MAPP, used for EPP | October: DY1 Q2 QR due; January: DY1 Q3 QR due; April: DY1 Q4 QR due; July: DY2 Q1 QR due; October: DY2 Q2 QR due; January: DY2 Q3 QR due; April: DY2,3,4 Q4 QR due; July: DY3,4,5 Q1 QR due; October: DY3,4,5 Q2 QR due; January: DY3,4,5 Q3 QR due; April: DY5 Q4 QR due
| DOH sends Performance Achievement information to MCOs for EPP | December: MCOs receive EPP achievement DY1 Q2; March: MCOs receive EPP achievement DY1 Q3; June: MCOs receive EPP achievement DY1 Q4; September: MCOs receive EPP achievement DY2 Q1; December: MCOs receive EPP achievement DY2 Q2; March: MCOs receive EPP achievement DY2 Q3; June: MCOs receive EPP achievement DY2, 3, 4 Q4; September: MCOs receive EPP achievement DY3, 4, 5 Q1; December: MCOs receive EPP achievement DY3, 4, 5 Q2; March: MCOs receive EPP achievement DY3, 4, 5 Q3; June: MCOs receive EPP achievement DY5 Q4
| MCOs make EPP payments to PPSs* | April: DY1 Annual EPP Payment; April: DY2, 3, 4 Annual EPP Payment; April: DY5 Annual EPP Payment
| MCO-to-DOH EPP Reports on Payments | May: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report
* Schedule being provided as an example | bar: October to November
|  | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
Scenario 2: EPP Annual Reporting; Semi-Annual Payment
| DSRIP Demonstration Year | October: DSRIP DY1 (2015); April: DSRIP DY2 (2016); April: DSRIP DY3 (2017), DY4 (2018), & DY5 (2019); April: DY6 (2020, Post-DSRIP); April: DY7 (2021, Post-DSRIP)
| All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | January: EIP and EPP contracts complete; February: Updates to (EIP) Contracts; February: Updates to (EIP) Contracts (Years 3 & 4 only)
| All MCOs submit Equity Program Governance Document to DOH | January: EP Governance Document complete; February: Updates to EP Governance Document; February: Updates to EP Governance Document (Years 3 & 4 only)
| DOH begins monthly disbursement of EP payments to MCOs (EIP first payment retroactive to April 2015) | January: Monthly EIP Payments to MCOs begin; April: Monthly EPP Payments to MCOs begin; March: Last Monthly EIP Payment to MCOs; March: Last Monthly EPP Payment to MCOs
| DSRIP Quarterly Reporting in MAPP, used for EPP | October: DY1 Q2 QR due; January: DY1 Q3 QR due; April: DY1 Q4 QR due; July: DY2 Q1 QR due; October: DY2 Q2 QR due; January: DY2 Q3 QR due; April: DY2,3,4 Q4 QR due; July: DY3,4,5 Q1 QR due; October: DY3,4,5 Q2 QR due; January: DY3,4,5 Q3 QR due; April: DY5 Q4 QR due
| DOH sends Performance Achievement information to MCOs for EPP | December: MCOs receive EPP achievement DY1 Q2; March: MCOs receive EPP achievement DY1 Q3; June: MCOs receive EPP achievement DY1 Q4; September: MCOs receive EPP achievement DY2 Q1; December: MCOs receive EPP achievement DY2 Q2; March: MCOs receive EPP achievement DY2 Q3; June: MCOs receive EPP achievement DY2, 3, 4 Q4; September: MCOs receive EPP achievement DY3, 4, 5 Q1; December: MCOs receive EPP achievement DY3, 4, 5 Q2; March: MCOs receive EPP achievement DY3, 4, 5 Q3; June: MCOs receive EPP achievement DY5 Q4
| MCOs make EPP payments to PPSs* | October: Semi-Annual EPP Payment; April: Semi-Annual EPP Payment; October: Semi-Annual EPP Payment; April: Semi-Annual EPP Payment; October: Semi-Annual EPP Payment; April: Semi-Annual EPP Payment
| MCO-to-DOH EPP Reports on Payments | November: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report; November: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report; November: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report
* Schedule being provided as an example | bar: October to November
|  | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
Scenario 3: EPP Annual Reporting; Quarterly Payment
| DSRIP Demonstration Year | October: DSRIP DY1 (2015); April: DSRIP DY2 (2016); April: DSRIP DY3 (2017), DY4 (2018), & DY5 (2019); April: DY6 (2020, Post-DSRIP); April: DY7 (2021, Post-DSRIP)
| All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | January: EIP and EPP contracts complete; February: Updates to (EIP) Contracts; February: Updates to (EIP) Contracts (Years 3 & 4 only)
| All MCOs submit Equity Program Governance Document to DOH | January: EP Governance Document complete; February: Updates to EP Governance Document; February: Updates to EP Governance Document (Years 3 & 4 only)
| DOH begins monthly disbursement of EP payments to MCOs (EIP first payment retroactive to April 2015) | January: Monthly EIP Payments to MCOs begin; April: Monthly EPP Payments to MCOs begin; March: Last Monthly EIP Payment to MCOs; March: Last Monthly EPP Payment to MCOs
| DSRIP Quarterly Reporting in MAPP, used for EPP | October: DY1 Q2 QR due; January: DY1 Q3 QR due; April: DY1 Q4 QR due; July: DY2 Q1 QR due; October: DY2 Q2 QR due; January: DY2 Q3 QR due; April: DY2,3,4 Q4 QR due; July: DY3,4,5 Q1 QR due; October: DY3,4,5 Q2 QR due; January: DY3,4,5 Q3 QR due; April: DY5 Q4 QR due
| DOH sends Performance Achievement information to MCOs for EPP | December: MCOs receive EPP achievement DY1 Q2; March: MCOs receive EPP achievement DY1 Q3; June: MCOs receive EPP achievement DY1 Q4; September: MCOs receive EPP achievement DY2 Q1; December: MCOs receive EPP achievement DY2 Q2; March: MCOs receive EPP achievement DY2 Q3; June: MCOs receive EPP achievement DY2, 3, 4 Q4; September: MCOs receive EPP achievement DY3, 4, 5 Q1; December: MCOs receive EPP achievement DY3, 4, 5 Q2; March: MCOs receive EPP achievement DY3, 4, 5 Q3; June: MCOs receive EPP achievement DY5 Q4
| MCOs make EPP payments to PPSs* | July: Quarterly EPP Payment; October: Quarterly EPP Payment; January: Quarterly EPP Payment; April: Quarterly EPP Payment; July: Quarterly EPP Payment; October: Quarterly EPP Payment; January: Quarterly EPP Payment; April: Quarterly EPP Payment; July: Quarterly EPP Payment; October: Quarterly EPP Payment; January: Quarterly EPP Payment; April: Quarterly EPP Payment
| MCO-to-DOH EPP Reports on Payments | August: MCO-to-DOH EPP Report; November: MCO-to-DOH EPP Report; February: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report; August: MCO-to-DOH EPP Report; November: MCO-to-DOH EPP Report; February: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report; August: MCO-to-DOH EPP Report; November: MCO-to-DOH EPP Report; February: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report
* Schedule being provided as an example | bar: October to November
|  | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
EPP Measurement and Payment Timeline
| DSRIP Demonstration Year | April: DSRIP DY1 (2015-2016); April: DSRIP DY2 (2016-2017); April: DSRIP DY3 (2017-2018); April: DSRIP DY4 (2018-2019); April: DSRIP DY5 (2019-2020); April: Post-DSRIP (2020-2021)
| DSRIP Measurement Year | April: DSRIP MY1 (2015); July: DSRIP MY2 (2015-2016); July: DSRIP MY3 (2016-2017); July: DSRIP MY4 (2017-2018); July: DSRIP MY5 (2018-2019)
| Data is compiled (unavailable to anyone) | July: MY1 Data Compiling; July: MY2 Data Compiling; July: MY3 Data Compiling; July: MY4 Data Compiling; July: MY5 Data Compiling
| IA Analyzes Data | December: IA Analyzes MY1 Data; December: IA Analyzes MY2 Data; December: IA Analyzes MY3 Data; December: IA Analyzes MY4 Data; December: IA Analyzes MY5 Data
| PMPM Rate determination/ reconciliation | March: DY1 PMPM rate determined; March: DY2 PMPM rate determined; March: DY3 PMPM rate determined; March: DY4 PMPM rate determined; March: DY5 PMPM rate determined; September: Final PMPM Reconciliation based on DY5 Performance Data
| DOH monthly disbursement of EPP payments to MCOs | April: DY1 PMPM monthly payments to MCO; April: DY2 PMPM monthly payments to MCO; April: DY3 PMPM monthly payments to MCO; April: DY4 PMPM monthly payments to MCO; April: First DY5 PMPM monthly payments to MCO; October: Second DY5 PMPM monthly payments to MCO
| DSRIP Quarterly Reporting in MAPP, used for EPP | July: DY1 Q1 QR due; October: DY1 Q2 QR due; January: DY1 Q3 QR due; April: DY1 Q4 QR due; July: DY2 Q1 QR due; October: DY2 Q2 QR due; January: DY2 Q3 QR due; April: DY2 Q4 QR due; July: DY3 Q1 QR due; October: DY3 Q2 QR due; January: DY3 Q3 QR due; April: DY3 Q4 QR due; July: DY4 Q1 QR due; October: DY4 Q2 QR due; January: DY4 Q3 QR due; April: DY4 Q4 QR due; July: DY5 Q1 QR due; October: DY5 Q2 QR due; January: DY5 Q3 QR due; April: DY5 Q4 QR due
| DOH sends Performance Achievement information to MCOs for EPP | June: MCOs receive EPP achievement DY1; June: MCOs receive EPP achievement DY2; June: MCOs receive EPP achievement DY3; June: MCOs receive EPP achievement DY4; June: MCOs receive EPP achievement DY5
| MCOs make EPP payments to PPSs* | [15 empty] | Monthly EPP Payment - MY1 | Monthly EPP Payment - MY1 | Monthly EPP Payment - MY1 | Monthly EPP Payment - MY1 | Monthly EPP Payment - MY1 | Monthly EPP Payment - MY1 | Monthly EPP Payment - MY1 | Monthly EPP Payment - MY1 | Monthly EPP Payment - MY1 | Monthly EPP Payment - MY1 | Monthly EPP Payment - MY1 | Monthly EPP Payment - MY1 | Monthly EPP Payment - MY2 | Monthly EPP Payment - MY2 | Monthly EPP Payment - MY2 | Monthly EPP Payment - MY2 | Monthly EPP Payment - MY2 | Monthly EPP Payment - MY2 | Monthly EPP Payment - MY2 | Monthly EPP Payment - MY2 | Monthly EPP Payment - MY2 | Monthly EPP Payment - MY2 | Monthly EPP Payment - MY2 | Monthly EPP Payment - MY2 | Monthly EPP Payment - MY3 | Monthly EPP Payment - MY3 | Monthly EPP Payment - MY3 | Monthly EPP Payment - MY3 | Monthly EPP Payment - MY3 | Monthly EPP Payment - MY3 | Monthly EPP Payment - MY3 | Monthly EPP Payment - MY3 | Monthly EPP Payment - MY3 | Monthly EPP Payment - MY3 | Monthly EPP Payment - MY3 | Monthly EPP Payment - MY3 | Monthly EPP Payment - MY4 | Monthly EPP Payment - MY4 | Monthly EPP Payment - MY4 | Monthly EPP Payment - MY4 | Monthly EPP Payment - MY4 | Monthly EPP Payment - MY4 | Monthly EPP Payment - MY4 | Monthly EPP Payment - MY4 | Monthly EPP Payment - MY4 | Monthly EPP Payment - MY4 | Monthly EPP Payment - MY4 | Monthly EPP Payment - MY4 | Monthly EPP Payment - MY5 | Monthly EPP Payment - MY5 | Monthly EPP Payment - MY5 | Monthly EPP Payment - MY5 | Monthly EPP Payment - MY5 | Monthly EPP Payment - MY5 | Monthly EPP Payment - MY5 | Monthly EPP Payment - MY5 | Monthly EPP Payment - MY5 | Monthly EPP Payment - MY5 | Monthly EPP Payment - MY5 | Monthly EPP Payment - MY5
| MCO-to-DOH EPP Reports on Payments* | October: MCO-to-DOH EPP Report; January: MCO-to-DOH EPP Report; April: MCO-to-DOH EPP Report; July: MCO-to-DOH EPP Report; October: MCO-to-DOH EPP Report; January: MCO-to-DOH EPP Report; April: MCO-to-DOH EPP Report; July: MCO-to-DOH EPP Report; October: MCO-to-DOH EPP Report; January: MCO-to-DOH EPP Report; April: MCO-to-DOH EPP Report; July: MCO-to-DOH EPP Report; October: MCO-to-DOH EPP Report; January: MCO-to-DOH EPP Report; April: MCO-to-DOH EPP Report; July: MCO-to-DOH EPP Report; October: MCO-to-DOH EPP Report; January: MCO-to-DOH EPP Report; April: MCO-to-DOH EPP Report; July: MCO-to-DOH EPP Report
* Schedule being provided as an example
DY | Associated PMPM components
DY1 | PMPM = 0 (no EPP payments in DY1 )
DY2 | PMPM = DY1 PMPM Optimal
DY3 | PMPM = DY2 PMPM Optimal - Difference between DY1 PMPM Optimal & DY1 PMPM Actual
DY4 | PMPM = DY3 PMPM Optimal - Difference between DY2 PMPM Optimal & DY2 PMPM Actual
DY5 | PMPM = DY4 PMPM Optimal - Difference between DY3 PMPM Optimal & DY3 PMPM Actual
DY6 (1) | PMPM = DY5 PMPM Optimal - Difference between DY4 PMPM Optimal & DY4 PMPM Actual
DY6 (2) | PMPM = DY5 PMPM Optimal - Difference between DY5 PMPM Optimal & DY5 PMPM Actual

## Sheet1 (hidden)
Equity Performance Program - Measurement & Payment Timeline
Demo Year & Payment Period |  | MY for Regular DSRIP Pmts | P4R/P4P? | MY Dates | MY Results Available | Regular DSRIP Pmt Date | EPP Pmts Begin | EPP Pmts End
DY 1 | Pmt 1 | MY 0 (?) | P4R | Jul 2013 - Jun 2014 | Jan 2016 | Jan 2016 | Jul 2016 | Jun 2017
| Pmt 2 | MY 1 | P4R | Jul 2014 - Jun 2015 | Mar 2016 | Jul 2016 | Jul 2016 | Jun 2017
DY 2 | Pmt 1 | MY 1 | P4R | Jul 2014 - Jun 2015 | Mar 2016 | Jan 2017 | Jul 2017 | Jun 2018
| Pmt 2 | MY 2 | P4R/P4P | Jul 2015 - Jun 2016 | Mar 2017 | Jul 2017 | Jul 2017 | Jun 2018
DY 3 | Pmt 1 | MY 2 | P4R/P4P | Jul 2015 - Jun 2016 | Mar 2017 | Jan 2018 | Jul 2018 | Jun 2019
| Pmt 2 | MY 3 | P4R/P4P | Jul 2016 - Jun 2017 | Mar 2018 | Jul 2018 | Jul 2018 | Jun 2019
DY 4 | Pmt 1 | MY 3 | P4R/P4P | Jul 2016 - Jun 2017 | Mar 2018 | Jan 2019 | Jul 2019 | Jun 2020
| Pmt 2 | MY 4 | P4P | Jul 2017 - Jun 2018 | Mar 2019 | Jul 2019 | Jul 2019 | Jun 2020
DY 5 | Pmt 1 | MY 4 | P4P | Jul 2017 - Jun 2018 | Mar 2019 | Jan 2020 | Jul 2020 | Jun 2021
| Pmt 2 | MY 5 | P4P | Jul 2018 - Jun 2019 | Mar 2020 | Jul 2020 | Jul 2020 | Jun 2021

## EPP Timelines
EPP Timelines
| October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
Scenario 1: EPP Annual Reporting; Annual Payment
DSRIP Demonstration Year | October: DSRIP DY1 (2015); April: DSRIP DY2 (2016); April: DSRIP DY3 (2017), DY4 (2018), & DY5 (2019); April: DY6 (2020, Post-DSRIP); April: DY7 (2021, Post-DSRIP)
All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | January: EIP and EPP contracts complete; February: Updates to (EIP) Contracts; February: Updates to (EIP) Contracts (Years 3 & 4 only)
All MCOs submit Equity Program Governance Document to DOH | January: EP Governance Document complete; February: Updates to EP Governance Document; February: Updates to EP Governance Document (Years 3 & 4 only)
DOH begins monthly disbursement of EP payments to MCOs (EIP first payment retroactive to April 2015) | January: Monthly EIP Payments to MCOs begin; April: Monthly EPP Payments to MCOs begin; March: Last Monthly EIP Payment to MCOs; March: Last Monthly EPP Payment to MCOs
DSRIP Quarterly Reporting in MAPP, used for EPP | October: DY1 Q2 QR due; January: DY1 Q3 QR due; April: DY1 Q4 QR due; July: DY2 Q1 QR due; October: DY2 Q2 QR due; January: DY2 Q3 QR due; April: DY2,3,4 Q4 QR due; July: DY3,4,5 Q1 QR due; October: DY3,4,5 Q2 QR due; January: DY3,4,5 Q3 QR due; April: DY5 Q4 QR due
DOH sends Performance Achievement information to MCOs for EPP | December: MCOs receive EPP achievement DY1 Q2; March: MCOs receive EPP achievement DY1 Q3; June: MCOs receive EPP achievement DY1 Q4; September: MCOs receive EPP achievement DY2 Q1; December: MCOs receive EPP achievement DY2 Q2; March: MCOs receive EPP achievement DY2 Q3; June: MCOs receive EPP achievement DY2, 3, 4 Q4; September: MCOs receive EPP achievement DY3, 4, 5 Q1; December: MCOs receive EPP achievement DY3, 4, 5 Q2; March: MCOs receive EPP achievement DY3, 4, 5 Q3; June: MCOs receive EPP achievement DY5 Q4
MCOs make EPP payments to PPSs* | April: DY1 Annual EPP Payment; April: DY2, 3, 4 Annual EPP Payment; April: DY5 Annual EPP Payment
MCO-to-DOH EPP Reports on Payments | May: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report
* Schedule being provided as an example | bar: October to November
| October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
Scenario 2: EPP Annual Reporting; Semi-Annual Payment
DSRIP Demonstration Year | October: DSRIP DY1 (2015); April: DSRIP DY2 (2016); April: DSRIP DY3 (2017), DY4 (2018), & DY5 (2019); April: DY6 (2020, Post-DSRIP); April: DY7 (2021, Post-DSRIP)
All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | January: EIP and EPP contracts complete; February: Updates to (EIP) Contracts; February: Updates to (EIP) Contracts (Years 3 & 4 only)
All MCOs submit Equity Program Governance Document to DOH | January: EP Governance Document complete; February: Updates to EP Governance Document; February: Updates to EP Governance Document (Years 3 & 4 only)
DOH begins monthly disbursement of EP payments to MCOs (EIP first payment retroactive to April 2015) | January: Monthly EIP Payments to MCOs begin; April: Monthly EPP Payments to MCOs begin; March: Last Monthly EIP Payment to MCOs; March: Last Monthly EPP Payment to MCOs
DSRIP Quarterly Reporting in MAPP, used for EPP | October: DY1 Q2 QR due; January: DY1 Q3 QR due; April: DY1 Q4 QR due; July: DY2 Q1 QR due; October: DY2 Q2 QR due; January: DY2 Q3 QR due; April: DY2,3,4 Q4 QR due; July: DY3,4,5 Q1 QR due; October: DY3,4,5 Q2 QR due; January: DY3,4,5 Q3 QR due; April: DY5 Q4 QR due
DOH sends Performance Achievement information to MCOs for EPP | December: MCOs receive EPP achievement DY1 Q2; March: MCOs receive EPP achievement DY1 Q3; June: MCOs receive EPP achievement DY1 Q4; September: MCOs receive EPP achievement DY2 Q1; December: MCOs receive EPP achievement DY2 Q2; March: MCOs receive EPP achievement DY2 Q3; June: MCOs receive EPP achievement DY2, 3, 4 Q4; September: MCOs receive EPP achievement DY3, 4, 5 Q1; December: MCOs receive EPP achievement DY3, 4, 5 Q2; March: MCOs receive EPP achievement DY3, 4, 5 Q3; June: MCOs receive EPP achievement DY5 Q4
MCOs make EPP payments to PPSs* | October: Semi-Annual EPP Payment; April: Semi-Annual EPP Payment; October: Semi-Annual EPP Payment; April: Semi-Annual EPP Payment; October: Semi-Annual EPP Payment; April: Semi-Annual EPP Payment
MCO-to-DOH EPP Reports on Payments | November: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report; November: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report; November: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report
* Schedule being provided as an example | bar: October to November
| October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
Scenario 3: EPP Annual Reporting; Quarterly Payment
DSRIP Demonstration Year | October: DSRIP DY1 (2015); April: DSRIP DY2 (2016); April: DSRIP DY3 (2017), DY4 (2018), & DY5 (2019); April: DY6 (2020, Post-DSRIP); April: DY7 (2021, Post-DSRIP)
All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | January: EIP and EPP contracts complete; February: Updates to (EIP) Contracts; February: Updates to (EIP) Contracts (Years 3 & 4 only)
All MCOs submit Equity Program Governance Document to DOH | January: EP Governance Document complete; February: Updates to EP Governance Document; February: Updates to EP Governance Document (Years 3 & 4 only)
DOH begins monthly disbursement of EP payments to MCOs (EIP first payment retroactive to April 2015) | January: Monthly EIP Payments to MCOs begin; April: Monthly EPP Payments to MCOs begin; March: Last Monthly EIP Payment to MCOs; March: Last Monthly EPP Payment to MCOs
DSRIP Quarterly Reporting in MAPP, used for EPP | October: DY1 Q2 QR due; January: DY1 Q3 QR due; April: DY1 Q4 QR due; July: DY2 Q1 QR due; October: DY2 Q2 QR due; January: DY2 Q3 QR due; April: DY2,3,4 Q4 QR due; July: DY3,4,5 Q1 QR due; October: DY3,4,5 Q2 QR due; January: DY3,4,5 Q3 QR due; April: DY5 Q4 QR due
DOH sends Performance Achievement information to MCOs for EPP | December: MCOs receive EPP achievement DY1 Q2; March: MCOs receive EPP achievement DY1 Q3; June: MCOs receive EPP achievement DY1 Q4; September: MCOs receive EPP achievement DY2 Q1; December: MCOs receive EPP achievement DY2 Q2; March: MCOs receive EPP achievement DY2 Q3; June: MCOs receive EPP achievement DY2, 3, 4 Q4; September: MCOs receive EPP achievement DY3, 4, 5 Q1; December: MCOs receive EPP achievement DY3, 4, 5 Q2; March: MCOs receive EPP achievement DY3, 4, 5 Q3; June: MCOs receive EPP achievement DY5 Q4
MCOs make EPP payments to PPSs* | July: Quarterly EPP Payment; October: Quarterly EPP Payment; January: Quarterly EPP Payment; April: Quarterly EPP Payment; July: Quarterly EPP Payment; October: Quarterly EPP Payment; January: Quarterly EPP Payment; April: Quarterly EPP Payment; July: Quarterly EPP Payment; October: Quarterly EPP Payment; January: Quarterly EPP Payment; April: Quarterly EPP Payment
MCO-to-DOH EPP Reports on Payments | August: MCO-to-DOH EPP Report; November: MCO-to-DOH EPP Report; February: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report; August: MCO-to-DOH EPP Report; November: MCO-to-DOH EPP Report; February: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report; August: MCO-to-DOH EPP Report; November: MCO-to-DOH EPP Report; February: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report
* Schedule being provided as an example | bar: October to November
| October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
Scenario 4: EPP Annual Reporting, Monthly Payment
DSRIP Demonstration Year | October: DSRIP DY1 (2015); April: DSRIP DY2 (2016); April: DSRIP DY3 (2017), DY4 (2018), & DY5 (2019); April: DY6 (2020, Post-DSRIP); April: DY7 (2021, Post-DSRIP)
All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | January: EIP and EPP contracts complete; February: Updates to (EIP) Contracts; February: Updates to (EIP) Contracts (Years 3 & 4 only)
All MCOs submit Equity Program Governance Document to DOH | January: EP Governance Document complete; February: Updates to EP Governance Document; February: Updates to EP Governance Document (Years 3 & 4 only)
DOH begins monthly disbursement of EP payments to MCOs (EIP first payment retroactive to April 2015) | January: Monthly EIP Payments to MCOs begin; April: Monthly EPP Payments to MCOs begin; March: Last Monthly EIP Payment to MCOs; March: Last Monthly EPP Payment to MCOs
DSRIP Quarterly Reporting in MAPP, used for EPP | October: DY1 Q2 QR due; January: DY1 Q3 QR due; April: DY1 Q4 QR due; July: DY2 Q1 QR due; October: DY2 Q2 QR due; January: DY2 Q3 QR due; April: DY2,3,4 Q4 QR due; July: DY3,4,5 Q1 QR due; October: DY3,4,5 Q2 QR due; January: DY3,4,5 Q3 QR due; April: DY5 Q4 QR due
DOH sends Performance Achievement information to MCOs for EPP | December: MCOs receive EPP achievement DY1 Q2; March: MCOs receive EPP achievement DY1 Q3; June: MCOs receive EPP achievement DY1 Q4; September: MCOs receive EPP achievement DY2 Q1; December: MCOs receive EPP achievement DY2 Q2; March: MCOs receive EPP achievement DY2 Q3; June: MCOs receive EPP achievement DY2, 3, 4 Q4; September: MCOs receive EPP achievement DY3, 4, 5 Q1; December: MCOs receive EPP achievement DY3, 4, 5 Q2; March: MCOs receive EPP achievement DY3, 4, 5 Q3; June: MCOs receive EPP achievement DY5 Q4
MCOs make EPP payments to PPSs* | [9 empty] | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment
MCO-to-DOH EPP Reports on Payments | October: MCO-to-DOH EPP Report; January: MCO-to-DOH EPP Report; April: MCO-to-DOH EPP Report; July: MCO-to-DOH EPP Report; October: MCO-to-DOH EPP Report; January: MCO-to-DOH EPP Report; April: MCO-to-DOH EPP Report; July: MCO-to-DOH EPP Report; October: MCO-to-DOH EPP Report; January: MCO-to-DOH EPP Report; April: MCO-to-DOH EPP Report; July: MCO-to-DOH EPP Report
* Schedule being provided as an example | bar: October to November

## EIP Timelines
EIP Timelines
| October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
Scenario 1: EIP Annual Reporting; Annual Payment
DSRIP Demonstration Year | October: DSRIP DY1 (2015); April: DSRIP DY2 (2016); April: DSRIP DY3 (2017), DY4 (2018), & DY5 (2019); April: DY6 (2020, Post-DSRIP); April: DY7 (2021, Post-DSRIP)
All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | January: EIP and EPP contracts complete; February: Updates to (EIP) Contracts; February: Updates to (EIP) Contracts (Years 3 & 4 only)
All MCOs submit Equity Program Governance Document to DOH | January: EP Governance Document complete; February: Updates to EP Governance Document; February: Updates to EP Governance Document (Years 3 & 4 only)
DOH begins monthly disbursement of EP payments to MCOs (EIP first payment retroactive to April 2015) | January: Monthly EIP Payments to MCOs begin; April: Monthly EPP Payments to MCOs begin; March: Last Monthly EIP Payment to MCOs; March: Last Monthly EPP Payment to MCOs
DSRIP Quarterly Reporting in MAPP, used for EPP | October: DY1 Q2 QR due; January: DY1 Q3 QR due; April: DY1 Q4 QR due; July: DY2 Q1 QR due; October: DY2 Q2 QR due; January: DY2 Q3 QR due; April: DY2,3,4 Q4 QR due; July: DY3,4,5 Q1 QR due; October: DY3,4,5 Q2 QR due; January: DY3,4,5 Q3 QR due; April: DY5 Q4 QR due
PPSs report on EIP Activities to MCOs* | April: Annual EIP Report; April: Annual EIP Report; April: Annual EIP Report
MCOs make EIP payments to PPSs* | May: Annual EIP Payment; May: Annual EIP Payment; May: Annual EIP Payment
MCO-to-DOH EIP Reports on Payments | June: MCO-to-DOH EIP Report; June: MCO-to-DOH EIP Report; June: MCO-to-DOH EIP Report
* Schedule being provided as an example | bar: October to November
| October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
Scenario 2: EIP Annual Reporting; Semi-Annual Payment
DSRIP Demonstration Year | October: DSRIP DY1 (2015); April: DSRIP DY2 (2016); April: DSRIP DY3 (2017), DY4 (2018), & DY5 (2019); April: DY6 (2020, Post-DSRIP); April: DY7 (2021, Post-DSRIP)
All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | January: EIP and EPP contracts complete; February: Updates to (EIP) Contracts; February: Updates to (EIP) Contracts (Years 3 & 4 only)
All MCOs submit Equity Program Governance Document to DOH | January: EP Governance Document complete; February: Updates to EP Governance Document; February: Updates to EP Governance Document (Years 3 & 4 only)
DOH begins monthly disbursement of EP payments to MCOs (EIP first payment retroactive to April 2015) | January: Monthly EIP Payments to MCOs begin; April: Monthly EPP Payments to MCOs begin; March: Last Monthly EIP Payment to MCOs; March: Last Monthly EPP Payment to MCOs
DSRIP Quarterly Reporting in MAPP, used for EPP | October: DY1 Q2 QR due; January: DY1 Q3 QR due; April: DY1 Q4 QR due; July: DY2 Q1 QR due; October: DY2 Q2 QR due; January: DY2 Q3 QR due; April: DY2,3,4 Q4 QR due; July: DY3,4,5 Q1 QR due; October: DY3,4,5 Q2 QR due; January: DY3,4,5 Q3 QR due; April: DY5 Q4 QR due
PPSs report on EIP Activities to MCOs* | April: Annual EIP Report; April: Annual EIP Report; April: Annual EIP Report
MCOs make EIP payments to PPSs* | May: Semi-Annual EIP Payment; November: Semi-Annual EIP Payment; May: Semi-Annual EIP Payment; November: Semi-Annual EIP Payment; May: Semi-Annual EIP Payment; November: Semi-Annual EIP Payment
MCO-to-DOH EIP Reports on Payments | June: MCO-to-DOH EIP Report; December: MCO-to-DOH EIP Report; June: MCO-to-DOH EIP Report; December: MCO-to-DOH EIP Report; June: MCO-to-DOH EIP Report; December: MCO-to-DOH EIP Report
* Schedule being provided as an example | bar: October to November
| October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
Scenario 3: EIP Annual Reporting; Quarterly Payment
DSRIP Demonstration Year | October: DSRIP DY1 (2015); April: DSRIP DY2 (2016); April: DSRIP DY3 (2017), DY4 (2018), & DY5 (2019); April: DY6 (2020, Post-DSRIP); April: DY7 (2021, Post-DSRIP)
All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | January: EIP and EPP contracts complete; February: Updates to (EIP) Contracts; February: Updates to (EIP) Contracts (Years 3 & 4 only)
All MCOs submit Equity Program Governance Document to DOH | January: EP Governance Document complete; February: Updates to EP Governance Document; February: Updates to EP Governance Document (Years 3 & 4 only)
DOH begins monthly disbursement of EP payments to MCOs (EIP first payment retroactive to April 2015) | January: Monthly EIP Payments to MCOs begin; April: Monthly EPP Payments to MCOs begin; March: Last Monthly EIP Payment to MCOs; March: Last Monthly EPP Payment to MCOs
DSRIP Quarterly Reporting in MAPP, used for EPP | October: DY1 Q2 QR due; January: DY1 Q3 QR due; April: DY1 Q4 QR due; July: DY2 Q1 QR due; October: DY2 Q2 QR due; January: DY2 Q3 QR due; April: DY2,3,4 Q4 QR due; July: DY3,4,5 Q1 QR due; October: DY3,4,5 Q2 QR due; January: DY3,4,5 Q3 QR due; April: DY5 Q4 QR due
PPSs report on EIP Activities to MCOs* | April: Annual EIP Report; April: Annual EIP Report; April: Annual EIP Report
MCOs make EIP payments to PPSs* | May: Quarterly EIP Payment; August: Quarterly EIP Payment; November: Quarterly EIP Payment; February: Quarterly EIP Payment; May: Quarterly EIP Payment; August: Quarterly EIP Payment; November: Quarterly EIP Payment; February: Quarterly EIP Payment; May: Quarterly EIP Payment; August: Quarterly EIP Payment; November: Quarterly EIP Payment; February: Quarterly EIP Payment
MCO-to-DOH EIP Reports on Payments | June: MCO-to-DOH EIP Report; September: MCO-to-DOH EIP Report; December: MCO-to-DOH EIP Report; March: MCO-to-DOH EIP Report; June: MCO-to-DOH EIP Report; September: MCO-to-DOH EIP Report; December: MCO-to-DOH EIP Report; March: MCO-to-DOH EIP Report; June: MCO-to-DOH EIP Report; September: MCO-to-DOH EIP Report; December: MCO-to-DOH EIP Report; March: MCO-to-DOH EIP Report
* Schedule being provided as an example | bar: October to November
| October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
Scenario 4: EIP Annual Reporting, Monthly Payment
DSRIP Demonstration Year | October: DSRIP DY1 (2015); April: DSRIP DY2 (2016); April: DSRIP DY3 (2017), DY4 (2018), & DY5 (2019); April: DY6 (2020, Post-DSRIP); April: DY7 (2021, Post-DSRIP)
All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | January: EIP and EPP contracts complete; February: Updates to (EIP) Contracts; February: Updates to (EIP) Contracts (Years 3 & 4 only)
All MCOs submit Equity Program Governance Document to DOH | January: EP Governance Document complete; February: Updates to EP Governance Document; February: Updates to EP Governance Document (Years 3 & 4 only)
DOH begins monthly disbursement of EP payments to MCOs (EIP first payment retroactive to April 2015) | January: Monthly EIP Payments to MCOs begin; April: Monthly EPP Payments to MCOs begin; March: Last Monthly EIP Payment to MCOs; March: Last Monthly EPP Payment to MCOs
DSRIP Quarterly Reporting in MAPP, used for EPP | October: DY1 Q2 QR due; January: DY1 Q3 QR due; April: DY1 Q4 QR due; July: DY2 Q1 QR due; October: DY2 Q2 QR due; January: DY2 Q3 QR due; April: DY2,3,4 Q4 QR due; July: DY3,4,5 Q1 QR due; October: DY3,4,5 Q2 QR due; January: DY3,4,5 Q3 QR due; April: DY5 Q4 QR due
PPSs report on EIP Activities to MCOs* | April: Annual EIP Report; April: Annual EIP Report; April: Annual EIP Report
MCOs make EIP payments to PPSs* | [7 empty] | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment
MCO-to-DOH EIP Reports on Payments | May: MCO-to-DOH EIP Report; May: MCO-to-DOH EIP Report; May: MCO-to-DOH EIP Report
* Schedule being provided as an example | bar: October to November
| October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
Scenario 5: EIP Semi-Annual Reporting, Quarterly Payment
DSRIP Demonstration Year | October: DSRIP DY1 (2015); April: DSRIP DY2 (2016); April: DSRIP DY3 (2017), DY4 (2018), & DY5 (2019); April: DY6 (2020, Post-DSRIP); April: DY7 (2021, Post-DSRIP)
All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | January: EIP and EPP contracts complete; February: Updates to (EIP) Contracts; February: Updates to (EIP) Contracts (Years 3 & 4 only)
All MCOs submit Equity Program Governance Document to DOH | January: EP Governance Document complete; February: Updates to EP Governance Document; February: Updates to EP Governance Document (Years 3 & 4 only)
DOH begins monthly disbursement of EP payments to MCOs (EIP first payment retroactive to April 2015) | January: Monthly EIP Payments to MCOs begin; April: Monthly EPP Payments to MCOs begin; March: Last Monthly EIP Payment to MCOs; March: Last Monthly EPP Payment to MCOs
DSRIP Quarterly Reporting in MAPP, used for EPP | October: DY1 Q2 QR due; January: DY1 Q3 QR due; April: DY1 Q4 QR due; July: DY2 Q1 QR due; October: DY2 Q2 QR due; January: DY2 Q3 QR due; April: DY2,3,4 Q4 QR due; July: DY3,4,5 Q1 QR due; October: DY3,4,5 Q2 QR due; January: DY3,4,5 Q3 QR due; April: DY5 Q4 QR due
PPSs report on EIP Activities to MCOs* | April: Semi-Annual EIP Report; October: Semi-Annual EIP Report; April: Semi-Annual EIP Report; October: Semi-Annual EIP Report; April: Semi-Annual EIP Report; October: Semi-Annual EIP Report
MCOs make EIP payments to PPSs* | May: Quarterly EIP Payment; August: Quarterly EIP Payment; November: Quarterly EIP Payment; February: Quarterly EIP Payment; May: Quarterly EIP Payment; August: Quarterly EIP Payment; November: Quarterly EIP Payment; February: Quarterly EIP Payment; May: Quarterly EIP Payment; August: Quarterly EIP Payment; November: Quarterly EIP Payment; February: Quarterly EIP Payment
MCO-to-DOH EIP Reports on Payments | June: MCO-to-DOH EIP Report; September: MCO-to-DOH EIP Report; December: MCO-to-DOH EIP Report; March: MCO-to-DOH EIP Report; June: MCO-to-DOH EIP Report; September: MCO-to-DOH EIP Report; December: MCO-to-DOH EIP Report; March: MCO-to-DOH EIP Report; June: MCO-to-DOH EIP Report; September: MCO-to-DOH EIP Report; December: MCO-to-DOH EIP Report; March: MCO-to-DOH EIP Report
* Schedule being provided as an example | bar: October to November

## EP Timelines (hidden)
EP Timelines
| October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
Scenario 1: Quarterly EIP reporting, quarterly EIP payment, annual EPP payment
DSRIP Demonstration Year | October: DSRIP DY1 (2015); April: DSRIP DY2 (2016); April: DSRIP DY3 (2017), DY4 (2018), & DY5 (2019); April: DY6 (2020, Post-DSRIP); April: DY7 (2021, Post-DSRIP)
All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | January: EIP and EPP contracts complete; February: Updates to (EIP) Contracts; February: Updates to (EIP) Contracts (Years 3 & 4 only)
All MCOs submit Equity Program Governance Document to DOH | January: EP Governance Document complete; February: Updates to EP Governance Document; February: Updates to EP Governance Document (Years 3 & 4 only)
DOH begins monthly disbursement of EP payments to MCOs (first payment retroactive to April 2015) | January: Monthly EIP Payments to MCOs begin; April: Monthly EPP Payments to MCOs begin
DSRIP Quarterly Reporting in MAPP, used for EPP | January: DY1 Q3 QR due; April: DY1 Q4 QR due; July: DY2 Q1 QR due; October: DY2 Q2 QR due; January: DY2 Q3 QR due; April: DY2,3,4 Q4 QR due; July: DY3,4,5 Q1 QR due; October: DY3,4,5 Q2 QR due; January: DY3,4,5 Q3 QR due; April: DY5 Q4 QR due
PPSs report on EIP Activities to MCOs* | February: Quarterly EIP Report; May: Quarterly EIP Report; August: Quarterly EIP Report; November: Quarterly EIP Report; February: Quarterly EIP Report; May: Quarterly EIP Report; August: Quarterly EIP Report; November: Quarterly EIP Report; February: Quarterly EIP Report; May: Quarterly EIP Report
MCOs make EIP payments to PPSs* | March: Quarterly EIP Payment; June: Quarterly EIP Payment; September: Quarterly EIP Payment; December: Quarterly EIP Payment; March: Quarterly EIP Payment; June: Quarterly EIP Payment; September: Quarterly EIP Payment; December: Quarterly EIP Payment; March: Quarterly EIP Payment; June: Quarterly EIP Payment
MCO-to-DOH EIP Reports on Payments | April: MCO-to-DOH EIP Report; July: MCO-to-DOH EIP Report; October: MCO-to-DOH EIP Report; January: MCO-to-DOH EIP Report; April: MCO-to-DOH EIP Report; July: MCO-to-DOH EIP Report; October: MCO-to-DOH EIP Report; January: MCO-to-DOH EIP Report; April: MCO-to-DOH EIP Report; July: MCO-to-DOH EIP Report
DOH sends Performance Achievement information to MCOs for EPP | June: MCOs review EPP measures; September: MCOs review EPP measures; December: MCOs review EPP measures; March: MCOs review EPP measures; June: MCOs review EPP measures; September: MCOs review EPP measures; December: MCOs review EPP measures; March: MCOs review EPP measures; June: MCOs review EPP measures
MCOs make EPP payments to PPSs* | March: Annual EPP Payment; March: Annual EPP Payment; March: Annual EPP Payment
MCO-to-DOH EPP Reports on Payments | April: MCO-to-DOH EPP Report; April: MCO-to-DOH EPP Report; April: MCO-to-DOH EPP Report
* Schedule being provided as an example | bar: October to November
| October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
Scenario 2: Annual EIP reporting, annual EIP payment, quarterly EPP payment
DSRIP Demonstration Year | October: DSRIP DY1 (as of April 2015); April: DSRIP DY2; April: DSRIP DY3 (2017), DY4 (2018), & DY5 (2019); April: DY6 (2020, Post-DSRIP); April: DY7 (2021, Post-DSRIP)
All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | January: EIP and EPP contracts complete; February: Updates to (EIP) Contracts; February: Updates to (EIP) Contracts (Years 3 & 4 only)
All MCOs submit Equity Program Governance Document to DOH | January: EP Governance Document complete; February: Updates to EP Governance Document; February: Updates to EP Governance Document (Years 3 & 4 only)
DOH begins monthly disbursement of EP payments to MCOs (first payment retroactive to April 2015) | January: Monthly EIP Payments to MCOs begin; April: Monthly EPP Payments to MCOs begin
DSRIP Quarterly Reporting in MAPP, used for EPP | January: DY1 Q3 QR due; April: DY1 Q4 QR due; July: DY2 Q1 QR due; October: DY2 Q2 QR due; January: DY2 Q3 QR due; April: DY2,3,4 Q4 QR due; July: DY3,4,5 Q1 QR due; October: DY3,4,5 Q2 QR due; January: DY3,4,5 Q3 QR due; April: DY5 Q4 QR due
PPSs report on EIP Activities to MCOs* | April: Annual EIP Report; April: Annual EIP Report; April: Annual EIP Report
MCOs make EIP payments to PPSs* | May: Annual EIP Payment; May: Annual EIP Payment; May: Annual EIP Payment
MCO-to-DOH EIP Reports on Payments | June: MCO-to-DOH EIP Report; June: MCO-to-DOH EIP Report; June: MCO-to-DOH EIP Report
DOH sends Performance Achievement information to MCOs for EPP | June: MCOs review EPP measures; September: MCOs review EPP measures; December: MCOs review EPP measures; March: MCOs review EPP measures; June: MCOs review EPP measures; September: MCOs review EPP measures; December: MCOs review EPP measures; March: MCOs review EPP measures; June: MCOs review EPP measures
MCOs make EPP payments to PPSs* | July: Quarterly EPP Payment; October: Quarterly EPP Payment; January: Quarterly EPP Payment; April: Quarterly EPP Payment; July: Quarterly EPP Payment; October: Quarterly EPP Payment; January: Quarterly EPP Payment; April: Quarterly EPP Payment; July: Quarterly EPP Payment
MCO-to-DOH EPP Reports on Payments | August: MCO-to-DOH EPP Report; November: MCO-to-DOH EPP Report; February: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report; August: MCO-to-DOH EPP Report; November: MCO-to-DOH EPP Report; February: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report; August: MCO-to-DOH EPP Report
* Schedule being provided as an example | bar: October to November
| October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
Scenario 3: Annual EIP reporting, quarterly EIP payment, monthly EPP payment
DSRIP Demonstration Year | October: DSRIP DY1 (as of April 2015); April: DSRIP DY2; April: DSRIP DY3 (2017), DY4 (2018), & DY5 (2019); April: DY6 (2020, Post-DSRIP); April: DY7 (2021, Post-DSRIP)
All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | January: EIP and EPP contracts complete; February: Updates to (EIP) Contracts; February: Updates to (EIP) Contracts (Years 3 & 4 only)
All MCOs submit Equity Program Governance Document to DOH | January: EP Governance Document complete; February: Updates to EP Governance Document; February: Updates to EP Governance Document (Years 3 & 4 only)
DOH begins monthly disbursement of EP payments to MCOs (first payment retroactive to April 2015) | January: Monthly EIP Payments to MCOs begin; April: Monthly EPP Payments to MCOs begin
DSRIP Quarterly Reporting in MAPP, used for EPP | January: DY1 Q3 QR due; April: DY1 Q4 QR due; July: DY2 Q1 QR due; October: DY2 Q2 QR due; January: DY2 Q3 QR due; April: DY2,3,4 Q4 QR due; July: DY3,4,5 Q1 QR due; October: DY3,4,5 Q2 QR due; January: DY3,4,5 Q3 QR due; April: DY5 Q4 QR due
PPSs report on EIP Activities to MCOs* | April: Annual EIP Report; April: Annual EIP Report; April: Annual EIP Report
MCOs make EIP payments to PPSs* | May: Quarterly EIP Payment; August: Quarterly EIP Payment; November: Quarterly EIP Payment; February: Quarterly EIP Payment; May: Quarterly EIP Payment; August: Quarterly EIP Payment; November: Quarterly EIP Payment; February: Quarterly EIP Payment; May: Quarterly EIP Payment; August: Quarterly EIP Payment; November: Quarterly EIP Payment; February: Quarterly EIP Payment
MCO-to-DOH EIP Reports on Payments | June: MCO-to-DOH EIP Report; September: MCO-to-DOH EIP Report; December: MCO-to-DOH EIP Report; March: MCO-to-DOH EIP Report; June: MCO-to-DOH EIP Report; September: MCO-to-DOH EIP Report; December: MCO-to-DOH EIP Report; March: MCO-to-DOH EIP Report; June: MCO-to-DOH EIP Report; September: MCO-to-DOH EIP Report; December: MCO-to-DOH EIP Report; March: MCO-to-DOH EIP Report
DOH sends Performance Achievement information to MCOs for EPP | June: MCOs review EPP measures; September: MCOs review EPP measures; December: MCOs review EPP measures; March: MCOs review EPP measures; June: MCOs review EPP measures; September: MCOs review EPP measures; December: MCOs review EPP measures; March: MCOs review EPP measures; June: MCOs review EPP measures
MCOs make EPP payments to PPSs* | [9 empty] | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment
MCO-to-DOH EPP Reports on Payments | October: MCO-to-DOH EPP Report; January: MCO-to-DOH EPP Report; April: MCO-to-DOH EPP Report; July: MCO-to-DOH EPP Report; October: MCO-to-DOH EPP Report; January: MCO-to-DOH EPP Report; April: MCO-to-DOH EPP Report; July: MCO-to-DOH EPP Report; October: MCO-to-DOH EPP Report; January: MCO-to-DOH EPP Report; April: MCO-to-DOH EPP Report; July: MCO-to-DOH EPP Report
* Schedule being provided as an example | bar: October to November
| October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
Scenario 4: Quarterly EIP reporting, monthly EIP payment, quarterly EPP payment
DSRIP Demonstration Year | October: DSRIP DY1 (as of April 2015); April: DSRIP DY2; April: DSRIP DY3 (2017), DY4 (2018), & DY5 (2019); April: DY6 (2020, Post-DSRIP); April: DY7 (2021, Post-DSRIP)
All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | January: EIP and EPP contracts complete; February: Updates to (EIP) Contracts; February: Updates to (EIP) Contracts (Years 3 & 4 only)
All MCOs submit Equity Program Governance Document to DOH | January: EP Governance Document complete; February: Updates to EP Governance Document; February: Updates to EP Governance Document (Years 3 & 4 only)
DOH begins monthly disbursement of EP payments to MCOs (first payment retroactive to April 2015) | January: Monthly EIP Payments to MCOs begin; April: Monthly EPP Payments to MCOs begin
DSRIP Quarterly Reporting in MAPP, used for EPP | January: DY1 Q3 QR due; April: DY1 Q4 QR due; July: DY2 Q1 QR due; October: DY2 Q2 QR due; January: DY2 Q3 QR due; April: DY2,3,4 Q4 QR due; July: DY3,4,5 Q1 QR due; October: DY3,4,5 Q2 QR due; January: DY3,4,5 Q3 QR due; April: DY5 Q4 QR due
PPSs report on EIP Activities to MCOs* | February: Quarterly EIP Report; May: Quarterly EIP Report; August: Quarterly EIP Report; November: Quarterly EIP Report; February: Quarterly EIP Report; May: Quarterly EIP Report; August: Quarterly EIP Report; November: Quarterly EIP Report; February: Quarterly EIP Report; May: Quarterly EIP Report
MCOs make EIP payments to PPSs* | [5 empty] | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment
MCO-to-DOH EIP Reports on Payments | June: MCO-to-DOH EIP Report; September: MCO-to-DOH EIP Report; December: MCO-to-DOH EIP Report; March: MCO-to-DOH EIP Report; June: MCO-to-DOH EIP Report; September: MCO-to-DOH EIP Report; December: MCO-to-DOH EIP Report; March: MCO-to-DOH EIP Report; June: MCO-to-DOH EIP Report; September: MCO-to-DOH EIP Report
DOH sends Performance Achievement information to MCOs for EPP | June: MCOs review EPP measures; September: MCOs review EPP measures; December: MCOs review EPP measures; March: MCOs review EPP measures; June: MCOs review EPP measures; September: MCOs review EPP measures; December: MCOs review EPP measures; March: MCOs review EPP measures; June: MCOs review EPP measures
MCOs make EPP payments to PPSs* | July: Quarterly EPP Payment; October: Quarterly EPP Payment; January: Quarterly EPP Payment; April: Quarterly EPP Payment; July: Quarterly EPP Payment; October: Quarterly EPP Payment; January: Quarterly EPP Payment; April: Quarterly EPP Payment; July: Quarterly EPP Payment
MCO-to-DOH EPP Reports on Payments | August: MCO-to-DOH EPP Report; November: MCO-to-DOH EPP Report; February: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report; August: MCO-to-DOH EPP Report; November: MCO-to-DOH EPP Report; February: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report; August: MCO-to-DOH EPP Report
* Schedule being provided as an example | bar: October to November
| October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
Scenario 5: Annual EIP reporting, annual EIP payment, annual EPP payment
DSRIP Demonstration Year | October: DSRIP DY1 (as of April 2015); April: DSRIP DY2; April: DSRIP DY3 (2017), DY4 (2018), & DY5 (2019); April: DY6 (2020, Post-DSRIP); April: DY7 (2021, Post-DSRIP)
All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | January: EIP and EPP contracts complete; February: Updates to (EIP) Contracts; February: Updates to (EIP) Contracts (Years 3 & 4 only)
All MCOs submit Equity Program Governance Document to DOH | January: EP Governance Document complete; February: Updates to EP Governance Document; February: Updates to EP Governance Document (Years 3 & 4 only)
DOH begins monthly disbursement of EP payments to MCOs (first payment retroactive to April 2015) | January: Monthly EIP Payments to MCOs begin; April: Monthly EPP Payments to MCOs begin
DSRIP Quarterly Reporting in MAPP, used for EPP | January: DY1 Q3 QR due; April: DY1 Q4 QR due; July: DY2 Q1 QR due; October: DY2 Q2 QR due; January: DY2 Q3 QR due; April: DY2,3,4 Q4 QR due; July: DY3,4,5 Q1 QR due; October: DY3,4,5 Q2 QR due; January: DY3,4,5 Q3 QR due; April: DY5 Q4 QR due
PPSs report on EIP Activities to MCOs* | April: Annual EIP Report; April: Annual EIP Report; April: Annual EIP Report
MCOs make EIP payments to PPSs* | May: Annual EIP Payment; May: Annual EIP Payment; May: Annual EIP Payment
MCO-to-DOH EIP Reports on Payments | June: MCO-to-DOH EIP Report; June: MCO-to-DOH EIP Report; June: MCO-to-DOH EIP Report
DOH sends Performance Achievement information to MCOs for EPP | June: MCOs review EPP measures; September: MCOs review EPP measures; December: MCOs review EPP measures; March: MCOs review EPP measures; June: MCOs review EPP measures; September: MCOs review EPP measures; December: MCOs review EPP measures; March: MCOs review EPP measures; June: MCOs review EPP measures
MCOs make EPP payments to PPSs* | March: Annual EPP Payment; March: Annual EPP Payment; March: Annual EPP Payment
MCO-to-DOH EPP Reports on Payments | April: MCO-to-DOH EPP Report; April: MCO-to-DOH EPP Report; April: MCO-to-DOH EPP Report
* Schedule being provided as an example | bar: October to November

## EP Timelines (unique names) (hidden)
EP Timelines
| 2015-10-01 | 2015-11-01 | 2015-12-01 | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | Apr-17-18-19 | May-17-18-19 | Jun-17-18-19 | Jul-17-18-19 | Aug-17-18-19 | Sep-17-18-18 | Oct-17-18-19 | Nov-17-18-19 | Dec-17-18-19 | Jan-18-19-20 | Feb-18-19-20 | Mar-18-19-20 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01
Scenario 1: Quarterly EIP reporting, quarterly EIP payment, annual EPP payment
DSRIP Demonstration Year | 2015-10-01: DSRIP DY1 (as of April 2015); 2016-04-01: DSRIP DY2 | DSRIP DY3, DY4, & DY5 | [11 empty] | DY6 (Post-DSRIP)
All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | 2016-01-01: EIP and EPP contracts complete; 2017-02-01: Updates to EIP Contracts | [10 empty] | Updates to EIP Contracts
All MCOs submit Equity Program Governance Document to DOH | 2016-01-01: EP Governance Document complete; 2017-02-01: Updates to EP Governance Document Complete | [10 empty] | Updates to EP Governance Document Complete
DOH begins monthly disbursement of EP payments to MCOs (first payment retroactive to April 2015) | 2016-01-01: Monthly EIP Payments to MCOs begin; 2016-04-01: Monthly EPP Payments to MCOs begin
DSRIP Quarterly Reporting in MAPP, used for EPP | 2016-01-01: DY1 Q3 QR due; 2016-04-01: DY1 Q4 QR due; 2016-07-01: DY2 Q1 QR due; 2016-10-01: DY2 Q2 QR due; 2017-01-01: DY2 Q3 QR due | DY4 Q4 QR due |  |  | DY5 Q1 QR due |  |  | DY5 Q2 QR due |  |  | DY5 Q3 QR due |  |  | DY5 Q4 QR due
PPSs report on EIP Activities to MCOs* | 2016-02-01: DY1 Q1,2,3 EIP Report; 2016-05-01: DY1 Q4 EIP Report; 2016-08-01: DY2 Q1 EIP Report; 2016-11-01: DY2 Q2 EIP Report; 2017-02-01: DY2 Q3 EIP Report |  | DY4 Q4 EIP Report |  |  | DY5 Q1 EIP Report |  |  | DY5 Q2 EIP Report |  |  | DY5 Q3 EIP Report |  |  | DY5 Q4 EIP Report
MCOs make EIP payments to PPSs* | 2016-03-01: DY1 Q1, Q2, & Q3 EIP payments; 2016-06-01: DY1 Q4 EIP payment made to PPSs; 2016-09-01: DY2 Q1 EIP payment made to PPSs; 2016-12-01: DY2 Q2 EIP payment made to PPSs; 2017-03-01: DY2 Q3 EIP payment made to PPSs |  |  | DY4 Q4 EIP payment made to PPSs |  |  | DY5 Q1 EIP payment made to PPSs |  |  | DY5 Q2 EIP payment made to PPSs |  |  | DY5 Q3 EIP payment made to PPSs |  |  | DY5 Q4 EIP payment made to PPSs
MCO-to-DOH EIP Reports on Payments | 2016-04-01: DY1 Q3 EIP QR due; 2016-07-01: DY1 Q4 EIP QR due; 2016-10-01: DY2 Q1 EIP QR due; 2017-01-01: DY2 Q2 EIP QR due | DY4 Q3 EIP QR due |  |  | DY4 Q4 EIP QR due |  |  | DY5 Q1 EIP QR due |  |  | DY5 Q2 EIP QR due |  |  | DY5 Q3 EIP QR due |  |  | DY5 Q4 EIP QR due
DOH sends Performance Achievement information to MCOs for EPP | 2016-06-01: MCOs review EPP measures; 2016-09-01: MCOs review EPP measures; 2016-12-01: MCOs review EPP measures; 2017-03-01: MCOs review EPP measures |  |  | MCOs review EPP measures |  |  | MCOs review EPP measures |  |  | MCOs review EPP measures |  |  | MCOs review EPP measures |  |  | MCOs review EPP measures
MCOs make EPP payments to PPSs* | 2016-07-01: DY1 EPP payment made to PPSs |  |  |  | DY4 EPP payment made to PPSs | [11 empty] | DY5 EPP payment made to PPSs
MCO-to-DOH EPP Reports on Payments | 2016-08-01: DY1 EPP Annual report due |  |  |  |  | DY4 EPP Annual Report due | [11 empty] | DY5 EPP Annual Report due
* Schedule being provided as an example | bar: 2015-10-01 to 2015-11-01
| 2015-10-01 | 2015-11-01 | 2015-12-01 | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | Apr-17-18-19 | May-17-18-19 | Jun-17-18-19 | Jul-17-18-19 | Aug-17-18-19 | Sep-17-18-18 | Oct-17-18-19 | Nov-17-18-19 | Dec-17-18-19 | Jan-18-19-20 | Feb-18-19-20 | Mar-18-19-20 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01
Scenario 2: Annual EIP reporting, annual EIP payment, quarterly EPP payment
DSRIP Demonstration Year | 2015-10-01: DSRIP DY1 (as of April 2015); 2016-04-01: DSRIP DY2 | DSRIP DY3, DY4, & DY5 | [11 empty] | DY6 (Post-DSRIP)
All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | 2016-01-01: EIP and EPP contracts complete; 2017-02-01: Updates to EIP Contracts | [10 empty] | Updates to EIP Contracts
All MCOs submit Equity Program Governance Document to DOH | 2016-01-01: EP Governance Document complete; 2017-02-01: Updates to EP Governance Document Complete | [10 empty] | Updates to EP Governance Document Complete
DOH begins monthly disbursement of EP payments to MCOs (first payment retroactive to April 2015) | 2016-01-01: Monthly EIP Payments to MCOs begin; 2016-04-01: Monthly EPP Payments to MCOs begin
DSRIP Quarterly Reporting in MAPP, used for EPP | 2016-01-01: DY1 Q3 QR due; 2016-04-01: DY1 Q4 QR due; 2016-07-01: DY2 Q1 QR due; 2016-10-01: DY2 Q2 QR due; 2017-01-01: DY2 Q3 QR due | DY4 Q4 QR due |  |  | DY5 Q1 QR due |  |  | DY5 Q2 QR due |  |  | DY5 Q3 QR due |  |  | DY5 Q4 QR due
PPSs report on EIP Activities to MCOs* | 2016-04-01: DY1 EIP Report | DY4 EIP Report | [11 empty] | DY5 EIP Report
MCOs make EIP payments to PPSs* | 2016-05-01: DY1 EIP payment made to PPSs |  | DY4 EIP payment made to PPSs | [11 empty] | DY5 EIP payment made to PPSs
MCO-to-DOH EIP Reports on Payments | 2016-06-01: DY1 Q3 EIP QR due |  |  | DY4 Q3 EIP QR due | [11 empty] | DY5 Q3 EIP QR due
DOH sends Performance Achievement information to MCOs for EPP | 2016-06-01: MCOs review EPP measures; 2016-09-01: MCOs review EPP measures; 2016-12-01: MCOs review EPP measures; 2017-03-01: MCOs review EPP measures |  |  | MCOs review EPP measures |  |  | MCOs review EPP measures |  |  | MCOs review EPP measures |  |  | MCOs review EPP measures |  |  | MCOs review EPP measures
MCOs make EPP payments to PPSs* | 2016-07-01: DY1 Q1, Q2, Q3, Q4 EPP payment made to PPSs; 2016-10-01: DY2 Q1 EPP payment made to PPSs; 2017-01-01: DY2 Q2 EPP payment made to PPSs | DY2 Q3 EPP payment made to PPSs |  |  | DY4 Q4 EPP payment made to PPSs |  |  | DY5 Q1 EPP payment made to PPSs |  |  | DY5 Q2 EPP payment made to PPSs |  |  | DY5 Q3 EPP payment made to PPSs |  |  | DY5 Q4 EPP payment made to PPSs
MCO-to-DOH EPP Reports on Payments | 2016-08-01: DY1 EPP Annual report due |  |  |  |  | DY4 EPP Annual Report due | [11 empty] | DY5 EPP Annual Report due
* Schedule being provided as an example | bar: 2015-10-01 to 2015-11-01
| 2015-10-01 | 2015-11-01 | 2015-12-01 | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | Apr-17-18-19 | May-17-18-19 | Jun-17-18-19 | Jul-17-18-19 | Aug-17-18-19 | Sep-17-18-18 | Oct-17-18-19 | Nov-17-18-19 | Dec-17-18-19 | Jan-18-19-20 | Feb-18-19-20 | Mar-18-19-20 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01
Scenario 3: Annual EIP reporting, quarterly EIP payment, monthly EPP payment
DSRIP Demonstration Year | 2015-10-01: DSRIP DY1 (as of April 2015); 2016-04-01: DSRIP DY2 | DSRIP DY3, DY4, & DY5 | [11 empty] | DY6 (Post-DSRIP)
All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | 2016-01-01: EIP and EPP contracts complete; 2017-02-01: Updates to EIP Contracts | [10 empty] | Updates to EIP Contracts
All MCOs submit Equity Program Governance Document to DOH | 2016-01-01: EP Governance Document complete; 2017-02-01: Updates to EP Governance Document Complete | [10 empty] | Updates to EP Governance Document Complete
DOH begins monthly disbursement of EP payments to MCOs (first payment retroactive to April 2015) | 2016-01-01: Monthly EIP Payments to MCOs begin; 2016-04-01: Monthly EPP Payments to MCOs begin
DSRIP Quarterly Reporting in MAPP, used for EPP | 2016-01-01: DY1 Q3 QR due; 2016-04-01: DY1 Q4 QR due; 2016-07-01: DY2 Q1 QR due; 2016-10-01: DY2 Q2 QR due; 2017-01-01: DY2 Q3 QR due | DY4 Q4 QR due |  |  | DY5 Q1 QR due |  |  | DY5 Q2 QR due |  |  | DY5 Q3 QR due |  |  | DY5 Q4 QR due
PPSs report on EIP Activities to MCOs* | 2016-04-01: DY1 EIP Report | DY4 EIP Report | [11 empty] | DY5 EIP Report
MCOs make EIP payments to PPSs* | 2016-05-01: DY1 Q1 EIP payment made to PPSs; 2016-08-01: DY1 Q2 EIP payment made to PPSs; 2016-11-01: DY1 Q3 EIP payment made to PPSs; 2017-02-01: DY1 Q4 EIP payment made to PPSs |  | DY4 Q1 EIP payment made to PPSs |  |  | DY4 Q2 EIP payment made to PPSs |  |  | DY4 Q3 EIP payment made to PPSs |  |  | DY4 Q4 EIP payment made to PPSs |  |  | DY5 Q1 EIP payment made to PPSs |  |  | DY5 Q2 EIP payment made to PPSs |  |  | DY5 Q3 EIP payment made to PPSs |  |  | DY5 Q4 EIP payment made to PPSs
MCO-to-DOH EIP Reports on Payments | 2016-06-01: DY1 Q1 EIP QR due; 2016-09-01: DY1 Q2 EIP QR due; 2016-12-01: DY1 Q3 EIP QR due; 2017-03-01: DY3 Q4 EIP QR due |  |  | DY4 Q1 EIP QR due |  |  | DY4 Q2 EIP QR due |  |  | DY4 Q3 EIP QR due |  |  | DY4 Q4 EIP QR due |  |  | DY5 Q1 EIP QR due |  |  | DY5 Q2 EIP QR due |  |  | DY5 Q3 EIP QR due |  |  | DY5 Q4 EIP QR due
DOH sends Performance Achievement information to MCOs for EPP | 2016-06-01: MCOs review EPP measures; 2016-09-01: MCOs review EPP measures; 2016-12-01: MCOs review EPP measures; 2017-03-01: MCOs review EPP measures |  |  | MCOs review EPP measures |  |  | MCOs review EPP measures |  |  | MCOs review EPP measures |  |  | MCOs review EPP measures |  |  | MCOs review EPP measures
MCOs make EPP payments to PPSs* | 2016-07-01: Monthly EPP Payment (retroactive); 2016-08-01: Monthly EPP Payment; 2016-09-01: Monthly EPP Payment; 2016-10-01: Monthly EPP Payment; 2016-11-01: Monthly EPP Payment; 2016-12-01: Monthly EPP Payment; 2017-01-01: Monthly EPP Payment; 2017-02-01: Monthly EPP Payment; 2017-03-01: Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment | Monthly EPP Payment
MCO-to-DOH EPP Reports on Payments | 2016-10-01: DY1 EPP Annual report due | [6 empty] | DY1 EPP Annual report due | [11 empty] | DY1 EPP Annual report due
* Schedule being provided as an example | bar: 2015-10-01 to 2015-11-01
| 2015-10-01 | 2015-11-01 | 2015-12-01 | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | Apr-17-18-19 | May-17-18-19 | Jun-17-18-19 | Jul-17-18-19 | Aug-17-18-19 | Sep-17-18-18 | Oct-17-18-19 | Nov-17-18-19 | Dec-17-18-19 | Jan-18-19-20 | Feb-18-19-20 | Mar-18-19-20 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01
Scenario 4: Quarterly EIP reporting, monthly EIP payment, quarterly EPP payment
DSRIP Demonstration Year | 2015-10-01: DSRIP DY1 (as of April 2015); 2016-04-01: DSRIP DY2 | DSRIP DY3, DY4, & DY5 | [11 empty] | DY6 (Post-DSRIP)
All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | 2016-01-01: EIP and EPP contracts complete; 2017-02-01: Updates to EIP Contracts | [10 empty] | Updates to EIP Contracts
All MCOs submit Equity Program Governance Document to DOH | 2016-01-01: EP Governance Document complete; 2017-02-01: Updates to EP Governance Document Complete | [10 empty] | Updates to EP Governance Document Complete
DOH begins monthly disbursement of EP payments to MCOs (first payment retroactive to April 2015) | 2016-01-01: Monthly EIP Payments to MCOs begin; 2016-04-01: Monthly EPP Payments to MCOs begin
DSRIP Quarterly Reporting in MAPP, used for EPP | 2016-01-01: DY1 Q3 QR due; 2016-04-01: DY1 Q4 QR due; 2016-07-01: DY2 Q1 QR due; 2016-10-01: DY2 Q2 QR due; 2017-01-01: DY2 Q3 QR due | DY4 Q4 QR due |  |  | DY5 Q1 QR due |  |  | DY5 Q2 QR due |  |  | DY5 Q3 QR due |  |  | DY5 Q4 QR due
PPSs report on EIP Activities to MCOs* | 2016-02-01: DY1 Q1,2,3 EIP Report; 2016-05-01: DY1 Q4 EIP Report; 2016-08-01: DY2 Q1 EIP Report; 2016-11-01: DY2 Q2 EIP Report; 2017-02-01: DY2 Q3 EIP Report |  | DY4 Q4 EIP Report |  |  | DY5 Q1 EIP Report |  |  | DY5 Q2 EIP Report |  |  | DY5 Q3 EIP Report |  |  | DY5 Q4 EIP Report
MCOs make EIP payments to PPSs* | [5 empty] | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment | Monthly EIP Payment
MCO-to-DOH EIP Reports on Payments | 2016-06-01: DY1 Q3 EIP QR due; 2016-09-01: DY1 Q4 EIP QR due; 2016-12-01: DY2 Q1 EIP QR due; 2017-03-01: DY2 Q2 EIP QR due |  |  | DY4 Q3 EIP QR due |  |  | DY4 Q4 EIP QR due |  |  | DY5 Q1 EIP QR due |  |  | DY5 Q2 EIP QR due |  |  | DY5 Q3 EIP QR due |  |  | DY5 Q4 EIP QR due
DOH sends Performance Achievement information to MCOs for EPP | 2016-06-01: MCOs review EPP measures; 2016-09-01: MCOs review EPP measures; 2016-12-01: MCOs review EPP measures; 2017-03-01: MCOs review EPP measures |  |  | MCOs review EPP measures |  |  | MCOs review EPP measures |  |  | MCOs review EPP measures |  |  | MCOs review EPP measures |  |  | MCOs review EPP measures
MCOs make EPP payments to PPSs* | 2016-07-01: DY1 Q1, Q2, Q3, Q4 EPP payment made to PPSs; 2016-10-01: DY2 Q1 EPP payment made to PPSs; 2017-01-01: DY2 Q2 EPP payment made to PPSs | DY2 Q3 EPP payment made to PPSs |  |  | DY4 Q4 EPP payment made to PPSs |  |  | DY5 Q1 EPP payment made to PPSs |  |  | DY5 Q2 EPP payment made to PPSs |  |  | DY5 Q3 EPP payment made to PPSs |  |  | DY5 Q4 EPP payment made to PPSs
MCO-to-DOH EPP Reports on Payments | 2016-08-01: DY1 EPP Annual report due |  |  |  |  | DY4 EPP Annual Report due | [11 empty] | DY5 EPP Annual Report due
* Schedule being provided as an example | bar: 2015-10-01 to 2015-11-01

## EP Timeline (old) (hidden)
EP Timeline
 | time axis 2015-10-01 to 2020-08-01
| DSRIP Demonstration Year | 2015-10-01: DSRIP DY1 (as of April 2015); 2016-04-01: DSRIP DY2; 2017-04-01: DSRIP DY3; 2018-04-01: DSRIP DY4; 2019-04-01: DSRIP DY5
| All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | 2016-01-01: EIP and EPP contracts complete; 2017-02-01: Updates to EIP Contracts; 2018-02-01: Updates to EIP Contracts; 2019-02-01: Updates to EIP Contracts; 2020-02-01: Updates to EIP Contracts
| All MCOs submit Equity Program Governance Document to DOH | 2016-01-01: EP Governance Document complete; 2017-02-01: Updates to EP Governance Document Complete; 2018-02-01: Updates to EP Governance Document Complete; 2019-02-01: Updates to EP Governance Document Complete; 2020-02-01: Updates to EP Governance Document Complete
| DOH begins monthly disbursement of EP payments to MCOs (first payment retroactive to April 2015) | 2016-01-01: Monthly EIP Payments to MCOs begin; 2016-04-01: Monthly EPP Payments to MCOs begin
| DSRIP Quarterly Reports | 2016-01-01: DY1 Q3 QR due; 2016-04-01: DY1 Q4 QR due; 2016-07-01: DY2 Q1 QR due; 2016-10-01: DY2 Q2 QR due; 2017-01-01: DY2 Q3 QR due; 2017-04-01: DY2 Q4 QR due; 2017-07-01: DY3 Q1 QR due; 2017-10-01: DY3 Q2 QR due; 2018-01-01: DY3 Q3 QR due; 2018-04-01: DY3 Q4 QR due; 2018-07-01: DY4 Q1 QR due; 2018-10-01: DY4 Q2 QR due; 2019-01-01: DY4 Q3 QR due; 2019-04-01: DY4 Q4 QR due; 2019-07-01: DY5 Q1 QR due; 2019-10-01: DY5 Q2 QR due; 2020-01-01: DY5 Q3 QR due; 2020-04-01: DY5 Q4 QR due
| MCOs make quarterly EIP payments to PPSs* | 2016-02-01: DY1 Q1, Q2, & Q3 EIP payments made to PPSs; 2016-05-01: DY1 Q4 EIP payment made to PPSs; 2016-08-01: DY2 Q1 EIP payment made to PPSs; 2016-11-01: DY2 Q2 EIP payment made to PPSs; 2017-02-01: DY2 Q3 EIP payment made to PPSs; 2017-05-01: DY2 Q4 EIP payment made to PPSs; 2017-08-01: DY3 Q1 EIP payment made to PPSs; 2017-11-01: DY3 Q2 EIP payment made to PPSs; 2018-02-01: DY3 Q3 EIP payment made to PPSs; 2018-05-01: DY3 Q4 EIP payment made to PPSs; 2018-08-01: DY4 Q1 EIP payment made to PPSs; 2018-11-01: DY4 Q2 EIP payment made to PPSs; 2019-02-01: DY4 Q3 EIP payment made to PPSs; 2019-05-01: DY4 Q4 EIP payment made to PPSs; 2019-08-01: DY5 Q1 EIP payment made to PPSs; 2019-11-01: DY5 Q2 EIP payment made to PPSs; 2020-02-01: DY5 Q3 EIP payment made to PPSs; 2020-05-01: DY5 Q4 EIP payment made to PPSs
| MCO-to-DOH EIP Quarterly Reports | 2016-05-01: DY1 Q3 EIP QR due; 2016-08-01: DY1 Q4 EIP QR due; 2016-11-01: DY2 Q1 EIP QR due; 2017-02-01: DY2 Q2 EIP QR due; 2017-05-01: DY2 Q3 EIP QR due; 2017-08-01: DY2 Q4 EIP QR due; 2017-11-01: DY3 Q1 EIP QR due; 2018-02-01: DY3 Q2 EIP QR due; 2018-05-01: DY3 Q3 EIP QR due; 2018-08-01: DY3 Q4 EIP QR due; 2018-11-01: DY4 Q1 EIP QR due; 2019-02-01: DY4 Q2 EIP QR due; 2019-05-01: DY4 Q3 EIP QR due; 2019-08-01: DY4 Q4 EIP QR due; 2019-11-01: DY5 Q1 EIP QR due; 2020-02-01: DY5 Q2 EIP QR due; 2020-05-01: DY5 Q3 EIP QR due; 2020-08-01: DY5 Q3 EIP QR due
* | MCOs make annual EPP payments to PPSs* | 2016-04-01: DY1 EPP payment made to PPSs; 2017-04-01: DY2 EPP payment made to PPSs; 2018-04-01: DY3 EPP payment made to PPSs; 2019-04-01: DY4 EPP payment made to PPSs; 2020-04-01: DY5 EPP payment made to PPSs
| MCO-to-DOH Annual EPP Reports | 2016-06-01: DY1 EPP Annual report due; 2017-06-01: DY2 EPP Annual Report due; 2018-06-01: DY3 EPP Annual Report due; 2019-06-01: DY4 EPP Annual Report due; 2020-06-01: DY5 EPP Annual Report due
| DOH sends EPP measures from Quarterly Measurement Reports to MCOs | 2016-04-01: MCO EPP measures review; 2016-07-01: MCO EPP measures review; 2016-10-01: MCO EPP measures review; 2017-01-01: MCO EPP measures review; 2017-04-01: MCO EPP measures review; 2017-07-01: MCO EPP measures review; 2017-10-01: MCO EPP measures review; 2018-01-01: MCO EPP measures review; 2018-04-01: MCO EPP measures review; 2018-07-01: MCO EPP measures review; 2018-10-01: MCO EPP measures review; 2019-01-01: MCO EPP measures review; 2019-04-01: MCO EPP measures review; 2019-07-01: MCO EPP measures review; 2019-10-01: MCO EPP measures review; 2020-01-01: MCO EPP measures review; 2020-04-01: MCO EPP measures review
* Schedule being provided as an example | bar: 2015-10-01 to 2015-11-01
EP Timeline (Reflective of Annual EIP Reporting and Payments)
 | time axis 2015-10-01 to 2020-08-01
| DSRIP Demonstration Year | 2015-10-01: DSRIP DY1 (as of April 2015); 2016-04-01: DSRIP DY2; 2017-04-01: DSRIP DY3; 2018-04-01: DSRIP DY4; 2019-04-01: DSRIP DY5
| All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | 2016-01-01: EIP and EPP contracts complete; 2017-02-01: Updates to EIP Contracts; 2018-02-01: Updates to EIP Contracts; 2019-02-01: Updates to EIP Contracts; 2020-02-01: Updates to EIP Contracts
| All MCOs submit Equity Program Governance Document to DOH | 2016-01-01: EP Governance Document complete; 2017-02-01: Updates to EP Governance Document Complete; 2018-02-01: Updates to EP Governance Document Complete; 2019-02-01: Updates to EP Governance Document Complete; 2020-02-01: Updates to EP Governance Document Complete
| DOH begins monthly disbursement of EP payments to MCOs (first payment retroactive to April 2015) | 2016-01-01: Monthly EIP Payments to MCOs begin; 2016-04-01: Monthly EPP Payments to MCOs begin
| DSRIP Quarterly Reports | 2016-01-01: DY1 Q3 QR due; 2016-04-01: DY1 Q4 QR due; 2016-07-01: DY2 Q1 QR due; 2016-10-01: DY2 Q2 QR due; 2017-01-01: DY2 Q3 QR due; 2017-04-01: DY2 Q4 QR due; 2017-07-01: DY3 Q1 QR due; 2017-10-01: DY3 Q2 QR due; 2018-01-01: DY3 Q3 QR due; 2018-04-01: DY3 Q4 QR due; 2018-07-01: DY4 Q1 QR due; 2018-10-01: DY4 Q2 QR due; 2019-01-01: DY4 Q3 QR due; 2019-04-01: DY4 Q4 QR due; 2019-07-01: DY5 Q1 QR due; 2019-10-01: DY5 Q2 QR due; 2020-01-01: DY5 Q3 QR due; 2020-04-01: DY5 Q4 QR due
| MCOs make Annual EIP payment to PPSs | 2016-04-01: DY 1 EIP payment made to PPSs; 2017-04-01: DY2 EIP payment made to PPSs; 2018-04-01: DY3 EIP payment made to PPSs; 2019-04-01: DY4 EIP payment made to PPSs; 2020-04-01: Annual EIP payment made to PPSs
| MCO-to-DOH EIP Annual Reports* | 2016-06-01: DY1 EIP Annual Report due; 2017-06-01: DY2 EIP Annual Report due; 2018-06-01: DY3 EIP Annual Report due; 2019-06-01: DY4EIP Annual Report due; 2020-06-01: DY5 EIP Annual Report due
| MCOs make annual EPP payments to PPSs | 2016-04-01: DY1 EPP payment made to PPSs; 2017-04-01: DY2 EPP payment made to PPSs; 2018-04-01: DY3 EPP payment made to PPSs; 2019-04-01: DY4 EPP payment made to PPSs; 2020-04-01: DY5 EPP payment made to PPSs
| MCO-to-DOH Annual EPP Reports* | 2016-06-01: DY1 EPP Annual report due; 2017-06-01: DY2 EPP Annual Report due; 2018-06-01: DY3 EPP Annual Report due; 2019-06-01: DY4 EPP Annual Report due; 2020-06-01: DY5 EPP Annual Report due
| DOH sends EPP measures from Quarterly Measurement Reports to MCOs | 2016-07-01: MCO EPP measures review; 2016-10-01: MCO EPP measures review; 2017-01-01: MCO EPP measures review; 2017-04-01: MCO EPP measures review; 2017-07-01: MCO EPP measures review; 2017-10-01: MCO EPP measures review; 2018-01-01: MCO EPP measures review; 2018-04-01: MCO EPP measures review; 2018-07-01: MCO EPP measures review; 2018-10-01: MCO EPP measures review; 2019-01-01: MCO EPP measures review; 2019-04-01: MCO EPP measures review; 2019-07-01: MCO EPP measures review; 2019-10-01: MCO EPP measures review; 2020-01-01: MCO EPP measures review; 2020-04-01: MCO EPP measures review
* Schedule being provided as an example | bar: 2015-10-01 to 2015-11-01
EP Timeline (Reflective of Monthly EIP Reporting and Payments)
 | time axis 2015-10-01 to 2020-08-01
| DSRIP Demonstration Year | 2015-10-01: DSRIP DY1 (as of April 2015); 2016-04-01: DSRIP DY2; 2017-04-01: DSRIP DY3; 2018-04-01: DSRIP DY4; 2019-04-01: DSRIP DY5
| All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | 2016-01-01: EIP and EPP contracts complete; 2017-02-01: Updates to EIP Contracts; 2018-02-01: Updates to EIP Contracts; 2019-02-01: Updates to EIP Contracts; 2020-02-01: Updates to EIP Contracts
| All MCOs submit Equity Program Governance Document to DOH | 2016-01-01: EP Governance Document complete; 2017-02-01: Updates to EP Governance Document Complete; 2018-02-01: Updates to EP Governance Document Complete; 2019-02-01: Updates to EP Governance Document Complete; 2020-02-01: Updates to EP Governance Document Complete
| DOH begins monthly disbursement of EP payments to MCOs (first payment retroactive to April 2015) | 2016-01-01: Monthly EIP Payments to MCOs begin; 2016-04-01: Monthly EPP Payments to MCOs begin
| DSRIP Quarterly Reports | 2016-01-01: DY1 Q3 QR due; 2016-04-01: DY1 Q4 QR due; 2016-07-01: DY2 Q1 QR due; 2016-10-01: DY2 Q2 QR due; 2017-01-01: DY2 Q3 QR due; 2017-04-01: DY2 Q4 QR due; 2017-07-01: DY3 Q1 QR due; 2017-10-01: DY3 Q2 QR due; 2018-01-01: DY3 Q3 QR due; 2018-04-01: DY3 Q4 QR due; 2018-07-01: DY4 Q1 QR due; 2018-10-01: DY4 Q2 QR due; 2019-01-01: DY4 Q3 QR due; 2019-04-01: DY4 Q4 QR due; 2019-07-01: DY5 Q1 QR due; 2019-10-01: DY5 Q2 QR due; 2020-01-01: DY5 Q3 QR due; 2020-04-01: DY5 Q4 QR due
| MCOs make monthly EIP payments to PPSs |  |  |  |  | DY1 Feb EIP payment made to PPSs | DY1 Mar EIP payment made to PPSs | DY2 Apr EIP payment made to PPSs | DY2 Mar EIP payment made to PPSs | DY2 Jun EIP payment made to PPSs | DY2 July EIP payment made to PPSs | DY2 Aug EIP payment made to PPSs | DY2 Sep EIP payment made to PPSs | DY2 Oct EIP payment made to PPSs | DY2 Nov EIP payment made to PPSs | DY2 Dec EIP payment made to PPSs | DY2 Jan EIP payment made to PPSs | DY2 Feb EIP payment made to PPSs | DY2 Mar EIP payment made to PPSs | DY3 Apr EIP payment made to PPSs | DY3 Mar EIP payment made to PPSs | DY3 Jun EIP payment made to PPSs | DY3 July EIP payment made to PPSs | DY3 Aug EIP payment made to PPSs | DY3 Sep EIP payment made to PPSs | DY3 Oct EIP payment made to PPSs | DY3 Nov EIP payment made to PPSs | DY3 Dec EIP payment made to PPSs | DY3 Jan EIP payment made to PPSs | DY3 Feb EIP payment made to PPSs | DY3 Mar EIP payment made to PPSs | DY4 Apr EIP payment made to PPSs | DY4 Mar EIP payment made to PPSs | DY4 Jun EIP payment made to PPSs | DY4 July EIP payment made to PPSs | DY4 Aug EIP payment made to PPSs | DY4 Sep EIP payment made to PPSs | DY4 Oct EIP payment made to PPSs | DY4 Nov EIP payment made to PPSs | DY4 Dec EIP payment made to PPSs | DY4 Jan EIP payment made to PPSs | DY4 Feb EIP payment made to PPSs | DY4 Mar EIP payment made to PPSs | DY4 Apr EIP payment made to PPSs | DY4 Mar EIP payment made to PPSs | DY4 Jun EIP payment made to PPSs | DY4 July EIP payment made to PPSs | DY4 Aug EIP payment made to PPSs | DY4 Sep EIP payment made to PPSs | DY4 Oct EIP payment made to PPSs | DY4 Nov EIP payment made to PPSs | DY4 Dec EIP payment made to PPSs | DY4 Jan EIP payment made to PPSs | DY4 Feb EIP payment made to PPSs | DY4 Mar EIP payment made to PPSs
| MCO-to-DOH EIP Monthly Reports* | [5 empty] | DY1 Feb EIP Report due | DY1 Mar EIP Report due | DY2 Apr EIP Report due | DY2 May EIP Report due | DY2 Jun EIP Report due | DY2 Jul EIP Report due | DY2 Aug EIP Report due | DY2 Sep EIP Report due | DY2 Oct EIP Report due | DY2 Nov EIP Report due | DY2 Dec EIP Report due | DY2 Jan EIP Report due | DY2 Feb EIP Report due | DY2 Mar EIP Report due | DY3 Apr EIP Report due | DY3 May EIP Report due | DY3 Jun EIP Report due | DY3 Jul EIP Report due | DY3 Aug EIP Report due | DY3 Sep EIP Report due | DY3 Oct EIP Report due | DY3 Nov EIP Report due | DY3 Dec EIP Report due | DY3 Jan EIP Report due | DY3 Feb EIP Report due | DY3 Mar EIP Report due | DY4 Apr EIP Report due | DY4 May EIP Report due | DY4 Jun EIP Report due | DY4 Jul EIP Report due | DY4 Aug EIP Report due | DY4 Sep EIP Report due | DY4 Oct EIP Report due | DY4 Nov EIP Report due | DY4 Dec EIP Report due | DY4 Jan EIP Report due | DY4 Feb EIP Report due | DY4 Mar EIP Report due | DY5 Apr EIP Report due | DY5 May EIP Report due | DY5 Jun EIP Report due | DY5 Jul EIP Report due | DY5 Aug EIP Report due | DY5 Sep EIP Report due | DY5 Oct EIP Report due | DY5 Nov EIP Report due | DY Dec EIP Report due | DY5 Jan EIP Report due | DY5 Feb EIP Report due | DY5 Mar EIP Report due
| MCOs make annual EPP payments to PPSs | 2016-04-01: DY1 EPP payment made to PPSs; 2017-04-01: DY2 EPP payment made to PPSs; 2018-04-01: DY3 EPP payment made to PPSs; 2019-04-01: DY4 EPP payment made to PPSs; 2020-04-01: DY5 EPP payment made to PPSs
| MCO-to-DOH Annual EPP Reports* | 2016-06-01: DY1 EPP Annual report due; 2017-06-01: DY2 EPP Annual Report due; 2018-06-01: DY3 EPP Annual Report due; 2019-06-01: DY4 EPP Annual Report due; 2020-06-01: DY5 EPP Annual Report due
| DOH sends EPP measures from Quarterly Measurement Reports to MCOs | 2016-07-01: MCO EPP measures review; 2016-10-01: MCO EPP measures review; 2017-01-01: MCO EPP measures review; 2017-04-01: MCO EPP measures review; 2017-07-01: MCO EPP measures review; 2017-10-01: MCO EPP measures review; 2018-01-01: MCO EPP measures review; 2018-04-01: MCO EPP measures review; 2018-07-01: MCO EPP measures review; 2018-10-01: MCO EPP measures review; 2019-01-01: MCO EPP measures review; 2019-04-01: MCO EPP measures review; 2019-07-01: MCO EPP measures review; 2019-10-01: MCO EPP measures review; 2020-01-01: MCO EPP measures review; 2020-04-01: MCO EPP measures review
* Schedule being provided as an example | bar: 2015-10-01 to 2015-11-01
EP Timeline (Reflective of Binnual Reporting and Payments)
 | time axis 2015-10-01 to 2020-08-01
| DSRIP Demonstration Year | 2015-10-01: DSRIP DY1 (as of April 2015); 2016-04-01: DSRIP DY2; 2017-04-01: DSRIP DY3; 2018-04-01: DSRIP DY4; 2019-04-01: DSRIP DY5
| All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | 2016-01-01: EIP and EPP contracts complete; 2017-02-01: Updates to EIP Contracts; 2018-02-01: Updates to EIP Contracts; 2019-02-01: Updates to EIP Contracts; 2020-02-01: Updates to EIP Contracts
| All MCOs submit Equity Program Governance Document to DOH | 2016-01-01: EP Governance Document complete; 2017-02-01: Updates to EP Governance Document Complete; 2018-02-01: Updates to EP Governance Document Complete; 2019-02-01: Updates to EP Governance Document Complete; 2020-02-01: Updates to EP Governance Document Complete
| DOH begins monthly disbursement of EP payments to MCOs (first payment retroactive to April 2015) | 2016-01-01: Monthly EIP Payments to MCOs begin; 2016-04-01: Monthly EPP Payments to MCOs begin
| DSRIP Quarterly Reports | 2016-01-01: DY1 Q3 QR due; 2016-04-01: DY1 Q4 QR due; 2016-07-01: DY2 Q1 QR due; 2016-10-01: DY2 Q2 QR due; 2017-01-01: DY2 Q3 QR due; 2017-04-01: DY2 Q4 QR due; 2017-07-01: DY3 Q1 QR due; 2017-10-01: DY3 Q2 QR due; 2018-01-01: DY3 Q3 QR due; 2018-04-01: DY3 Q4 QR due; 2018-07-01: DY4 Q1 QR due; 2018-10-01: DY4 Q2 QR due; 2019-01-01: DY4 Q3 QR due; 2019-04-01: DY4 Q4 QR due; 2019-07-01: DY5 Q1 QR due; 2019-10-01: DY5 Q2 QR due; 2020-01-01: DY5 Q3 QR due; 2020-04-01: DY5 Q4 QR due
| MCOs make Biannual EIP payments to PPSs | 2016-02-01: DY1 EIP payments made to PPSs; 2016-10-01: DY2 1st EIP payments made to PPSs; 2017-05-01: DY2 2nd EIP payments made to PPSs; 2017-10-01: DY3 1st EIP payments made to PPSs; 2018-05-01: DY3 2nd EIP payments made to PPSs; 2018-11-01: DY4 1st EIP payments made to PPSs; 2019-05-01: DY4 2nd EIP payments made to PPSs; 2019-10-01: DY5 1st EIP payments made to PPSs; 2020-05-01: DY5 2nd EIP payments made to PPSs
| MCO-to-DOH EIP Biannual Reports* | 2016-04-01: DY1 EIP biannual report due; 2016-12-01: DY2 1st EIP biannual report due; 2017-07-01: DY2 2nd EIP biannual report due; 2017-12-01: DY3 1st EIP biannual report due; 2018-07-01: DY3 2nd EIP biannual report due; 2019-01-01: DY4 1st EIP biannual report due; 2019-07-01: DY4 2nd EIP biannual report due; 2019-12-01: DY5 1st EIP biannual report due; 2020-07-01: DY5 2nd EIP biannual report due
| MCOs make annual EPP payments to PPSs | 2016-04-01: DY1 EPP payment made to PPSs; 2017-04-01: DY2 EPP payment made to PPSs; 2018-04-01: DY3 EPP payment made to PPSs; 2019-04-01: DY4 EPP payment made to PPSs; 2020-04-01: DY5 EPP payment made to PPSs
| MCO-to-DOH Annual EPP Reports* | 2016-06-01: DY1 EPP Annual report due; 2017-06-01: DY2 EPP Annual Report due; 2018-06-01: DY3 EPP Annual Report due; 2019-06-01: DY4 EPP Annual Report due; 2020-06-01: DY5 EPP Annual Report due
| DOH sends EPP measures from Quarterly Measurement Reports to MCOs | 2016-07-01: MCO EPP measures review; 2016-10-01: MCO EPP measures review; 2017-01-01: MCO EPP measures review; 2017-04-01: MCO EPP measures review; 2017-07-01: MCO EPP measures review; 2017-10-01: MCO EPP measures review; 2018-01-01: MCO EPP measures review; 2018-04-01: MCO EPP measures review; 2018-07-01: MCO EPP measures review; 2018-10-01: MCO EPP measures review; 2019-01-01: MCO EPP measures review; 2019-04-01: MCO EPP measures review; 2019-07-01: MCO EPP measures review; 2019-10-01: MCO EPP measures review; 2020-01-01: MCO EPP measures review; 2020-04-01: MCO EPP measures review
* Schedule being provided as an example | bar: 2015-10-01 to 2015-11-01