## EPP Timelines
EPP Timelines
| November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
Scenario 1: EPP Annual Reporting; Annual Payment
DSRIP Demonstration Year | November: DSRIP DY1 / EPP Year 0 (April 2015 - March 2016); April: DSRIP DY2 / EPP Year 1 (April 2016 - March 2017); April: DSRIP DY3 / EPP Year 2 (April 2017 - March 2018); April: DSRIP DY4 / EPP Year 3 (April 2018 - March 2019), & DY5 / EPP Year 4 (April 2019 - March 2020); April: Post-DSRIP Year 6 (April 2020 - March 2021) / EPP Year 5; April: Post-DSRIP Year 7 (2022) / EPP Year 6
All PPS/MCO pairings complete Equity Program Contracts (including EPP Payment Frequency) | January: EPP contracts complete; February: EPP Contracts Updated (Payment Frequency Only)
All PPS/MCOs submit List of Equity Program Performance Measures to DOH | January: EPP Measures for Year 1 Finalized; February: EPP Measures Updated and Locked (EPP Y2-Y5)
DOH monthly disbursement of EP payments to MCOs | April: Monthly EPP Payments to MCOs; January: Last Monthly EPP Payment to MCOs
PPS Submits Quarterly DSRIP Report in MAPP | April: PPS DSRIP Y1 Q4 Report Due; April: PPS DSRIP Y2 Q4 Reports Due; April: PPS DSRIP Y3 and Y4 Q4 Reports Due; April: PPS DSRIP Y5 Q4 Report Due
DOH sends Performance Achievement information to MCOs for EPP | June: MCOs receive EPP achievement for DSRIP Y1 from IA; June: MCOs receive EPP achievement for DSRIP Y2 Q4; June: MCOs receive EPP achievement for DSRIP Y3 and Y4 Q4; June: MCOs receive EPP achievement for DSRIP Y5 Q4
MCOs make EPP payments to PPSs* | April: Annual EPP Payment for DSRIP Y1; April: Annual EPP Payment for DSRIP Y2 and Y3; April: Annual EPP Payment for DSRIP Y4; April: Annual EPP Payment for DSRIP Y5
MCO-to-DOH EPP Reports on Payments | May: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report
* Schedule being provided as an example
| November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
Scenario 2: EPP Annual Reporting; Semi-Annual Payment
DSRIP Demonstration Year | November: DSRIP DY1 / EPP Year 0 (April 2015 - March 2016); April: DSRIP DY2 / EPP Year 1 (April 2016 - March 2017); April: DSRIP DY3 / EPP Year 2 (April 2017 - March 2018); April: DSRIP DY4 / EPP Year 3 (April 2018 - March 2019), & DY5 / EPP Year 4 (April 2019 - March 2020); April: Post-DSRIP Year 6 (April 2020 - March 2021) / EPP Year 5; April: Post-DSRIP Year 7 (2022) / EPP Year 6
All PPS/MCO pairings complete Equity Program Contracts (including EPP Payment Frequency) | January: EPP contracts complete; February: EPP Contracts Updated (Payment Frequency Only)
All PPS/MCOs submit List of Equity Program Performance Measures to DOH | January: EPP Measures for Year 1 Finalized; February: EPP Measures Updated and Locked (EPP Y2-Y5); February: Updates to EP Governance Document (Years 3 & 4 only)
DOH monthly disbursement of EP payments to MCOs | April: Monthly EPP Payments to MCOs; January: Last Monthly EPP Payment to MCOs
PPS Submits Quarterly DSRIP Report in MAPP | April: PPS DSRIP Y1 Q4 Report Due; April: PPS DSRIP Y2 Q4 Reports Due; April: PPS DSRIP Y3 and Y4 Q4 Reports Due; April: PPS DSRIP Y5 Q4 Report Due
DOH sends Performance Achievement information to MCOs for EPP | June: MCOs receive EPP achievement for DSRIP Y1 from IA; June: MCOs receive EPP achievement for DSRIP Y2 Q4; June: MCOs receive EPP achievement for DSRIP Y3 and Y4 Q4; June: MCOs receive EPP achievement for DSRIP Y5 Q4
MCOs make EPP payments to PPSs* | October: Semi-Annual EPP Payment for DSRIP Y1 (first Payment); April: Semi-Annual EPP Payment for DSRIP Y1 (second payment); October: Semi-Annual EPP Payment for DSRIP Y2 (first payment); April: Semi-Annual EPP Payment for DSRIP Y2 and Y3 (second payment); October: Semi-Annual EPP Payment for DSRIP Y3 and Y4 (first payment); April: Semi-Annual EPP Payment for DSRIP Y4 (second payment); October: Semi-Annual EPP Payment for DSRIP Y5 (first payment); April: Semi-Annual EPP Payment for DSRIP Y5 (second payment)
MCO-to-DOH EPP Reports on Payments | November: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report; November: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report; November: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report; November: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report
* Schedule being provided as an example
| November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
Scenario 3: EPP Annual Reporting; Quarterly Payment
DSRIP Demonstration Year | November: DSRIP DY1 / EPP Year 0 (April 2015 - March 2016); April: DSRIP DY2 / EPP Year 1 (April 2016 - March 2017); April: DSRIP DY3 / EPP Year 2 (April 2017 - March 2018); April: DSRIP DY4 / EPP Year 3 (April 2018 - March 2019), & DY5 / EPP Year 4 (April 2019 - March 2020); April: Post-DSRIP Year 6 (April 2020 - March 2021) / EPP Year 5; April: Post-DSRIP Year 7 (2022) / EPP Year 6
All PPS/MCO pairings complete Equity Program Contracts (including EPP Payment Frequency) | January: EPP contracts complete; February: EPP Contracts Updated (Payment Frequency Only)
All PPS/MCOs submit List of Equity Program Performance Measures to DOH | January: EPP Measures for Year 1 Finalized; February: EPP Measures Updated and Locked (EPP Y2-Y5); February: Updates to EP Governance Document (Years 3 & 4 only)
DOH monthly disbursement of EP payments to MCOs | April: Monthly EPP Payments to MCOs; January: Last Monthly EPP Payment to MCOs
PPS Submits Quarterly DSRIP Report in MAPP | April: PPS DSRIP Y1 Q4 Report Due; April: PPS DSRIP Y2 Q4 Reports Due; April: PPS DSRIP Y3 and Y4 Q4 Reports Due; April: PPS DSRIP Y5 Q4 Report Due
DOH sends Performance Achievement information to MCOs for EPP | June: MCOs receive EPP achievement for DSRIP Y1 from IA; June: MCOs receive EPP achievement for DSRIP Y2 Q4; June: MCOs receive EPP achievement for DSRIP Y3 and Y4 Q4; June: MCOs receive EPP achievement for DSRIP Y5 Q4
MCOs make EPP payments to PPSs* | July: Quarterly EPP Payment for DSRIP Y1 Q1; October: Quarterly EPP Payment for DSRIP Y1 Q2; January: Quarterly EPP Payment for DSRIP Y1 Q3; April: Quarterly EPP Payment for DSRIP Y1 Q4; July: Quarterly EPP Payment for DSRIP Y2 Q1; October: Quarterly EPP Payment for DSRIP Y2 Q2; January: Quarterly EPP Payment for DSRIP Y2 Q3; April: Quarterly EPP Payment for DSRIP Y2 and Y3 Q4; July: Quarterly EPP Payment for DSRIP Y3 and Y4 Q1; October: Quarterly EPP Payment for DSRIP Y3 and Y4 Q2; January: Quarterly EPP Payment for DSRIP Y3 and Y4 Q3; April: Quarterly EPP Payment for DSRIP Y4 Q4; July: Quarterly EPP Payment for DSRIP Y5 Q1; October: Quarterly EPP Payment for DSRIP Y5 Q2; January: Quarterly EPP Payment for DSRIP Y5 Q3; April: Quarterly EPP Payment for DSRIP Y5 Q4
MCO-to-DOH EPP Reports on Payments | August: MCO-to-DOH EPP Report; November: MCO-to-DOH EPP Report; February: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report; August: MCO-to-DOH EPP Report; November: MCO-to-DOH EPP Report; February: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report; August: MCO-to-DOH EPP Report; November: MCO-to-DOH EPP Report; February: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report; August: MCO-to-DOH EPP Report; November: MCO-to-DOH EPP Report; February: MCO-to-DOH EPP Report; May: MCO-to-DOH EPP Report
* Schedule being provided as an example
| November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
Scenario 4: EPP Annual Reporting, Monthly Payment
DSRIP Demonstration Year | November: DSRIP DY1 / EPP Year 0 (April 2015 - March 2016); April: DSRIP DY2 / EPP Year 1 (April 2016 - March 2017); April: DSRIP DY3 / EPP Year 2 (April 2017 - March 2018); April: DSRIP DY4 / EPP Year 3 (April 2018 - March 2019), & DY5 / EPP Year 4 (April 2019 - March 2020); April: Post-DSRIP Year 6 (April 2020 - March 2021) / EPP Year 5; April: Post-DSRIP Year 7 (2022) / EPP Year 6
All PPS/MCO pairings complete Equity Program Contracts (including EPP Payment Frequency) | January: EPP contracts complete; February: EPP Contracts Updated (Payment Frequency Only)
All PPS/MCOs submit List of Equity Program Performance Measures to DOH | January: EPP Measures for Year 1 Finalized; February: EPP Measures Updated and Locked (EPP Y2-Y5); February: Updates to EP Governance Document (Years 3 & 4 only)
DOH monthly disbursement of EP payments to MCOs | April: Monthly EPP Payments to MCOs; January: Last Monthly EPP Payment to MCOs
PPS Submits Quarterly DSRIP Report in MAPP | April: PPS DSRIP Y1 Q4 Report Due; April: PPS DSRIP Y2 Q4 Reports Due; April: PPS DSRIP Y3 and Y4 Q4 Reports Due; April: PPS DSRIP Y5 Q4 Report Due
DOH sends Performance Achievement information to MCOs for EPP | June: MCOs receive EPP achievement for DSRIP Y1 from IA; June: MCOs receive EPP achievement for DSRIP Y2 Q4; June: MCOs receive EPP achievement for DSRIP Y3 and Y4 Q4; June: MCOs receive EPP achievement for DSRIP Y5 Q4
MCOs make EPP payments to PPSs* | [8 empty] | Monthly EPP Payment for DSRIP Y1 | Monthly EPP Payment for DSRIP Y1 | Monthly EPP Payment for DSRIP Y1 | Monthly EPP Payment for DSRIP Y1 | Monthly EPP Payment for DSRIP Y1 | Monthly EPP Payment for DSRIP Y1 | Monthly EPP Payment for DSRIP Y1 | Monthly EPP Payment for DSRIP Y1 | Monthly EPP Payment for DSRIP Y1 | Monthly EPP Payment for DSRIP Y1 | Monthly EPP Payment for DSRIP Y1 | Monthly EPP Payment for DSRIP Y1 | Monthly EPP Payment DSRIP Y2 | Monthly EPP Payment DSRIP Y2 | Monthly EPP Payment DSRIP Y2 | Monthly EPP Payment DSRIP Y2 | Monthly EPP Payment DSRIP Y2 | Monthly EPP Payment DSRIP Y2 | Monthly EPP Payment DSRIP Y2 | Monthly EPP Payment DSRIP Y2 | Monthly EPP Payment DSRIP Y2 | Monthly EPP Payment for DSRIP Y2 and Y3 | Monthly EPP Payment for DSRIP Y2 and Y3 | Monthly EPP Payment for DSRIP Y2 and Y3 | Monthly EPP Payment DSRIP Y3 and Y4 | Monthly EPP Payment DSRIP Y3 and Y4 | Monthly EPP Payment DSRIP Y3 and Y4 | Monthly EPP Payment DSRIP Y3 and Y4 | Monthly EPP Payment DSRIP Y3 and Y4 | Monthly EPP Payment DSRIP Y3 and Y4 | Monthly EPP Payment DSRIP Y3 and Y4 | Monthly EPP Payment DSRIP Y3 and Y4 | Monthly EPP Payment DSRIP Y3 and Y4 | Monthly EPP Payment for DSRIP Y4 | Monthly EPP Payment for DSRIP Y4 | Monthly EPP Payment for DSRIP Y4 | Monthly EPP Payment for DSRIP Y5 | Monthly EPP Payment for DSRIP Y5 | Monthly EPP Payment for DSRIP Y5 | Monthly EPP Payment for DSRIP Y5 | Monthly EPP Payment for DSRIP Y5 | Monthly EPP Payment for DSRIP Y5 | Monthly EPP Payment for DSRIP Y5 | Monthly EPP Payment for DSRIP Y5 | Monthly EPP Payment for DSRIP Y5 | Monthly EPP Payment for DSRIP Y5 | Monthly EPP Payment for DSRIP Y5 | Monthly EPP Payment for DSRIP Y5
MCO-to-DOH EPP Reports on Payments | [9 empty] | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report | MCO-to-DOH EPP Report
* Schedule being provided as an example

## EIP Timelines
EIP Timelines
| November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March
Scenario 1: Monthly Reporting, Monthly Payment
DSRIP Demonstration Year | November: DSRIP DY0 / EIP Year 0 (April 2014 - March 2015); April: DSRIP DY1 / EIP Year 1 (April 2015 - March 2016); April: DSRIP DY2 / EIP Year 2 (April 2016 - March 2017), DY3 / EIP Year 3 (April 2017 - March 2018), DY4 / EIP Year 4 (April 2018 - March 2019), DY5 / EIP Year 5 (April 2019 - March 2020); April: Post-DSRIP Year 6 (April 2020 - March 2021) / EIP Year 6
All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | January: EIP Contracts Complete (Reporting & Payment Frequency); February: EIP Reporting and Payment Frequency Updates for DY2; February: EIP Reporting and Payment Frequency Updates (for DY3, DY4, DY5)
All MCOs submit Equity Program Governance Document to DOH | January: EIP DY1 Activities Finalized; February: EIP DY2 Activities Finalized; February: EIP DY3, DY4, DY5 Activities Finalized
DOH monthly disbursement of EP payments to MCOs (EIP first payment retroactive to April 2015) | April: Monthly EIP Payments to MCOs; March: Last Monthly EIP Payment to MCOs
PPSs report on EIP Activities to MCOs* | May: Monthly EIP Report for DSRIP Y1; June: Monthly EIP Report for DSRIP Y1; July: Monthly EIP Report for DSRIP Y1; August: Monthly EIP Report for DSRIP Y1; September: Monthly EIP Report for DSRIP Y1; October: Monthly EIP Report for DSRIP Y1; November: Monthly EIP Report for DSRIP Y1; December: Monthly EIP Report for DSRIP Y1; January: Monthly EIP Report for DSRIP Y1; February: Monthly EIP Report for DSRIP Y1; March: Monthly EIP Report for DSRIP Y1; April: Monthly EIP Report for DSRIP Y1, Y2, Y3, and Y4; May: Monthly EIP Report for DSRIP Y2, Y3, Y4, and Y5; June: Monthly EIP Report for DSRIP Y2, Y3, Y4, and Y5; July: Monthly EIP Report for DSRIP Y2, Y3, Y4, and Y5; August: Monthly EIP Report for DSRIP Y2, Y3, Y4, and Y5; September: Monthly EIP Report for DSRIP Y2, Y3, Y4, and Y5; October: Monthly EIP Report for DSRIP Y2, Y3, Y4, and Y5; November: Monthly EIP Report for DSRIP Y2, Y3, Y4, and Y5; December: Monthly EIP Report for DSRIP Y2, Y3, Y4, and Y5; January: Monthly EIP Report for DSRIP Y2, Y3, Y4, and Y5; February: Monthly EIP Report for DSRIP Y2, Y3, Y4, and Y5; March: Monthly EIP Report for DSRIP Y2, Y3, Y4, and Y5; April: Monthly EIP Report for DSRIP Y5
MCOs make EIP payments to PPSs* | June: Monthly EIP Payment for DSRIP Y1; July: Monthly EIP Payment for DSRIP Y1; August: Monthly EIP Payment for DSRIP Y1; September: Monthly EIP Payment for DSRIP Y1; October: Monthly EIP Payment for DSRIP Y1; November: Monthly EIP Payment for DSRIP Y1; December: Monthly EIP Payment for DSRIP Y1; January: Monthly EIP Payment for DSRIP Y1; February: Monthly EIP Payment for DSRIP Y1; March: Monthly EIP Payment for DSRIP Y1; April: Monthly EIP Payment for DSRIP Y1, Y2, Y3, and Y4; May: Monthly EIP Payment for DSRIP Y1, Y2, Y3, and Y4; June: Monthly EIP Payment for DSRIP Y2, Y3, Y4, and Y5; July: Monthly EIP Payment for DSRIP Y2, Y3, Y4, and Y5; August: Monthly EIP Payment for DSRIP Y2, Y3, Y4, and Y5; September: Monthly EIP Payment for DSRIP Y2, Y3, Y4, and Y5; October: Monthly EIP Payment for DSRIP Y2, Y3, Y4, and Y5; November: Monthly EIP Payment for DSRIP Y2, Y3, Y4, and Y5; December: Monthly EIP Payment for DSRIP Y2, Y3, Y4, and Y5; January: Monthly EIP Payment for DSRIP Y2, Y3, Y4, and Y5; February: Monthly EIP Payment for DSRIP Y2, Y3, Y4, and Y5; March: Monthly EIP Payment for DSRIP Y2, Y3, Y4, and Y5; April: DSRIP Y5 Monthly EIP Payment; May: DSRIP Y5 Monthly EIP Payment
MCO-to-DOH EIP Reports on Payments | July: MCO-to-DOH EIP Report; August: MCO-to-DOH EIP Report; September: MCO-to-DOH EIP Report; October: MCO-to-DOH EIP Report; November: MCO-to-DOH EIP Report; December: MCO-to-DOH EIP Report; January: MCO-to-DOH EIP Report; February: MCO-to-DOH EIP Report; March: MCO-to-DOH EIP Report; April: MCO-to-DOH EIP Report; May: MCO-to-DOH EIP Report; June: MCO-to-DOH EIP Report; July: MCO-to-DOH EIP Report; August: MCO-to-DOH EIP Report; September: MCO-to-DOH EIP Report; October: MCO-to-DOH EIP Report; November: MCO-to-DOH EIP Report; December: MCO-to-DOH EIP Report; January: MCO-to-DOH EIP Report; February: MCO-to-DOH EIP Report; March: MCO-to-DOH EIP Report; April: MCO-to-DOH EIP Report; May: MCO-to-DOH EIP Report; June: MCO-to-DOH EIP Report
* Schedule being provided as an example
| November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March
Scenario 2: EIP Quarterly Reporting, Quarterly Payment
DSRIP Demonstration Year | November: DSRIP DY0 / EIP Year 0 (April 2014 - March 2015); April: DSRIP DY1 / EIP Year 1 (April 2015 - March 2016); April: DSRIP DY2 / EIP Year 2 (April 2016 - March 2017), DY3 / EIP Year 3 (April 2017 - March 2018), DY4 / EIP Year 4 (April 2018 - March 2019), DY5 / EIP Year 5 (April 2019 - March 2020); April: Post-DSRIP Year 6 (April 2020 - March 2021) / EIP Year 6
All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | January: EIP Contracts Complete (Reporting & Payment Frequency); February: EIP Reporting and Payment Frequency Updates for DY2; February: EIP Reporting and Payment Frequency Updates (for DY3, DY4, DY5)
All MCOs submit Equity Program Governance Document to DOH | January: EIP DY1 Activities Finalized; February: EIP DY2 Activities Finalized; February: EIP DY3, DY4, DY5 Activities Finalized
DOH monthly disbursement of EP payments to MCOs (EIP first payment retroactive to April 2015) | April: Monthly EIP Payments to MCOs; March: Last Monthly EIP Payment to MCOs
PPSs report on EIP Activities to MCOs* | July: EIP Report for DSRIP Y1 Q1; October: EIP Report for DSRIP Y1 Q2; January: EIP Report for DSRIP Y1 Q3; April: EIP Report for DSRIP Y1, Y2, Y3, and Y4 Q4; July: EIP Report for DSRIP Y2, Y3, Y4, and Y5 Q1; October: EIP Report for DSRIP Y2, Y3, Y4, and Y5 Q2; January: EIP Report for DSRIP Y2, Y3, Y4, and Y5 Q3; April: EIP Report for DSRIP Y5 Q4
MCOs make EIP payments to PPSs* | August: EIP Payment for DSRIP Y1 Q1; November: EIP Payment for DSRIP Y1 Q2; February: EIP Payment for DSRIP Y1 Q3; May: EIP Payment for DSRIP Y1, Y2, Y3, and Y4 Q4; August: EIP Payment for DSRIP Y2, Y3, Y4, and Y5 Q1; November: EIP Payment for DSRIP Y2, Y3, Y4, and Y5 Q2; February: EIP Payment for DSRIP Y2, Y3, Y4, and Y5 Q3; May: EIP Payment for DSRIP Y5 Q4
MCO-to-DOH EIP Reports on Payments | September: MCO-to-DOH EIP Report; December: MCO-to-DOH EIP Report; March: MCO-to-DOH EIP Report; June: MCO-to-DOH EIP Report; September: MCO-to-DOH EIP Report; December: MCO-to-DOH EIP Report; March: MCO-to-DOH EIP Report; June: MCO-to-DOH EIP Report
* Schedule being provided as an example
| November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March
Scenario 3: EIP Monthly Reporting, Quarterly Payment
DSRIP Demonstration Year | November: DSRIP DY0 / EIP Year 0 (April 2014 - March 2015); April: DSRIP DY1 / EIP Year 1 (April 2015 - March 2016); April: DSRIP DY2 / EIP Year 2 (April 2016 - March 2017), DY3 / EIP Year 3 (April 2017 - March 2018), DY4 / EIP Year 4 (April 2018 - March 2019), DY5 / EIP Year 5 (April 2019 - March 2020); April: Post-DSRIP Year 6 (April 2020 - March 2021) / EIP Year 6
All PPS/MCO pairings complete Equity Program Contracts and Updates to EIP Contracts | January: EIP Contracts Complete (Reporting & Payment Frequency); February: EIP Reporting and Payment Frequency Updates for DY2; February: EIP Reporting and Payment Frequency Updates (for DY3, DY4, DY5)
All MCOs submit Equity Program Governance Document to DOH | January: EIP DY1 Activities Finalized; February: EIP DY2 Activities Finalized; February: EIP DY3, DY4, DY5 Activities Finalized
DOH monthly disbursement of EP payments to MCOs (EIP first payment retroactive to April 2015) | April: Monthly EIP Payments to MCOs; March: Last Monthly EIP Payment to MCOs
PPSs report on EIP Activities to MCOs* | May: Monthly EIP Report for DSRIP Y1; June: Monthly EIP Report for DSRIP Y1; July: Monthly EIP Report for DSRIP Y1; August: Monthly EIP Report for DSRIP Y1; September: Monthly EIP Report for DSRIP Y1; October: Monthly EIP Report for DSRIP Y1; November: Monthly EIP Report for DSRIP Y1; December: Monthly EIP Report for DSRIP Y1; January: Monthly EIP Report for DSRIP Y1; February: Monthly EIP Report for DSRIP Y1; March: Monthly EIP Report for DSRIP Y1; April: Monthly EIP Report for DSRIP Y1, Y2, Y3, and Y4; May: Monthly EIP Report for DSRIP Y2, Y3, Y4, and Y5; June: Monthly EIP Report for DSRIP Y2, Y3, Y4, and Y5; July: Monthly EIP Report for DSRIP Y2, Y3, Y4, and Y5; August: Monthly EIP Report for DSRIP Y2, Y3, Y4, and Y5; September: Monthly EIP Report for DSRIP Y2, Y3, Y4, and Y5; October: Monthly EIP Report for DSRIP Y2, Y3, Y4, and Y5; November: Monthly EIP Report for DSRIP Y2, Y3, Y4, and Y5; December: Monthly EIP Report for DSRIP Y2, Y3, Y4, and Y5; January: Monthly EIP Report for DSRIP Y2, Y3, Y4, and Y5; February: Monthly EIP Report for DSRIP Y2, Y3, Y4, and Y5; March: Monthly EIP Report for DSRIP Y2, Y3, Y4, and Y5; April: Monthly EIP Report for DSRIP Y5
MCOs make EIP payments to PPSs* | August: EIP Payment for DSRIP Y1 Q1; November: EIP Payment for DSRIP Y1 Q2; February: EIP Payment for DSRIP Y1 Q3; May: EIP Payment for DSRIP Y1, Y2, Y3, and Y4 Q4; August: EIP Payment for DSRIP Y2, Y3, Y4, and Y5 Q1; November: EIP Payment for DSRIP Y2, Y3, Y4, and Y5 Q2; February: EIP Payment for DSRIP Y2, Y3, Y4, and Y5 Q3; May: EIP Payment for DSRIP Y5 Q4
MCO-to-DOH EIP Reports on Payments | September: MCO-to-DOH EIP Report; December: MCO-to-DOH EIP Report; March: MCO-to-DOH EIP Report; June: MCO-to-DOH EIP Report; September: MCO-to-DOH EIP Report; December: MCO-to-DOH EIP Report; March: MCO-to-DOH EIP Report; June: MCO-to-DOH EIP Report
* Schedule being provided as an example