## Phase 2 original (hidden)
MRT Project # | Project/Task Description | Status | Date Completed | Division Lead | Team Lead | Remarks and Updates to associated documents
Program Streamlining and State/Local Responsibliities Work Group
5001 | Develop and Implement Core Exchange Business Processes | In Progress |  | Exchange Staff
5002 | Restructure Medicaid Financing | Completed | Janurary 2014 | Eligibility | Judy Arnold
5003A | Transition Medicaid Administration from Counties to the State: Secure Legislative Authority and Resources | Completed | April 2013 | Eligibility | Judy Arnold
5003B | Transition Medicaid Administration from Counties to the State: Identify Functions for Early State Administration and Implement | Completed | June 2013 | Eligibility | Judy Arnold
5003C | Transition Medicaid Administration from Counties to the State: Centralize MAGI Eligbility Determinations | In Progress |  | Eligibility | Judy Arnold
5004A | Centralize and automate eligibility and enrollment processes for the Medicare Savings Programs. | In Progress |  | Eligibility | Wendy Butz
5004B | Expand Aged, Blind, and Disabled Automated Renewals | Cancelled |  | Eligibility | Ralph Bielefeldt
5004C | Asset Verification System (AVS) | In Progress |  | Eligibility | Ralph Bielefeldt
5004D | Automate Spend Down | Cancelled |  | Eligibility | Wendy Butz
5004E | Address Vulnerable Population Consumer Assistance Needs | Completed |  | Eligibility | Gabrielle Armenia
5005 | Improve Access to Emergency Medicaid | Completed |  | DCE | Kathleen Johnson
Behavioral Health Reform Work Group
5101 | Create Risk-Bearing Managed Care Entities for High-Need Behavioral Health Populations | In Progress |  | OMH | Bob Myers
5101A | Identify/Develop Mechanisms for improving behavioral health screening and treatment in primary care settings | Completed | May 2013 | OMH | Dr. Lloyd Sederer
5101B | Implement Joint licensure for clinics | Completed |  | OMH | Marcia Fazio | Reflected in MRT Phase 4 WP & DSRIP WP
5101C | Care coordination model for children with behavioral health needs | In Progress |  | OMH | Donna Bradbury
MLTC Implementation & Waiver Redesign Work Group
5201 | Quality Measures for CCM Performance | Merged #5602 |  | Division of Quality Improvement and Evaluation | Pat Roohan
5202 | Improve Fair Hearing Process | Merged #7003 |  | Division of Long Term Care | Mark Kissinger
5203 | Workgroup on integration of self-directed program models | Completed | Janurary 2014 | Division of Long Term Care | Mark Kissinger
Health Disparities Work Group
5301 | Data Collection/Metrics to Measure Health Disparities | Completed |  | OPH | Geraldine Johnson
5302 | Improve Language Access to improve disparities | In Progress |  | DFRS | John Gahan
5303 | Promote Language Accessible Prescription Labels | Completed |  | NYS ED |  | Refered to Department of Ed
5304A | Chronic Disease Preventive Services: Diabetes | In Waiver |  | OPH | Maureen Spence | 5304 - Project overall lead is Barb Wallace.
5304B | Chronic Disease Preventive Services: Asthma | In Waiver |  | OPH | Jennifer Mane
5304C | Chronic Disease Preventive Services: Lead Poisoning | In Waiver |  | OPH | Mike Cambridge
5304D | Chronic Disease Preventive Services: Automated blood pressure cuffs for home use | Completed | December 2012 | OPH | Barb Dennison
5305 | Streamline and Improve Access to Emergency Medicaid | Merged #5005 |  |  |  | No Division or team lead name listed
5306 | Address Disparities in Treatment at Teaching Facilities | Cancelled |  | Office of Primary Care | Tom Burke
5307A | Expand access for contraception and other family planning services | Cancelled |  | OPH | Wendy Butz
5307B | Expand Medicaid coverage for inter-conceptional care | Cancelled |  | OPH | Kristine Mesler
5307C | Expand Medicaid coverage to include breastfeeding education and lactation counseling and provide financial incentives to hospitals to provide breastfeeding support | Merged #5402D |  |  |  | No Division or team lead name listed
5307D | Support initiatives to demonstrate effective and efficient use of HIT technology to improve care delivery for women and infants | Completed |  | OPH | Marilyn Kacica, Rudy Lewis
5308 | Address Disparities through Targeted Training for NYS Health Care Workforce | Cancelled |  |  | Barry Gray | No Division listed Ask Barry.
5309 | Enhance Services for Youth in Transition with Psychiatric Disabilities | Merged #5101C |  | OMH |  | No team lead name listed.
5310 | Promote Effective Use of Charity Care Funds | Merged #5603 |  |  |  | No Division or team lead name listed.
5311A | Design an integrated HCV disease management initiative for HCV screening, care and treatment, and other supports in a variety of treatment settings: primary care clinics, HIV clinics and OASAS clinic programs. Include in Medicaid managed care plans chronic disease infrastructure. | Completed |  | OPH | Ira Feldman
5311B | Promote Hepatitis C Care and Treatment through Service Integration: Primary Care Settings | Completed |  | OPH | Ira Feldman
5311C | Promote Hepatitis C Care and Treatment through Service Integration: Health Home Expansion | Merged Ph 4, Health Home Plan |  | OPH | Ira Feldman
5312 | Promote Full Access to the Mental Health Medication on the Medicaid Formulary | Merged #5914 |  |  |  | No Division or team lead name listed - merged w/#5914, Promote Full Access to the Mental Health Medication on the Medicaid Formulary (Catch-All work sheet)
5313 | Medicaid Support of Water Fluoridation | Completed - Implemented through enacted Budget 2015-2016 |  |  |  | No Division or team lead name listed. Pending budget 2015-2016
5314A | Medicaid Coverage of Harm Reduction Activities: Clarify Regulations | Completed | April 2013 | OPH | Dan O'Connell
5314B | Medicaid Coverage of Harm Reduction Activities: OASAS Provider Reimbursement | Completed | February 2013 | OPH | Dan O'Connell
5314C | Medicaid Coverage of Harm Reduction Activities: AI providers reimbursement | Merged #8021 |  | OPH | Dan O'Connell
5315 | Expand HIV SNPs enrollment to include non-HIV high-need/high-cost populations (e.g., homeless) | Completed |  | OPH | Ira Feldman
Basic Benefit Review Work Group
5401 | Benefit Review Process | Completed | October 2012 | Office of Medical Director | Foster Gesten
5402A | Podiatry for Diabetics | Completed | September 2012 | DPDM | Connie Donohue, Ron Bass
5402B | Knee Arthroscopy | Completed | September 2012 | DPDM | Constance Donohue, Ron Bass
5402C | Back Pain Treatments | Completed | September 2012 | DPDM | Constance Donohue, Ron Bass
5402D | Breastfeeding Support | Completed | March 2012 | DPDM | Constance Donohue, Ron Bass
5402E | Percutaneous Coronary Intervention (PCI) | Completed | June 2013 | DPDM | Constance Donohue, Ron Bass
5402F | Reduce payments for elective Cesarean sections and inductions | Completed | July 2013 | DPDM | Constance Donohue, Ron Bass
5402G | Growth Hormone | Completed | September 2012 | DPDM | May Carroll
5402H | Tobacco Cessation Counseling by Dentists | Completed |  | DPDM | Constance Donohue, Ron Bass
5403A | Obesity Treatment | Cancelled |  | DPDM | Constance Donohue, Ron Bass | Not in budget
5403B | Nurse Family Partnership (NFP) | In Waiver |  | DPDM | Constance Donohue, Ron Bass
Workforce Flexibility/Change of Scope of Practice Work Group
5501 | Advisory Committee to the Office of the Professions of the State Education Department. | Cancelled |  | OPCHSM | Barry Gray | No Division listed (Lisa Ullman)
5502A | Advanced Aides | Cancelled |  |  | Becky Gray | No Division listed (Caleb Wistar); per 2015/2016 budget
5502B | Advanced Home Care Aide Certification | Cancelled |  |  | Becky Gray | No Division listed (Caleb Wistar); per 2015/2016 budget
5502C | Remove collaboration practice agreement requirement for Certified Nurse Practitioners | Completed | April 2014 |  | Wendy Shaw | No Division listed (Caleb Wistar)
5502D | Collaborative Practice of Dental Hygienists/Definition of Dental Hygiene | Completed | May 2013 |  | Jay Kumar (check) | No Division listed (Caleb Wistar)
5502E | Removal of physician supervisory ratio of physician assistants (PAs) | Completed | Mar 2015 |  | Caleb Wistar | No Division listed (Caleb Wistar)
5502F | Children’s Dental Health Certificate | Completed | August 2013 |  | Jay Kumar (check) | No Division listed (Caleb Wistar)
5503A | Standing Orders/Physician Practice Protocols | Cancelled |  |  | Caleb Wistar, Gus Birkhead | No Division listed (Lisa Ullman). Status needs to be included in the Workforce Flexibility Work Plan.
5503B | Enable physician home visits | Cancelled |  |  | John Gahan | No Division listed (Barry Gray)
5503C | Stackable certification and credentials for direct care workers | Cancelled |  |  | Becky Gray | No Division listed
5504 | New York State Primary Care Service Corps (PCSC) | Completed | March 2013 |  | Caleb Wistar | No Division listed. Status needs to be included in the Workforce Flexibility Work Plan.
5505 | Exempt license requirement for certain titles in NYS agencies | Suspended |  | OMH OPCHSM | Henry Fernandez
5506 | Promote programs such as CDPAP | Completed | June 2012 |  | Leslie Galusha | No Division listed. Status needs to be included in the Workforce Flexibility Work Plan.
Payment Reform & Quality Measurement Work Group
5601 | Integrate Medicaid & Medicare service delivery and financing | Merged #90 |  | DLTC | Mark Kissinger | Merged with MRT 90, Mandatory Enrollment in MLTCs.
5602 | Quality Measurement | Completed | May 2012 | DQIE | Pat Roohan
5603 | Indigent Care Funding Program Reform | Completed | Date? | DFRS | Rolan Guilz
5604 | Essential Community Provider Network &Vital Access Providers | Merged #67 |  | DFRS/OHSM | Lora Lefebvre | Merged with MRT #67, Safety Net.
Affordable Housing Work Group
5700 | Re-engage the MRT Affordable Housing Work Group | Completed |  |  | Liz Misa, Mark Kissinger
5701 | New York/New York IV Agreement | Merged #5700 |  | NYC | Andrea Cohen
5702 | Establish dedicated fund for supportive housing development | Completed | December 2012 | Div of Long Term Care and Div of Finance Development | Mark Kissinger, John Ulberg, Ken Evans
5703 | Provide immediate support to supportive housing development. | Completed | May 2013 | Div of Long Term Care | Liz Misa, Mark Kissinger
5704 | Unfreeze OMH capital funding | Completed | April 2012 | OMH | Bob Myers
5705 | Increase set-asides and incentives for supportive housing | Merged #5700 |  | HCR | Sean Fitzgerald
5706 | Include funds for ongoing services and operating costs in MRT 1115 Medicaid Waiver | In Waiver |  | Div of Long Term Care | Liz Misa
5707 | Pilot "Social Impact Investment Bonds" for supportive housing | Merged #5700 |  |  |  | No Division or team lead name listed - merged with MRT 5700
5708 | Improve interagency coordination of supportive housing policy and implementation | Merged #5700 |  |  |  | No Division or team lead name listed - merged with MRT 5700
5709 | Establish a work group to identify and improve the supportive/affordable housing capital development process | Completed | September 2012 | OHIP | Liz Misa, Mark Kissinger
5710 | Evaluate perceived barriers to maximizing existing resources and expanding opportunities | Merged #5700 |  |  |  | No Division or team lead name listed - merged with MRT 5700
5711 | Identify and resolve barriers to transitioning individuals to supportive housing; Establish “Moving On” initiative | Merged #5700 |  | Div of Long Term Care | Mark Kissinger, Becky Corso | No Division or team lead name listed - merged with MRT 5700
5712A | Registered Nurse Assessment for ALP services. | Completed |  |  |  | No contacts listed
5712B | Increase ALP Reimbursement | In Progress |  |  | John Ulberg
5712C | Establish Post-Admission Audits for ALP enrollment | Completed | July 2012 |  |  | No contacts listed
5712D | Nursing Home Beds/ALP | Completed | June 2012 |  |  | No contacts listed; see 5712 Project information
5712E | Lift CHHA moratorium | Completed | December 2012 |  |  | No contacts listed
5712F | LHCSA Aides scope of practice | Completed | July 2013 |  |  | No contacts listed
5712G | ALP/CHHA/LTHHCP Contracting | Completed | July 2015 |  |  | No contacts listed
5712H | ALP & Therapy Services | Completed | March 2015 |  |  | No contacts listed
5712I | ALP Survey Process | Completed | March 2015 |  | Keith Servis
5712J | ALP Program Forum to evaluate implementation | Completed | March 2015 |  |  | No contacts listed
5713 | Co-Locate Community Health Centers for Supportive Housing Residents | Cancelled | August 2015 |  | Karen Westervelt
5714 | Notice and best effort education | Completed | March 2013 | Div of Long Term Care | Karen Meier
5715 | Expand and improve independent senior housing opportunities | Merged #7106 |  | Div of Long Term Care | Mark Kissinger
5716 | Maintain housing subsidies and focus of NHTD/TBI Waivers | Merged #5700 |  | Div of Long Term Care | Lydia Kosinski
5717 | Medical Respite for homeless individuals | Completed | January 2013 | OASAS | Rob Kent
5718 | Coordinate supportive housing with Health Homes Initiative | Merged #89 |  |  |  | No contacts listed -merged with MRT 89, Health Homes
Catch-All Workplans
5901 | Payment for Enteral Formula with Medical Necessity Criteria (Revision) | Completed | May 2014 | DPRUM | Kevin Hepp
5902 | EQUAL Program | Completed | May 2013 | Center for Health Care and Surveillance | Dorothy Persico
5903 | Emergency Department Triage | Completed | May 2014 | DHFP | Joe DiMura
5904 | Stakeholder Consultation for Nursing Home Capital Reimbursement | In Waiver |  | DFRS | John Ulberg
5905 | Workgroup on Medically Fragile Children | Completed | February 2013 | OHIP, DHCBS, OPWDD | Lana Earie
5906 | Limited Administrative Review (FQHC) | Completed | May 2014 | OHIP | John Gahan
5907 | Exclusive Pharmacy Network Criteria in Managed Care | Cancelled |  | DPDM | Patty Keller, Anne Blanchard
5908 | Rural Telehealth Demonstration | Completed | June 2013 | Office of Primary Care | Rebecca Fuller Gray
5909 | Doctors Across New York Physician Loan Repayment and Physician Practice Support | Completed | December 2012 | Office of Primary Care | Thomas Burke
5910 | Prescriber Prevails in Managed Care | Completed | May 2013 | DPDM | Patty Keller, Anne Blanchard
5911 | EPIC Coverage Expansion | Completed | April 2013 | DPDM | Rhonda Cooper
5912 | Reduction of APG Hospital Investment by $25M | Completed | February 2013 | DFRS | Janet Baggetta
5913 | Promote Full Access to the Mental Health Medication on the Medicaid Formulary | Completed | November 2013 | OHIP | Janet Elkind

## Phase 2
MRT Phase 2 Project Status
MRT Project # | Project/Task Description | Status
Program Streamlining and State/Local Responsibliities Work Group
5001 | Develop and Implement Core Exchange Business Processes | Completed
5002 | Restructure Medicaid Financing | Completed
5003A | Transition Medicaid Administration from Counties to the State: Secure Legislative Authority and Resources | Completed
5003B | Transition Medicaid Administration from Counties to the State: Identify Functions for Early State Administration and Implement | Completed
5003C | Transition Medicaid Administration from Counties to the State: Centralize MAGI Eligbility Determinations | Merged #11001
5004A | Centralize and automate eligibility and enrollment processes for the Medicare Savings Programs. | Suspended
5004B | Expand Aged, Blind, and Disabled Automated Renewals | Cancelled
5004C | Asset Verification System (AVS) | Merged #11001
5004D | Automate Spend Down | Cancelled
5004E | Address Vulnerable Population Consumer Assistance Needs | Completed
5005 | Improve Access to Emergency Medicaid | Completed
Behavioral Health Reform Work Group
5101 | Create Risk-Bearing Managed Care Entities for High-Need Behavioral Health Populations | Completed
5101A | Identify/Develop Mechanisms for improving behavioral health screening and treatment in primary care settings | Completed
5101B | Implement Joint licensure for clinics | Completed
5101C | Care coordination model for children with behavioral health needs | Merged 1115 Phase 7
MLTC Implementation & Waiver Redesign Work Group
5201 | Quality Measures for CCM Performance | Merged #5602
5202 | Improve Fair Hearing Process | Merged #7003
5203 | Workgroup on integration of self-directed program models | Completed
Health Disparities Work Group
5301 | Data Collection/Metrics to Measure Health Disparities | Completed
5302 | Improve Language Access to improve disparities | Completed
5303 | Promote Language Accessible Prescription Labels | Completed
5304A | Chronic Disease Preventive Services: Diabetes | In Waiver
5304B | Chronic Disease Preventive Services: Asthma | In Waiver
5304C | Chronic Disease Preventive Services: Lead Poisoning | In Waiver
5304D | Chronic Disease Preventive Services: Automated blood pressure cuffs for home use | Completed
5305 | Streamline and Improve Access to Emergency Medicaid | Merged #5005
5306 | Address Disparities in Treatment at Teaching Facilities | Cancelled
5307A | Expand access for contraception and other family planning services | Cancelled
5307B | Expand Medicaid coverage for inter-conceptional care | Cancelled
5307C | Expand Medicaid coverage to include breastfeeding education and lactation counseling and provide financial incentives to hospitals to provide breastfeeding support | Merged #5402D
5307D | Support initiatives to demonstrate effective and efficient use of HIT technology to improve care delivery for women and infants | Completed
5308 | Address Disparities through Targeted Training for NYS Health Care Workforce | Cancelled
5309 | Enhance Services for Youth in Transition with Psychiatric Disabilities | Merged #5101C
5310 | Promote Effective Use of Charity Care Funds | Merged #5603
5311A | Design an integrated HCV disease management initiative for HCV screening, care and treatment, and other supports in a variety of treatment settings: primary care clinics, HIV clinics and OASAS clinic programs. Include in Medicaid managed care plans chronic disease infrastructure. | Completed
5311B | Promote Hepatitis C Care and Treatment through Service Integration: Primary Care Settings | Completed
5311C | Promote Hepatitis C Care and Treatment through Service Integration: Health Home Expansion | Merged Ph 4, Health Home Plan
5312 | Promote Full Access to the Mental Health Medication on the Medicaid Formulary | Merged #5914
5313 | Medicaid Support of Water Fluoridation | Completed - Implemented through enacted Budget 2015-2016
5314A | Medicaid Coverage of Harm Reduction Activities: Clarify Regulations | Completed
5314B | Medicaid Coverage of Harm Reduction Activities: OASAS Provider Reimbursement | Completed
5314C | Medicaid Coverage of Harm Reduction Activities: AI providers reimbursement | Merged #8021
5315 | Expand HIV SNPs enrollment to include non-HIV high-need/high-cost populations (e.g., homeless) | Completed
Basic Benefit Review Work Group
5401 | Benefit Review Process | Completed
5402A | Podiatry for Diabetics | Completed
5402B | Knee Arthroscopy | Completed
5402C | Back Pain Treatments | Completed
5402D | Breastfeeding Support | Completed
5402E | Percutaneous Coronary Intervention (PCI) | Completed
5402F | Reduce payments for elective Cesarean sections and inductions | Completed
5402G | Growth Hormone | Completed
5402H | Tobacco Cessation Counseling by Dentists | Completed
5403A | Obesity Treatment | Cancelled
5403B | Nurse Family Partnership (NFP) | In Waiver
Workforce Flexibility/Change of Scope of Practice Work Group
5501 | Advisory Committee to the Office of the Professions of the State Education Department. | Cancelled
5502A | Advanced Aides | Cancelled
5502B | Advanced Home Care Aide Certification | Cancelled
5502C | Remove collaboration practice agreement requirement for Certified Nurse Practitioners | Completed
5502D | Collaborative Practice of Dental Hygienists/Definition of Dental Hygiene | Completed
5502E | Removal of physician supervisory ratio of physician assistants (PAs) | Completed
5502F | Children’s Dental Health Certificate | Completed
5503A | Standing Orders/Physician Practice Protocols | Cancelled
5503B | Enable physician home visits | Cancelled
5503C | Stackable certification and credentials for direct care workers | Cancelled
5504 | New York State Primary Care Service Corps (PCSC) | Completed
5505 | Exempt license requirement for certain titles in NYS agencies | Suspended
5506 | Promote programs such as CDPAP | Completed
Payment Reform & Quality Measurement Work Group
5601 | Integrate Medicaid & Medicare service delivery and financing | Merged #90
5602 | Quality Measurement | Completed
5603 | Indigent Care Funding Program Reform | Completed
5604 | Essential Community Provider Network &Vital Access Providers | Merged #67
Affordable Housing Work Group
5700 | Re-engage the MRT Affordable Housing Work Group | Completed
5701 | New York/New York IV Agreement | Merged #5700
5702 | Establish dedicated fund for supportive housing development | Completed
5703 | Provide immediate support to supportive housing development. | Completed
5704 | Unfreeze OMH capital funding | Completed
5705 | Increase set-asides and incentives for supportive housing | Merged #5700
5706 | Include funds for ongoing services and operating costs in MRT 1115 Medicaid Waiver | In Waiver
5707 | Pilot "Social Impact Investment Bonds" for supportive housing | Merged #5700
5708 | Improve interagency coordination of supportive housing policy and implementation | Merged #5700
5709 | Establish a work group to identify and improve the supportive/affordable housing capital development process | Completed
5710 | Evaluate perceived barriers to maximizing existing resources and expanding opportunities | Merged #5700
5711 | Identify and resolve barriers to transitioning individuals to supportive housing; Establish “Moving On” initiative | Merged #5700
5712A | Registered Nurse Assessment for ALP services. | Completed
5712B | Increase ALP Reimbursement | Completed
5712C | Establish Post-Admission Audits for ALP enrollment | Completed
5712D | Nursing Home Beds/ALP | Completed
5712E | Lift CHHA moratorium | Completed
5712F | LHCSA Aides scope of practice | Completed
5712G | ALP/CHHA/LTHHCP Contracting | Completed
5712H | ALP & Therapy Services | Completed
5712I | ALP Survey Process | Completed
5712J | ALP Program Forum to evaluate implementation | Completed
5713 | Co-Locate Community Health Centers for Supportive Housing Residents | Cancelled
5714 | Notice and best effort education | Completed
5715 | Expand and improve independent senior housing opportunities | Merged #7106
5716 | Maintain housing subsidies and focus of NHTD/TBI Waivers | Merged #5700
5717 | Medical Respite for homeless individuals | Completed
5718 | Coordinate supportive housing with Health Homes Initiative | Merged #89
Catch-All Workplans
5901 | Payment for Enteral Formula with Medical Necessity Criteria (Revision) | Completed
5902 | EQUAL Program | Completed
5903 | Emergency Department Triage | Completed
5904 | Stakeholder Consultation for Nursing Home Capital Reimbursement | In Waiver
5905 | Workgroup on Medically Fragile Children | Completed
5906 | Limited Administrative Review (FQHC) | Completed
5907 | Exclusive Pharmacy Network Criteria in Managed Care | Cancelled
5908 | Rural Telehealth Demonstration | Completed
5909 | Doctors Across New York Physician Loan Repayment and Physician Practice Support | Completed
5910 | Prescriber Prevails in Managed Care | Completed
5911 | EPIC Coverage Expansion | Completed
5912 | Reduction of APG Hospital Investment by $25M | Completed
5913 | Promote Full Access to the Mental Health Medication on the Medicaid Formulary | Completed
Phase 2
|  | Cancelled | 15
|  | Completed | 66
|  | Merged | 23
|  | Included in MRT Waiver | 6
|  | Substantively complete | 0
|  | Suspended | 2
|  | In Progress | 0
|  | Total | 112
|  |  | 1.786% | Remain open