## Ph 3 Catch-All
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2013-2014 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
As of: | 2018-05-23
6001 |  |  |  |  | Project Name: Gold STAMP Program to Reduce Pressure Ulcers Division Lead: Division of Nursing Homes and ICF/IID Surveillance, Center for Health Care Quality and Surveillance Team Lead: Jackie Pappalardi Additional Staff: Paula Grogin, Rick Rees, Elizabeth Coppernoll, Angela Frimpong Description: Promote collaboration and communication within the continuum of care, provide information and education regarding evidence-based practices and provide strategic direction and support for pressure ulcer performance management. | 26.0 | Completed - Moved to Phase 4 Gold STAMP activities are carried out through an MOU with the University at Albany School of Public Health
| 2013-05-23 | P | P | P | Plan and convene a one-day general meeting for Collaboratives.
| 2013-06-30 | P | P | P | Consolidate the currently discrete activities of Gold STAMP partners into a broad functional structure which allows for the collaborative development of an ideal Gold STAMP model.
| 6/30/13 8/31/13 | P | P | P | Develop six new Collaboratives in areas of the State that are not represented or among those facilities with the highest prevalence of pressure ulcers.
| 2013-09-17 | P | P | P | Collaborate with Foundation for Quality Care, Inc. in hosting a Statewide Gold STAMP Conference.
| 2013-12-31 | P | P | P | Establish universal Gold STAMP website.
| 2013-12-31 | P | P | P | Review/compare evaluations of the impact of Gold STAMP and analyze the effectiveness of specific interventions.
| 12/31/13 3/31/14 6/30/14 | P | P | P | Develop a listing of recommended best practices as appropriate for integration into an ideal Gold STAMP model.
| 2014-03-31 | P | P | P | Produce four webinars/webcasts on education topics related to prevention and care of pressure ulcers and post to Gold STAMP website.
| 2014-03-31 | P | P | P | Continue to support the six previously established Collaboratives when necessary or requested.
| 3/31/14 6/30/14 | P | P | P | Begin development of a Gold STAMP best practice model.
6002 |  |  |  |  | Project Name: Balancing Incentive Program (BIP) Division Lead: Mark L. Kissinger DLTC Team Lead: Karen M. Ambros Additional Staff: Phyllis Howard Laurie Lucinski Description: Administrative Requirements - Develop Final Work Plan |  | Merged -#8010
| 5/31/13 | P | P | P | Prepare and send CMS answers to their questions.
| 6/13/13 6/20/13 | P | P | P | Participate in training webinar conducted by TA.
| 7/5/13 8/2/13 8/15/13 9/13/13 | P | P | P | Hire BIP project manager (IPRO).
| 7/31/13 8/12/13 | P | P | P | Prepare first draft of detailed work plan (CMS format).
| 8/8/13 8/19/13 | P | P | P | Revise work plan based on interagency comments.
| 8/21/13 | P | P | P | Submit final draft to Chamber, DOB.
| 8/30/13 | P | P | P | Submit to CMS.
| 9/30/13 10/30/13 10/29/13 | P | P | P | CMS to submit feedback on the work plan with request for response.
| 10/17/13 11/17/13 11/12/13 | P | P | P | Agency's submit their responses to DOH.
| 10/18/13 11/18/13 11/15/13 | P | P | P | DOH compiles Agency responses.
| 10/21/13 11/21/13 11/15/13 | P | P | P | DOH distributes compiled response to agencies, DOB and Chamber for their review.
| 10/23/13 11/23/13 11/20/13 | P | P | P | Agency's, DOB and Chamber send their final changes to DOH.
| 10/25/13 11/25/13 | 8 | 8 | 8 | DOH submits final draft to Chamber, DOB for review.
| 10/30/13 11/30/13 11/22/13 11/25/13 | P | P | P | Work plan response submitted to CMS.
| 12/11/13 | P | P | P | Work plan response re-submitted to CMS.
| 1/24/14 | 8 | 8 | 8 | Work groups submit their qtrly progress reports to DOH.
| 1/29/14 | 8 | 8 | 8 | DOH compiles work groups qtrly progress report.
| 1/30/14 | 8 | 8 | 8 | DOH distributes compiled qtrly progress to agencies for their review.
| 2/5/14 | 8 | 8 | 8 | Agency's send their final changes to DOH.
| 2/7/14 | 8 | 8 | 8 | DOH submits final Draft to Chamber, DOB
BIP REPORTING DELIVERABLES
| 1/29/14 | P | P | P | BIP team completes orientation/training for on-line reporting
| 2/21/14 | P | P | P | Qtrly on-line progress report due to CMS
| 5/15/14 | P | P | P | Qtrly on-line progress report due to CMS
| 7/1/14 | P | P | P | Monitoring Plan to CMS
| 7/25/14 8/19/14 | P | P | P | NYS response to CMS questions on monitoring plan
| 8/15/14 | P | P | P | Qtrly on-line progress report due to CMS
| 9/1/14 | P | P | P | Projected Expenditures (and other documents) through 9.8.14 due to CMS
| 9/25/14 | P | P | P | NYS Response to CMS questions on Qtrly on-line progress report
| 11/1/14 | P | P | P | Monitoring Plan FQE 9.30.14 to CMS
| 11/15/14 | P | P | P | Qtrly on-line progress report due to CMS
| none given | P | P | P | Responses to CMS questions on Q3 on-line progress report.
| 2/17/15 | P | P | P | Qtrly on-line progress report due to CMS for 12/31/14
| 5/15/15 5/27/15 | P | P | P | Qrtly on-line progress report due to CMS for 3/31/15
| 2015-07-01 | P | P | P | Budget vs. Revised budget with requests for extension requests to CMS. Includes projected expenditures through 9/30/17 with sustainability. |  | Sent to CMS on 6/26/15
| 2015-07-31 | P | P | P | BIP Monitoring Plan due to CMS |  | Sent to CMS on 7/31/15
| 2015-08-14 | P | P | P | Qrtly on-line progress report due to CMS for 6/30/15 |  | Submitted on 8/14/15
| 2015-11-06 | P | P | P | BIP Monitoring Plan due to CMS |  | Sent to CMS on 11/12/16
| 11/30/15 12/1/15 | P | P | P | Qrtly on-line progress report due to CMS for 9/30/15 |  | CMS approved extension. Sent on 12/1/15
BIP WORK PLAN DELIVERABLES
IMPLEMENT NO WRONG DOOR/SINGLE ENTRY POINT (NWD/SEP) STRUCTURE
| 2013-08-30 | P | P | P | Design system (initial overview)
| 2013-08-30 | P | P | P | Identify the Operating Agency (DOH is operating agency)
| 2013-08-30 | P | P | P | Identify potential NWD/SEP entities/locations. Need to finalize.
| 2013-08-30 | P | P | P | Identify or develop URL for website
| 4/1/14 | P | P | P | Design system (final detailed design)
| 4/1/14 6/1/14 7/1/14 1/1/15 3/15/15 5/15/15 7/31/15 | P | P | P | Develop and implement MOU across agencies
| 2014-05-31 | P | P | P | Assure NWD/SEPs are accessible to older adults and individuals with disabilities |  | Completed, will be reported in the On line qtrly report due to CMS 8.15.14
| 2015-02-17 | P | P | P | Stakeholder engagement activities; developing materials for stakeholder engagement across agency's and their populations and (including individuals) for the NWD/SEP proposal
| 06/15/14 11/15/14 2/15/15 | P | P | P | Develop standardized informational materials for NWD/SEP
| 7/15/14 2/1/15 4/9/15 6/30/15 9/30/15 | P | P | P | Develop and incorporate content for URL
| 08/14/14 1/15/15 3/31/15 5/15/15 9/25/15 2/1/16 | P | P | P | Train all participating agencies/staff on eligibility determination and enrollment
| 08/31/14 12/1/14 2/9/15 | P | P | P | Select vendor for system build
| 2014-09-30 | P | P | P | Develop advertising plan for NWD/SEP system
| 2014-11-01 | P | P | P | Incorporate the consumer initial (Level I) screen into the website (recommended, not required)
| 11/1/14 2/15/15 | P | P | P | Contract 1-800 number service | Done. Will be submitted with Quarterly Report due 2/17/15. NY Connects will use Senior Help Line 1-800# with enhanced features. Submitted with Quarterly Report on 2/17/15.
| 8/14/14 1/15/15 3/31/15 5/15/15 9/25/15 2/1/16 | P | P | P | Train staff on answering phones, providing information and conducting the Level I screen
| 12/31/14 8/31/15 | P | P | P | Implement advertising plan
| 2015-01-01 | P | P | P | Identify service coverage of all NWD/SEPs
| 2/28/15 3/31/15 5/15/15 | P | P | P | Implement and test system Description of Pilot Roll-out.
| 8/31/15 9/30/15 | P | P | P | System goes live |  | Includes new website, resource directory and expanded network.
| semi annual after 8/31/15 | 8 | 8 | 8 | System updates
DEVELOP CORE STANDARD ASSESSMENTS (CSA) WHICH INCLUDE THE CORE DATA SET (CDS) AND SUPPORTS ELIGIBILITY, NEEDS ASSESSMENT, AND SERVICE PLANNING PROCESSES.
| 2013-08-30 | P | P | P | Fill out CDS crosswalk to determine if current assessments include required domains and topics
| 2/28/14 7/15/14 10/15/14 2/15/15 | P | P | P | Identify qualified personnel to conduct the CSA
| 2014-03-31 | P | P | P | Incorporate additional domains and topics in CSA
| 2014-04-01 | P | P | P | Develop questions for Level I screen
| 08/14/14 1/15/15 3/31/15 5/15/15 9/25/15 10/27/15 | P | P | P | Train staff members at NWD/SEPs to coordinate the CSA
| semi-annual after 08/31/14 | 8 | 8 | 8 | Updates
ESTABLISH CONFLICT FREE CASE MANAGEMENT STANDARDS
| 2013-08-30 | P | P | P | Describe current case management system, including conflict-free policies and areas of potential conflict
| 07/1/14 12/31/14 3/15/15 | P | P | P | Establish protocol for removing conflict of interest
DATA COLLECTION AND REPORTING
| 2013-08-30 | P | P | P | Identify data collection protocol for service data
| 2013-08-30 | P | P | P | Identify data collection protocol for quality data
| 2013-08-30 | P | P | P | Identify data collection protocol for outcome measures
| 2014-02-28 | 8 | 8 | 8 | Report updates to data collection protocol and instances of service data collection
| 2014-02-28 | 8 | 8 | 8 | Report updates to data collection protocol and instances of quality data collection
| 2014-02-28 | 8 | 8 | 8 | Report updates to data collection protocol and instances of outcome measurers collection
SUSTAINABILITY
| 2013-08-30 | P | P | P | Identify funding sources to implement structural changes
| 2013-08-30 | P | P | P | Describe planned usage for the enhanced funding
| 2014-08-31 | P | P | P | Develop sustainability plan
| 2/1/15 4/1/15 7/1/15 | 8 | 8 | 8 | Sustainability plan update to correspond with NYS budget process
| 4/1/15 7/1/15 | P | P | P | Sustainability plan update to correspond with NYS budget process
EXCHANGE IT COORDINATION
| 2014-02-28 | 8 | 8 | 8 | Provide updates on coordination, including the technological infrastructure
| 2014-04-01 | P | P | P | Describe plans to coordinate the NWD/SEP system with the Health Insurance Exchange IT system
6003 |  |  |  |  | Project Name: Federal Revenue from Additional Emergency Medicaid Claiming and Other Possible Efforts Division Lead: DFRS Team Lead: Phil Mossman Additional Staff: Maria Payne, Woo Hwang, FMG Description: Aliessa population is claimed as FNP except for emergency services. However, none of the emergency services provided to Aliessa individuals in a managed care setting are claimed as FP. This project will identify and submit these services to FP. |  | Completed - Dec 2013
| 2013-03-01 | P | P | P | Complete fiscal analysis for calendar years 2011/2012 and begin discussions with CMS
| 2013-06-15 | P | P | P | Request formal approval and waiver of two year claim limitation from CMS
| 2013-06-30 | P | P | P | Submit claim for federal match for calendar years 2011 and 2012
| 9/30/13 12/31/13 | P | P | P | Submit claim for federal match for January 1-March 31, 2013
| 10/1/13 11/1/13 3/1/14 | P | P | P | Establish separate premium groups for Aliessa individuals to be effective April 1, 2013
6004 |  |  |  |  | Project Name: PCMH Savings Division Lead: DPDM Team Lead: Greg Allen Additional Staff: Description: Eliminate payments for 2008 PCMH recognized Level 2 providers and reduce payments from $6 pmpm to $5 pmpm for 2008 PCMH recognized Level 3 providers. Assumes that some providers will meet 2011 standards to receive incentive payment. |  | Completed - January 2014
| 9/16/13 | P | P | P | Final approval of Functional Review Document (FRD) to implement EP 1817 sent to CSC
| 10/1/13 1/1/14 5/22/14 | P | P | P | Evolution project to edit the eMedNY to implement PCMH changes into the system (System Test scheduled for 3/24/13)
6005 |  |  |  |  | Project Name: Increase Efficiency of Transportation Utilization by Transportation Manager Division Lead: Div of Program Development and Management Team Lead: Mark Bertozzi Additional Staff: Tim Perry-Coon, Heidi Seney, Lani Rafferty Description: Achieve savings in transportation management by accelerating migration to livery and public transportation as appropriate. Improve quality and transportation through administrative actions against low performing providers. |  | Completed - April 2013
| 1/30/13 | P | P | P | Develop livery and other lower cost alternatives to transportation with Transportation Managers
| 2/1/13 | P | P | P | Identify initial group of low performing transportation providers
| 2/16/13 | P | P | P | Transportation Manager to hire Utilization Review manager
| 2/20/13 | P | P | P | Provide information on low performing transportation providers to DLA, OHIP Operations and OMIG
| 3/1/13 | P | P | P | Ambulatory assessment of transportation use and needs
| 3/5/13 | P | P | P | Initial meeting with OHIP Operations and OMIG staff to discuss evidence based performance records of selected providers
| 3/22/13 | P | P | P | Reach agreement with OMIG on administrative actions against low performing transportation providers
| 4/1/13 | P | P | P | Take administrative action against low performing transportation providers
| 4/1/13 | P | P | P | Begin implementation of lower cost modes of transport
6006 |  |  |  |  | Project Name: Managed Care Efficiency Adjustment Division Lead: Division of Finance & Rate Setting/Bureau of Managed Care Reimbursement Team Lead: Megan Ryan Joe Naglieri/Mike Dembrosky Additional Staff: Phil Mossman/Stephanie Fargnoli Connor Gemerek, Nick Cioffi, Mike Ogborn Description: Generate $50M gross savings ($25M State share) by implementing Plan specific quality rate adjustment in Managed Care premiums | $25.00 | Merged: will be reflected in ongoing VBP tracking
DATA ANALYSIS
| 4/19/13 | P | P | P | Complete plan specific & regional analysis on Inpatient metrics (PQIs, PPRs, PPCs)
| 7/12/13 7/26/13 8/30/13 10/30/13 10/10/13 | P | P | P | Aggregate all quality metrics on a plan specific & regional basis
EDUCATION
| 4/1/13 | P | P | P | 3M webinar with the Plans on the 3M suite of potentially preventable metrics
| 6/26/13 7/18/13 8/15/13 9/19/13 11/15/13 10/17/13 | P | P | P | Present ambulatory metrics to the Plans at Monthly Policy and Planning Meeting or a separate webinar
| 6/26/13 7/18/13 8/15/13 9/19/13 | 8 | 8 | 8 | Present PPC analysis to the Plans at Monthly Policy and Planning Meeting
| 6/26/13 7/18/13 8/15/13 9/19/13 11/15/13 10/17/13 | P | P | P | Present aggregated plan specific & regional information and discuss approaches to incorporate into the premiums at the Monthly Policy and Planning Meeting or an interim meeting
METHODOLOGY/RATE DEVELOPMENT
| 7/12/13 7/26/13 8/30/13 9/30/13 11/29/13 1/1/14 2/1/14 5/1/2014 12/1/14 1/30/15 | P | P | P | Discuss/determine interaction with other quality metrics currently reflected in the premiums
| 7/12/13 7/26/13 8/30/13 9/30/13 11/29/13 1/1/14 2/1/14 5/1/14 12/1/14 1/30/16 8/15/15 12/1/15 1/1/16 1/1/17 | 8 | 8 | 8 | Discuss/determine whether aggregate or individual metrics will be utilized and how they will be treated in determining Plan's adjustment
| 7/12/13 7/26/13 8/30/13 9/30/13 11/29/13 1/1/14 2/1/14 5/1/14 12/1/14 1/30/17 | 8 | 8 | 8 | Discuss/determine whether benchmark for adjustment will be Statewide, Regional or a percentage of the same
| 7/12/13 7/26/13 8/30/13 9/30/13 11/29/13 1/1/14 2/1/14 5/1/14 12/1/14 1/30/18 8/1/15 12/1/15 2/1/16 2/1/17 | 8 | 8 | 8 | Discuss/determine the frequency of future updates and update to the base data
| 7/12/13 7/26/13 8/30/13 9/30/13 11/29/13 1/1/14 2/1/14 5/1/14 12/1/14 1/30/22 8/15/15 12/1/15 2/1/16 2/1/17 | 8 | 8 | 8 | Discuss/determine whether a performance incentive will be considered in future adjustments
| 7/12/13 7/26/13 8/30/13 9/30/13 11/29/13 1/1/14 2/1/14 5/1/14 12/1/14 1/30/20 8/15/15 12/1/15 2/1/16 2/1/17 | 8 | 8 | 8 | Discuss/determine how the adjustment will be incorporated into the premium
| 7/12/13 7/26/13 8/30/13 9/30/13 11/29/13 1/1/14 2/1/14 5/1/14 12/1/14 1/30/22 8/15/15 12/1/15 2/1/16 2/1/17 | 8 | 8 | 8 | Decide how new adjustment will interact with the existing Mercer efficiency adjustment (LANE, PPA) and the impact on the 2% ATB
| 7/12/13 7/26/13 8/30/13 9/30/13 11/29/13 1/1/14 2/1/14 5/1/14 12/1/14 1/30/22 8/15/15 12/1/15 2/1/16 2/1/17 | 8 | 8 | 8 | Complete modeling the adjustment by Plan; by region
| 7/19/13 8/2/13 | 8 | 8 | 8 | Provide data to Mercer for consideration in the rate range
| 8/9/13 | 8 | 8 | 8 | Mercer to provide rate range information to the Department
| 3/1/15 8/15/15 12/1/15 2/1/16 2/1/17 | 8 | 8 | 8 | DOH to complete premium build up with the efficiency adjustment
| 3/17/15 9/1/15 1/1/15 1/1/16 3/1/16 3/1/17 | 8 | 8 | 8 | Provide rates to DOB and CMS for approval
| 3/17/15 9/1/15 1/1/15 1/1/16 3/1/16 3/1/17 | 8 | 8 | 8 | Brief plans on premiums, which will include the efficiency adjustment
| 4/1/15 10/1/15 4/30/15 4/1/16 4/1/17 | 8 | 8 | 8 | Receive DOB and CMS approval
| 4/1/15 10/1/15 4/30/15 4/30/16 4/30/17 | 8 | 8 | 8 | Transmit October April 2016 Rate package to EMedNY for payment
DEBRIEF/NEXT STEPS
| Complete | P | P | P | Pulling data for metrics
| Ongoing | 8 | 8 | 8 | Running metrics
| Ongoing | 8 | 8 | 8 | Collapsing metrics
| Ongoing | 8 | 8 | 8 | Update/refine methodology for future adjustment
6007 |  |  |  |  | Project Name: Reduce Accounts Receivable Balances Division Lead: John Ulberg/Ann Foster Rebecca Corso DFRS Donna Cater Team Lead: Adele Compton, Phyllis Stanton, , John Gahan Mark Shutts Kevin Wright Additional Staff: Adele Compton, Donna Choiniere, , Tim Casey, Jason Corvino, Terry Provost, Steve Simmons , Kenny Ferro, Bob Loftus from MFM Peter LaVenia, Laura VanValkenburg, Matt Lomaestro Description: Implement an aggressive recovery program to reclaim Accounts Receivable liabilities from providers by March 31, 2015 and March 2016 March 2017 December 2017 for high balance providers . | $50.0 $300M $152 | Merged June 2017 10204
| 2013-02-22 | P | P | P | Develop a summary document which outlines the specifics of the proposal and circulate to DOB/FMG for review and comment.
| 2013-02-22 | P | P | P | Meet with DOB and FMG to assess the feasibility of the proposal. Decide if statute is required or if proposal can be implemented administratively.
| 4/1/13 6/1/13 | P | P | P | Compile a list of current Accounts Receivable balances by provider and the payment option selected by each.
| 4/30/13 6/20/13 7/11/13 | P | P | P | Distribute a letter to notify providers about the change in the State's collection policy and the date by which they will must notify DOH which payment option they select (due date August 16, 2013) .
| 7/31/13 9/30/13 | P | P | P | Finalize all provider collections for Option #1 - paid in full by 9/01/13 (interest waived).
| 2013-09-16 | P | P | P | Reported Collections to date provided to Division: Option #1: 42 providers submitted $36.6M for 100% interest abatement; Option #2: 5 providers have indicated their intent to full pay by 3/31/13 for 1/2 of interest abatement totaling $6.3M
| 2013-10-16 | P | P | P | Reported Collections to date - Option #1 43 providers, $62M paid to date. All providers who selected Option 1 have paid as agreed.
| 10/15/13 11/1/13 12/1/13 2/1/14 3/15/14 | P | P | P | Prepare 2nd letter to all providers, summarizing collections to date, annual target, & outline of Departments next steps.
| 2014-01-27 | P | P | P | Prepare letter to top 16 delinquent providers to set up meetings to discuss their large liabilities currently in Medicaid recoupment and negotiate repayment terms for full payment by March 2016. Letter mailed 1/27/14
| 12/1/13 2/1/14 | P | P | P | Contact top 25 16 providers/set up meetings to negotiate re-payment agreement. 6 Meetings set up and/or held week ending Fri Feb 21
| 2014-03-01 | P | P | P | March 1, recoupment will be suspended for those Option #2 providers; payoff figures issued to providers and await receipt of money
| 2014-03-31 | P | P | P | Finalize all provider collections for Option #2 paid in full by 3/01/14 (50% interest waived).
| 2014-05-19 | P | P | P | Focus is on top 16 providers that owe us over $3m. Proposals received and reviewed. No determination has been made on the ones that seem reasonable but not within the two year target date of March 2016. Emphasis is now to determine whether these facilities should stay open. Working with CON and nursing home surveillance unit (Jackie Pappalardi) for input.
| 5/27/14 7/28/14 | P | P | P | Expected date of CON and Surveillance Unit review and recommendations - Not Received
| 2014-09-16 | P | P | P | Dan Sheppard and Charlie Abel to provide input on letter to 5 CHHAs and 4 of the top 16 providers increasing their Medicaid recoupment %.
| 2014-09-12 | P | P | P | Discussed with DLA options for collection of Bankrupt facilities, legislation changes
| 2014-09-16 | P | P | P | 4-5 high liability facilities to be discussed in more detail with Dan Sheppard and Courtney
| 3/31/15 March 2017 | 8 | 8 | 8 | Finalize all provider collections for Option #3.
TOP 18 30 PROVIDERS
| 2014-01-27 | P | P | P | Identified top 18 Providers
|  | P | P | P | Obtain most current Balance from MFM, by MMIS#
| 9/15/15 11/15/15 01/15/16 | P | P | P | Negotiate with each provider that does not have an existing agreement for a two year repayment plan; set up meetings to discuss - 15 agreements are final; 2 are paid
| 2015-01-15 | P | P | P | Calculate weekly recoupment $$ amount needed to full pay by March 2017
| 2015-03-01 | P | P | P | Create repayment agreement, previously approved by DLA; send to provider for their signature
| 2015-03-31 | P | P | P | Send signed agreement to DOH Deputy Director for signature and return to provider
| 2015-04-01 | P | P | P | Notify MFM of completed agreements and terms. MFM to initiate recoupment amounts as soon as practible.
| 2016-06-01 | P | P | P | Top 18 increased to Top 30. Letters mailed 5/27/16 to 16 providers without agreements requesting conference call.
| 7/29/16 12/31/16 3/31/17 8/31/17 | 8 | 8 | 8 | Hold Conference Call Meetings with providers in top 30 to arrange payment plans.
| 3/31/2017 8/31/2017 | 8 | 8 | 8 | Review collections and determine next steps for those not fully recouped.
| 2017-07-01 | 8 | 8 | 8 | Review current A/R list and determine 13 additional providers to add to top 30 group - initiate conference calls to negotiate repayment
ALL OTHER PROVIDERS (EXCEPT NURSINGHOMES AND OPWDD) OWING RETRO RATE AND HFCAP- LETTER SENT FEB 11, 2015 TO THOSE THAT OWE AND CANNOT FULL PAY BY MARCH DECEMBER 2017
| 2015-02-11 | P | P | P | Issued letter in Feb 2015 informing each provider owing $$, that could not full pay at the current rate by March 2017, to submit a repayment proposal within 14 days. Failure to do so resulted in increased recoupment % that would ensure full pay by March 2017
| 2015-02-11 | P | P | P | Letter sent to 300+ targeted facilities with a Medicaid liability to submit a proposal to pay back debt within 2 years. Due date of proposal is 2/27/15. Those without a response - increase recoupment to ensure 2 yr. payback.
| 2015-02-11 | P | P | P | 2/11/15 letter also notifies facilities that effective 4/1/15, all new liabilities were be recouped within 12 months
| 3/1/15 4/15/15 5/15/15 | 8 | 8 | 8 | Letter to be sent to 400+ OPWDD facilities with a Medicaid liability to submit a proposal within 14 days to pay back debt within 2 years. Those without a response - increase recoupment to ensure 2 yr. payback.
| 3/1/15 4/15/15 5/15/15 | 8 | 8 | 8 | OPWDD letter will also notifies facilities that effective 4/1/15, all new liabilities were be recouped within 12 months Part of mailing described in next row completed 6/17/15
| 5/15/15 6/17/15 | P | P | P | Letter to be mailed to all provider types and plans that receive a Medicaid rate that all new retroactive rate liabilities or Health Facility Cash Assessment liabilities must be full paid with 12 months; recoupment percentage will be increased to ensure that it will be full paid within that time period. Provider letter to be mailed stating all Medicaid retro rate and Cash Asmt liabilities processed thru eMedNY August 1st 2015 and forward will have a recoupment percentage calculated that will full pay within 12 months.
| 2015-06-17 | P | P | P | Those providers that did not submit a payment proposal from our Feb 2015 letter will get a letter increasing their recoupment percentage to a percentage that will full pay by March 2017. Letter to go out today, 6/17. 41 Providers totaling $9M
PROVIDERS WHO SUBMITTED PROPOSALS
|  | P | P | P | Accept those with proposals full paying by March 2017 that require an increase in recoupment percentage
|  | P | P | P | For those accepted proposals that cannot be fully paid by March 2017 through increasement in recoupment percentage, and require all or additional money to be mailed to MFM, create a written payment agreement for provider signature
|  | P | P | P | Send signed agreement to DOH Deputy Director for signature and return to provider
|  | P | P | P | Renegotiate with those that submitted proposals but will not full pay by March 2017
|  | P | P | P | Notify MFM of agreement details, on a weekly basis as requested by MFM, providing info on increased recoupment amount or percentage, and to initiate with next available cycle.
PROVIDERS THAT DID NOT SUBMIT PROPOSAL
|  | P | P | P | Identify those providers who did not submit proposal, determine what percentage will be necessary to ensure full payment by March 2017, based on updated avg weekly Medicaid cycle payment report from MFM.
| 2015-06-17 | P | P | P | Send letter informing provider that their failure to respond or commit to an agreement to full pay by March 2017 results in their recoupment percentage to be increased to ensure payment by March 2017.
| 2015-06-17 | P | P | P | Include an enclosure with letter that lists the facility name, the current recoupment percentage, and the new recoupment percentage.
| 2015-06-20 | P | P | P | Provide MFM with list of those we are increasing their recoupment percentage and the new percentage amount, due to failure to enter into an agreement to full pay by March 2017
| 2016-06-01 | P | P | P | Letters mailed 6/1/16 to 34 providers without agreements requesting payment proposals within 14 days. If no response with increase recoup to percent that will full pay by March 2017 or 100% whichever is less.
| 9/22/15 11/15/15 1/15/16 4/1/16 8/31/16 | P | P | P | Hold Conference Call Meetings with providers to arrange payment plans.
| 2016-08-31 | P | P | P | Increased recoupment rates to provide full payment by 12/17
| 2016-12-31 | P | P | P | OPCHSM to determine essential vs non essential providers - Received NH & Clinics 12/16 - waiting for Home Care
| 2016-12-31 | P | P | P | Send 2nd final notice to 70 providers who did not comply to 11/16 letter - give 5 days to respond - no response increase recoup rate.
| 4/1/16 3/31/17 | P | P | P | Review collections and determine next steps for those not fully recouped. Increased recoupment rate 2/01/17 for providers who did not establish agreement.
PROVIDERS WITH NEW LIABILITIES (AFTER FEB 2015)
| 2015-06-05 | P | P | P | Identify those that owe RR and HFCAP, that did not owe when February letter was sent
| 2015-06-23 | P | P | P | Send clone of February letter to providers that now owe RR and /or HFCAP.
| 7/15/15 9/15/15 | P | P | P | Request reports through MFM for updated balances - ongoing function.
| 7/20/15 9/15/15 | P | P | P | Accept those with proposals full paying by March 2017 that require an increase in recoupment percentage - ongoing function
| 7/20/15 9/15/15 | P | P | P | For those accepted proposals that cannot be fully paid by March 2017 through increasement in recoupment percentage, and require all or additional money to be mailed to MFM, create a written payment agreement for provider signature - ongoing function
| 2015-09-15 | P | P | P | Send signed agreement to DOH Deputy Director for signature and return to provider - ongoing function.
| 2015-09-15 | P | P | P | Renegotiate with those that submitted proposals but will not full pay by March 2017 - ongoing function
| 2015-09-15 | P | P | P | Notify MFM of agreement details, on a weekly basis as requested by MFM, providing info on increased recoupment amount or percentage, and to initiate with next available cycle - ongoing function.
NEW POLICY REQUIRING LIABILITIES BE REPAID WITHIN A 12 MONTH PERIOD
| 2015-06-17 | P | P | P | Email letter notifying the following active providers: hospitals, DTCs, home cares (CHHAs, LTHHCP, Personal Care Providers), hospice and foster care, that any new RRs and or HFCAP liabilities processed thru to MFM's FoxPro system, August 1, 2015 and forward, recoupment percentage will be calculated to full pay within a 12 month period.
| 2015-06-17 | P | P | P | Notify MFM of this letter
| 2015-09-22 | P | P | P | MFM notifies OHIP each week of all new RR liabilities (new HFCAP liabilities is known)
| 2015-09-22 | P | P | P | OHIP to establish a recoupment percentage on all new RR and HFCAP liabilities to provide full payment with a 12 month period utilizing MFM's quarterly list of each provider's average Medicaid claim cycle checks
| 2015-09-22 | P | P | P | OHIP to forward newly established recoupment percentages to MFM each week to implement against new RRs and HFCAPs
| 2015-09-17 | P | P | P | Identified top 30 (includes top 18)
| 9/22/15 11/15/15 1/15/16 4/1/16 12/31/16 | P | P | P | Negotiate with each provider that does not have an existing agreement for a two year repayment plan; set up meetings to discuss
| 4/1/16 12/31/16 | P | P | P | Review project progress and determine next steps - Continue to review new liabilities established and set rate to full pay within 12 months
UPDATE BUCKET LIST - IDENTIFY PROVIDERS WITH NEW LIABILITIES WHO WILL NOT FULL PAY BY 12/17 AT CURRENT RATE.
| 2017-05-01 | P | P | P | Mail collection letter to providers who now will not full pay by 12/17 at current rate, plus those that are open but not submitting claims.
| 2017-08-01 | 8 | 8 | 8 | Respond to letters, negotiate repayment agreements
6008 |  |  |  |  | Project Name: Reduce Accounts Receivable Balances (Part B) Division Lead: John Ulberg/Ann Foster Rebecco Corso DFRS, Donna Cater Team Lead: Adele Compton, Phyllis Stanton, Kevin Wright Rebecca Corso Mark Shutts Additional Staff: Adele Compton, Kevin Wright, Mark Shutts, Michelle Levesque, Donna Choiniere Bill Hogan, Laura Vanvalkenburgh, Matt Lomaestro, Peter LaVenia Bob Loftus James Demateo MFM, OPCHSM, DLA, OMIG, OMH, OPWDD Description: Implement a process to collect Accounts Receivable liabilities that currently do not have recoupment procedures in place. | $60M | Merged June 2017 10204
| 2/1/12 3/1/13 | P | P | P | Identify providers with liabilities that currently do not have a recovery structure in place.
| 2013-08-01 | P | P | P | Develop a list of Providers for Grp #1 (Change of Ownership) to determine which liabilities can be transferred to new owner
| 9/1/13 7/21/13 | P | P | P | Work with FMG and Counsel's Office on solutions for recovery methods.
| 11/1/13 12/1/13 2/1/14 2/10/14 | P | P | P | Implement recovery procedures for providers in group #1 (providers still in business, but is billing under a different provider i.d.) Assign staff to access DOH databases to retrieve new provider IDs; send letter to affected providers notifying them that there are outstanding liabilities under old provider ID#s. Work to transfer liabilities, as applicable, to provider's current provider ID#. Research is complete. New provider ID# is identified. Data provided to Bob Loftus from MFM. Bob to reach out to provider informing them of their liability from their old provider ID# before transferring liability to their new provider ID#.
| 12/1/13 2/1/14 3/15/14 | P | P | P | Submit Referral to Attorney General's Office to collect liabilities for providers in group #2 (providers no longer in business). $500 or more in liability - forward to the AG for collection
| 11/1/13 2/1/14 3/15/14 7/28/14 | P | P | P | Develop and implement provider-specific recovery plans for group #3 (providers with no recoupment percentage in the system) - send letter to provider explaining they appear to have outstanding liabilities, but at zero recoupment - allow them time to contact us to discuss; we will increase their recoupment percentage from zero, to a minimum of 15% if no response.
| 2014-05-13 | P | P | P | $25M of Uncollectables has been under the oversight of Bob Loftus of MFM
| 2014-05-13 | P | P | P | List has been actively worked on and new balance is approx. $25M. 25 providers represent $20M of the $25M balance
| 2014-05-13 | P | P | P | Expected actual receivable is more like $13M
| 2014-05-23 | P | P | P | Letter created and in review with DLA giving providers 30 days to pay or referral to AG
| 10/15/15 11/1/15 1/15/16 4/1/16 | P | P | P | For Federal share refund, CMS is waiting on justification from DOH on bypassing the AG. AG is giving push back on taking these uncollectable. MFM to write justification. Reached out to the AG and they may take these debts and if deemed uncollectible, will provide an affadavit needed to send to CMS for federal share refund. Mtg for 12/21/15 with the AG to discuss their decision.
| 7/1/14 8/15/14 4/30/15 6/15/15 | 8 | 8 | 8 | Refer to AG those providers who have not responded- asking for a quick turnaround 45-60 days
| 9/1/14 6/1/15 | 8 | 8 | 8 | Expected date of AG response to collection efforts
| 5/30/14 7/1/14 | P | P | P | Letter mailed to facilities
| 2014-07-31 | P | P | P | $66M of Uncollectables are being Reviewed as a possible AR Receivable - Uncollectables are either sitting on an unused Provider ID# or are suspended. Expected that only 1/3 is actually collectible
| 2/12/14 | P | P | P | Develop and implement provider-specific recovery plan for group #4 (Bankrupt providers). Research bankruptcy petition date, bankruptcy type (7 or 11) identify whether liabilities are pre-petition (and therefore not collectible) or post-petition and possibly collectible. Forward pre-petition liabilities to OAG and submit refund request to Feds for potential Federal match refund. Continue to investigate post petition liabilities and implement a recovery plan. Working with Bob Loftus of MFM on this initiative. As of 2/19/14, research has continued identifying liabilities.
| 2014-09-01 | P | P | P | $27M of $66M Uncollectible Bucket Considered to be Collectible
| 11/1/14 3/1/15 4/8/15 6/15/15 9/15/15 | P | P | P | Balance of $33M Pre-petition Bankruptcy liabilities; Approx. 1/3 of $33 Federal Refund expected (retro rate liabilities only)
| 2015-06-05 | P | P | P | Obtain updated AR list from MFM - Determine uncollectible receivables based on average weekly Medicaid claim ck and/or recoup % at 0 or 100%
| 2015-06-20 | P | P | P | Identify providers with alternative active mms#s from average Medicaid claim cycle list from FMG.
| 2015-06-29 | P | P | P | Send list to MFM of adjustments to Foxpro moving liabilities on inactive MMIS#s to active MMIS#
| 2015-07-01 | P | P | P | Send list to MFM of adjustments for out of state providers to 100% recoupment.
| 2015-07-21 | P | P | P | Identify closed providers. Determine if acquired by new provider, if new provider is responsible for debts. Send list to MFM of adjustments from old provider mmis# to new mmis# for those acquired and responsible.
| 2015-07-15 | P | P | P | Discussed with CMS about alternative to AG signed affidavits to deem debts of closed providers uncollectible, to receive CMS approval for federal share refund on retro rate unpaid liabilities.
| 2015-07-21 | P | P | P | DLA to develop an alternative for CMS acceptance
| 10/15/15 1/15/16 4/1/16 6/2/16 | P | P | P | Work with DLA and AG on pre-petition bankruptcy debts to determine if settlement pmt was rcvd, and/or obtain affidavit to obtain Fed share refund. Write off balance. Part of AG Uncollectible Discussion. Determine if DLA can submit affidavits to CMS to draw down the Federal share.
| 2016-12-31 | P | P | P | Subdivide uncollectible liabilities in buckets - Suspended, Closed, Open no claims, Sold - new operator responsible, new owner not responsible, to determine reason uncollectible.
| 2016-10-01 | P | P | P | DLA to assist in interpretation of Federal Regs on requesting Federal Share back
| 2017-02-28 | P | P | P | Meetings held with Caroline Brown & DLA to determine process to obtain refund of Fed Share. Prepared letter to CMS.
| 2017-02-28 | P | P | P | Meeting held with AG, OMIG & DLA to discuss current practice to obtain Fed Share of OMIG liabilities & obtain copy of affidavit prepared by OMIG sent to CMS.
| 2017-02-28 | P | P | P | Meeting held with MFM to determine process to request refund of Fed Share
| 12/31/16 3/01/17 | P | P | P | Prepare list of of uncollectible liabilities documenting closure dates, collection efforts to be sent to CMS Prepare list of liabilities from 3 buckets-Uncollectible- Open No claims, Uncollectible- Bankruptcy & Uncollectible Sold- New owner not responsible. Lists includes approx 150M gross liabilities including 76M gross with Fed Share to obtain refund of approx 33M.
| 2017-04-01 | P | P | P | Determine from CMS if DOH DLA can prepare affidavit on DOH liabilities similar to AG affidavit, and if so, would DOH be able to obtain refund on liabilities created > 1 year from closed date.
| 11/30/2016 2/1/17 | 8 | 8 | 8 | Submit uncollectables and supporting documentation to DLA for review and signoff.
| 10/1/14 8/1/15 12/1/15 2/15/16 4/1/16 12/31/16 1/31/17 3/1/17 5/1/17 | 8 | 8 | 8 | Request Federal share back with Feds
| 3/31/2017 5/1/17 | 8 | 8 | 8 | Draw down Federal share on uncollected balances.
| 11/1/15 2/15/16 4/1/16 12/31/16 3/1/17 7/1/17 | 8 | 8 | 8 | Work with DLA & AG to submit All other liabilities not past statute (to be determined) to AG to pursue collection and/or obtain affidavit for Federal refund.
| 4/1/16 12/31/16 3/31/17 | 8 | 8 | 8 | Review collections and determine next steps.
6009 |  |  |  |  | Project Name: Accelerate MLTC Enrollment Division Lead: DLTC Team Lead: Mark Kissinger Additional Staff: Margaret Willard Description: Accelerate FFS to MLTC transition |  | Completed - Aug 2013
| 2013-04-01 | P | P | P | Secure approval for the LTHHCP population to move into MLTC in Westchester, Nassau, Suffolk and NYC
| 4/1/13 7/1/13 | P | P | P | Work with Maximus to evaluate the people who are falling off the path to auto-assignment
| 4/5/13 | P | P | P | Move private duty nursing population into MLTC
| 5/1/13 8/1/13 | P | P | P | Evaluate enrollment plan to expedite additional counties with capacity
| 5/10/13 7/1/13 | P | P | P | Evaluate remaining personal care population in NYC
6010 |  |  |  |  | Project Name: Develop Initiatives to Integrate and Manage Care for Dual Eligibles (Fully Integrated Duals Advantage - FIDA) Division Lead: DLTC Team Lead: Joseph Shunk, Mark Kissinger , Rebecca Corso Additional Staff: Andrew Segal, John Ulberg, Ken Evans, Pavel Terpelets, Description: Develop approaches for serving dual eligibles |  | Completed June 2017
| 6/6/13 6/26/13 7/24/13 7/29/13 8/15/13 8/26/13 | P | P | P | Resolution of outstanding MOU issues
| 2013-06-15 | P | P | P | Develop Base Data - Summarize Historical Data
| 6/30/13 8/1/13 8/25/13 8/29/13 | P | P | P | Quarterly stakeholder engagement
| 6/30/13 7/31/13 8/28/13 | P | P | P | Release of NYS Data Book (Phase 3 - 2011)
| 7/1/13 7/2/13 8/2/13 8/16/13 8/26/13 | P | P | P | Finalize MOU between CMS/NYSDOH
| 7/8/13 8/5/13 8/15/13 8/29/13 | P | P | P | CMS and State release draft Readiness Review tool to plans
| 7/15/13 8/15/13 9/5/13 9/9/13 9/20/13 | P | P | P | Issue desk review letter to begin readiness review process
| 2013-07-15 | P | P | P | Develop Base Data - Remove costs for historical HR&R funds embedded in the raw data, adjust for IBNR claims
| 8/1/13 9/12/13 9/30/13 10/18/13 | P | P | P | Plans submit documentation for desk review (Phase 1)
| 8/8/13 TBD | 8 | 8 | 8 | Plans submit documentation for desk review (Phase 2)
| 8/15/13 8/30/13 9/15/13 | P | P | P | Adjust base data for any changes to the populations and or financial impacts that may have taken place from the base period to the rate period
| 10/15/13 11/7/13 | P | P | P | Establish a finalized methodology for rate setting
| 10/1/13 10/30/13 11/8/13 | P | P | P | Present rate development to stakeholders
| 11/27/13 | P | P | P | Send Phase 1 reports to plans to correct desk review deficiencies
| 10/1/13 12/6/13 12/20/13 | 8 | 8 | 8 | Letters to plans to correct desk review deficiencies
| 12/31/13 12/1/13 12/23/13 1/10/14 | P | P | P | Quarterly stakeholder engagement
| 9/15/13 11/22/13 12/9/13 12/24/13 | P | P | P | CMS/State/NORC submit draft desk review deficiencies reports to plans
| 12/24/13 | P | P | P | Plans submit responses to correct desk review deficiencies Phase 1
| 12/24/13 1/9/14 | P | P | P | Send Phase 2 reports to plans to correct desk review deficiencies
| 10/31/13 1/1/14 | 8 | 8 | 8 | Draft Medicaid rates ready for DOB/CMS approval
| 2014-01-15 | 8 | 8 | 8 | Publish PMPM for the Demo
| 10/15/13 12/31/13 1/15/14 1/27/14 2/19/14 | P | P | P | Plans submit responses to correct desk review deficiencies Phase 2
| 2014-01-29 | P | P | P | Policy site visits complete
| 2014-03-10 | P | P | P | Plans receive interim network results
| 1/31/14 8/15/14 11/15/14 | P | P | P | Plans establish connectivity with CMS enrollment, payment systems
| 11/7/13 1/15/14 2/28/14 5/2/14 | P | P | P | Systems testing complete
| 2014-04-18 | P | P | P | CMS sends draft Three-way Contract to Plans for review
| 2014-04-18 | P | P | P | Plans submit final networks
| 2014-05-02 | P | P | P | Plans submit 1-2 page priority comments on the Three-Way contract
| 2014-05-02 | P | P | P | CMS/State finalize and release all required plan model templates
| 2014-05-16 | P | P | P | CMS/State/Plans have a call to discuss Three-Way contract
| 11/15/13 3/15/14 5/2/14 | P | P | P | CMS sends Pre-enrollment validation tool to Plans (e.g., filling vacant positions, website, phone lines)
| 5/28/14 | P | P | P | Plans return pre-enrollment validation tool and documentation to address all remaining deficiencies
| 1/1/14 3/1/14 4/9/14 | P | P | P | Submit 6-month progress report to CMS
| 12/1/13 3/1/14 3/7/14 7/7/14 | P | P | P | Three-way Contract signed
| 3/31/14 | P | P | P | Quarterly stakeholder engagement
| 2014-04-01 | P | P | P | Adjust the Base data for the SNF population
| 6/16/14 6/19/14 | P | P | P | State/CMS sends revised Three-Way contract back to Plans for their signature
| 2014-06-16 | P | P | P | Marketing materials required must be submitted by Plans via HPMS for review and approval
| 2014-06-26 | P | P | P | Brief FIDA Plans on draft rates
| 2014-06-30 | P | P | P | Quarterly Stakeholder meeting
| 2014-09-30 | P | P | P | Quarterly Stakeholder meeting
| 7/1/14 9/1/14 9/30/14 | P | P | P | Submit 6 month progress report to cms
| 1/3/14 4/25/14 4/22/14 8/14 Nov 2014 | P | P | P | Final Readiness Review Determination
| 8/1/14 11/1/14 | P | P | P | Education/Training for Plans and Providers
| Aug 2014 11/1/14 | P | P | P | Plans print approved marketing materials and prepare for approved website posting
| 12/1/13 1/31/14 9/15/14 11/26/14 11/20/14 | P | P | P | Brief FIDA Plans on new rates
| 2/1/14 5/15/14 5/1/14 6/1/14 9/1/14 12/1/14 | P | P | P | 30 day Marketing begins to community-based LTSS participants and facility based LTSS participants for Region 1
| 7/1/14 11/1/14 12/5/14 12/19/14 | P | P | P | Establish and Publish a revised PMPM including SNF Residents Publish Community Based FIDA rates
| 2014-12-01 | P | P | P | FIDA Demonstration Announcement letter sent
| 2014-12-31 | P | P | P | Quarterly Stakeholder meeting
| 4/1/14 7/1/14 10/1/14 1/1/15 | P | P | P | Opt-in enrollment takes effect for community-based LTSS participants and facility-based LTSS participants for Region 1
| 9/1/14 1/1/15 | P | P | P | 90 day passive notice sent to community-based and facility-based LTSS participants for Region 1
| 5/1/14 7/1/14 10/1/14 1/30/15 | P | P | P | 60-day beneficiary notices sent for community-based LTSS and facility-based passive enrollment for Region 1
| 6/1/14 8/1/14 11/1/14 3/1/15 | P | P | P | 30-day beneficiary notices sent for community-based LTSS and facility-based LTSS passive enrollment for Region 1
| 1/1/15 3/1/15 3/31/15 | P | P | P | Submit 6 month progress report to CMS
| 3/31/15 | P | P | P | Quarterly Stakeholder meeting
| 7/1/14 9/1/14 10/1/14 1/1/15 4/1/15 | P | P | P | Passive enrollment takes effect for community-based LTSS and facility-based LTSS participants for Region 1
| 10/1/14 | 8 | 8 | 8 | Opt-in enrollment takes effect for facility-based LTSS participants (Phase 2)
| 11/1/14 | 8 | 8 | 8 | 60-day beneficiary notices sent for facility-based LTSS passive enrollment (Phase 2)
| 2014-12-01 | 8 | 8 | 8 | 30-day beneficiary notices sent for facility-based LTSS passive enrollment (Phase 2)
| 3/1/15 9/1/15 12/1/15 mid 2016 10/1/16 3/1/17 5/17/17 | P | P | P | Region II FIDA Announcement Letter sent
| 3/1/15 12/1/15 Mid 2016 11/1/16 1/1/17 2/1/17 | P | P | P | 30-day Plan marketing begins for Region II (Suffolk and Westchester Counties)
| 3/15/15 4/30/15 5/15/15 6/1/15 6/30/15 | 8 | 8 | 8 | Establish rate report for SNF residents
| 4/1/15 10/1/15 1/1/16 7/1/16 2/1/17 | P | P | P | Opt-in enrollment takes effect for community-based LTSS participants and facility-based LTSS participants for Region II
| 2015-04-01 | 8 | 8 | 8 | 90 day passive notice sent to community-based and facility-based LTSS participants for Region II
| 4/15/15 6/15/15 10/30/15 | P | P | P | Circulate a revised PMPM including SNF Residents
| 8/1/15 11/1/15 2/1/16 | 8 | 8 | 8 | 60-day beneficiary notices sent for community-based LTSS and facility-based passive enrollment for Region II
| 9/1/15 12/1/15 3/1/16 | 8 | 8 | 8 | 30-day beneficiary notices sent for community-based LTSS and facility-based LTSS passive enrollment for Region II
| 10/1/15 1/1/16 4/1/16 | 8 | 8 | 8 | Passive enrollment takes effect for community-based LTSS and facility-based LTSS participants for Region II
| 6/30/15 9/9/15 | P | P | P | Quarterly stakeholder engagement
| 7/1/15 9/30/15 12/31/15 2/15/16 3/15/16 4/15/16 | P | P | P | Submit 6-month progress report to CMS
| 2015-09-30 | P | P | P | Quarterly stakeholder engagement
| 12/31/15 12/22/15 | P | P | P | Quarterly stakeholder engagement
| 1/1/16 3/1/16 | 8 | 8 | 8 | Submit 6-month progress report to CMS
| 2016-03-31 | P | P | P | Quarterly stakeholder engagement
| 6/30/2016 7/22/2016 | P | P | P | Quarterly stakeholder engagement
| 7/1/16 9/1/16 | 8 | 8 | 8 | Submit 6-month progress report to CMS
| 2016-09-30 | P | P | P | Quarterly stakeholder engagement
| 12/31/2016 12/7/16 | P | P | P | Quarterly stakeholder engagement
| 2017-01-01 | 8 | 8 | 8 | Submit 6-month progress report to CMS
| 3/31/2017 4/28/17 | P | P | P | Quarterly stakeholder engagement
| 2017-06-30 | 8 | 8 | 8 | Quarterly stakeholder engagement
| 2017-07-01 | 8 | 8 | 8 | Submit 6-month progress report to CMS
| 2017-09-30 | 8 | 8 | 8 | Quarterly stakeholder engagement
| 2017-12-31 | 8 | 8 | 8 | Quarterly stakeholder engagement
6011 |  |  |  |  | Project Name: OPWDD Fully Integrated Duals Advantage - FIDA Division Lead: OPWDD Team Lead: Kate Marlay Additional Staff: John Ulberg, Ken Evans, Mark Kissinger, Rebecca Corso, Donna Cater, Jack Pitera Description: Develop approaches for serving dual eligibles in OPWDD |  | Complete - April 2016
| 2013-05-29 | P | P | P | State Implementation Grant Application Submitted to CMS through the Research Foundation for Mental Hygiene (RFMH)
| 8/30/13 9/15/13 10/15/13 | P | P | P | Update to NYS DD FIDA Databook
| 10/30/13 | 8 | 8 | 8 | Quarterly stakeholder engagement
| 1/30/14 4/30/14 7/30/14 7/18/14 | P | P | P | Quarterly stakeholder engagement
| 11/15/13 1/2/14 2/1/14 3/14/14 8/1/15 10/1/14 | P | P | P | Develop Base Data - Summarize Historical Data
| 1/15/14 3/5/14 4/1/14 8/15/14 11/15/14 | P | P | P | Develop Base Data - Remove costs for historical HR&R funds embedded in the raw data, adjust for IBNR claims
| 2/1/14 3/1/14 4/15/14 6/30/14 9/30/14 12/30/14 2/16/15 3/15/15 3/31/15 5/15/15 8/15/15 9/1/15 9/30/15 10/30/15 | P | P | P | Resolution of outstanding MOU issues
| 2/15/14 3/15/14 5/1/14 8/1/14 9/1/14 12/1/14 | P | P | P | Adjust base data for any changes to the populations and or financial impacts that may have taken place from the base period to the rate period
| 11/1/13 11/29/13 1/30/14 5/1/14 8/1/14 9/1/14 12/1/14 1/15/15 2/16/15 3/15/15 4/30/15 7/1/15 7/31/15 8/28/15 9/15/15 10/9/15 10/30/15 | P | P | P | Finalize MOU between CMS/NYSDOH
| 11/8/13 12/15/13 2/15/14 5/14/14 8/14/14 9/14/14 12/12/14 1/20/15 2/16/15 3/31/15 5/1/15 5/29/14 6/17/15 8/1/15 | P | P | P | CMS and State release draft Readiness Review tool to plans
| 4/15/14 5/30/14 8/30/14 9/14/14 12/14/14 1/30/15 3/15/15 4/30/15 6/15/15 7/1/15 8/1/15 9/30/15 10/30/15 12/31/15 | P | P | P | Establish a finalized methodology for rate setting (DOH)
| 1/15/14 3/15/14 6/16/14 9/16/14 12/16/14 1/30/15 2/16/15 3/15/15 5/01/15 7/15/15 6/29/15 8/15/15 9/15/15 | P | P | P | Issue desk review letter to begin readiness review process
| 2/1/14 3/1/14 4/15/14 6/30/14 9/30/14 12/30/14 2/16/15 3/15/15 3/31/15 5/15/15 8/15/15 7/16/15 9/1/15 9/25/15 | P | P | P | Plans submit documentation for desk review
| 4/31/14 7/1/14 10/1/14 1/15/15 | P | P | P | Quarterly stakeholder engagement
| 2015-03-12 | P | P | P | Quarterly stakeholder engagement (Joint Advisory Council)
| 6/12/15 7/24/15 | P | P | P | Quarterly stakeholder engagement (Joint Advisory Council)
| 2015-09-12 | P | P | P | Quarterly stakeholder engagement (Joint Advisory Council)
| 12/11/15 1/19/16 3/31/16 | P | P | P | Quarterly stakeholder engagement (Joint Advisory Council)
| 2015-04-23 | P | P | P | OPWDD Commissioner's Bi-weekly Transition Panel Mtg.
| 2015-05-05 | P | P | P | OPWDD Commissioner's Bi-weekly Transition Panel Mtg.
| 2015-05-21 | P | P | P | OPWDD Commissioner's Bi-weekly Transition Panel Mtg.
| 2015-06-02 | P | P | P | OPWDD Commissioner's Bi-weekly Transition Panel Mtg.
| 2015-09-17 | P | P | P | Transformation Panel Public Forums
| 4/31/14 7/31/14 10/1/14 2/27/15 5/15/15 9/11/15 10/30/15 11/13/15 12/31/15 | P | P | P | Medicaid rates finalized (DOH)
| 4/31/14 7/31/14 10/1/14 2/27/15 5/15/15 9/11/15 10/30/15 11/13/15 12/31/15 | P | P | P | Present rate development to stakeholders (DOH)
| 7/1/14 10/1/14 | 8 | 8 | 8 | Submit 6-month progress report to CMS
| 3/15/14 7/1/14 10/1/14 1/5/15 2/27/15 3/15/15 4/15/15 8/15/15 10/1/15 10/15/15 | P | P | P | CMS reviews draft desk review deficiencies
| 4/1/14 7/15/14 10/15/14 1/15/15 2/27/15 3/31/15 5/1/15 9/4/15 10/5/15 11/6/15 | P | P | P | Letters to plans to correct desk review deficiencies
| 3/15/14 7/1/14 10/1/14 1/5/15 2/27/15 3/15/15 4/15/15 8/15/15 10/1/15 10/30/15 | P | P | P | Three-way Contracts shared with plans and the State for signature
| 5/7/14 8/7/14 11/7/14 2/7/15 4/1/15 6/19/15 9/18/15 9/4/15 10/1/15 1/1/16 | P | P | P | Site visits (including systems testing)
| 5/15/14 8/15/14 11/15/14 2/15/15 4/6/15 6/29/15 9/15/15 9/11/15 10/16/15 12/8/16 2/29/16 | P | P | P | Pre-enrollment validation (e.g., filling vacant positions, website, phone lines)
| 4/15/14 8/18/14 11/15/14 2/15/15 3/20/15 5/15/15 9/18/15 8/24/15 10/23/15 1/15/16 | P | P | P | Plans submit responses to correct desk review deficiencies
| 6/1/14 9/1/14 12/1/14 2/1/15 5/1/15 6/05/15 9/25/15 9/11/15 10/15/15 11/13/15 12/31/15 | P | P | P | State and Plan signed Three-way Contract returned to CMS
| 6/1/14 9/2/14 12/2/14 2/2/15 5/15/15 9/25/15 9/4/15 12/29/15 | P | P | P | Brief OPWDD FIDA plans on new rates
| Ongoing | P | P | P | Weekly Tech Development Calls (OPWDD, OPWDD ITS, DOH, Maximus, PHP)
| 2016-01-14 | P | P | P | Maximus Front Door Training
| 1/29/16 2/1/16 | P | P | P | Video Conference Training for DDROs in FIDA-IDD regions
| 2016-02-16 | P | P | P | Maximus Training on Care Coordination Model
| 2/22/16 2/26/16 | P | P | P | LDSS Training Conference Calls: Nassau, Suffolk, Westchester, Rockland, HRA
| 2016-02-25 | P | P | P | OPWDD/DOH to resubmit Plan provider network to CMS
| 2016-03-01 | P | P | P | 3-Way Contract Executed (signed by AG/OSC)
| 2016-03-01 | P | P | P | Appeals process training for OPWDD/OTDA/MAC
| 3/1/16 3/9/16 | P | P | P | 30-day Plan marketing for individuals and families begins (Community Sessions and Webinars) | Multiple sessions scheduled with expectation for additional sessions through April and May
| 2016-03-07 | P | P | P | ICAN Training
| 2016-03-07 | P | P | P | Announcement Letters mailings begin
| 2016-03-15 | P | P | P | Plan establishes connectivity with CMS enrollment payment systems
| 2016-03-15 | P | P | P | Systems testing complete
| 7/3/14 9/2/14 12/2/14 2/1/15 4/1/15 6/19/15 9/25/15 9/18/15 10/30/15 2/12/16 2/29/16 3/20/16 | P | P | P | Final Readiness Review Determination
| 2016-04-01 | P | P | P | First date of enrollments into FIDA-IDD
6012 is part of DSRIP and tracked separately.
6013 |  |  |  |  | Project Name: NYCOTB Division Lead: Health Reform and Health Insurance Exchange Integration Team Lead: Dawn M. Oliver Additional Staff: Kathleen Jackson, Rita Zink, Mark Malone, Peter Sheremeta Description: Implement a state only Medicaid benefit program for former NYC OTB retirees |  | Completed - July 2013
| 2013-04-08 | P | P | P | Establish work team to create the benefit structure
| 2013-04-09 | P | P | P | Workgroup identifies system changes needed to WMS and eMedNY
| 4/11/13 | P | P | P | Application and FAQ distributed to OTB retirees
| 2013-04-22 | P | P | P | eMedNY evolution project request and WMS system change request submitted
| 5/6/13 | P | P | P | Client notice language drafted and submitted for legal review
| 2013-06-11 | P | P | P | 620 applications received from OTB retirees
| 6/18/13 | P | P | P | WMS and eMedNY system changes scheduled for implementation
| 7/9/13 | P | P | P | Complete Eligibility determinations
| 7/10/13 | P | P | P | OTB retiree Medicaid benefits active
6014 |  |  |  |  | Project Name: Family Health Plus Program discontinuation Division Lead: Bureau of Medicaid Enrollment & Exchange Integration Team Lead: Kathleen Johnson Additional Staff: Judith Layton and Peggy Noonan Description: Family Health Plus Program is ending 12/31/2014, no new enrollment after 12/31/2013 |  | Completed - Dec 2013
PART 1
POLICY AND PROCEDURE
| 5/20/13 | P | P | P | Complete preliminary review of policy issues
| 10/1/13 11/1/13 | P | P | P | Submit draft Administrative Directive (ADM) for clearance
| 10/1/13 11/1/13 | P | P | P | Draft Medicaid Update Article for clearance
| 2013-10-15 | P | P | P | Submit changes to 1115 waiver amendment
| 11/1/13 1/1/14 | 8 | 8 | 8 | Update MARG
| 11/1/13 | P | P | P | Update trainings
| 12/1/13 | 8 | 8 | 8 | Update AccessNY application
| 12/15/13 | P | P | P | Issue ADM
| 12/15/13 1/1/14 | P | P | P | Issue Medicaid Update Article
| 12/31/13 | P | P | P | Eliminate FHPlus brochures
| 1/1/14 | P | P | P | Cease acceptance of new applications
TAKE FINAL STEPS TO DISCONTINUE FHPLUS- INCLUDE IN 1115 WAIVER AMENDMENT
| 5/29/13 | P | P | P | Develop Tribal notification letter
| 5/29/13 | P | P | P | Develop Public Notice
| 5/30/13 | P | P | P | Submit Tribal notification letter for approval
| 5/30/13 | P | P | P | Submit Public Notice for approval/clearance
| 7/15/13 | P | P | P | Mail Tribal notification letter
| 8/1/13 | P | P | P | Submit Public Notice for publication
| 9/1/13 12/31/13 10/11/13 11/1/13 | P | P | P | Receive/Respond to Tribal and Public comments
| 11/1/13 | P | P | P | Submit changes to 1115 waiver amendment
INTERNET
| 1/1/15 1/1/14 2/1/14 3/1/14 | P | P | P | Disable website
SYSTEMS
Heart/WMS
| 3/1/13 | P | P | P | Explore necessary system changes (cease acceptance of new applications)
| 4/4/13 | P | P | P | Submit System Change Request Form
| 4/4/13 | P | P | P | Finalize System Change requirements
| 4/24/13 | P | P | P | Finalize System Action request
| 11/30/13 | P | P | P | Development/Coding changes
| 12/23/13 | P | P | P | Unit testing
| 12/31/13 | P | P | P | User acceptance
CNS
| 6/12/13 | P | P | P | Explore CNS notice issues
| 11/21/13 6/17/14 2/17/15 | P | P | P | Eliminate/Revise CNS notices
PART 2
MOVE S/CC INTO MANAGED CARE & TRANSITION PARENTS AT RENEWAL
POLICY AND PROCEDURE
| 5/20/13 | P | P | P | Complete preliminary review of policy issues
| 10/1/13 11/1/13 | P | P | P | Submit draft GIS for clearance- S/CC flip into Medicaid Managed Care
| 12/15/13 | P | P | P | Issue GIS
| 12/31/13 | P | P | P | Amend 1115 Waiver STC (if necessary)
| 12/31/13 | P | P | P | Move parents/caretaker relatives out of FHPlus into MAGI
SYSTEMS
WMS
| 1/1/13 | P | P | P | Explore necessary system changes- move recipients into other coverage
| 2/13/13 | P | P | P | Submit System Change Request From
| 5/28/13 | P | P | P | Finalize System Change requirements
| 6/3/13 | P | P | P | Finalize System Action request
| 11/30/13 | P | P | P | Development/coding changes
| 12/23/13 | P | P | P | Unit testing
| 12/31/13 | P | P | P | User acceptance
CNS
| 6/12/13 | P | P | P | Explore CNS notice issues
| 11/21/13 6/17/14 2/17/15 | P | P | P | Finalize and submit CNS notices
PART 3
REPEAL OF FHPLUS PROGRAM
POLICY AND PROCEDURE
| 5/20/13 | P | P | P | Complete preliminary review of policy issues
| 12/31/13 2/1/14 | P | P | P | Final Waiver Approval
INTERNET
| 5/1/14 | P | P | P | Disable FHPlus mailbox
PART 4
PREMIUM "WRAP" FOR PARENTS/CARETAKERS INCOME 138-150%
| 5/15/13 | P | P | P | Discussion with CMS
| 5/16/13 | P | P | P | Discussion with CSS
| 10/1/13 11/1/13 1/1/14 | P | P | P | Negotiate STC for Waiver
| 12/31/13 2/1/14 | P | P | P | Final Waiver approval
6015 |  |  |  |  | Project Name: Home Care Workers Benefits Division Lead: Robert Loftus Team Lead: Tim Casey Additional Staff: Robert Loftus, Ann Foster Description: Distribute funding to SEIU Home Care Workers Benefit Fund to minimize or avoid the loss of health care benefits. |  | Completed - Sept 2013
| 2013-06-25 | P | P | P | Review and reconcile 2012-13 data
| 2013-06-28 | P | P | P | Review 2013-14 data provided in Milliman Report
| 7/12/13 8/2/13 | P | P | P | Calculate rate change/fiscal impact
| 7/20/13 8/9/13 | P | P | P | Submit to DOB/Governor's Office for approval of rate change
| 8/16/13 9/15/13 | P | P | P | DOB/Governor's office approves rate change
| 7/26/13 8/16/13 8/23/13 9/23/13 | P | P | P | Load rates into eMedNY
| Ongoing | P | P | P | Monitor monthly spending plan
6016 |  |  |  |  | Project Name: Inappropriate Suboxone (buprenorphine/naloxone) Utilization Division Lead: DPDM Team Leads: Monica Toohey RPh. (Clinical Operations/Implementation/Evolution), Steve Brooks (Salient tracking) Additional Staff: Barbara Rogler PharmD. MS (SUNY Buffalo Liaison) Description: Pharmacy claims data was reviewed to identify beneficiaries receiving Suboxone (buprenorphine/naloxone) who also had a claim for a narcotic prescription while on their therapy. Suboxone is used to treat narcotic (opiate) addiction. Buprenorphine is an opioid medication and naloxone is a special narcotic drug that reverses the effects of other narcotic medications. There was evidence that there may be concurrent use of narcotics, including extended-release narcotics, when the prescriber may or may not be aware of the concurrent use of Suboxone and a narcotic. |  | Completed - April 2014
OPERATIONAL
| 6/20/13 | P | P | P | Begin developing a report with Barbara Rogler (SUNY Buffalo) to evaluate clinical & claims data for Drug Utilization Review (DUR) Board meeting
| 8/12/13 | P | P | P | Post DUR Agenda (with Suboxone included)
| 9/12/13 | P | P | P | DUR Board meeting held
| 9/13/13 | P | P | P | Begin development of clinical criteria with Health Information Designs (HID)
| 9/13/13 | P | P | P | Begin working with Magellan Medicaid Administration (MMA) to develop the Managed Access Care Program (MAP) criteria for the call center.
| 10/25/13 | P | P | P | Post DURB final recommendations & summary
| 10/25/13 11/22/13 | P | P | P | Begin to finalize clinical criteria with HID
| 10/25/13 11/29/13 | P | P | P | Begin to finalize MAP criteria with MMA call center
| 11/18/13 11/29/13 | P | P | P | Begin testing of criteria with HID
| 2013-11-21 | P | P | P | Finalize Map criteria with call center/train reps on new criteria
| 2013-12-02 | P | P | P | Finalize testing with HID
| 2013-12-05 | P | P | P | Implement clinical editing with HID
NOTIFICATIONS
| 2013-11-07 | P | P | P | Notification to providers (Medicaid Update), DUR letters to prescribers
POST IMPLEMENTATION
| 2013-12-05 | P | P | P | Monitor and address systemic issues (if necessary)
| 2014-03-01 | P | P | P | Begin to evaluate claims data 3 months post implementation for utilization changes and savings (Steve-Salient tracking & Barb-SUNY Buffalo tracking)
EVOLUTION
| 2013-12-06 | P | P | P | Work with MC plans, through our DURB collaborative, to implement recommendations across MMC
| 12/6/13 12/12/13 | P | P | P | Expand to include benzodiazepines. This was presented & recommendation excepted at the DURB meeting. Need to implement. Date TBD...
| 2014-03-20 | P | P | P | Implement BZD edit
| 12/6/13 4/1/14 | P | P | P | Work with SUNY Prescriber Education Program (PEP) on outreach. They have an opioid module currently being worked on. Date TBD…
6017 |  |  |  |  | Project Name: Provider on Review (edit 1142) Division Lead: DPRUM Team Lead: Kevin Hepp Additional Staff: Deborah Henderson, Bill Hamilton, Frank Hunt Description: Expand the use of edit 1142 to address potential billing errors, duplication, fraud and abuse. |  | Completed - July 2014
| 2013-07-17 | P | P | P | OHIP listserv notice informing staff of the project and soliciting response
| 2013-07-19 | P | P | P | Complete DOO initial data analysis
| 8/1/13 9/1/13 | P | P | P | Brainstorming session internally with Div of Operations re: staff resources, potential providers for review
| 10/1/13 | P | P | P | Send notification to providers re: review status and requirements (Round 1)
| 11/1/13 | P | P | P | Evaluate incoming claims volume and data based on initial set of providers. Determine ability to add providers (Round 1)
| 12/1/13 | P | P | P | Assess providers on review to determine need for continued oversight (Round 1)
| 12/1/13 | P | P | P | Determine to date cost savings (End of Round 1)
| 12/15/13 3/1/14 | P | P | P | Identify providers appropriate for review (Round 2)
| 1/1/14 3/15/14 | P | P | P | Send notification to providers re: review status and requirements (Round 2)
| 2/1/14 4/1/14 | P | P | P | Evaluate incoming claims volume and data based on initial set of providers. Determine ability to add providers (Round 2)
| 3/1/14 5/1/14 | P | P | P | Assess providers on review to determine need for continued oversight (Round 2)
| 3/1/14 5/1/14 | P | P | P | Determine to date cost savings (End of Round 2)
| 3/15/14 5/15/14 6/15/14 7/1/14 8/15/14 | P | P | P | Identify providers appropriate for review (Round 3)
| 4/1/14 6/1/14 7/1/14 8/15/14 | P | P | P | Send notification to providers re: review status and requirements (Round 3)
| 5/1/14 7/1/14 9/1/14 | P | P | P | Evaluate incoming claims volume and data based on initial set of providers. Determine ability to add providers (Round 3) (ongoing)
| 6/1/14 8/1/14 9/1/14 | P | P | P | Assess providers on review to determine need for continued oversight (Round 3) (ongoing)
| 7/1/14 9/1/14 10/1/14 | P | P | P | Determine final cost savings
6018 |  |  |  |  | Project Name: Upcoding and Billing Inconsistencies in Assisted Living Programs (ALP) Division Lead: DLTC Team Lead: Mark Kissinger Additional Staff: Karis Browder Description: Identify ALPs that appear to be placing residents higher Resource Utilization Group (RUG) category than is necessary. The follow-up is to release reminder DALs to encourage assessment consistency and compliance. |  | Completed - Dec 2013
| 8/1/13 8/14/13 | P | P | P | Prepare first draft of Dear Administrator Letter (DAL)
| 8/5/13 8/15/13 8/16/13 | P | P | P | Submit DAL to Division Director for review
| 8/6/13 8/21/13 | P | P | P | Revise DAL with changes and suggestions
| 8/13/13 8/23/13 8/22/13 | P | P | P | Submit final draft to Division Director for approval
| 8/19/13 8/27/13 8/30/13 9/13/13 9/20/13 9/24/13 | P | P | P | Distribute letters to ALPs identified as non-compliant
| ongoing | P | P | P | Provide technical support/policy interpretation to ALPs
| 9/30/13 10/29/13 11/27/13 | P | P | P | Re-evaluate any movement between RUGS categories for the targeted ALPs
| 11/1/13 12/2/13 12/6/13 | P | P | P | Complete final review of the ALPs and determine if any additional action is necessary to ensure compliance.
6019 |  |  |  |  | Project Name: Salient Challenge - High Opioid Prescriber Awareness Division Lead: DPDM Team Lead: Mike Colabufo Description: Prescribers identified as one of the Top 20 prescribers for individual opioid drug products will be provided a letter informing them of their ranking and include educational materials around opioid dependency. |  | Cancelled
| 8/2/13 | P | P | P | Re-convene with outside project partners.
| 8/17/13 8/23/13 9/6/13 11/21/14 | 8 | 8 | 8 | Finalize list of letter recipients, products included. First six months of 2014.
| 2014-12-01 | 8 | 8 | 8 | Have letter produced by DUR Unit.
| 8/31/13 9/6/13 9/20/13 10/03/13 11/8/13 11/28/14 | 8 | 8 | 8 | Vet list with OMIG to ensure no pending investigations will be negatively impacted by letter.
| 2014-12-17 | 8 | 8 | 8 | Approval of letter by management.
| 9/7/13 9/13/13 9/27/13 10/11/13 11/15/13 12/15/13 1/15/14 12/23/14 | 8 | 8 | 8 | Mail letters.
| 10/1/13 10/11/13 11/15/13 12/15/13 1/15/14 1/15/15 | 8 | 8 | 8 | Develop Salient Bookmarks to track prescribing patterns and calculate savings.
| 11/1/13 11/15/13 1/31/14 4/1/15 | 8 | 8 | 8 | Continue updating savings.
6020 |  |  |  |  | Project Name: Dose Optimization Division Lead: DPDM Team Leads: Monica Toohey RPh. (Clinical Operations/Implementation/Evolution), Mike Colabufo (MDW/Salient tracking) Description: Dose optimization can reduce prescription costs by reducing the number of pills at patient needs to take each day. The focus of this initiative will be drugs which have been identified as having FDA approval for once-a-day doses and have different strengths available at similar costs. Doctors may prescribe drugs at a lower dose when people start taking a medication and then gradually increase the dose (titrating). In a lot of cases this dosing continues beyond a typical titration period. Example, a 10mg dose of medication taken twice per day or two daily would be changed to a 20mg dose taken only once per day. |  | Completed - Dec 2013
OPERATIONAL
| 2013-08-09 | P | P | P | Re-run data (Q1 &Q2 -2013) & verify targeted list
| 2013-08-15 | P | P | P | Begin development of clinical criteria with Health Information Designs (HID)
| 2013-09-16 | P | P | P | Begin working with Magellan Medicaid Administration (MMA) to develop the Managed Access Care Program (MAP) criteria for the call center.
| 2013-10-01 | P | P | P | Begin to finalize clinical criteria with HID
| 2013-10-01 | P | P | P | Begin to finalize MAP criteria with MMA call center
| 10/7/13 10/14/13 | P | P | P | Begin testing of criteria with HID
| 10/15/13 10/30/13 | P | P | P | Finalize Map criteria with call center/train reps on new criteria
| 10/21/13 11/7/13 | P | P | P | Finalize testing with HID
| 10/31/13 11/14/13 | P | P | P | Implement clinical editing with HID
NOTIFICATIONS
| 10/1/13 10/21/13 11/21/13 | P | P | P | Notification to providers (Medicaid Update)
| 10/31/13 11/14/13 | P | P | P | Post list to DOH Pharmacy Website
POST IMPLEMENTATION
| 10/1/13 11/14/13 | P | P | P | Monitor and address systemic issues (if necessary)
| 2013-12-12 |  |  |  | DUR Board Meeting- Report on initiative?
| 1/31/14 3/1/14 | P | P | P | Begin to evaluate claims data 3 months post implementation for utilization changes and savings (Mike-MDW/Salient tracking)
EVOLUTION
| 11/4/13 1/21/14 | P | P | P | Run quarterly report (start Q4) & expand to include drugs as necessary
6021 |  |  |  |  | Project Name: Enforce billing restriction to prevent Nurse Practitioners, Physician Assistants, and Nurse-Midwives from being paid separately for practitioner claims for services provided in (Article 28) hospitals. Division Lead: Division of Program Development and Management / Greg Allen Team Lead: Mark Tremblay/Ron Bass Mary Jane O'Brien Additional Staff: Bill Bruno, Ron Bass, Donna Haskin Description: Do not permit Nurse Practitioners, Physician Assistants, or Nurse-Midwives from submitting and being reimbursed for separate professional claims when they provide services in (Article 28) hospitals. | ($1.5) | Merged - Moved to Phase 8 #11002
PROGRAM DEVELOPMENT
| 8/7/13 9/6/13 9/12/13 | P | P | P | Meet with OHIP staff (policy and operations) to discuss policy details and steps to implement.
| 9/20/13 | P | P | P | Met with OHIP Operations to discuss utilizing Edit 01142 to pend claims for providers with the most claims and/or dollars paid for non-physician practitioner services (e.g., Nurse Practitioners, Physician Assistants, and Licensed Midwives) outside of the all inclusive rates in violation of Medicaid policy.
| 10/4/13 10/23/13 | P | P | P | Analyze claims data to identify providers with the most claims and/or dollars paid for non-physician practitioner services in violation of current Medicaid policy and submit request to OHIP operations to pend claims utilizing the 01142 Edit.
| 8/21/13 9/6/13 9/13/13 | P | P | P | Meet with OHIP staff (rate setting/MMC) to discuss rate impacts and managed care implications.
| 10/1/13 11/1/13 4/1/14 5/1/15 3/15/16 5/15/16 8/1/16 9/1/16 11/1/16 2/1/17 4/1/17 6/1/17 8/1/17 2/1/18 8/1/18 | 8 | 8 | 8 | Program implementation
NOTIFICATIONS
| 8/28/13 9/6/13 9/13/13 | P | P | P | Meet with staff to outline details of policy guidance documents including Medicaid Update and eMedNY list serve notification.
| 11/1/13 1/14/14 | P | P | P | Submit Medicaid Update and eMedNY list serve notification that DOH will begin enforcing this policy beginning 1/1/2014 7/1/2014 (without billing system edits to deny payment).
| 11/15/13 | P | P | P | Meet with OHIP Operations to discuss revising practitioner fee schedules for NPs. PAs, and Nurse Midwives to eliminate "institutional" category.
| 12/31/13 1/1/14 4/1/14 | P | P | P | Change Provider fee schedules for NPs. PAs, and Nurse Midwives to eliminate/revise "institutional" category.
| 4/1/14 | P | P | P | Revise all billing guidance, manuals, and DOH online material to conform with Medicaid Update guidance regarding new incompatible rate code/COS/POS combinations policy.
EVOLUTION
| 8/21/13 10/4/13 11/1/13 12/18/13 1/1/14 | P | P | P | Finalize EP to deny claims for NPs, PAs, and Nurse Midwives if billed as rendering provider for services provided in an Article 28 clinic.
| 9/14/13 11/15/13 1/3/14 4/1/14 5/27/14 | P | P | P | Meet to reconsider EP priority rankings to advance the case for implementing this systems change due to: OSC Audit, Budget, and MRT implications.
| 12/1/13 1/1/14 5/7/14 | P | P | P | EP moves to Functional Review Document.
| 4/1/14 6/26/14 | P | P | P | EP is implemented to "pay and report" effective 4/1/14 through 4/15/16 current
| 2016-06-28 | P | P | P | Post implementation enhancement was instituted and after numerous data reviews the EP was determined to be ineffective.
| 2017-06-22 | P | P | P | In order to accomplish this objective a new EP was submitted to refine system editing
| 8/1/2017 10/1/17 2/1/18 8/1/18 | 8 | 8 | 8 | New EP moves to functional review
| 10/1/2017 12/1/17 4/1/18 10/1/18 | 8 | 8 | 8 | New EP is implemented to "pay and report" effective
| 7/1/14 6/26/14 5/1/16 8/1/16 9/1/16 11/1/16 2/1/17 4/1/17 6/1/17 8/1/17 12/1/17 2/1/18 6/1/18 12/1/18 | 8 | 8 | 8 | EP is implemented as "deny payment" effective 7/1/14 5/1/16
POST IMPLEMENTATION
| 9/1/14 9/1/15 3/15/16 5/15/16 8/1/16 9/1/16 11/1/16 2/1/17 4/1/17 6/1/17 8/1/17 2/1/18 4/1/18 10/1/18 | 8 | 8 | 8 | Collect claims data to track savings
| 11/1/14 11/1/15 3/15/16 5/15/16 8/1/16 9/1/16 11/1/16 2/1/17 4/1/17 6/1/17 8/1/17 2/1/18 4/1/18 6/1/18 10/1/18 4/1/19 | 8 | 8 | 8 | Monitor and resolve complaints. Address systemic issues (if necessary)
6022 |  |  |  |  | Project Name: Restrict reimbursement to providers for incompatible rate code and/or Category of Service combinations. Division Lead: Greg Allen/Division of Program Development and Management Team Lead: Mark Tremblay Mary Jane O'Brien Additional Staff: Connie Donohue, Ron Bass, Bill Bruno, Donna Haskin Description: Disallow payment to providers for incompatible inpatient and outpatient/DTC clinic visit/service combinations determined by category of service, rate code and/or admit discharge dates on header of the claim. | ($4.0) | Completed - Jan 2016
PROGRAM DEVELOPMENT
| 7/9/13 | P | P | P | Meet with OHIP staff to discuss ambulatory care rate code combinations that should be subject to eMedNY system duplicate edits which will cause the second claim to be denied/paid $0.
| 8/1/13 8/28/13 | P | P | P | Meet with OHIP staff to finalize list of rate code combinations.
| 8/7/13 8/28/13 | P | P | P | Develop and review final document (Utilization Review/Medical Contra Edit Form) to implement rate code combination edits in the eMedNY billing system.
| 8/14/13 8/28/13 | P | P | P | Submit finalized form to eMedNY.
| 10/4/13 10/11/13 | P | P | P | Meet Integrated Services Workgroup to discuss rate code combination edits Integrated Services visits
| 10/4/13 11/6/13 | P | P | P | Meet with OHIP staff to discuss rate code combination edits for FQHCs
NOTIFICATIONS
| 9/13/13 | P | P | P | Meet with staff to outline details of policy guidance documents including Medicaid Update and eMedNY list serve notification.
| 10/4/13 10/30/13 1/3/14 1/14/14 | P | P | P | Finalize and submit Medicaid Update for October February 2014 release and notify providers through eMedNY Listserve that DOH will begin to alert providers if they submit incompatible rate code combinations for claims dated beginning 10/1/13 11/1/13 1/1/14 and deny payment for claims dated beginning 1/1/14 7/1/14 2/1/14.
| 10/4/13 11/7/13 6/19/14 | P | P | P | Medicaid Update published and eMedNY list serve notification sent to providers
| 10/4/13 1/1/14 2/1/14 7/1/14 | P | P | P | Revise all billing guidance, manuals, and DOH online material to conform with Medicaid Update guidance regarding new incompatible rate code combinations.
POST IMPLEMENTATION
| 2014-07-01 | P | P | P | Collect claims data to track savings
| 9/1/14 | P | P | P | Monitor and resolve complaints. Address systemic issues (if necessary)
INCOMPATIBLE CATEGORY OF SERVICE COMBINATIONS
PROGRAM DEVELOPMENT
| 10/4/13 | P | P | P | Meet with OHIP staff (inpatient/outpatient rate setting and policy) to discuss policy issues/options including: Medicare's "3 Day Payment Window" policy, current Medicaid inpatient/outpatient billing restrictions, and other potential Category of Service (COS) combinations that should be subject to duplicate edits.
| 10/11/13 | P | P | P | Finalize incompatible category of service policy.
NOTIFICATIONS
| 10/23/13 | P | P | P | Meet with staff to outline details of policy guidance documents including Medicaid Update and eMedNY list serve notification.
| 1/3/14 2/1/14 7/1/14 6/1/15 3/15/16 3/1/14 10/1/15 | P | P | P | 1. Finalize and submit Medicaid Update for January April August March 2014 and reminder notice October 2015 release and notify providers through eMedNY List serve that DOH will begin to alert providers if they submit incompatible service categories combinations for claims dated beginning 3/1/14 and deny payment for claims dated beginning 7/1/14 3/26/15
| 10/4/13 11/7/13 1/3/14 2/12/14 7/1/14 6/1/15 3/15/16 3/1/14 10/1/15 | P | P | P | Medicaid Update published and eMedNY list serve notification sent to providers
| 1/3/14 2/1/14 8/1/14 7/1/15 3/15/16 3/1/14 | P | P | P | Revise all billing guidance, manuals, and DOH online material to conform with Medicaid Update guidance regarding new incompatible rate code combinations.
EVOLUTION
| 10/4/13 10/23/13 | P | P | P | Finalize inpatient/outpatient claims edit policy to be implemented through the eMedNY billing system.
| 11/1/13 12/18/13 1/22/14 6/19/14 | P | P | P | Finalize EP and submit it to eMedNY
| 11/15/13 1/3/14 4/1/14 8/1/14 9/1/15 3/15/16 | 8 | 8 | 8 | Meet to reconsider EP priority rankings to advance the case for implementing this systems change due to: OSC Audit, Budget, and MRT implications.
| 1/1/14 4/1/14 8/1/14 3/30/15 3/15/16 10/15/14 | P | P | P | EP moves to Functional Review Document.
| 4/1/14 9/1/14 5/1/15 5/1/15 3/15/16 | 8 | 8 | 8 | EP is implemented to "pay and report" effective 4/1/14 7/1/14
| 7/1/14 9/1/14 8/1/15 3/15/16 3/26/15 | P | P | P | EP is implemented as "deny payment" effective 7/1/14 9/1/14 3/26/15
POST IMPLEMENTATION
| 9/1/14 12/1/15 3/15/16 4/15/16 | 8 | 8 | 8 | Collect claims data to track savings
| 11/1/14 3/1/16 4/30/16 | 8 | 8 | 8 | Monitor and resolve complaints. Address systemic issues (if necessary)
Note on B267: Adele M Compton:

## Ph 3 Affordable Housing (Comp)
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2012-2013 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
6101 |  |  |  |  | Project Name: Health Homes Supportive Housing Pilot Project Division Lead: Lana Earle (DPDM) & Mark Kissinger (DLTC) Additional Staff: Barry Kinlan, Becky Corso Description: Funding will support $5 million of rent and service subsidies to supportive housing providers to house and serve unstably housed high cost Medicaid recipients enrolled in Health Homes. |  | Completed
| 2013-05-17 | P | P | P | Participated in a call with Agency staff and circulated the work plan
| 2013-06-17 | P | P | P | Participated in an internal meeting to discuss funding distributions (RFP, RFA, single source procurement)
| 2013-07-09 | P | P | P | Participated in a MRT Affordable Housing Roundtable w stakeholders to gain additional information as how best to distribute the funds
| 2013-08-01 | P | P | P | Determine funding distribution mechanism
| 2013-08-19 | P | P | P | Draft Completed and circulated for editing and comments among internal staff
| 8/23/13 8/30/13 9/23/13 | P | P | P | Apply edits, send to DOH RFP Work Group
| 2013-09-27 | P | P | P | Receive Final Comments from DOH RFP Work Group
| 8/30/13 9/06/13 10/1/13 | P | P | P | Draft Complete
| 11/1/13 11/15/13 | P | P | P | Finalize comments to RFP
| 11/22/13 12/23/13 1/16/14 | P | P | P | Submit project to EDCC and BOC for approval of document and evaluation criteria
| 11/22/13 12/23/13 1/16/14 | P | P | P | Finalize RFA
| 2/1/14 2/20/14 3/6/14 | P | P | P | With Waiting for EDCC approval, will post to Contract Reporter and new RFA Gateway Portal when approved.
| 2014-03-11 | P | P | P | RFA Posted to NYSDOH public website
| 2014-03-12 | P | P | P | Post RFA ad to Contract Reporter
| 2012-03-21 | P | P | P | Letter of Interest Due
| 2014-03-28 | P | P | P | Written Questions Due, 4:00 pm
| 4/25/14 4/28/14 | P | P | P | Questions, Answers and Updates Posted
| 2014-05-23 | P | P | P | Applications Due, 4:00 pm
| 2014-05-29 | P | P | P | Complete Pass/Fail Review
| 2014-06-01 | P | P | P | Begin Review/Scoring Process
| 2014-07-25 | P | P | P | Anticipated completion of RFA scoring and anticipated award release date
6102 |  |  |  |  | Project Name: OMH Supported Housing Services Supplement Division Lead: Bob Myers, Moira Tashjian (OMH) Description: Funding will support rent and service subsidies to supplement OMH Supported Housing in order to provide necessary day-to-day continuity of place-based, wraparound support services through a flexible critical time intervention approach. |  | Completed - Feb 2014
| 2013-05-17 | P | P | P | Participated in a call with Agency staff and circulated the work plan
| 2013-07-01 | P | P | P | Determine funding distribution mechanism
| 2013-09-15 | P | P | P | Draft of RFP in development
| 2013-10-15 | P | P | P | Draft Complete
| 2013-11-01 | P | P | P | Release RFP - Project not released as RFP. Direct pay to provider.
| 3/24/14 5/28/14 6/17/14 | P | P | P | Program design complete however mechanism to do direct payment to provider is still in process due to procurement/payment processes
| 5/1/14 6/1/14 6/30/14 7/30/14 | P | P | P | Anticipate awards to go into contract amendments and state aid letters |  | The agencies have been identified for funding. In process of addressing the contract amendments for these agencies.
6103 |  |  |  |  | Project Name: Homeless Senior Placement Pilot Project Division Lead: Linda Glassman (OTDA), Jeffrey Gaskell (OTDA) Description: Funding will support rent and service subsidies to seniors currently residing within the shelter system. Funding will transition this population into the community. |  | Completed
| 2013-05-17 | P | P | P | Participated in a call with Agency staff and circulated the work plan
| 2013-05-28 | P | P | P | Internal meeting to discuss program development
| 2013-05-29 | P | P | P | Meet with NYC to discuss MOU development
| 2013-06-14 | P | P | P | Draft MOU sent to NYC
| 2013-06-28 | P | P | P | Meeting with NYC to discuss needed changes to MOU
| 2013-07-12 | P | P | P | NYC identifies service provider
| 2013-11-01 | P | P | P | MOU signed by both parties
| 11/15/13 2/1/14 | P | P | P | Program begins
6104 |  |  |  |  | Project Name: Health Home HIV + Rental Assistance Pilot Project Division Lead: Joseph Losowski (AIDS Institute) Description: Funding will support rental assistance for homeless and unstably housed health home participants diagnosed with HIV infection but medically ineligible for the existing HIV-specific enhanced rental assistance program for New Yorkers with AIDS or advanced HIV-illness. |  | Completed
| 2013-05-17 | P | P | P | Participated in a call with Agency staff and circulated the work plan
| 2013-06-17 | P | P | P | Participated in an internal meeting to discuss funding distributions (RFP, RFA, single source procurement)
| 2013-07-09 | P | P | P | Participated in a MRT Affordable Housing Roundtable w stakeholders to gain additional information as how best to distribute the funds
| 8/1/13 9/15/13 | P | P | P | Determine funding distribution mechanism
| 2013-10-15 | P | P | P | Finalize funding mechanism (MOU or RFA)
| 4/1/14 6/15/14 7/15/14 | P | P | P | Develop Contract Reporter Exemption Request (CRER) for submission to OSC.
| 11/15/13 1/1/14 7/1/14 8/1/14 | P | P | P | Program begins
6105 |  |  |  |  | Project Name: Senior Supportive Housing Pilot Project Team Lead: Mark Kissinger, Liz Misa, Rebecca Corso, Denard Cummings, Emily Engel Description: Funding will support capital and supportive services to enable low-income seniors to remain in the community. |  | Completed
| 2013-05-17 | P | P | P | Participated in a call with Agency staff and circulated the work plan
| 2013-06-17 | P | P | P | Participated in an internal meeting to discuss funding distributions (RFP, RFA, single source procurement)
| 2013-07-29 | P | P | P | Develop project details and complete B1184
| 2013-08-01 | P | P | P | Submit project to FMG and BOC for approval of document and evaluation criteria
| 11/15/12 11/20/13 12/30/13 3/3/14 | P | P | P | Develop draft RFA/RFP with establish project details and parameters
| 12/15/13 12/30/13 3/3/14 | P | P | P | Finalize RFA
| 2014-03-21 | P | P | P | RFA Posted to NYSDOH public website
| 2014-03-24 | P | P | P | Ad posted to Contract Reporter
| 2014-04-04 | P | P | P | Letter of Interest Due
| 2014-04-04 | P | P | P | Written Questions Due
| 4/11/14 4/23/14 4/29/14 | P | P | P | Updates, Questions and Answers Posted
| 5/15/14 5/30/14 | P | P | P | Applications Due by 4:00 PM
| 2014-06-03 | P | P | P | Complete Pass/Fail Review
| 2014-06-04 | P | P | P | Begin Review/Scoring Process
| 7/18/14 7/25/14 | P | P | P | Anticipated completion of RFA scoring and anticipated award release date
6106 |  |  |  |  | Project Name: Step-Down/Crisis Residence Capital Conversion Pilot Project Division Lead: Bob Myers, Moira Tashjian (OMH) Description: Funding will support capital and operating funding to allow for a specified number of existing community residential service providers to convert a certain number of beds in crisis or step-down service units. |  | Completed
| 2013-05-17 | P | P | P | Participated in a call with Agency staff and circulated the work plan
| 2013-06-14 | P | P | P | Draft RFP for 12 to 15 agencies to provide existing providers to expand or convert a certain # of units for individuals in need of crisis stabilization/hospital diversion or hospital step-down.
| 2013-08-15 | P | P | P | RFP under development
| 2013-10-15 | P | P | P | RFP Complete
| 2013-12-15 | P | P | P | Revised RFP to redesign due to input from Affordable Housing Workgroup subcommittee
| 2014-03-07 | P | P | P | New RFP written, approved and released
| 4/21/14 | P | P | P | Q and A on web
| 5/7/14 | P | P | P | Proposals are due
| 6/30/14 7/30/14 | P | P | P | Anticipated award release date
6107 |  |  |  |  | Project Name: Nursing Home to Independent Living Rapid Transition Division Lead: Mark Kissinger, Liz Misa, Rebecca Corso, Denard Cummings, Emily Engel Description: Funding will support rent and service subsidies to offer individuals with mobility impairments or other severe physical disabilities an alternative pathway to community living. |  | Completed - July 2014
| 2013-05-17 | P | P | P | Participated in a call with Agency staff and circulated the work plan
| 2013-06-17 | P | P | P | Participated in an internal meeting to discuss funding distributions (RFP, RFA, Sole Source Contract)
| 2013-07-29 | P | P | P | Facilitate meeting to develop project details and initiate B1184
| 2013-08-01 | P | P | P | Submit project to EDCC and BOC for approval of document and evaluation criteria
| 8/15/13 9/15/13 | P | P | P | Develop draft RFA/RFP with establish project details and parameters
| 10/15/13 11/30/13 12/23/13 3/3/14 | P | P | P | Finalize RFA
| 11/1/13 12/15/13 12/30/13 3/3/14 | P | P | P | Receive internal DOH approvals
| 2014-03-24 | P | P | P | RFA Posted to NYSDOH public website
| 2014-03-25 | P | P | P | Ad posted to Contract Reporter
| 2014-04-04 | P | P | P | Letter of Interest Due
| 2014-04-04 | P | P | P | Deadline to Submit Questions
| 4/11/14 4/23/14 4/25/14 | P | P | P | Updates, Questions and Answers Posted
| 5/15/14 5/30/14 | P | P | P | Applications Due by 4:00 PM
| 2014-06-02 | P | P | P | Complete Pass/Fail Review
| 2014-06-04 | P | P | P | Begin Review/Scoring Process
| 7/18/14 7/25/14 | P | P | P | Anticipated completion of RFA scoring and anticipated award release date

## Ph 3 Operations
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2013-2014 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
6201 |  |  |  |  | Project Name: Activating Ordering/Prescribing/Referring/Attending Edits Division Lead: OHIP Operations Team Lead: Jonathan Bick Additional Staff: Nancy Tumey Description: Savings identified through implementation of ACA requirement that ordering/referring practitioners be enrolled in Medicaid for FFS claims to be paid. |  | Completed -Feb 2014
| 5/20/13 | P | P | P | Post FAQs on web
| 7/1/13 7/11/13 | P | P | P | Conduct Webinar to encourage and facilitate enrollment
| 2013-07-01 | P | P | P | Review current claims activity (excluding pharmacy) against new edits
| 7/15/13 8/23/13 | P | P | P | Reach out to the subset of providers whose current claims activity reveals the greatest potential of future claims denials
| 7/1/13 | P | P | P | Issue a Medicaid Update article. Outline pend and release process, encourage enrollment, highlight the FAQ document and restate that edits will be set to deny in October.
| 8/1/13 8/9/13 | P | P | P | Reach out to OOS hospitals with whom Medicaid has entered into special pricing arrangements
| 8/1/13 8/23/13 | P | P | P | Begin pend and release
| 9/1/13 | P | P | P | Determine rollout schedule of edits/claim type to deny
| 9/1/13 9/20/13 10/1/13 10/31/13 | P | P | P | Finalize rate code bypass for services ordered/referred by non-enrollable professionals
| 9/1/13 | P | P | P | eMedNY listerv on pend and release, rollout of edits
| 10/1/13 10/3/13 1/1/14 | P | P | P | Begin setting edits to deny Evaluate the impact of claims edits and number of pending OPRA enrollments to determine whether the claims edits should be set to deny or whether other steps should be taken. A request was sent to CMS on Sept 23 for a delay in turning on the claims edits to deny. The request seeks a January 1, 2014 implementation to allow the Bureau of Provider Enrollment to process the surge in provider applications received by Oct 1. CMS approved request. Transmittal submitted 12/30/13 to set ordering and referring edits to 'pend & recycle' each week for up to four weeks/cycles. This affects service dates 1/1/14 and later. If ordering/referring provider is not enrolled within 30 days, claim will be denied. The OPRA Pharmacy edit will not be activated at this time.
| 11/1/13 | P | P | P | Establish bi-weekly meetings/check-ins with DOH programs and staff from OASAS, OMH, OPWDD and OCFS
| 11/20/13 12/18/13 | P | P | P | Finalize a Special Edition Medicaid Update on OPRA which will consolidate OPRA FAQ's issued by all agencies and programs into one place.
| 2/3/14 2/20/14 | P | P | P | OPRA Pharmacy edit will be turned on
6202 |  |  |  |  | Project Name: Incontinence Supply Contractor Division Lead: OHIP Operations Team Lead: Kevin Hepp Thomas Heckert, Anton Venter Additional Staff: Jonathan Bick, Debby Henderson, Ellen Harris, William Hamilton, Tony Guiliano Description: Achieve savings through bulk purchasing, rebates, and/or additional utilization management initiatives | $0.8 | Completed December 2016
| 2013-04-01 | P | P | P | Obtain statutory authority
| 6/15/13 7/15/13 | P | P | P | Publish RFI to solicit industry feedback on approaches
| 7/22/13 8/22/13 9/1/13 11/1/13 12/1/13 2/1/14 | P | P | P | Complete review of RFI responses and recommend approach
| 8/1/13 9/1/13 11/1/13 12/1/13 2/1/14 | P | P | P | Contracting/procurement approach determined
| 9/1/13 10/1/13 11/1/13 1/1/14 | P | P | P | Determine feasibility of combining effort with existing or future state/local government procurements
| 9/1/13 10/1/13 12/1/13 2/1/14 3/15/14 5/1/14 7/1/14 9/1/14 10/1/14 11/7/14 | P | P | P | Initiate procurement activities
| 10/1/13 11/1/13 1/1/14 3/1/14 5/1/14 7/1/14 9/1/14 12/1/14 12/22/14 1/8/15 3/31/15 5/6/15 | P | P | P | Initiate review of proposals
| 10/15/13 11/15/13 1/15/14 4/1/14 6/1/14 8/1/14 10/1/14 1/2/15 4/15/15 5/22/15 7/15/15 | P | P | P | Select contractor(s)
| 10/22/13 11/22/13 1/22/14 4/15/14 6/15/14 8/15/14 10/15/14 1/9/15 5/1/15 6/15/15 8/15/15 1/1/16 12/11/15 | P | P | P | Initial provider notification
| 11/15/13 12/15/13 2/15/14 4/15/14 6/15/14 9/15/14 11/15/14 2/2/15 6/15/15 8/15/15 1/1/16 4/1/16 6/1/16 | P | P | P | Approval of contract(s)
| 1/1/14 2/1/13 4/1/14 7/1/14 9/1/14 11/1/14 1/1/15 2/2/15 3/16//15 7/16/15 9/15/15 3/3/16 6/1/16 | P | P | P | Begin implementing initiative
| 2016-09-01 | P | P | P | Implementation date completion
6203 |  |  |  |  | Project Name: Increase Manual Review of Claims Division Lead: OHIP Operations Team Lead: Ellen Harris Additional Staff: Jonathan Bick Description: Hiring package of 5 claims reviewers to increase cost effective manual review of FFS claims. | $8.25 | Completed - June 2014
| 2013-03-18 | P | P | P | Waiver package submitted to DOB
| 6/14/13 7/31/13 | P | P | P | DOB approval of waiver package (5 of 5 positions)
| 6/28/13 8/26/13 | P | P | P | Positions posted (5 of 5 positions)
| 7/15/13 9/17/13 | P | P | P | Begin interviews
| 8/2/13 10/17/13 | P | P | P | Nominate candidates
| 8/14/13 10/24/13 | P | P | P | Offer positions
| 8/29/13 11/7/13 | P | P | P | Staff begin training period
| 11/29/13 1/31/14 | P | P | P | Initial training period complete
| 12/31/13 1/31/14 4/4/14 6/30/14 | P | P | P | First report on savings results (to include 1st Qtr SFY 2014)
6204 |  |  |  |  | Project Name: Hearing Aid Administrative Streamlining Division Lead: OHIP Operations Team Lead: Erin K. Finigan Additional Staff: Jonathan Bick, TBD, Deb Henderson Description: Propose regulation change to facilitate transition from paper to electronic billing to reduce administrative burden on providers and the State. Develop maximum fees based on an average cost of products representative of each type of hearing aid. This will allow automated processing of claims and is consistent with current regulations and procedures for complex wheelchairs and other equipment as well as other payers nationwide. | $0.25 | Completed - Aug 2014
| 2013-05-17 | P | P | P | Amendment packet submitted to DLA
| 2013-07-30 | P | P | P | Amendment packet submitted to Regulatory Affairs
| 8/31/13 10/31/13 12/31/13 1/31/14 | P | P | P | Obtain approval for amendment proposal
| 10/31/13 12/31/13 1/31/14 3/30/14 4/30/14 5/30/14 | P | P | P | Obtain feedback from provider and beneficiary stakeholder groups
| 11/30/13 1/31/14 | P | P | P | Establish MRAs for each code
| 12/15/13 2/15/14 4/30/14 5/30/14 7/31/14 | P | P | P | Update eMedNY system to reflect fees
| 12/15/13 2/15/14 4/30/14 5/30/14 7/15/14 | P | P | P | Update Hearing aid fee schedule
| 12/15/13 2/15/14 | P | P | P | Educate staff
| 12/31/13 3/1/14 4/30/14 5/30/14 7/31/14 | P | P | P | Educate provider community
| 1/31/14 4/1/14 5/1/14 6/1/14 8/1/14 | P | P | P | Begin implementing initiative

## Ph 3 Pharmacy (Completed)
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2013-2014 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
6301 |  |  |  |  | Project Name: Implement Appropriateness Edits on Emergency Medicaid Claims Division Lead: DPDM Team Lead: Mary Carroll Additional Staff: Monica Toohey RPh, Tony Merola RPh, Lyn Hohmann, MD Description: Implement an edit which will eliminate inappropriate emergency Medicaid pharmacy claims provided to individuals who are eligible for emergency services only |  | Completed - Mar 2013
| 2013-03-01 | P | P | P | Develop list of drugs that are eligible for emergency services
| 2013-03-07 | P | P | P | e-blast reminder re: emergency service program to providers
| 2013-03-11 | P | P | P | Implement edits in eMedNY system
| 2013-03-11 | P | P | P | Develop Medicaid Update article for April publication
6302 |  |  |  |  | Project Name: Expand Prescriber Prevails to additional classes in Managed Care Division Lead: DPDM Team Lead: Mary Carroll Additional Staff: Patty Keller RPh, Carol Lindley, Connie Donohue Description: Expand the prescriber prevails provision to include medically necessary prescription drugs in the anti-depressant, anti-retroviral, anti-rejection, seizure, epilepsy, endocrine, hematologic and immunologic therapeutic classes, including non-formulary drugs, upon demonstration by the prescriber, after consulting with the managed care provider, that such drugs, in the prescriber's reasonable professional judgment, are medically necessary and warranted. |  | Completed - April 2014
ADMINISTRATIVE
| 4/1/13 | P | P | P | Article VII legislation change/passing of executive budget
| 4/1/13 | P | P | P | Identify Work Group
PROGRAM DEVELOPMENT
| 4/19/13 4/26/13 | P | P | P | Identify list of drugs
| 5/15/13 | P | P | P | Provide additional guidance to MC plans, as needed
| 5/20/13 | P | P | P | Establish consensus for additional guidance
| 7/1/13 | P | P | P | Program implementation
NOTIFICATIONS
| 5/20/13 6/5/13 | P | P | P | Develop and distribute Medicaid Update and communications with stakeholders
PREPAID CAPITATION RATE
| 6/7/13 8/16/13 9/16/13 10/16/13 | P | P | P | DOH/Mercer develops assumptions used to augment rates; share with plans
| 6/14/13 8/23/13 9/23/13 10/23/13 | P | P | P | DOH/Mercer develops draft rates; share with plans
| 6/28/13 8/30/13 9/30/13 10/30/13 11/8/13 | P | P | P | Plans provide feedback on assumptions/draft rates
| 7/3/13 8/30/13 9/30/13 10/30/13 11/8/13 | P | P | P | DOH/Mercer finalize rate adjustments
| 7/17/13 9/13/13 10/13/13 11/13/13 11/22/13 1/3/14 4/3/14 | P | P | P | Rates approved by DOB, CMS
| 7/31/13 9/27/13 10/27/13 11/27/13 12/6/13 1/17/14 4/17/14 | P | P | P | Rates loaded to the system
EVOLUTION
| 2013-07-01 | P | P | P | Update MC formulary file submission data to identify provider prevails meds
POST IMPLEMENTATION
| 2013-08-15 | P | P | P | Collect PA data
| 7/1/13 | P | P | P | Monitor and resolve complaints. Address systemic issues (if necessary)
6303 |  |  |  |  | Project Name: Mail Order Pharmacy Division Lead: DPDM Team Lead: Carol Lindley Additional Staff: Patty Keller, RPh., Connie Donohue Description: A managed care provider that provides coverage for prescription drugs shall permit each participant to fill any mail order covered prescription, at his or her option, at any mail order pharmacy or non-mail order retail pharmacy in the managed care provider network. If the managed care provider has designated one or more pharmacies for filling prescriptions for a particular drug or drugs, then such prescriptions may be filled, at the participant's option, at any other pharmacy in the network, if the network pharmacy chosen by the participant offers to accept a price that is comparable to that of the pharmacy designated by the managed care provider. |  | Completed - April 2014
ADMINISTRATIVE
| 2013-04-01 | P | P | P | Article VII legislation change/passing of executive budget | 13-14 savings based on 10-1-13 "fiscal impact" date
| 2013-04-01 | P | P | P | Identify Work Group
PROGRAM DEVELOPMENT
| 4/2/13 | P | P | P | Send Initial guidance to Plan Association Reps
| 4/4/13 | P | P | P | Send initial guidance to Plan Pharmacy Directors
| 4/12/13 | P | P | P | Provide additional interim policy and procedure guidance to plans
| 4/22/13 5/1/13 | P | P | P | DOH assessment of conformance of plan interim processes with legislative/statutory intent
| 4/24/13 | P | P | P | Plan conformance with interim guidance
| 5/1/13 | P | P | P | Plans to finalize provider contracting strategy
| 5/17/13 6/7/13 | P | P | P | Provider contract changes implemented
| 5/17/13 6/7/13 | P | P | P | PBM/Plan contract negotiations finalized
| 5/17/13 6/7/13 | P | P | P | Plans to submit final operational processes to DOH
| 6/1/13 6/7/13 | P | P | P | DOH assessment of final conformance of plan operational processes with legislative/statutory intent
| 7/1/13 | P | P | P | Full Managed Care Plan Program implementation
NOTIFICATIONS
| 4/19/13 6/4/13 | P | P | P | Finalize and implement Interim communications and strategy (Medicaid Updates, eblasts, oral communications with stakeholders, plan web site updates, etc)
| 6/5/13 6/12/13 | P | P | P | Finalize Final MC communications and strategy
| 2013-06-12 | P | P | P | Determine Final outreach for MC members
| 2013-06-12 | P | P | P | Determine Final outreach for MC providers
| 6/19/13 6/28/13 | P | P | P | Provider and Member Final Communications sent by MC Plans
| 6/21/13 6/28/13 | P | P | P | Develop and distribute Medicaid Update, eblasts, and oral communications with stakeholders by DOH of Final strategy
| 6/26/13 6/30/13 | P | P | P | MC plans update websites with Final strategy
| 7/1/13 7/26/13 | P | P | P | Implement process of Final strategy
PREPAID CAPITATION RATE
| 4/19/13 6/7/13 9/16/13 10/16/13 | P | P | P | DOH/Mercer develops assumptions used to augment rates; share with plans
| 4/19/13 6/7/13 9/23/13 10/23/13 | P | P | P | DOH/Mercer develops draft rates; share with plans
| 4/26/13 6/14/13 9/30/13 10/30/13 11/8/13 | P | P | P | Plans provide feedback on assumptions/draft rates
| 5/3/13 6/21/13 9/30/13 10/30/13 11/8/13 | P | P | P | DOH/Mercer finalize rate adjustments
| 5/17/13 7/5/13 10/13/13 11/13/13 11/22/13 1/3/14 4/3/14 | P | P | P | Rates approved by DOB, CMS
| 5/31/13 7/19/13 10/27/13 11/27/13 12/6/13 1/17/14 4/17/14 | P | P | P | Rates loaded to the system
POST IMPLEMENTATION MONITORING
| 6/15/13 6/28/13 | P | P | P | Determine reporting requirements
| 4/1/13 | P | P | P | Monitor and resolve complaints. Address systemic issues (if necessary)
6304 |  |  |  |  | Project Name: Merge P&T Committee and DUR Board Division Lead: DPDM Team Lead: Mary Carroll Additional Staff: Anthony Merola, John Naioti, Daniel Mcnamara Description: Merge responsibilities of the P&T Committee and DUR Board under one body/entity called the DUR Board |  | Completed - June 2013
| 2013-04-01 | P | P | P | Article VII legislation change/passing of executive budget
| 2013-04-15 | P | P | P | Notify DURB and P&TC membership of the merger
| 2013-04-20 | P | P | P | Determine which current DURB members can be transition directly into new DURB seats
| 2013-04-20 | P | P | P | Identify which recently reappointed P&TC members can be transition into new DURB seats.
| 2013-04-30 | P | P | P | Official notification to P&TC members (via Commissioner letter) indicating that the P&TC no longer exists (with invite to submit CV for new DURB membership).
| 2013-05-01 | P | P | P | Revise P&TC web-page including removal of P&TC membership information.
| 2013-05-01 | P | P | P | Revise DUB web-page including legislative language link, membership information and General Operating procedures
| 2013-05-15 | P | P | P | Modify DURB membership as detailed in Social Services Law Title 11-c 369 BB
| 2013-05-17 | P | P | P | Notify current DURB members of their new seat or their released for those that cannot be transitioned into a new seat
| 2013-05-15 | P | P | P | Revise pandtc@health.state.ny.us BML to instruct e-mail senders to the DUR@health.state.ny.us
| 2013-05-15 | P | P | P | Vet and re-vetting process to be completed by 5/22/2013 and new creation of DURB officially complete.
| 6/1/13 6/11/13 | P | P | P | Educate members on new roles/responsivities/processes
| 2013-06-01 | P | P | P | Revise P&TC general operating procedures for DURB and post to DUR web-page
| 2013-06-27 | P | P | P | Implement - hold first meeting with the newly established DURB

## Ph 3 Health Homes
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2013-2014 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
[5 empty] | Project Name: Health Homes (HH) for High Cost, High Need Enrollees Division Lead: DPMD - Lana Earle, Deirdre Astin | 0
6401 |  |  |  |  | Project Name: Develop and Implement Health Home Portal (Move Tracking System off HCS Platform) Division Lead: DPDM, DPPG Team Lead: Chip Barnes, Jim Bryant, Sue Antoinette, Jim Lembo Additional Staff: Lyn Hohmann, Mike Jabonaski, Laura Moretti, Aaron Roe, Maria Payne, Nancy Pleickhardt | 0 | Completed - February 2018
| 2013-06-30 | P | P | P | Establish Oversight Portal Team from all interested agencies
| 10/1/13 10/15/13 11/1/13 | P | P | P | Complete technical requirements
| 10/1/13 10/15/13 11/1/14 | P | P | P | Complete financial methodology including APD process
| 10/30/13 1/1/14 3/1/14 6/1/14 8/31/14 | P | P | P | Establish external MAPP/SHIN-NY Executive Advisory workgroup of RHIOs to address RHIO connectivity
| 2014-01-02 | P | P | P | Begin implementation of portal development
| 2014-01-02 | P | P | P | Project Manager on board developing detailed project plan for implementation
| 6/30/14 9/19/14 | P | P | P | Establish project governance structure
| 2014-06-30 | P | P | P | Assess project requirements readiness
| 6/30/14 10/3/14 | P | P | P | Create PMO and project management plan
| 5/9/14 7/8/14 | P | P | P | Jumpstart pilot completed with end user testing
| 5/31/15 6/30/15 8/10/15 9/1/15 9/15/15 | P | P | P | 2 Factor Authentication implemented for MAPP |  | New requirement added that System can not go live until 2 Factor implemented
| 1/5/15 2/28/15 7/1/15 8/15/15 10/1/15 10/8/15 10/15/15 3/23/16 4/20/16 | P | P | P | Phase 1A Complete
| 6/1/16 6/5/16 6/30/16 7/10/16 | P | P | P | Phase 1B Complete - denied claims functionality |  | Phase 1B have been collapsed into Phase 1, all of which is tracking to be released on 7/1
| 10/17/2016 10/24/16 | P | P | P | CANS Assessment Go Live
| 2016-10-24 | P | P | P | Begin UAT/File Testing Environment updated to Phase 2 Specifications
| 12/2/15 10/1/15 1/1/16 9/30/16 10/1/16 12/1/16 12/5/16 12/8/16 | P | P | P | Phase 2 Complete
| 2017-05-01 | P | P | P | HH tracking system enhancement release |  | New Milestone
| 12/16/2016 TBD | 8 | 8 | 8 | Phase 3 Initiation/Strategy Session |  | New Milestone
| 2/1/2017 TBD | 8 | 8 | 8 | Phase 3 Strategy Complete |  | New Milestone
| 12/2/15 9/1/16 TBD | 8 | 8 | 8 | Phase 3 Complete
6402 |  |  |  |  | Project Name: Enrolling Children into Health Homes (HH) Division Lead: DPDM, OPH, AI. Team Lead: Lana Earle, Deirdre Astin, Rachel DeLong Additional Staff: Cynthia Buswell, Janice Thompson, Chris Kus, Marilyn Kaccica, Susan Slade, and Jackie Treanor Description: Enhance existing Health Homes to include expanded network partnerships that serve children. |  | Completed December 2016
| 2013-08-19 | P | P | P | DOH, OCFS, OMH leaders meet to establish proposed framework for enrolling children in Health Homes
| 2013-10-21 | P | P | P | Children's Quarterly Workgroup meeting will be held to discuss HH Vision and Next steps
| 2013-10-25 | P | P | P | MFC workgroup meeting to discuss HH vision and next steps
| 7/1/13 7/15/13 12/1/13 | P | P | P | Meetings (ongoing) with Children's Interagency Team to update data, suggest recommendations to principals on an approach to prioritize enrollment of children with chronic condition(s)
| 7/15/13 7/29/13 10/1/13 10/31/13 | 8 | 8 | 8 | Meet with Stakeholder Work Group, including MFC workgroup, to discuss recommended approach to prioritize enrollment. Develop recommendations and list of open issues to be addressed
| 7/22/13 8/6/13 11/1/13 3/31/14 | P | P | P | Collaborate with stakeholders to refine Health Home Model and develop more detailed work plan to implement recommended steps from Workgroups and to develop Health Home Application for Children (Nov 2013 - March 2014)
| 7/29/13 8/13/13 11/15/13 | P | P | P | Determine need to develop additional State Plan Amendment
| 3/31/14 8/1/14 | P | P | P | Draft New State Plan Amendment for Health Homes serving Children
| 4/30/14 6/30/14 | P | P | P | Draft Application for Health Homes Serving Children will be made available
| 7/31/14 7/30/14 | P | P | P | Comments collected on Draft application
| 8/1/14 7/30/14 | P | P | P | Due Date for Submission of Letter of Interest for Health Homes Serving Children
| 6/1/14 8/31/14 11/1/14 | P | P | P | Applications for Health Homes Serving Children will be made available
| 8/31/14 9/30/14 2/1/15 3/2/15 | P | P | P | Due Date for Submission of Applications for Health Homes Serving Children
| 10/31/14 5/1/15 6/15/15 | P | P | P | Health Home State Agency Team review and approval of applications
| 12/31/14 7/1/15 10/15/15 12/31/15 9/30/16 10/1/16 12/1/16 12/8/16 | P | P | P | Develop and distribute Health Home assignment lists for children (Nov 2014 - Dec 2014) (May 2015 - July 2015) (October 2015) Develop outreach and assignment portal in MAPP
| 1/31/15 7/1/15 10/15/15 1/1/16 9/30/16 10/1/16 12/1/16 12/5/16 12/8/16 | P | P | P | Begin the enrollment of children in Health Homes
6403 |  |  |  |  | Project Name: Guidance for Hospitals to Refer Patients to the HH Program Division Lead: DPDM Team Lead: Lana Earle, Deirdre Astin, Lyn Hohman, Andrea Swire, Alda Osinaga |  | Completed 2/15/17
| 2013-06-15 | P | P | P | Consult and collaborate with Hospital Associations to discuss hospital referral process. Develop recommendations and list of open issues to be addressed.
| 2013-06-21 | P | P | P | Reach out to other states with a Health Home Program regarding their hospital referral process and summarize findings.
| 7/15/13 8/15/13 | P | P | P | Schedule Stakeholder meeting
| 8/29/13 9/30/13 | P | P | P | Meeting scheduled with HANYS and GNYHA to collaborate on hospital referral process guidance.
| 2013-12-02 | P | P | P | Meeting with HH Assignment and Referral Subcommittee for input on process and guidance tool.
| 11/1/13 12/1/13 1/31/14 | P | P | P | Continue work with Hospital Associations to develop guidance tool
| 2014-01-31 | P | P | P | Present to MCO Workgroup/receive comments
| 9/15/13 10/1/13 11/1/13 2/28/14 3/31/14 4/30/14 6/30/14 7/31/14 11/1/14 | P | P | P | Develop Final Hospital referral guidance
| 6/30/14 7/31/14 11/1/14 12/31/14 7/1/15 10/1/15 11/16/15 1/30/16 2/17/16 3/9/16 4/1/16 | P | P | P | Re-evaluate the Hospital referral guidance as it relates to the CMS SPA clarification and new language on assurances that was added and in light of DSRIP. (Language shifting from 'guidance' to 'requirements'). The SPA now says " The State provides assurance that hospitals participating under the State Plan or a waiver of such plan will be instructed to establish procedures for referring eligible individuals with chronic conditions who seek or need treatment in a hospital emergency department to designated Health Homes providers." SPA #NY-13-0018 has been updated to direct NYS hospitals regarding the referral of patients in emergency rooms and inpatient settings to Health Homes. Language in updated SPA # NY-13-0063 reflects a shift from 'guidance' to 'requirement' stating, "The State provides assurance that hospitals participating under the State Plan or a waiver of such plan will be instructed to establish procedures for referring eligible individuals with chronic conditions who seek or need treatment in a hospital emergency department to designated Health Homes providers." Hospital referral guidance is currently being prepared for distribution to NYS hospitals as it relates to this CMS SPA clarification and new language on assurances. Verification of connectivity for hospitals to make referrals via the MAPP will be included as appropriate in this guidance. Guidance document is being reviewed by DSRIP staff regarding making a connection with PPS. A meeting to be scheduled with the Hospital Associations to review the letter.
| 10/1/13 10/15/13 11/30/13 2/28/14 4/30/14 5/31/14 6/30/14 7/31/14 11/1/14 10/1/15 9/1/16 TBD 2/15/17 | P | P | P | Distribute Hospital referral guidance / conduct Webinar (Determine if regional or statewide) Hospital referrals begin once web based MAPP portal is operational. Once the MAPP referral portal is operational, hospitals will have the ability to refer thru the MAPP portal.
| 2016-07-25 | P | P | P | Meeting with Hospital Associations to roll out the protocol
| 2016-11-21 | P | P | P | Follow up Meeting with Hospital Associations for additional discussion
| 8/31/2016 11/17/16 12/31/16 1/7/17 TBD 3/31/17 2/15/17 | P | P | P | Establish R/E code to identify Health Home Status - CMA working on system connectivity
| 11/1/2016 1/1/17 5/1/17 2/15/17 | P | P | P | Implementation of policy and receipt of hospital's policy on HH referral
| 10/15/13 10/31/13 12/15/13 2/28/14 5/31/14 7/31/14 9/30/14 12/1/14 | 8 | 8 | 8 | Publish Medicaid Update article
| 10/30/13 11/15/13 12/1/13 2/28/14 | 8 | 8 | 8 | Conduct Outreach meetings
6404 |  |  |  |  | Project Name: Oversight of Grievances/Complaints, Incident Reporting, and Site Visits Division Lead: DPDM Team Lead: Lana Earle, Deirdre Astin, Lyn Hohman, Andrea Swire, Cynthia Buswell, Kristen Lema Also staff from the following offices: OMH, AI , Managed Care, and OASAS. |  | Completed - Oct 2014
| 2013-06-06 | P | P | P | Schedule meeting with State Inter and Intra Agency staff to review existing policies and procedures and establish Workgroup(s) to propose and draft new policies/procedures and other guidance documents specific to HHs |  | 5/17/13 HH Oversight meeting held to discuss the scope of work.
| 2013-06-06 | P | P | P | Develop and circulate to Workgroup an Inventory Tool to collect pertinent data from Workgroup participants regarding current policies/procedures for Care Management programs |  | 5/23/13 List of Workgroup participants from OASIS, OMH, DOH, OHITT, and AI confirmed
| 2013-06-01 | P | P | P | Ongoing HH Workgroup biweekly meetings to draft HH policies and procedures |  | 5/24/13 DRAFT HH Monitoring Guidance Inventory Tool in final stage of development.
| 6/20/13 6/28/13 | P | P | P | Ongoing HH Workgroup meetings to draft HH policies and procedures
| 7/4/13 7/11/13 | P | P | P | Ongoing HH Workgroup meetings to draft HH policies and procedures
| 7/18/13 7/25/13 | P | P | P | Ongoing HH Workgroup meetings to draft HH policies and procedures (Site Visits)
| 8/1/13 8/8/13 | P | P | P | Ongoing HH Workgroup meetings to draft HH policies and procedures (Site Visits)
| 8/15/13 8/22/13 | P | P | P | Ongoing HH Workgroup meetings to draft HH policies and procedures (Site Visits)
| 2013-09-05 | P | P | P | Ongoing HH Workgroup meetings to draft HH policies and procedures (Site Visits)
| 2013-09-19 | P | P | P | Ongoing HH Workgroup meetings to draft HH policies and procedures (Complaints/Grievances)
| 2013-10-03 | P | P | P | Ongoing HH Workgroup meetings to draft HH policies and procedures (Complaints/Grievances)
| 2013-10-17 | P | P | P | Ongoing HH Workgroup meetings to draft HH policies and procedures (Complaints/Grievances)
| 2013-10-31 | P | P | P | Ongoing HH Workgroup meetings to draft HH policies and procedures (Complaints/Grievances)
| 2013-11-14 | P | P | P | Ongoing HH Workgroup meetings to draft HH policies and procedures (Incident Reporting) (Complaints/Grievances)
| 11/28/13 | P | P | P | Ongoing HH Workgroup meetings to draft HH policies and procedures (Incident Reporting) (Complaints/Grievances)
| 2013-12-05 | P | P | P | Ongoing HH Workgroup meetings to draft HH policies and procedures (Incident Reporting) (Complaints/Grievances)
| 2013-12-19 | P | P | P | Ongoing HH Workgroup meetings to draft HH policies and procedures (Incident Reporting) (Complaints/Grievances)
| 1/2/14 1/8/14 | P | P | P | Ongoing HH Workgroup meetings to draft HH policies and procedures (Incident Reporting)
| 1/16/14 1/22/14 | P | P | P | Ongoing HH Workgroup meetings to draft HH policies and procedures (Incident Reporting)
| 1/30/14 2/5/14 | P | P | P | Ongoing HH Workgroup meetings to draft HH policies and procedures (Incident Reporting)
| 2/14/14 2/19/14 | P | P | P | Ongoing HH Workgroup meetings to draft HH policies and procedures (Incident Reporting)
| 8/29/13 1/10/14 2/28/14 4/30/14 5/31/14 | P | P | P | Complete DRAFT policies, procedures and guidance documents
| 2014-07-31 | P | P | P | Complete internal review of DRAFT policies.
| 9/12/13 1/24/14 3/31/14 5/15/14 6/30/14 7/25/31 | 8 | 8 | 8 | Schedule workgroup meeting with HHs and Stakeholders to review, discuss, and edit draft policies and procedures, as needed, and finalize adopted guidance documents
| 8/25/14 9/26/14 | P | P | P | Complete review of policies by upper management of State Partner agencies.
| 10/1/13 2/15/14 3/31/14 5/15/14 8/30/14 11/1/14 | P | P | P | Publish Medicaid Update article introducing adopted guidance documents
| 2014-10-15 | P | P | P | Verify policies consistent with development of new Health Home standards (Behavioral Health, HARP)
| 10/18/13 2/28/14 3/31/14 5/15/14 | P | P | P | Establish Statewide Steering Committee comprised of Intra and Inter Agency partners to review and monitor incoming complaints/grievances, incident reports
| 2014-10-01 | P | P | P | Present completed policies via Health Home Webinar
| 2014-10-02 | P | P | P | Post policies on the DOH Health Home website and send ListServ announcement
6405 |  |  |  |  | Project Name: Health Home Implementation Grants Division Lead: DPDM Team Lead: Lana Earle, Lyn Hohmann, Deirdre Astin Additional Staff: Barry Kinlan Description: Designated Health Homes will be reviewed on a case by case basis to determine if they qualify for additional funding through this grant to aide in implementation of the Health Home Program. |  | Completed - Mar 2014
| 5/15/13 | P | P | P | Develop elements of grant formula for Phase I (SFY 13-14) Distribution (Dependent on Identifying Savings in 13-14)
| 5/24/13 | P | P | P | Share elements of grant formula with HH/MCO Workgroup for review and comment
| 6/5/13 | P | P | P | Receive comments from HH/MCO Workgroup
| 6/25/13 | P | P | P | Finalize distribution formula for Phase 1 and Identify 13-14 Savings
| 6/27/13 | P | P | P | Score Health Homes and determine Phase 1 grant recipients
| 7/1/13 | P | P | P | Distribute Phase 1 implementation grants
| 2/1/14 | P | P | P | Monitor Cap to Determine if Additional Savings can be identified to make supplemental Phase 1, SFY 13-14 Payments
| 4/1/14 | P | P | P | Discuss and refine elements of grant distribution formula for potential additional Phase I grants and Phase II (SFY 14-15) grants with HH/MCO Workgroup
| 5/1/14 | P | P | P | Distribute Phase 2 implementation grants | 15
6406 |  |  |  |  | Project Name: Shared Savings SPA 12-09 Division Lead: DPDM Team Lead: Lana Earle, Deirdre Astin and Maria Payne Additional Staff: Joann Susser, Laura Moretti and Cynthia Buswell Description: Approve State Plan Amendment to Develop a methodology to estimate and distribute shared savings from the Health Home Program |  | In Progress Cancelled
| 1/1/12 | P | P | P | NYS submitted SPA 12-09 to CMS
| 6/15/12 | P | P | P | DOH received Request for Additional Information (RAI) from CMS
| 8/29/12 | P | P | P | DOH submitted requested information in response to RAI
| 10/17/12 | P | P | P | DOH and CMS agreed to convert response to draft and revisit once SPAs for remaining Health Home Phases were approved.
| 4/10/13 | P | P | P | Revised shared savings methodology shared informally with CMS
| 5/10/13 | P | P | P | Informal comments regarding framework for development of shared savings methodology received from CMS
| 2013-08-01 | P | P | P | As part of the Health Home evaluation project, identify outside experts to help develop shared savings methodology for CMS
| 6/28/13 7/15/13 8/15/13 9/1/13 9/15/13 | P | P | P | Schedule Bi-Weekly (or as needed) meetings to Develop Components and Approach to Savings Methodology
| 6/28/13 7/15/13 8/15/13 9/1/13 | P | P | P | Schedule Quarterly (or as needed) meetings with CMS Methodology Team to Review Components of Savings Methodology
| 12/1/13 4/1/14 9/1/14 11/1/14 12/1/14 2/1/15 3/1/15 6/1/15 9/1/15 9/23/15 2/2/16 2/8/16 4/14/16 | P | P | P | Develop a Shared Savings Methodology (in conjunction/coordination with Health Home Evaluation efforts) Meeting scheduled with Greg Allen/KPMG. Tenatative meeting scheduled with Greg Allen and Mercer staff to develop a work-plan as per the CMS Medicaid Directors Letter. Follow up meeting scheduled for 4/14/16.
| 6/1/2016 7/19/16 8/31/16 9/26/16 | 8 | 8 | 8 | Determine timeframe for shared savings prior to VBP
| 6/7/2016 7/19/16 8/5/16 | P | P | P | Schedule follow up meeting with Mercer to further develop the workplan and methodology
| 2016-09-26 | 8 | 8 | 8 | following meeting scheduled with Mercer
| 12/1/13 12/31/13 4/30/14 8/1/14 11/1/14 12/1/14 2/1/15 3/1/15 6/1/15 9/1/15 10/1/15 | 8 | 8 | 8 | Review / Provide Status Update of Savings Methodology with HH/MCO Work Group
| 12/20/14 2/15/15 3/15/15 7/15/15 10/15/15 | 8 | 8 | 8 | Preliminary Meeting with CMS on Methodology. Meeting information will be used to create a more detailed and accurate work plan
| 3/31/14 6/1/14 10/1/14 12/1/14 2/15/15 3/1/15 4/1/15 7/1/15 12/1/15 | 8 | 8 | 8 | CMS approval of SPA 12-09
| 1/1/14 4/1/14 11/1/14 1/15/15 3/15/15 7/15/15 1/15/16 | 8 | 8 | 8 | Data analysis to calculate savings for Phase 1 begins (1/1/13 to 12/31/13 Measurement Yr.)
| 6/1/14 8/1/14 12/1/14 2/1/15 5/1/15 2/15/16 | 8 | 8 | 8 | Payments made to Phase 1 Health Homes
| 4/1/14 6/1/14 2/1/15 4/1/15 7/1/15 3/15/16 | 8 | 8 | 8 | Data analysis to calculate savings for Phase 2 begins (4/1/13 to 3/31/14 Measurement Yr.)
| 10/1/14 12/31/14 3/1/15 5/1/15 4/15/16 | 8 | 8 | 8 | Payments made to Phase 2 Health Homes
| 7/1/14 9/1/14 4/1/15 6/1/15 5/15/16 | 8 | 8 | 8 | Data analysis to calculate savings for Phase 3 begins (7/1/13 to 6/30/14 Measurement Yr.)
| 12/1/14 2/1/15 5/1/15 7/1/15 6/15/16 | 8 | 8 | 8 | Payments made to Phase 3 Health Homes
| 7/1/14 | 8 | 8 | 8 | Data analysis to calculate savings for Phase 3 begins (7/1/13 to 6/30/14 Measurement Yr.)
| 12/1/14 | 8 | 8 | 8 | Payments made to Phase 3 Health Homes

## Ph 3 Basic Benefit(Complete)
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2013-2014 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
6501 |  |  |  |  | Project Name: Lumbar Discography Division Lead: Greg Allen/Division of Program Development and Management Team Lead: Ron Bass/Connie Donohue Additional Staff: Cyndy Sauer, Joan Sicard Description: Discontinue coverage of lumbar discography for chronic low back pain due to lack of medical evidence and potential for patient harm. |  | Completed - Nov 2013
| 5/3/13 | P | P | P | Prepare coverage guidelines and identify ICD-9 diagnosis codes and CPT/HCPCS procedure code(s) that apply.
| 5/3/13 | P | P | P | Identify systems impact/if changes are necessary to implement MRT.
| 6/13/13 5/10/13 | P | P | P | Confer with DOH medical director(s) on coverage guidelines.
| 5/17/13 | P | P | P | Submit evolution project, if required.
| 9/19/13 8/30/13 7/19/13 6/7/13 | P | P | P | Share policy and billing guidance with Managed Care Plan staff and Plan directors.
| 9/13/13 8/30/13 7/31/13 6/21/13 | P | P | P | Share policy and billing guidance with GNYHA and HANYS.
| 7/12/13 | P | P | P | Prepare a Medicaid Update article outlining changes to coverage policy.
| 9/6/13 8/30/13 8/2/13 7/31/13 | P | P | P | Circulate Medicaid Update article for review/comments.
| 9/30/13 | P | P | P | Publish Medicaid Update article
| 8/16/13 9/30/13 10/23/13 | P | P | P | Develop outcome metrics.
| 9/13/13 8/30/13 | P | P | P | Prepare Q&As for Helpline staff.
| 10/23/13 9/18/13 | P | P | P | Educate Helpline staff to ensure that accurate policy information is communicated to providers and enrollees.
| 11/1/13 10/1/13 | P | P | P | Implement policy.
6502 |  |  |  |  | Project Name: Transcutaneous Nerve Stimulation (TENS) for Treatment of Pain Division Lead: Greg Allen/Division of Program Development and Management Team Lead: Ron Bass/ Connie Donohue Additional Staff: Debbie Bush, Cyndy Sauer, Joan Sicard Description: Limit coverage of TENS to pain associated with osteoarthritis of the knee only. |  | Completed - Nov 2013
| 5/3/13 | P | P | P | Prepare coverage guidelines and identify ICD-9 diagnosis codes and CPT/HCPCS procedure code(s) that apply.
| 5/3/13 | P | P | P | Discuss diagnosis editing needed.
| 6/13/13 5/3/13 | P | P | P | Identify systems impact/if changes are necessary to implement MRT.
| 6/13/13 5/10/13 | P | P | P | Confer with DOH medical director(s) on coverage guidelines.
| 7/19/13 5/17/13 | 8 | 8 | 8 | Submit evolution project, if required.
| 9/19/13 8/30/13 7/19/13 6/7/13 | P | P | P | Share policy and billing guidance with Managed Care Plan staff and Plan directors.
| 9/13/13 8/30/13 7/31/13 6/21/13 | P | P | P | Share policy and billing guidance with GNYHA and HANYS.
| 8/30/13 8/2/13 7/12/13 | P | P | P | Prepare a Medicaid Update article outlining changes to coverage policy.
| 9/6/13 8/30/13 8/9/13 7/31/13 | P | P | P | Circulate Medicaid Update article for review/comments.
| 9/30/13 | P | P | P | Publish Medicaid Update article
| 10/23/13 9/30/13 8/16/13 | P | P | P | Develop outcome metrics.
| 9/13/13 8/30/13 | P | P | P | Prepare Q&As for Helpline staff.
| 10/23/13 9/18/13 | P | P | P | Educate Helpline staff to ensure that accurate policy information is communicated to providers and enrollees.
| 11/1/13 10/1/13 | P | P | P | Implement policy.
6503 |  |  |  |  | Project Name: Implantable Infusion Pumps for Non-Cancer Pain Division Lead: Greg Allen/Division of Program Development and Management Team Lead: Ron Bass/ Connie Donohue Additional Staff: Donna Urban, Joan Sicard Description: Coverage of implantable infusion pumps, except in case of intractable cancer pain, will be discontinued due to insufficient evidence and the potential for patient harm. |  | Completed - Nov 2013
| 5/3/13 | P | P | P | Prepare coverage guidelines and identify ICD-9 diagnosis codes and CPT/HCPCS procedure code(s) that apply.
| 5/3/13 | P | P | P | Discuss diagnosis editing needed.
| 6/13/13 5/3/13 | P | P | P | Identify systems impact/if changes are necessary to implement MRT.
| 6/13/13 5/10/13 | P | P | P | Confer with DOH medical director(s) on coverage guidelines.
| 7/19/13 5/17/13 |  |  |  | Submit evolution project, if required.
| 9/19/13 8/30/13 7/19/13 6/7/13 | P | P | P | Share policy and billing guidance with Managed Care Plan staff and Plan directors.
| 9/13/13 8/30/13 7/31/13 6/21/13 | P | P | P | Share policy and billing guidance with GNYHA and HANYS.
| 7/12/13 | P | P | P | Prepare a Medicaid Update article outlining changes to coverage policy.
| 9/6/13 8/30/13 7/31/13 | P | P | P | Circulate Medicaid Update article for review/comments.
| 9/30/13 | P | P | P | Publish Medicaid Update article
| 10/23/13 9/30/13 8/16/13 | P | P | P | Develop outcome metrics.
| 9/13/13 8/30/13 | P | P | P | Prepare Q&As for Helpline staff.
| 10/23/13 9/18/13 | P | P | P | Educate Helpline staff to ensure that accurate policy information is communicated to providers and enrollees.
| 11/1/13 10/1/13 | P | P | P | Implement policy.
6504 |  |  |  |  | Project Name: Functional Electrical Stimulators (FES) Division Lead: Greg Allen/Division of Program Development and Management Team Lead: Ron Bass/ Connie Donohue Additional Staff: Cyndy Sauer, Joan Sicard Description: Discontinue coverage of functional electrical stimulators (FES) for spinal cord and head injury, cerebral palsy, and upper motor neuron disease. |  | Completed - Nov 2013
| 5/3/13 | P | P | P | Prepare coverage guidelines and identify ICD-9 diagnosis codes and CPT/HCPCS procedure code(s) that apply.
| 5/3/13 | P | P | P | Discuss diagnosis editing needed.
| 6/13/13 5/3/13 | P | P | P | Identify systems impact/if changes are necessary to implement MRT.
| 6/13/13 5/10/13 | P | P | P | Confer with DOH medical director(s) on coverage guidelines.
| 8/1/13 | P | P | P | Meet with DME staff to review current coverage policy
| 7/19/13 5/17/13 | P | P | P | Submit evolution project, if required.
| 9/6/13 | P | P | P | Follow-up meeting with medical director to clarify diagnosis and procedure coding
| 9/19/13 8/30/13 7/19/13 6/7/13 | P | P | P | Share policy and billing guidance with Managed Care Plan staff and Plan directors.
| 9/13/13 8/30/13 7/31/12 6/21/13 | P | P | P | Share policy and billing guidance with GNYHA and HANYS.
| 9/6/13 8/23/13 7/12/13 | P | P | P | Prepare a Medicaid Update article outlining changes to coverage policy.
| 9/13/13 8/30/13 7/31/13 | P | P | P | Circulate Medicaid Update article for review/comments.
| 9/30/13 | P | P | P | Publish Medicaid Update article
| 10/23/13 9/30/13 8/16/13 | P | P | P | Develop outcome metrics.
| 9/13/13 8/30/13 | P | P | P | Prepare Q&As for Helpline staff.
| 10/23/13 9/18/13 | P | P | P | Educate Helpline staff to ensure that accurate policy information is communicated to providers and enrollees.
| 10/1/13 11/1/13 | P | P | P | Implement policy. | Date changed to November 1st, but still working toward possible October 1st implementation

## Boo Yah
BOO-YAH!

## Boo-yah (hidden)
BOO-YAH!