## Ph 5 Catch-All
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2015-2016 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
As of: | 2018-10-24
8001 |  |  |  |  | Project Name: Cost-sharing Limits for Medicare Part B Claims Division Lead: DPDM Team Lead: Ron Bass, Connie Donohue, Cristin Carter Additional Staff: Ruth Rivera Description: Effective July 1, 2015, Medicaid will limit reimbursement of Medicare Part B coinsurance for professional claims so that the total Medicare/Medicaid payment does not exceed the amount that Medicaid would have paid for the service if those services had been provided to a Medicaid-only eligible recipient. | $9,687,629 | Completed December 2016
| 4/1/2015 | P | P | P | STATUATORY AUTHORITY - ARTICLE 7
SYSTEMS REQUIREMENTS
| 2015-04-08 | P | P | P | Meet to discuss Evolution Project Request (EPR) requirements
| 2015-04-27 | P | P | P | Draft EP completed
| 2015-05-01 | P | P | P | Evolution Project request submitted
| 2015-06-01 | P | P | P | Functional Review Document (FRD)
| 6/8/15 7/1/15 | P | P | P | Meet with eMedNY staff to review FRD
| 2015-09-17 | P | P | P | Meet with eMedNY staff to review the policy change
| 9/1/15 10/31/15 10/1/15 | P | P | P | Review and Approval of Assessment of EP2026
| 2015-12-17 | P | P | P | System capability in place for EP 2026
| 8/1/15 10/1/15 12/31/15 1/1/16 | P | P | P | Implementation of EP 2026 retro-actively to July 1, 2015
| 12/31/15 3/31/16 6/30/16 10/1/16 | P | P | P | Special input to reprocess claims retroactively to July 1, 2016 2015
STATE PLAN AMENDMENT SPA #15-38
| 2015-04-17 | P | P | P | Obtain SPA pages to be amended
| 2015-05-01 | P | P | P | SPA drafted
| 6/1/15 6/24/15 8/5/15 | P | P | P | SPA #15-38 reviewed/approved by DPDM
| 2015-08-11 | P | P | P | SPA #15-38 transmitted for counsel approval
| 6/8/15 7/1/15 8/6/15 9/22/15 | P | P | P | SPA #15-38 transmitted for OHIP approvals (J. Ulberg/J. Helgerson)
| 8/30/15 9/22/15 | P | P | P | SPA #15-38 transmitted for DOB/Governor approvals
| 9/15/15 9/30/15 | P | P | P | SPA #15-38 transmitted to CMS (needs to be prior to September 30, 2015 to be effective July 1, 2015)
| 9/8/15 11/30/15 3/31/16 12/15/15 | P | P | P | SPA approved
NOTIFICATIONS
| 2015-04-08 | P | P | P | Meet to discuss policy guidance to be included in a Medicaid Update article and/or an eMedNY list serve notification
| 2015-05-15 | P | P | P | Draft of Medicaid Update article and/or eMedNY list serve e-blast completed
| 2015-06-01 | P | P | P | Review Draft of Medicaid Update and/or eMedNY list serve e-blast
| 2015-06-25 | P | P | P | Submit final Medicaid Update article for inclusion in Medicaid Update and/or eMedNY list serve e-blast
| 7/1/15 6/30/15 | P | P | P | Medicaid Update and/or eMedNY list serve e-blast published
| 2015-07-30 | P | P | P | Medicaid Update published to clarify pharmacy is not excluded
| 2015-11-25 | P | P | P | November 2015 Medicaid Update article published to remind/notify providers of 1/1/2016 effective date
8002 |  |  |  |  | Project Name: Gold STAMP Program to Reduce Pressure Ulcers Division Lead: Division of Nursing Homes and ICF/IID Surveillance, Center for Health Care Provider Services and Oversight Team Lead: Paula Grogin Additional Staff: Shelly Glock, Rick Rees Description: The Gold STAMP Program to Reduce Pressure Ulcers is a coalition of organizations convened in New York State to provide resources and education across the continuum of care to improve the assessment, management and prevention of pressure ulcers. |  | Complete - April 2016
| 6/1/15 8/17/15 9/8/15 | P | P | P | Hire a Project Manager to assist with the physician engagement component of the Program, as well as webinar/webcast logistics and processing webinar/webcast honorarium payments; manage the online learning platform; and communicate with Collaboratives.
| 2015-06-30 | P | P | P | As the initial step to engage New York State physicians in the prevention and treatment of pressure ulcers, conduct a literature review and needs assessment of existing Collaboratives to guide the content of three webinars/webcasts directed to physicians.
| 6/30/15 9/30/15 | P | P | P | Develop an online learning platform (Moodle) to allow Collaboratives to share best practices and lessons learned, as well as allow for informal coaching and technical assistance with the help of Gold STAMP coaches.
| 3/31/16 | P | P | P | Produce one webinar/webcast for Collaborative members and Gold STAMP Toolkit users on how to engage physicians and keep them engaged. |  | Scheduled for Held on 3/31/16
| 7/31/15 11/30/15 3/31/16 | P | P | P | Offer up to three webinars/webcasts directed to physicians based on literature review and needs assessment of existing Collaboratives. |  | Webinar #1 9/3/15 Webinar #2 11/17/15 Webinar #3 12/8/15
| 12/31/15 3/1/16 3/18/16 3/25/16 | P | P | P | Maintain and update the Gold STAMP Toolkit on the Gold STAMP website, including the addition of a video vignette to engage physicians and other physician engagement materials.
| 2015-12-31 | P | P | P | Finalize the Gold STAMP model with input from the Gold STAMP Coordinating Committee and, specifically, representatives of hospitals, nursing homes and home care. Post model on Gold STAMP website as a resource for application in other areas.
| 2/1/16 3/18/16 3/24/16 | P | P | P | Produce and duplicate DVDs thumb drives to include recorded webinars/webcasts and other materials for hospitals to use during Grand Rounds.
| 3/1/16 3/18/16 3/31/16 | P | P | P | Develop a Physicians' Toolkit that includes printed materials.
| 5/4/15 8/31/15 3/31/16 | P | P | P | Produce three webinars/webcasts on educational topics based on the 2014 Gold STAMP Focus Group Summary Report related to Collaborative sustainability and post to Gold STAMP website. |  | Webinar #1 5/4/15 Webinar #2 8/5/15 Webinar #3 1/14/16
| 7/31/15 11/30/15 12/31/15 3/31/16 | P | P | P | Add one Gold STAMP "success story" (one hospital, one nursing home, one home care agency) to Gold STAMP website on a triannual basis as an incentive to Collaboratives who have sustained their efforts. |  | Story #1 added 7/2015 Story #2 added 12/31/15
| 2016-03-31 | P | P | P | Build upon the Collaborative foundation established for the two New York State Veteran's Homes in 2014-15 to continue to improve performance in the area of pressure ulcer prevention/treatment, while promoting independent sustainability.
| 2016-03-31 | P | P | P | Continue to dialogue with all Collaboratives Statewide regarding their maintenance and sustainability.
| 2016-03-31 | P | P | P | Maintain and expand the Gold STAMP website to include comprehensive information on training programs, resources and links.
8003 |  |  |  |  | Project Name: Mainstream Managed Care Plan Profit Cap Division Lead: Team Lead: Connor Gemerek Additional Staff: Description: Effective April 1, 2015, this proposal implements a 5 percent profit cap on Mainstream Managed Care (MMC) plans. Any savings achieved would be reinvested through the MMC Quality Incentive (QI) Pool. The profit cap will be accomplished through a medical loss ratio (MLR) on premiums which will prescribe what plans must spend on health benefits in State Fiscal Year (SFY) 2015-16. |  | Cancelled
| 2015-07-01 | P | P | P | Create Recommendations/Methodology
| 2015-07-01 | P | P | P | Review Pending Federal Managed Care Rule
| 8/1/15 10/1/15 2/1/16 | 8 | 8 | 8 | Present Methodology to Plan Associations
| 10/1/15 11/1/15 2/1/16 | 8 | 8 | 8 | Review Plan Association Recommendations and Reach Consensus
| 10/1/15 11/1/15 2/1/16 | 8 | 8 | 8 | Determine Appropriate Effective Date
| 11/1/15 12/1/15 2/1/16 | 8 | 8 | 8 | Work with Program staff for Incorporation in Plan Contracts
| 11/1/15 12/1/15 2/1/16 | 8 | 8 | 8 | Solicit Input from Systems and FMG on Recoupment Process(if applicable)
| 12/1/15 1/1/15 3/1/16 | 8 | 8 | 8 | Implement Policy |  | 2016? yes MMCOR Data CY2014 and Final CMS MLR rule
8004 |  |  |  |  | Project Name: Alzheimer's Disease Caregiver Support Project Division Lead: Division of Long Term Care Bureau of Community Integration and Alzheimer Disease Team Lead: David Hoffman Additional Staff: Elizabeth Berberian, Erin Fay Description: This project will expand evidenced-based strategies to support AD patients and caregivers to increase early detection and care planning, improve quality of life, prevent and control complications and co-morbidities in patients and caregivers, and postpone or eliminate institutional placement. |  | Completed - June 2016
| 2015-04-01 | P | P | P | Develop Request for Staff Resources
| 2015-08-01 | P | P | P | Staff resources on board
| 2015-06-30 | P | P | P | Develop MOU with Ualbany & School of Public Health to Develop Evaluation Strategy
| 2015-04-01 | P | P | P | Draft Regional/Statewide Caregiver RFA
| 2015-04-15 | P | P | P | Initiate B1184
| 2015-04-15 | P | P | P | Initiate EDC
| 5/26/15 | P | P | P | Complete RFA Approval process
| 2015-06-01 | P | P | P | RFA Grants Gateway Translation
| 2015-06-01 | P | P | P | RFA Release
| 2015-08-01 | P | P | P | RFA Due Review Begins
| 9/15/15 10/15/15 | P | P | P | RFA Awards made
| 6/1/15 | P | P | P | Draft Focus Community Caregiver RFA
| 2015-06-01 | P | P | P | Initiate B1184
| 6/1/15 | P | P | P | Initiate EDC
| 7/15/15 8/15/15 9/15/15 10/15/15 11/15/15 | P | P | P | Complete RFA Approval Process |  | At FMG
| 7/31/15 8/15/15 9/15/15 10/15/15 11/15/15 | P | P | P | RFA Grants Gateway Translation
| 7/31/15 8/15/15 9/15/15 10/15/15 11/15/15 | P | P | P | RFA Release
| 10/1/15 11/1/15 1/15/16 | P | P | P | RFA Due Review Begins
| 11/1/15 2/1/16 4/1/16 5/9/16 | P | P | P | RFA Awards made
| 2015-04-10 | P | P | P | Draft Alzheimer's Disease Assistance Center/ Center of Excellence for Alzheimer's Disease RFA
| 2015-04-21 | P | P | P | Initiate B1184
| 2015-04-21 | P | P | P | Initiate EDC
| 5/22/15 6/23/15 | P | P | P | Complete RFA Approval Process
| 6/15/15 6/23/15 | P | P | P | RFA Grants Gateway Translation
| 6/15/15 6/23/15 | P | P | P | RFA Release
| 2015-08-15 | P | P | P | RFA Due Review begins
| 10/1/15 11/1/15 12/1/15 | P | P | P | RFA Awards made |  | Award package to JH 10/21/15
| 2015-06-15 | P | P | P | Process Contract Amendment for Alzheimer's Disease Community Assistance Program
| 2015-04-10 | P | P | P | Initiate B1184
| 2015-04-10 | P | P | P | Initiate CRER/EDC
| 6/1/15 6/19/15 | P | P | P | Process budgets/work plans
| 2016-06-01 | P | P | P | Convene Contractor Kick-off Meeting
| 2015-07-15 | P | P | P | Review Preliminary Evaluation Strategy
8005 |  |  |  |  | Project Name: MLTC Technology Demonstration Division Lead: Team Lead: Margaret Willard Andrew Segal Additional Staff: Erin Trowbridge Rose Avellino Krista McNally Description: Technology Demonstration with MLTC Plans |  | Complete Feb 2017
| 2015-06-18 | P | P | P | Develop survey of MLTC plans to gauge interest in demonstration
| 2015-07-13 | P | P | P | Review survey results
| 9/21/15 11/6/15 11/25/15 | P | P | P | Draft RFA
| 9/21/15 11/6/15 1/8/16 | P | P | P | Initiate B1184
| 11/27/15 2/1/16 | P | P | P | Prepare for executive review
| 11/30/15 2/1/16 | P | P | P | Send draft RFA to Division Executive staff for approval
| 12/11/15 2/15/16 3/1/16 | P | P | P | Receive draft RFA back and revise
| 12/14/15 2/15/16 3/10/16 | P | P | P | Send final RFA to Division Executive staff for approval
| 12/18/15 3/15/16 4/1/16 5/1/16 | P | P | P | Final RFA approval
| 12/8/15 3/15/16 4/1/16 5/1/16 | P | P | P | Complete RFA approval process
| 10/5/15 11/12/15 12/18/15 3/15/16 4/1/16 | P | P | P | Initiate EDC process
| 12/11/15 1/4/16 5/1/16 5/15/16 | P | P | P | RFA Release
| 2/12/16 7/1/16 | P | P | P | RFA application received
| 1/21/16 2/15/16 7/1/16 | P | P | P | RFA Review Process Initiated
| 2/19/16 2/29/16 10/1/16 12/1/16 1/1/17 3/1/17 | P | P | P | RFA Awards announced
8006 |  |  |  |  | Project Name: Advanced Training Initiative Division Lead: Team Lead: Frank Czernicki Additional Staff: Steve Simmons/ Jada Eberle Description: New advanced training program aimed at teaching staff to detect early changes in a resident's physical and mental or functional status that could lead to hospitalization. | ($46) Million | Completed January 2017
| 2015-04-15 | P | P | P | Meeting with DOH staff and 1199 representatives to discuss proposed program parameters
| 2015-04-29 | P | P | P | Meeting with OHIP and stakeholders to discuss data/detail program metrics and next steps
| 2015-04-29 | P | P | P | Review 2013 RHCF4 data looking for issues and explore options to correct
| 2015-04-29 | P | P | P | Discuss framework of project with NHQI staff - request advice - review Excellence Website data
| 2015-05-13 | P | P | P | Published FPN May 13, 2015
| 2015-05-28 | P | P | P | Prepare Preliminary SPA Package #15-0047
| 2015-06-05 | P | P | P | Review analysis and retention cost report data provided by 1199 - Determine Program Metrics
| 2015-06-12 | P | P | P | Provide proposal to NHQI and schedule internal meeting to review data metrics
| 2015-06-25 | P | P | P | Schedule internal meeting with DOH, DRS and NHQI to review data
| 2015-07-06 | P | P | P | Follow up meeting with Stakeholders to discuss analysis/data review and next steps
| 2015-07-06 | P | P | P | Discuss alternate program proposals with additional Stakeholders
| 2015-07-07 | P | P | P | Create questionnaire/ survey to collect necessary data from Nursing Homes to account for data issues with the 2013 Schedule P (if necessary)
| 2015-07-07 | P | P | P | Share proposed application with stakeholders for review and amendments
| 2015-07-20 | P | P | P | Group Meeting (1199, DRS and Associations) to discuss progress on application / payment methods.
| 2015-07-24 | P | P | P | Revise application and distribute to members for final review
| 2015-08-04 | P | P | P | Group Meeting (1199, DRS and Associations) to finalize application
| 2015-08-19 | P | P | P | Extract data from Schedule P for analysis and determine if data is reasonable
| 2015-08-19 | P | P | P | Analyze and distribute the data from Schedule P to group members
| 2015-08-21 | P | P | P | Finalize and determine most appropriate method for payment and determine data needed to complete project
| 8/22/15 9/24/15 | P | P | P | Review and approval by DOH executives
| 8/24/15 9/28/15 | P | P | P | Distribute the applications / requirements to facilities to collect data
| 9/5/15 10/10/15 | P | P | P | Receive Application and Finalize and Develop Criteria and Metrics to identify eligible facilities
| 9/5/15 10/12/15 | P | P | P | Finalize the methodology of allocating the funds
| 9/5/15 10/12/15 11/15/15 12/16/15 | P | P | P | Finalize SPA package
| 9/5/15 10/12/15 11/15/15 1/11/16 2/11/16 2/15/16 | P | P | P | Submit SPA for review and approval from DOH executives |  | RAI answered and awaiting approval from CMS
| 9/30/15 10/15/15 11/15/15 TBD 3/9/16 | P | P | P | SPA Approval from DOB
| 10/1/15 10/30/15 | P | P | P | Collect data to determine qualified facilities
| 10/1/15 10/30/15 1/18/16 | P | P | P | Request needed cost report changes
| 10/1/15 10/30/15 | P | P | P | Review qualified training programs and approve
| 10/15/15 11/15/15 | P | P | P | Process Rate Adjustment - Allocating funds among qualified facilities
| 10/30/15 11/17/15 | P | P | P | (State share only) Submit to DOH executives for rate adjustment approvals
| 11/15/15 12/22/15 | P | P | P | (State Share Only) Send Adjusted Rates to DOB for approval |  | Sent to DOB 12/22/15 - Waiting on Approval
| 12/1/15 12/15/15 12/30/15 2/9/16 | P | P | P | (State Share Only) Send Approved Rates to EMedNY FMG for Payment
| 2016-03-09 | P | P | P | (Fed Share) Submit to DOH executives for rate adjustment approvals
| 2016-03-09 | P | P | P | (Fed Share) Send Adjusted Rates to DOB for approval
| 2016-03-09 | P | P | P | (Fed Share) Send Approved Rates to EMedNy and FMG for Payment
| 1/1/16 4/1/16 | P | P | P | Monitor effectiveness of implemented programs
| 2016-07-15 | P | P | P | Receive Nursing Home Cost Reports
| 8/15/16 9/1/16 9/22/16 | P | P | P | Workgroup meeting to discuss next steps. Review results of implementation and modifications to next payment.
| 8/19/16 9/1/17 9/22/16 | P | P | P | Analyze and distribute the data from Schedule P to group members
| 2016-08-21 | 8 | 8 | 8 | Workgroup meeting to discuss cost report data.
| 8/25/2016 10/10/16 | P | P | P | Finalize and determine most appropriate method for payment and determine data needed to complete project
| 9/10/2016 10/20/16 | P | P | P | Review and approval by DOH executives
| 9/28/16 10/19/16 | P | P | P | Distribute the applications / requirements to facilities to collect data
| 10/10/16 10/20/16 10/31/16 | P | P | P | Receive Application and Finalize Criteria and Metrics to identify eligible facilities
| 10/12/16 11/20/16 | P | P | P | Finalize the methodology of allocating the funds
| 10/30/16 10/18/16 10/31/16 12/15/16 | P | P | P | Finalize SPA package (2nd payment approved by CMS but requires supporting documents)
| 2016-10-30 | 8 | 8 | 8 | Submit SPA for review and approval from DOH executives
| 10/30/16 11/20/16 | P | P | P | Collect data to determine qualified facilities
| 10/30/16 11/20/16 11/30/16 | P | P | P | Review qualified training programs and approve
| 11/15/16 12/15/16 12/20/16 | P | P | P | SPA Rate package approval from DOB
| 2016-12-01 | P | P | P | Process Rate Adjustment - Allocating funds among qualified facilities
| 12/15/16 12/31/16 | P | P | P | Release payments to facilities
8007 |  |  |  |  | Project Name: Medicaid Transportation Fee Enhancement- and Standardization Division Lead: Liz Misa Team Lead: Mark Bertozzi Additional Staff: Heidi Seney, Bob Schmit Description: |  | Completed - May 2015
| 2014-07-31 | P | P | P | Worked with Transportation Manager to perform assessment of Medicaid Transportation fee schedule.
| 2014-08-15 | P | P | P | Identified levels of transportation by County that could potentially lead to access issues.
| 2014-08-30 | P | P | P | Compared fees of those identified to contiguous counties and comparable markets to recommend proposed fee increases .
| 2014-09-07 | P | P | P | Performed fiscal analysis to project cost and fiscal impact.
| 2014-09-15 | P | P | P | Develop proposal.
| 2014-10-01 | P | P | P | Reach internal consensus and recommendation.
| 2015-04-01 | P | P | P | Executive Budget passing
| 2015-04-30 | P | P | P | Post budgetary Division Head approval.
| 2015-05-01 | P | P | P | Updated fee schedule and eMedNY accordingly.
8008 |  |  |  |  | Project Name: Health Home-Criminal Justice Initiative Division Lead: DPDM Team Lead: Deidre Astin Lana Earle, Amy Clinton Additional Staff: Lynda Hohmann, Joann Susser, Tracie Gardner, Jodi Munson, Amy Clinton, Stephanie Fuertes, Nancy Pleickhardt Description: The goal of this initiative is to provide Health Home eligible criminal justice involved persons coordinated access to Health Homes to improve their medical, behavioral and social health and reduce recidivism. This will required Health Homes to directly work with the Criminal Justice system to ensure such coordination is in place. |  | Completed April 2017
| 2015-12-01 |  |  |  | Creation and approval of criteria for funds distribution
| 12/1/15 12/2/15 | P | P | P | Finalization of distribution methodology
| 2/8/16 4/1/16 | 8 | 8 | 8 | Completion of back office Grants Gateway requirements
| 2/15/16 4/1/16 | 8 | 8 | 8 | Application Gateway opens
| 2016-04-01 | 8 | 8 | 8 | Approval for Recommendation for Distribution of funding 15-16
| 2016-04-15 | 8 | 8 | 8 | Contracting Complete/Fund distribution - pending legislation
| 2015-09-23 | P | P | P | Federal Notice for Waiver |  | FN withdrawn
| 2/1/16 4/1/16 | 8 | 8 | 8 | Submission of Waiver for payment of specific svcs.
| 2016-04-01 | P | P | P | Resolution of state law/regulation re: payment of svcs. Legislation submitted with the 16-17 Budget to expedite payment process to the Criminal Justice Health Home Pilots – this would avoid the longer more cumbersome Gateway process |  | Legislation approved
| 2016-05-13 | P | P | P | Finalize mechanics for distribution of funding
| 5/13/16 5/23/16 6/20/16 8/15/16 9/19/16 10/3/16 | P | P | P | Finalize reporting documentation for funding
| 6/15/2016 6/20/16 8/15/16 9/19/16 9/26/16 9/13/16 | P | P | P | Approval from DOB regarding funding distribution |  | NYS DOB has authorized the payment of $2.5 million
| 2/1/16 4/1/16 5/16/16 6/20/16 6/27/16 8/22/16 9/26/16 10/3/16 10/19/16 | P | P | P | Notification to Pilot Health Homes of Requirements for Funding
| 6/1/16 7/5/16 7/11/16 9/6/16 10/17/16 10/19/16 | P | P | P | Health Home Pilot Notice of Intent to participate Due
| 6/15/16 7/18/16 7/25/16 9/19/16 10/31/16 11/18/16 | P | P | P | Application/Preliminary Assessment documentation Due
| 2016-11-21 | P | P | P | Review of Preliminary documentation/Notify MFM of awards
| 7/1/16 8/1/16 8/8/16 9/26/16 11/7/16 12/21/16 | P | P | P | Approval for funding finalized by MFM
| 7/11/16 8/15/16 10/3/16 11/15/16 12/21/16 | P | P | P | First payment of funding distributed
| 10/15/16 10/17/16 1/16/17 | P | P | P | First quarterly report due - in progess - HH are reporting
| 2017-01-19 | P | P | P | First Monthly meeting with the HH pilots to discuss progress
| 1/20/2017 2/1/17 2/28/17 3/22/17 | P | P | P | Second payment of funding distributed after report review
| 1/15/2017 1/16/17 4/15/17 4/21/17 | P | P | P | Second quarterly report due created in error
| 4/15/2017 7/15/17 | P | P | P | Third quarterly report due - created in error
| 7/15/2017 10/16/17 | P | P | P | Fourth quarterly report due created in error
8009 |  |  |  |  | Project Name: ICAN Expansion Division Lead: Mark Kissinger DLTC Team Lead: Shanon Vollmer, Pavel Terpelets, Julie Oare, Heather Grimmer Additional Staff: Patricia Sheppard/Gary Rinaldi Description: Expansion of LTC Ombudsman to all Managed Care Recipients |  | Completed December 2017
| 2015-04-28 | P | P | P | Kick- Off Meeting
| 2015-05-07 | P | P | P | Weekly Team Meetings
| 2015-05-21 | P | P | P | Identify Scope
| 2015-05-21 | P | P | P | Identify Target Population(s)
| 2015-05-28 | P | P | P | Meet with Bureau of Contracts
| 2015-06-15 | P | P | P | Identify Contract Mechanism
| TBD | 8 | 8 | 8 | Contracting Subtasks - TBD
| 2015-06-15 | P | P | P | Implementation Timeline
| 2015-10-01 | 8 | 8 | 8 | Release RFA |  | on hold for 2016/2017 budget
| 2015-12-01 | 8 | 8 | 8 | DOH internal award approval
| 2016-01-15 | 8 | 8 | 8 | OSC approval of the procurement package
| 2016-01-30 | 8 | 8 | 8 | Contract package signed by DOH
| 2016-03-01 | 8 | 8 | 8 | Contract approved by AG/OSC
| 12/1/15 3/15/16 | 8 | 8 | 8 | Training Material Review and Approval
| 12/15/15 3/25/16 | 8 | 8 | 8 | Ombudsman Staff Training
| 1/1/16 4/1/16 | 8 | 8 | 8 | Program expansion
| 2/1/16 6/1/16 | 8 | 8 | 8 | Marketing/Outreach Plan Review and Approval
| 3/1/16 5/1/16 | P | P | P | Approval of B1184 to add HARP population
| 2016-06-08 | P | P | P | Approval of the CRER package by OSC
| 4/1/16 6/1/16 7/1/16 9/1/16 11/15/16 3/1/17 6/1/17 | P | P | P | Approval of contract amendment package
| 2/1/16 6/1/16 10/1/16 1/1/17 3/1/17 7/1/17 11/20/17 | P | P | P | Updates to all MLTC and Mainstream Medicaid notices to include information about ICAN
| 2/1/16 8/1/16 10/1/16 11/15/16 3/1/17 7/1/17 | P | P | P | Updated website
| 3/1/16 8/1/16 10/1/16 | P | P | P | Data Collection and Reporting requirements
8010 |  |  |  |  | Project Name: BIP NY Connects Expansion Division Lead: Mark Kissinger Andrew Segal Team Lead: Karen Ambros Laurie Lucinski, Karen Meier Additional Staff: Laurie Lucinski, Alicia Segura Description: Expand NY Connects for a statewide network to provide comprehensive information and assistance about LTSS's across disability populations. | 18.1 22.7 | Completed December 2017
Section A |  |  |  |  | DEVELOP STATEWIDE NETWORK OF NO WRONG DOOR (NWD) AGENCIES (NY CONNECTS) TO PROVIDE COMPREHENSIVE INFORMATION, ELIGIBILITY DETERMINATIONS, COMMUNITY LTSS PROGRAM OPTIONS COUNSELING AND ENROLLMENT ASSISTANCE. 3 COUNTY PILOT- 9/30/15, 6 COUNTY PILOT - 2/1/16, GROUP 1 COUNTIES- 8/1/16 6/15/16 4/1/16, GROUP 2 COUNTIES - TBD 10/1/16 7/1/16, GROUP 3 COUNTIES 10/1/16 |  | Pilot shortened by one month & added implementation group 7/1/16. 11/18/15: Combined Group 1 and 2.
| 2015-05-11 | P | P | P | PI for existing agencies issued Program Instruction for existing AAAs (Area Agencies on Aging) issued to enhance functionality required by BIP
| 5/29/15 6/29/15 7/31/15 | P | P | P | DOH-SOFA MOU executed Execute MOU between DOH and NYSOFA |  | MOU in clearance process.
| 2015-07-01 | 8 | 8 | 8 | Pilot County Selection
| 7/31/15 8/31/15 9/30/15 11/30/15 1/31/16 5/1/16 6/1/16 | P | P | P | Approve applications from existing AAAs (these include enhanced functionality financed through BIP grant) | As of 10/21, 30 out of 53 total NGAs have been issued. The rest are in the review process. 11/17/15 Update: 34 NGA's have been executed for existing NY Connects programs and for new counties. 12/17/15 Update: 40 NGAs have been executed. 2/17/16 Update: 49 NGAs executed. 3/17/16 update: 53 NGA's have been executed. 4/20/16 Update: 58 NGAs have been executed. One remains.
| 8/31/15 9/30/15 10/31/15 4/1/16 | P | P | P | Expand to provide statewide coverage: approve new applications for the 5 counties and NYC - not currently participating in NY Connects | NYC is executed, the other 4 are in process. 10/21 11/18/15: NYC, Oswego, Rensselaer are executed. Rockland and Seneca Nation is in process. Seneca County will need to be formalized via an RFA. NGAs with all new counties are executed.
| 7/31/15 9/30/15 11/30/15 12/31/15 3/31/16 9/1/16 | P | P | P | Local Implementation Teams formed to support expansion | All need to be formed before the statewide database is live.
| 9/30/15 11/30/15 12/31/15 3/31/16 5/30/16 6/30/16 | P | P | P | Local agency MOUs executed MOUs between local "hubs" (AAAs) and local partners executed | Initiated biweekly calls with AAA's. Questions & comments from the first call indicate AAA's are working on the MOU's. 9/17/15: We have 21 MOUs. Update 10/21/15: 27 MOUs are executed. Delays are due to timeline for approvals at the county level. Update 12/17/15: 40 MOUs are executed. 1/21/16: 44 MOU's are executed. 3/17/16 Update: 50 MOU's are executed. 4/20/16: 54 MOUs are executed. Five remain. 5/16/16: 55 MOUs have been executed. 6/14/16: 56 MOUs have been executed.
| 12/18/15 2/1/16 7/1/16 11/1/16 2/1/17 | P | P | P | DA contracts executed Enhance functional capacity of NY Connects - execute contracts with approximately 5 regional Disability Agencies (ILCs)
LAUNCH NEW WEBSITE FOR NY CONNECTS WITH RESOURCE DIRECTORY AND ONLINE QUESTIONNAIRE
| 2016-07-31 | 8 | 8 | 8 | Local Implementation Teams formed
| 6/15/15 6/29/15 7/13/15 7/24/15 8/31/15 | P | P | P | IT Vendor for new Website and Resource Directory contract start
| 8/31/15 9/21/15 9/30/15 | P | P | P | Data migration complete from existing NY Connects Resource Directory, OPWDD Directory and OMH Directory complete | Initial data migration complete; issues identified and being corrected for ongoing data feeds.
| 2015-09-24 | P | P | P | Deliver training to NY Connects staff in navigating the new website and resource directory
| 2015-09-24 | P | P | P | System Testing Complete
| 2015-09-30 | P | P | P | New Website and Resource Directory go live- expanded network for access goes live.
| 12/31/15 7/1/16 12/1/16 7/1/17 9/21/17 | P | P | P | Self-assessment/questionnaire live on the NY Connects website | Self-assessment is now a self-guided search on the improved NY Connects website to be unveiled by the third week in September. Work with contractor to accomplish both consumer facing and backend experience in ongoing.
IMPLEMENT NEW SCREENING TOOL FOR INDIVIDUALS SEEKING INFORMATION AND RESOURCES FOR LONG TERM SERVICES AND SUPPORTS (LTSS) - NO WRONG DOOR (NWD) SCREEN
| 2015-05-29 | P | P | P | Level 1 NWD Screen instrument finalized
| 2015-07-01 | P | P | P | Select counties to pilot the No Wrong Door (NWD) Screening Tool in UAS-NY | 3 selected & accepted; Erie, Onondaga, Oswego. 3 additional pilot counties are confirmed for a total of 6: Albany, Monroe and Schoharie.
| 8/20/15 1/1/16 2/1/16 | P | P | P | NWD Screen software development complete | Vendor is not able to meet original delivery date due to procurement delays. Pilot for enhanced functionality has been delayed to 2.1.16 1.1.16. The number of pilot counties has been is being increased from 3 to 6. Software was released to production 1/29/16. Specifications for the next release, planned for May 2016, are being developed.
| 9/1/16 9/25/15 12/31/15 1/31/16 4/1/16 | P | P | P | Mandatory System Training Complete for Pilot Counties | Delays in course development have required additional time for the Pilot Counties to complete training in the UAS-NY. Pilot counties have completed all courses available to them in the UAS-NY. Focus groups were conducted to determine readiness and determine how to revise training for statewide implementation. Based on feedback received, Pilots counties will receive additional training prior to opening up access to the NWD Screen in TEST Drive.
| 10/1/16 10/1/15 1/1/16 2/1/16 4/15/16 6/1/16 7/1/16 | P | P | P | Local NY Connects agencies Pilot counties conducting NWD screen in UAS-NY in TEST Drive | Delayed the Pilot Test Drive for further system development. Added focus group activity to begin 4/15/16. Based on focus group feedback, TEST Drive access is being moved to 6.1.16 Based on contract delays, TEST Drive access is being moved to 7.1.16.
| 2016-04-01 | 8 | 8 | 8 | Group 1 Counties conducting NWD Screen in UAS-NY
| 7/1/16 9/15/16 1/15/17 2/15/17 3/1/17 8/1/17 | P | P | P | Begin rolling implementation of Counties conducting NWD Screen in UAS-NY |  | Added implementation group.
| 10/1/16 9/15/16 12/1/16 4/15/17 | 8 | 8 | 8 | Group 2 3 2 Counties conducting NWD Screen in UAS-NY | The screen is in the process of being moved to Peer Place
ESTABLISH SINGLE STATE-WIDE 1-800# WITH ROUTING TO COUNTY-LEVEL NY CONNECTS AGENCIES FOR LTSS INFORMATION AND SERVICES
| 6/15/15 6/30/15 7/24/15 | P | P | P | Local NY Connects submit local numbers for routing |  | In process
| 6/15/15 6/30/15 7/24/15 | P | P | P | Specifications for 1-800 service complete |  | In process
| 9/1/15 9/30/15 | P | P | P | 1-800# Operational |  | Testing during September with switchover 9/29.
IMPLEMENT ADVERTISING AND OUTREACH CAMPAIGN TO PROMOTE NY CONNECTS AS THE "GO TO" SOURCE FOR INFORMATION AND SUPPORT RELATED TO LTSS
| 6/1/15 7/31/15 8/31/15 | P | P | P | Procurement authorizations complete for market research, education materials, and advertising campaign | B1184's approved; EDCC in clearance process approved
| 2015-09-30 | P | P | P | Year One Print materials (brochure and poster) Updated brochure complete and distributed to local NY Connects agencies
| 6/1/2016 1/31/17 10/1/16 | 8 | 8 | 8 | Conduct market research (Focus Groups) to inform advertising campaign development and media selection |  | Focus Groups were eliminated from the implementation plan. Campaign will be informed by existing data.
| 11/1/2016 2/1/17 5/1/17 6/1/17 7/31/17 | P | P | P | Media buys complete
| 1/31/2017 6/1/17 7/31/17 | P | P | P | Execute advertising campaign
TASK 6: INTEGRATE ALL COMPONENTS INTO AN OPERATING SYSTEM AND PREPARE FOR IMPLEMENTATION
| 6/12/15 8/1/15 | 8 | 8 | 8 | Finalize data sharing agreements across State agencies
| 7/30/15 8/15/15 | 8 | 8 | 8 | Organization Accounts established in UAS-NY
| 2016-09-01 | 8 | 8 | 8 | Finalize Operating Protocols
| 2016-08-30 | 8 | 8 | 8 | Deliver Programmatic Training
| 2016-09-01 | 8 | 8 | 8 | Issue Implementation Guide
| 2016-09-25 | 8 | 8 | 8 | Deliver System and Application Related Training
Section B |  |  |  |  | ADMINISTRATIVE REQUIREMENTS - FINAL WORK PLAN
REPORTING REQUIREMENTS TO CMS
| 2/16/16 TBD 3/1/16 | P | P | P | Online status update for quarter ending 12/31/15 | NYS is waiting for Truven to fix the reporting system and for CMS to announce a new due date once done. NYS submitted off-line version on 3/1/16.
| 4/30/16 5/15/16 5/16/16 | P | P | P | Monitoring Plan for quarter ending 3/31/16
| 5/15/16 5/17/16 | P | P | P | Online status update for quarter ending 3/31/16
| 7/30/16 8/26/16 | P | P | P | Monitoring Plan for quarter ending 6/30/16 | Extension recvd to 8/26/16
| 2016-08-15 | P | P | P | Online status update for quarter ending 6/30/16
| 10/31/16 11/15/16 | P | P | P | Monitoring Plan for quarter ending 9/30/16 | Report due date has been moved from 30 to 45 days after close of quarter.
| 2016-11-15 | P | P | P | Online status update for quarter ending 9/30/16
| 1/31/2017 2/15/17 | P | P | P | Monitoring Plan for quarter ending 12/31/16
| 2017-02-14 | P | P | P | Online status update for quarter ending 12/31/16
DISBURSEMENTS FROM THE BIP FUND
| 2015-07-31 | P | P | P | Develop and implement cross agency protocols for disbursement authorization and execution based on transaction type
| 2016-03-11 | P | P | P | Develop and communicate disbursement benchmarks for State agencies
| 2016-03-15 | P | P | P | Enter benchmark tasks on MRT workplan for tracking
| 2016-03-15 | P | P | P | Implement monthly reporting cycle for benchmark measures
| 2016-03-15 | P | P | P | Calculate and enter preliminary benchmark measures tasks on MRT workplan for tracking
| 3/23/16 and each month thereafter | P | P | P | Actual Expenditures vs. Expected Disbursements Projections Expenditures as of: 2/29/16 (Preliminary Estimate) 3/31/16 (With Updated Projections) 4/30/16 5/31/16 6/30/16 4/30/17 Goal: 100% |  | Projections are being calculated to align with new recast to be submitted May 15, 2017
| 3/23/16 and each month thereafter | 8 | 8 | 8 | Actual Disbursements vs. Expected Disbursements as of: 2/29/16 (Preliminary Estimate) 3/31/16 (With Updated Projections) 4/30/16 5/31/16 6/30/16 Goal: 100%
| 3/23/16 and each month thereafter | 8 | 8 | 8 | #/$ Disbursement Requests in Process as of: 2/29/16 (Preliminary Estimate) 3/31/16 4/30/16 5/31/16 6/30/16 |  | Focusing on 9/30/2017 expenditure deadline.
| 2016-04-27 | P | P | P | Improve and refine benchmark calculations.
PROJECTIONS & RECAST
| 2016-01-15 | P | P | P | Recast sent to CMS
| 6/8/16 3/31/16 | P | P | P | Spending projections recalculated
| 2016-06-15 | P | P | P | Recast sent to CMS
| 1/6/2017 and monthly thereafter | P | P | P | Spending projections recalculated
| 1/15/2017 3/31/17 5/1/17 6/1/17 | P | P | P | Recast sent to CMS
8011 |  |  |  |  | Project Name: HCBS Settings Statewide Transition Plan Division Lead: OPCHSM Project Lead: Mark Kissinger Team Lead: Karen Meier, Madeline Kennedy Description: Implement STP Across All Agencies/Offices |  | Merged - Moved to Phase 8 #11003
| 6/15/15 9/1/15 10/1/15 11/1/15 2/1/16 | P | P | P | Develop RFP to Hire Consultant to Implement STP
| 12/31/15 7/31/16 1/1/17 2/1/2017 4/1/17 5/1/17 | P | P | P | Procure Consultant
| 12/31/15 3/31/16 7/1/16 10/1/16 12/1/16 1/15/2017 5/1/2017 6/1/17 11/1/17 | P | P | P | DOH Staff Develops Surveys for Residential and Non-residential settings
| 5/31/16 7/1/16 10/1/16 12/1/16 2/1/2017 3/31/17 6/1/17 12/1/17 | P | P | P | Consultant DOH Implements Residential and Non-residential surveys
| 1/31/16 7/31/16 12/31/16 3/31/17 6/28/17 8/23/17 | P | P | P | Consultant Develops Evaluation Tool to Validate Survey Results and Remediation Efforts; Engages Stakeholders in Process
| Before 1/31/18 Through 12/1/18 | 8 | 8 | 8 | Consultant Reports to DOH/DLTC on Compliance Based on Survey Results
| Before 7/31/18 1/31/18 9/30/18 | P | P | P | Consultant Develops Remediation Plan for Approval by DOH/DLTC in consultation with service agencies and offices (OPWDD, OMH, OCFS, OASAS)
| Before 1/31/18 1/31/21 | 8 | 8 | 8 | Consultant State implements Remediation Plans, including heightened scrutiny process for settings that are presumed institutional but that can be shown to have the characteristics and qualities of home and community based settings. Process will include gathering public input for evidence to be submitted to CMS to support the assertion that these are community based settings.
| Before 7/31/18 7/31/21 | 8 | 8 | 8 | Consultant reports to DOH/DLTC on State reports compliance with remediation plans and progress on CMS designating presumed institutional settings as appropriate HCBS settings.
| Before 3/17/19 3/17/22 | 8 | 8 | 8 | Transition any individuals or programs that remain in settings not considered appropriate for HCBS to compliant settings or designate the illegal settings as institutional and not eligible for HCBS Medicaid funding.
8012 |  |  |  |  | Project Name: Air Ambulance Division Lead: Team Lead: Mark Bertozzi Additional Staff: Heidi Seney, Bob Schmit (POC) Description: |  | Completed - May 2015
| 2015-02-06 | P | P | P | Received fee increase request from Air Ambulance, later included in budget by Senate
| 2015-02-07 | P | P | P | Calculated fiscal impact of the request.
| 2015-02-07 | P | P | P | Developed and fiscalized counterproposal.
| 2015-02-07 | P | P | P | Submitted both fiscals to senior staff for recommendation.
| 2015-04-01 | P | P | P | Budget appropriation in Executive Budget.
| 2015-04-14 | P | P | P | Internal meetings to determine implications.
| 2015-04-30 | P | P | P | Approval by Division Lead.
| 2015-05-01 | P | P | P | Update system and fee schedules accordingly
8013 |  |  |  |  | Project Name: Supplemental Ambulance Division Lead: Liz Misa Team Lead: Mark Bertozzi Additional Staff: Mary Thatcher, Lani Rafferty Description: |  | Completed - June 2016
| 2015-04-01 | P | P | P | Budget appropriation in Executive Budget.
| 2015-04-14 | P | P | P | Submitted State Plan Amendment Request Form
| 2015-04-23 | P | P | P | Submitted SPA Package to Bureau of Federal Relations & Provider Assessments
| 2015-06-01 | P | P | P | SPA Approval by Jason Helgerson
| 8/15/15 8/5/15 | P | P | P | Request 1st quarter list of providers to receive payment
| 2015-09-01 | P | P | P | Notify Prepare 1st quarter information to be mailed to providers receiving Supplemental Payment once approved by CMS
| 2015-10-01 | 8 | 8 | 8 | Payments processed
| 2015-09-29 | P | P | P | CMS issued Request for Additional Information (RAI)
| 2015-10-28 | P | P | P | Response to RAI forwarded to CMS
| 2015-11-01 | P | P | P | Request 2nd quarter list of providers to receive payment
| 2015-11-15 | P | P | P | Notify Prepare 2nd quarter information to be mailed to providers receiving Supplemental Payment once approved by CMS
| 2015-12-15 | 8 | 8 | 8 | Payments processed
| 8/15/15 1/28/16 | P | P | P | SPA Approval by CMS
| 2016-02-01 | P | P | P | Request 3rd quarter list of providers to receive payment
| 2016-02-15 | P | P | P | Prepare/combine 1st, 2nd and 3rd quarter information to be mailed to providers receiving Supplemental Payment once approved by CMS
| 2/15/16 2/22/16 2/25/16 | P | P | P | Notify providers receiving Supplemental Payment (for quarters 1,2 & 3)
| 2016-03-15 | P | P | P | Payments processed (for quarters 1, 2 & 3)
| 5/1/16 6/30/16 | P | P | P | Request 4th quarter list of providers to receive payment
| 5/15/16 6/30/16 5/1/16 6/2/16 | P | P | P | Notify providers receiving Supplemental Payment
| 6/15/2016 6/29/2016 | P | P | P | Payments processed
8014 |  |  |  |  | Project Name: Rural Transportation Division Lead: Team Lead: Mark Bertozzi Additional Staff: Heidi Seney, Bob Schmit Description: |  | Complete - April 2016
| 2015-04-01 | P | P | P | Develop proposal- upstate rural ambulance standardization of paramedic intercept, bls, als and add on mileage.
| 2015-05-15 | P | P | P | Present proposal to Division Head
| 2015-05-29 | P | P | P | Meet with Senate to discuss proposal
| 2015-06-12 | P | P | P | Division Head approval
| 6/15/15 11/1/15 | P | P | P | Update fee schedule and systems. Disbursement to the rural public transit counties
| 2015-08-01 | P | P | P | Senate agrees to alternative proposal to dispersal disburse $4M to upstate Public Transit systems public transits
| 2015-10-24 | 8 | 8 | 8 | Response from CMS received
| 2016-02-01 | P | P | P | DOH, DOT, Senate agree on $4M disbursement methodology
| 2016-04-01 | P | P | P | Disbursement of $4M to the rural public transit counties
8015 |  |  |  |  | Project Name: Young Adult Special Populations Demo Division Lead: Team Lead: Michelle Santos Additional Staff: Description: An initiative to establish up to three demonstration program that will provide cost effective, necessary services and enhance quality of care for residents age 21-35 with severe/chronic medical conditions and are aging out of a pediatric unit. | -1000000 | In Progress
| 2015-04-15 | P | P | P | Request Federal Public Notice.
| 2015-04-16 | P | P | P | Meeting with Centerlight /DPL/ DFRS to discuss Centerlight Article VII authorization. |  | Meeting was requested by Centerlight
| 2015-04-27 | P | P | P | DOH inter-departmental meeting on program - SET NEXT STEPS FOR YOUNG ADULT ANALYSIS - discuss possible workgroup.
| 2015-05-05 | P | P | P | Meeting with DPL / DFRS and Center for discovery to discuss the Article VII authorization. |  | Meeting was requested by Center for discovery
| 2015-05-22 | P | P | P | Determine number of young adults within NYS Nursing Homes (21-35 yrs. old).
| 2015-05-28 | P | P | P | Prepare preliminary SPA package #15-0037. (SPA has been retracted - no longer required. Program will proceed with State funding only)
| 2015-09-23 | P | P | P | Completed RAI responses.
| 6/19/15 9/25/15 | P | P | P | DFRS/ DPL work plan discussion.
| 6/26/15 10/15/15 | P | P | P | Determine process for selection of young adult demonstration programs and deliverables for the report.
| 2015-10-16 | 8 | 8 | 8 | Prepare Letter of Interest to submit to prospective program participants
| 2015-11-13 | P | P | P | Progress discussion.
| 2015-11-18 | P | P | P | Meeting to discuss RFP/A process.
| 2015-11-23 | P | P | P | Meeting to discuss SPA elimination.
| 12/28/15 1/8/16 | P | P | P | RFP Refinement
| 2016-02-09 | P | P | P | RFP Discussion
| 2016-04-01 | P | P | P | Bureau of Contracts review
| 4/25/116 | P | P | P | Meeting to select reviewers for propsals
| 1/30/16 2/22/16 3/15/16 4/29/16 6/15/16 7/1/16 | P | P | P | RFP Public Notice
| 2016-08-15 | P | P | P | RFP Bidders questions / responses
| 10/20/15 02/15/17 3/31/17 | P | P | P | Review applications and determine awards.
| 10/20/15 11/18/16 | P | P | P | Panel completes review of applications.
| 2016-12-09 | P | P | P | Cordinator reviews evaluations
| 2/10/2017 02/22/17 6/8/17 | P | P | P | Submit/receive approvals |  | Estimate B1184 approval 6/8/17
| 2017-03-10 | P | P | P | BOC submits VAP /approval
| 5/12/2017 7/5/17 08/05/17 08/24/17 12/1/2017 01/26/18 | P | P | P | OSC submit and approve contracts
| 7/22/15 10/23/15 TBD 05/31/17 10/15/17 12/18/17 02/10/18 | P | P | P | Meet with awardees to discuss timeframes, deliverables, and reporting.
| 10/1/15 10/30/15 TBD 10/31/17 06/30/18 07/15/18 08/31/18 09/30/18 | P | P | P | Deliverables and awardee reports Due to DOH. |  | Initial report due within 6 months, final report due within 12 months
| 10/15/15 11/1/15 TBD 11/02/17 05/31/17 05/31/18 09/30/18 10/30/18 | 8 | 8 | 8 | Begin draft report of demo findings for legislature.
| 10/30/15 11/1/15 TBD 11/20/17 12/28/17 02/15/18 10/01/18 11/15/18 | 8 | 8 | 8 | Division Review/Approval.
| 11/13/15 TBD 12/15/17 03/28/18 08/15/18 10/15/18 12/15/18 | 8 | 8 | 8 | DOB Review/Approval.
| 11/23/15 12/15/15 TBD 01/01/18 04/01/18 06/01/18 09/01/18 11/01/18 | 8 | 8 | 8 | Release payments to awardees. |  | Once initial report has been submitted and after final report has been submitted
| 12/31/15 12/31/16 12/29/17 12/29/18 | 8 | 8 | 8 | Report Findings to Legislature.
8016 |  |  |  |  | Project Name: Community First Choice Option/ Investments in Olmstead Division Lead: Mark Kissinger, Andrew Segal Team Lead: Karen Meier Karis Browder Krista McNally Additional Staff: Krista McNally Hollie Kennedy Description: |  | In Progress
OBTAIN FEDERAL APPROVAL OF SPA SUBMITTED 12/29/2013 (13-35)
| Before 9/1/15 10/15/15 10/23/15 | P | P | P | Conclude current negotiations with CMS and obtain federal approval
OPERATIONALIZE SPA
| 12/30/15 3/1/16 | P | P | P | Draft Plan to Operationalize SPA Application Components, including claiming 6% | CMS and Rate Setting Staff continue to negotiate claim methodology.
| 2015-06-30 | P | P | P | Determine Any Differences in Implementation FFS/MC/MLTC
| 2015-06-30 | P | P | P | Determine MLTC Capitation Allocation for CFCO Operation
| 6/1/16 10/1/16 | P | P | P | Develop an operation plan for implementation in FFS system
| 2016-11-01 | P | P | P | Send notice to CMS regarding MMC/MLTC expanded scope of benefits to bring in CFCO services and supports
| 2016-11-01 | P | P | P | Send 60 day MCO notice of CFCO services carve-in
| 7/1/16 1/1/17 7/1/17 1/1/18 | P | P | P | Resolve conflict of interest SPA language dispute with CMS
| 10/1/16 7/1/17 | 8 | 8 | 8 | Amend MMC/MLTC contracts to include CFCO services and supports as plan benefits
| 11/1/16 2/1/17 5/1/17 11/1/17 2/1/18 7/1/18 11/1/18 | 8 | 8 | 8 | Complete MMC/MLTC Plan Readiness Activities
| 2016-11-01 | 8 | 8 | 8 | Establish an enhanced Provider Network Directory with MMC/MLTC plans to include providers of CFCO services and supports
| 4/1/17 7/1/17 1/1/18 4/1/18 | P | P | P | CFCO required services available in MCO and FFS
FISCAL IMPACT
| 2015-06-30 | P | P | P | Estimate Enrolled Individuals |  | annually
| 2015-06-30 | P | P | P | Estimate Service Dollar Expenditures |  | annually
| 2015-06-30 | P | P | P | Determine Maintenance of Expenditure Per Statute/Reg |  | one time
| 2015-06-30 | P | P | P | Establish criteria to allow fiscal division to determine utilization in FFS/MC
| 12/30/15 3/1/16 | P | P | P | Develop FMAP Submission Process | CMS and Rate Setting Staff continue to negotiate claim process.
| 2016-09-01 | P | P | P | Develop plan to address Olmstead issues with additional federal funds
| 1/1/2017 5/1/17 1/1/18 6/1/18 1/1/19 | 8 | 8 | 8 | CFCO Rate Development to ensure consistency across all agencies
MONITOR
| 2015-06-30 | P | P | P | Develop Staffing Plan to Implement CFCO
| 2015-06-30 | P | P | P | Determine how DOH will oversee program/ensure compliance
| 2015-08-31 | P | P | P | Consult and Collaborate with Development and Implementation Council to Provide Updates, Strategize and Facilitate Outreach and Monitoring Efforts | A letter to the D&I council will be mailed along with the SPA once we receive CMS approval.
| 2015-06-30 | P | P | P | Determine how UAS will be used to support Quality Assurance Efforts | Reviewed tool and indicated areas to be used to meet QA efforts, shared with UAS staff.
EDUCATION AND OUTREACH
| 2015-06-30 | P | P | P | Define Communication Materials to be Developed
| 2015-09-01 | P | P | P | Draft Agency/Office Policies and Procedures for Program
| 2015-09-01 | P | P | P | Develop Informational Packets on Program | Draft ADM went to LDSSs, D&I Council and sister agencies on 5-9-16
| 2016-05-31 | P | P | P | Draft ADM for the local districts
| 8/1/16 12/1/16 6/1/17 1/1/18 4/1/18 6/1/18 1/1/19 | 8 | 8 | 8 | Develop provider manuals
| 2016-06-30 | P | P | P | Provide training for districts via presentation at NYPWA
| 9/1/15 11/1/15 2/1/16 3/31/16 | P | P | P | Develop Contracts/MOU for FIs We will be using the current MOUs/contracts for Fis; no development is needed.
8017 |  |  |  |  | Project Name: Refinancing / Shared Savings Division Lead: OHIP Team Lead: Steve Simmons Cynthia Treis Additional Staff: Cindy Treis; Tatyana Ochilo Jason Corvino, David Szelest, Conor (James) Petter Description: To encourage facilities to refinance at a lower rate. |  | Completed July 2017
| 2015-06-15 | P | P | P | Determine the eligibility guidelines and policies for the program
| 2015-06-17 | P | P | P | Present program guidelines and policies to the Associations
| 2015-06-25 | P | P | P | Obtain DOH executive approvals
| 2015-06-30 | P | P | P | Submit SPA to CMS for approval.
| 8/1/15 9/11/15 | P | P | P | respond to RAI's with executive approvals
| 2015-11-01 | 8 | 8 | 8 | Release program guidelines to industry and begin implementation
| 9/15/15 11/1/15 2/11/16 2/29/16 3/31/16 5/31/16 7/1/16 8/1/16 10/1/16 11/1/16 12/1/16 | P | P | P | Obtain CMS approval
| 9/15/15 11/1/15 2/11/16 2/29/16 3/31/16 5/31/16 7/1/16 8/1/16 10/1/16 11/1/2016 12/1/16 2/1/17 4/1/17 7/7/17 | P | P | P | Release program guidelines to industry and begin implementation
| 9/15/15 11/1/15 2/11/16 2/29/16 3/31/16 5/31/16 7/1/16 8/1/16 10/1/16 11/1/2016 12/1/16 3/1/17 5/1/17 7/14/17 | 8 | 8 | 8 | DOB briefing
8018 |  |  |  |  | Project Name: Energy Efficiency Division Lead: OHIP Team Lead: Steve Simmons, Cindy Treis Additional Staff: Cindy Treis, Ken Ferro, Conor (James) Petter Description: To reduce energy costs for Residential Health Care Facilities |  | Complete - August 2018
| 2015-06-15 | P | P | P | Determine the payment mechanism for the audits/studies by DOH and NYSERDA
| 2015-06-19 | P | P | P | Identify the pilot facilities utilizing the energy survey results
| 2015-06-19 | P | P | P | Determine contractor selection
| 6/19/15 10/1/15 | P | P | P | Finalize the application and payment process with NYSERDA
| 6/28/15 10/2/15 | P | P | P | Obtain executive approvals for the payment process
| 7/1/15 10/15/15 | P | P | P | Workgroup meeting to finalize the pilot plan
| 7/7/15 10/22/15 | P | P | P | Contact the pilot facilities
| 2016-01-12 | P | P | P | Conduct Webinar outlining the program to the pilot facilities
| 7/15/15 11/30/15 2/1/16 | P | P | P | Begin audits
| 11/1/15 7/1/16 8/31/16 | P | P | P | Finalize audits and begin review of recommendations
| 12/4/15 8/1/16 10/3/16 12/1/16 1/30/17 3/30/17 5/31/17 8/18/17 | P | P | P | Obtain executive approvals to submit the resulting reports that include the findings and recommendations
| 11/1/15 8/15/16 10/3/16 12/1/16 2/27/17 4/28/17 6/16/17 9/15/17 | P | P | P | Submit reports to the workgroup/facilities and the DOH/DPL
| 12/8/15 9/1/16 10/15/16 12/15/16 3/15/17 5/15/17 6/30/17 9/29/17 10/29/18 | 8 | 8 | 8 | Submit reports to the senate and assembly health committees
| 4/1/16 Ongoing | 8 | 8 | 8 | Begin Group II audits/studies
| 9/15/15 9/15/16 11/1/16 12/1/16 4/15/17 6/15/17 | 8 | 8 | 8 | Obtain executive approvals to submit appropriation request for the 2016/2017 fiscal year for Group II audits/studies
| 10/1/15 10/1/16 11/4/16 12/5/16 5/1/17 7/3/17 | 8 | 8 | 8 | Submit appropriation language to DLA
| 10/15/15 10/15/16 11/15/16 12/15/16 5/15/17 7/17/17 | 8 | 8 | 8 | DLA submits appropriation language to DOB
8019 |  |  |  |  | Project Name: NAMI (Net Adjusted Medicaid Income) Division Lead: Team Lead: Frank Czernicki Additional Staff: Michelle Santos Description: A state proposal to establish a demonstration program that will assume the financial and organizational responsibility to collect NAMI from Medicaid recipients.. |  | Cancelled
| 2015-04-27 | P | P | P | Meeting with CMS / DFRS to discuss state's proposal to collect NAMI.
| 2015-04-30 | P | P | P | DOH internal meeting to discuss next steps from previous meeting.
| 2015-05-04 | P | P | P | Meeting with DFRS and program staff to discuss state takeover of eligibility process / estate collections.
| 2015-07-16 | P | P | P | Prepare and recirculate paper incorporating Leading age and NH Providers' ideas.
| 2015-09-17 | P | P | P | Determine total NAMI to include collected and uncollected amount.
| 9/30/15 11/17/15 TBD | 8 | 8 | 8 | Call w/ CMS to discuss: - Benefits of proposal, Collection data, Metrics for collection performances
| TBD | 8 | 8 | 8 | Conference call w/ Nursing Home Association to discuss proposal benefits and current collection process.
| TBD | 8 | 8 | 8 | Collection process discussion with providers.
| TBD | 8 | 8 | 8 | Prepare preliminary SPA package.
| TBD | 8 | 8 | 8 | Conference call to discuss NAMI collection process with Attorney Generals' office.
| TBD | 8 | 8 | 8 | Conference call to discuss NAMI collection process with NYS Tax Dept.
| TBD | 8 | 8 | 8 | Develop regulations and Statute
| TBD | 8 | 8 | 8 | Division review/approval.
| TBD | 8 | 8 | 8 | DOB review/approval.
| TBD | 8 | 8 | 8 | SPA approval.
| TBD | 8 | 8 | 8 | Establish workgroup to discuss collection process
| TBD | 8 | 8 | 8 | Meeting with Division to determine methods of collection.
| 2017-01-01 | 8 | 8 | 8 | Implement collection process.
8020 |  |  |  |  | Project Name: Neurodegenerative Initiative (ND) Division Lead: Team Lead: Frank Czernicki Additional Staff: Michelle Santos Description: An initiative to create a comprehensive care plan for patients/residents of the five centers for excellence who are identified as having a qualifying Neuro-Degenerative disease |  | Completed May 2017
| 2015-04-01 | P | P | P | Establish Finance Sub Group to work as part of the overall ND Project.
| 2015-04-01 | P | P | P | Develop a charter for the finance workgroup.
| 2015-04-01 | P | P | P | Examine resident data and report to group at large on population.
| 2015-05-01 | P | P | P | Data gathering regarding the specific populations which could qualify for a ND Specialty.
| 2015-05-08 | P | P | P | Advisory workgroup meeting to discuss progress of sub-workgroups.
| 2015-05-15 | P | P | P | Meeting between DLA & DOH staff to discuss SPA requirement and to determine required submission time.
| 2015-05-19 | P | P | P | Analysis of MDS/total case mix for respective diseases in comparison w/total case mix statewide.
| 2015-05-22 | P | P | P | Conference call w/OHSM /OHIP and Residential services to discuss population, associated cost and acuity.
| 2015-06-19 | P | P | P | Decision point regarding population, associated cost and acuity with DOH executive staff.
| 2015-06-29 | P | P | P | Finance sub-group meeting to discuss recommendations for workgroup.
| 2015-10-02 | P | P | P | Advisory workgroup meeting
| 2015-10-16 | P | P | P | Finance sub-group meeting to discuss cost analysis data for workgroup.
| 2015-10-13 | P | P | P | Progress discussion.
| 2015-11-30 | P | P | P | Advisory workgroup meeting.
| 2015-12-07 | P | P | P | Policy discussions - Governor's office
| 2015-12-11 | P | P | P | Policy discussions on regulations and SPA
| 2015-12-12 | P | P | P | Examine budgets and propose new regulations adding ND to the reimbursement Methodology
| 8/1/15 TBD 12/15/15 | P | P | P | Develop appropriate operating budgets for facilities along with Residential Services and CON.
| 2015-12-21 | P | P | P | Begin Work on Regulatory package
| 12/21/15 2/8/15 | P | P | P | Request VAP funding and rate effective date needs of the three ND programs
| 2015-12-22 | P | P | P | Begin work on SPA package
| 7/29/15 TBD 12/23/15 2/28/16 | P | P | P | Examine appropriate costs which would be affected Capital, Operating, MDS reporting for presentation to workgroup.
| 2015-12-28 | P | P | P | Workgroup Meeting and Update
| 2015-12-30 | P | P | P | Regulatory Package into Bureau Review
| 2016-01-28 | P | P | P | Finance sub-group meeting
| 2016-02-10 | P | P | P | Advisory workgroup meeting.
| 2016-01-10 | P | P | P | Regulatory Package to DLA
| 2016-03-03 | P | P | P | VAP Bridge- Funding meeting
| 2016-03-21 | P | P | P | VAP Bridge- Funding meeting
| 2016-03-22 | P | P | P | Advisory workgroup meeting.
| 8/1/15 TBD 1/15/16 2/15/16 3/22/16 Ongoing | P | P | P | Develop proposals for changes to cost report and patient acuity instruments to capture the target population.
| 7/29/15 TBD 2/28/16 | 8 | 8 | 8 | Examine appropriate costs which would be affected Capital, Operating, MDS reporting for presentation to workgroup.
| 2016-04-11 | P | P | P | VAP Bridge- Funding meeting
| 2016-04-13 | P | P | P | Public Health & Health Planning Council Meeting
| 2016-04-25 | P | P | P | Advisory Workgroup Meeting
| 2016-05-17 | P | P | P | Finance workgroup meeting -
| 2016-05-18 | P | P | P | Finance workgroup meeting -
| 2016-05-20 | P | P | P | Finance workgroup meeting - Regs timeline
| 8/1/15 TBD 3/29/16 4/30/16 5/30/16 8/1/16 | P | P | P | Determine MDS changes as needed to capture the targeted populations for reimbursement. (Changes are required only to Section S)
| 2016-08-15 | P | P | P | Changes submitted to CMS to be effective 10/1/17
| 8/1/15 TBD 12/15/15 | 8 | 8 | 8 | Develop appropriate operating budgets for facilities along with Residential Services and CON.
| 2016-08-01 | P | P | P | New Rate Codes Requested
| 10/28/2016 11/15/16 | P | P | P | Awaiting final approval of rate Codes
| 10/1/15 TBD 3/31/16 10/1/16 3/1/17 4/28/17 | P | P | P | Develop changes to HCS filing for specialty to be effective 4/1/17
| 2016-12-15 | P | P | P | CMS meeting to discuss SPA approval
| 4/1/16 6/1/16 7/1/16 11/1/17 11/1/16 01/01/17 02/01/17 02/27/17 04/30/17 | P | P | P | New ND rates effective 11/1/16
| 9/1/15 TBD | 8 | 8 | 8 | Work with DLA on Article vii language for rates to be included with 2016-17 Executive Budget.
| 9/24/15 TBD 1/6/16 | P | P | P | Develop regulations and SPA
| 4/1/16 TBD | 8 | 8 | 8 | Legislature approval of ND rates
| 4/15/16 TBD 4/1/16 7/1/16 | P | P | P | DOH & DOB Executive approval
| 2016-06-15 | P | P | P | Out for Public Comment
| 5/1/16 TBD 4/1/16 -6/1/16 7/15/16 11/1/16 01/31/17 03/03/17 05/04/17 | P | P | P | Submit rates to eMedNY
8021 |  |  |  |  | Project Name: Medicaid Coverage of Harm Reduction Activities: AI providers reimbursement Division Lead: Office of Public Health Team Lead: Ira Feldman Additional Staff: Frank Laufer, Jackie Treanor, Ann Maxwell Description: Authorize NYS DOH AIDS Institute Syringe Exchange providers (community-based organizations) to be reimbursed by Medicaid for harm reduction/syringe exchange program services provided to Medicaid eligible individuals. | 0 | Completed July 2018 - Merged from #5314C
| 7/1/14 10/15/14 6/1/15 8/1/15 10/15/15 1/1/16 4/1/16 10/1/16 1/1/17 4/1/17 10/1/17 6/26/17 | P | P | P | Federal approval of Harm reduction SPA or 1915 waiver received
| 7/15/14, 11/1/14 7/1/15 9/1/15 11/15/15 2/1/16 5/1/16 11/1/16 2/1/17 5/1/17 10/1/17 | P | P | P | DOB approval. |  | The State submitted responses to CMS on 5/3/17. No further communication has been received from CMS.
| 8/1/14, 1/1/15 8/1/15 11/1/15 12/15/15 3/1/16 6/1/16 12/1/16 3/1/17 9/1/17 1/1/18 7/1/18 | P | P | P | Harm reduction reimbursement incorporated in Medicaid managed care monthly premium calculations. | Request for additonal information was received from CMS and DOH submitted a response | Reimbursement will be incorporated into the managed care rates with the rates that would be effective July 2018.
| 9/1/14 1/1/15 9/1/15 11/1/15 12/15/15 3/1/16 6/1/16, 12/1/16 3/1/17 9/1/17 1/1/18 7/1/18 | P | P | P | Qualified harm reduction providers contracted with health plans to provide service. |  | Contracting is taking longer but enough are ready to go.
| 10/1/14 1/1/15 10/1/15 1/1/16 4/1/16 6/1/16 12/1/16 4/1/17 10/1/17 4/1/18 7/1/18 | P | P | P | Commence billing for HR services within a managed care reimbursement structure.
| 12/1/13 9/1/14 1/1/15 10/1/15 1/1/16 4/1/16 6/1/16 12/1/16 3/1/17 9/1/17 4/1/18 | 8 | 8 | 8 | With guidance from the Harm Reduction Services Standards and Quality Assurance MRT Advisory Work Group, complete the standards for the various services and develop the necessary regulation (or guidance) for their promulgation.
| 2016-04-01 | 8 | 8 | 8 | With guidance from the Harm Reduction Services Standards and Quality Assurance MRT Advisory Work Group, define the quality assurance metrics applicable to each of the Medicaid reimbursed services.
| 2014-04-01 | 8 | 8 | 8 | Incorporate the services standards developed by the Harm Reduction Services Standards and Quality Assurance MRT Advisory Work Group in the necessary regulations (or guidance) for their promulgation.

## Ph 5 Pharmacy Savings
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2015-2016 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
Leverage Pharmacy Rebates
8101 |  |  |  |  | Project Name: Statewide Supplemental Rebates (FFS/MCO) Division Lead: Janet Zachary-Elkind Team Lead: Tony Merola Additional Staff: Mike Colabufo, Mike Dembroski Description: Leverage/negotiate supplemental rebate across the entire Medicaid population (FFS and MCO) on: 1) anti-retrovirals (ARVs) used in the treatment of HIV/AIDS and 2) drug used in the treatment of Hepatitis C (Hep C). This project in directly related to MRT Phase 3 Project # 7501 - Antiretroviral (ARV) Supplemental Rebates (SR) associated with the Ending AIDS Epidemic Initiative | $13.3M | Completed - February 2018 Merged from #7501
1) This project is related to 2015 MRT Phase 3 Project #7501 - Antiretroviral (ARV) Supplemental Rebates (SR) associated with the Ending AIDS Epidemic Initiative. 2)The department is currently receiving supplemental rebates on Hepatitis C drug, Viekira, for the FFS program. MCOs may also be negotiating and receiving rebates for Hepatitis C drugs.
| 2015-06-01 | P | P | P | Receive SPA approval from CMS for the revised State Direct Contract (SDC) Supplemental Rebate Agreement.
| 2015-06-15 | P | P | P | ARVs - Notify the Managed Care Organizations (MCOs) of the Department's intent to enter into supplemental rebate negotiations for FFS and MCO utilization.
| 2015-06-19 | P | P | P | ARVs - Notify the Supplemental Rebate Contractor (currently Magellan Medicaid Administration) of the Department's intent to negotiate supplemental rebates across the entire Medicaid population.
| 2015-07-01 | P | P | P | ARVs - Notify affected pharmaceutical manufacturers of the Department's intent to negotiate to supplemental rebates across the entire Medicaid population (FFS and MCO).
| 7/8/15 8/1/15 | P | P | P | ARVs -Send the SDC to pharmaceutical manufacturers.
| 11/15/15 1/30/15 3/15/15 6/15/15 8/1/15 | P | P | P | Convert conceptual agreement parameters for each Pharmaceutical Manufacturer into a SDC. |  | From 7501
| 12/1/14 4/1/15 7/1/15 9/2/15 9/16/15 10/14/15 11/30/15 1/15/16 3/1/16 6/1/16 8/1/16 9/1/16 11/1/16 12/15/16 | P | P | P | ARVs - Receipt of SDC from pharmaceutical manufacturers. | From 7501. SDC received from Abbive, BI, BMS, Merck, Janssen, Gilead. SDC pending with Gilead and Viiv.
| 12/15/14 3/15/15 7/1/15 9/1/15 2/15/16 | P | P | P | Review of SDC financials and compare to conceptual agreement. | From 7501 - Marked "complete" as the conceptual agreements are now outdated given current contractual negotiations.
| 12/15/14 3/15/15 7/1/15 9/16/15 9/23/15 11/1/15 12/24/15 4/1/16 6/15/16 8/15/16 9/15/16 11/15/16 12/20/16 | P | P | P | ARVs - Complete evaluation or SDCs. | Complete for Abbvie, BI, BMS, Merck, Janssen. As of April 2016 evaluations pending for Janssen and Gilead.
| 1/1/15 4/1/15 7/1/15 10/1/15 12/31/15 4/15/16 5/1/16 8/1/16 9/15/16 10/15/16 12/31/16 1/1/2017 2/15/17 | P | P | P | ARVs - Execute SDC with pharmaceutical manufacturers. | from 7501. As of April 2016, contracts have been finalized with Abbive, BMS, BI and Merck. Contract from Janssen and Gilead have be received. Viiv contract has not been received.
| 10/1/15 2/28/16 6/1/16 7/1/16 10/15/16 1/15/17 1/15/17 4/1/17 7/1/17 | P | P | P | ARVs - Validate ARV coverage in FFS and MC programs to ensure coverage parameters meet the terms of the supplemental rebate agreement.
| 1/1/16 6/1/16 | P | P | P | Hep C - Evaluate market changes, competition and current MCP costs to determine if SDC is required to contain drug costs. | New drug to market anticipated 3Q2015 1Q2016. New drug called Zepatier (made by Merck) on the market as of Feb. 2016. NMPI supplemental rebate contracting offers 4Q2015 - 1Q2016. Evaluation of supplemental rebates and positioning on the FFS preferred drug list to take place in early March 2016.
| 2/28/15 7/28/15 2/1/16 2/28/16 5/31/16 2/15/17 2/28/17 | P | P | P | ARVs - Invoice supplemental rebate for 4Q2015 3Q2016 utilization | From 7501 Invoice for 1Q16 4Q15 identified as "new" utilization associated with Ending AIDS initiative. As of July 1, 2016, units are eligible for supplemental rebates - Abbvie, Merck, BI and BMS products.
| 3/1/16 8/1/16 10/1/16 12/1/16 1/1/17 1/30/17 | P | P | P | ARVs- Evaluate MCO rate for impact and make necessary adjustments.
| 4/1/15 8/15/15 3/15/16 4/15/16 4/1/17 5/1/17 6/1/17 | P | P | P | Receipt of SRs from Pharmaceutical Manufacturers. | From 7501. As of 4/27/2016 the only contract not received is ViiV.
PREPAID CAPITATION RATE
| 10/1/15 3/1/16 8/1/16 10/1/16 10/17/16 10/21/16 11/1/16 12/7/16 12/23/16 | P | P | P | DOH/Mercer develops assumptions used to augment rates; share with plans | From 7501. Background information sent to Mike Dembroski on April 7, 2016
| 10/15/15 3/31/16 8/31/16 10/15/16 10/24/16 11/14/16 12/14/16 12/26/16 | P | P | P | DOH/Mercer develops draft rates; share with plans |  | From 7501
| 11/1/15 3/1/16 8/15/16 11/1/16 11/23/16 11/25/16 12/18/16 12/30/16 1/30/17 | P | P | P | Plans provide feedback on assumptions/draft rates |  | From 7501
| 11/15/15 4/1/16 10/1/16 11/30/16 12/20/16 12/31/16 2/13/17 | P | P | P | DOH/Mercer finalize rate adjustments |  | From 7501
| 12/15/15 8/1/16 11/1/16 12/1/16 12/26/16 12/31/16 2/27/17 3/29/17 4/24/17 5/24/17 | P | P | P | Rates approved by DOB, CMS |  | From 7501
| 2017-12-31 | P | P | P | Report to the legislature analyzing the adequacy of rate adjustment to the managed care providers (if any). |  | Statutory requirement 367-a, e (iii)
| 1/1/16 1/1/17 3/1/17 4/1/17 5/1/17 5/31/17 | P | P | P | Rates loaded to the system |  | From 7501
POST IMPLEMENTATION
| 10/1/15 6/1/16 1/1/17 4/1/17 5/1/17 10/1/17 12/1/17 2/1/18 3/1/18 | P | P | P | Evaluate SR to determine financial impact. |  | From 7501
| 1/1/2017 7/1/2017 12/1/17 1/1/18 3/1/18 | P | P | P | Assess the impact of ARV supplemental rebates on FMG Federal/State share calculations
8102 |  |  |  |  | Project Name: Accelerate Rebate Collections (FFS/MCO) Division Lead: Janet Zachary-Elkind Rebecca Corso Team Lead: Tony Merola / Rebecca Corso Additional Staff: Chris DeSorbo, Julius Pasquariello, Lubna Chauhan, Samir Ahuja, Gloria LeBesco, Mike Colabufo, Bob Biggane, Ron Bass, Carol Lindley Description: Acceleration of rebate collections through improved management of MCO encounter data and FFS claims data. | $26.8M | Completed August 2016
| 2015-04-01 | P | P | P | Evaluate MCO encounter data rejections and reprocesses/resubmit claims
| 2015-04-01 | P | P | P | Establish protocol for making policy determination related to MCO encounter claim rejections/resubmissions.
| 2015-04-01 | P | P | P | Establish tracking/reporting system to ensure all MCO claim resubmissions are accounted for and invoiced.
| 2015-04-01 | P | P | P | Incorporate J-code with a NDC into the DataMart
| 2015-04-01 | P | P | P | Identify and compile NDCs that had not been included in the rebate process.
| 2015-04-01 | P | P | P | Identify compounded prescription claims and compile NDCs associated with these compound.
| 2015-04-01 | P | P | P | Require J-Code MCO encounter claims to require submission of NDC with encounter record for all categories of service.
| 2015-04-17 | P | P | P | Retrospectively invoice for rebate associated with J-code encounter claims submitted with NDCs, NDC not included in the rebate process and NDCs associated with compounded prescriptions. |  | Retrospective invoice total for Wave 1= $15M
| 5/31/15 8/15/15 9/16/15 11/1/15 1/1/16 6/1/16 | P | P | P | Retrospectively identify all J-codes with "one to many" NDC relationships not submitted by plans prior to system enhancement/enforcement and disallow MCO submissions with no NDC (i.e. all zeros)
| 7/30/15 | P | P | P | Determine if PACE/FIDA plan utilization qualify for rebate invoicing, make system changes to capture utilization and retroactively invoice.
| 7/16/15 8/15/15 9/16/15 9/30/15 12/31/15 4/1/16 6/1/16 8/6/16 | 8 | 8 | 8 | Evaluate all categories of service for utilization that can be included in the rebate invoice, make system changes to capture utilization and retrospectively invoice. | Wave 2 of retrospective invoicing scheduled for September 2015 . Wave 3 of retrospective invocing scheduled for 1Q16 or 2Q16
| 2015-07-31 | P | P | P | Evaluate current internal controls and implement improvements where needed |  | 2015 Risk management/Internal control report completed. Improvements in the rebate system will be will be ongoing
| 2015-10-01 | P | P | P | Evaluate 340B providers, modify rebate system to identify these providers and retrospectively invoice for misclassified 340B claims
8103 |  |  |  |  | Project Name: Expand Clinical Drug Editing in FFS Division Lead: Janet Zachary-Elkind Team Lead: Monica Toohey Additional Staff: Tracy Berger Description: Incorporates clinical pharmacy editing, to include consideration of non-pharmacy claims data elements such as diagnoses and/or relevant services. Customize PA criteria to target utilization concerns related to specific diagnoses, procedure codes etc. to verify appropriate use (FDA/Compendia supported). | State Share FY 2016 ($1.1M) FY 2017 ($2.3M) | Completed May 2017
1) September 17th DURB meeting topics: Topical Compounds, Synagis, PCSK9 Inhibitors, 2) November DURB meeting potential topics: Entresto, Kaledeco/Orkambi, drugs for opioid induced constipation, Lupron 3) April 27, 2016 Topics: Hepatitis C, PDP review 4) September 15, 2016 Topics: PDP review, Gabapentin, Injectable Anticoagulants, Products for IBS 5) February 16, 2017 DUR Review Atypical Antipsychotics, Persistent Asthma, HEp C DAA clinical updates and Drug Interactions, ARV Drug Interaction, zolpidem clinical update, Clinical Edit review 6) April 2017 -PDL class review -21 classes -see DUR agenda
Reduce Inappropriate Prescribing
| 2015-05-04 | P | P | P | Identify drugs/drug classes for clinical drug editing in FFS
| 2015-07-15 | P | P | P | Work with University of Buffalo to research & develop reports for the Sept. DURB meeting
| 2015-08-15 | P | P | P | Review reports & finalize
| 2015-08-18 | P | P | P | Post agenda
| 2015-09-17 | P | P | P | DUR Board Meeting-Obtain recommendations from DURB
| 2015-09-18 | P | P | P | Work with University of Buffalo to research & develop reports for the Nov. DURB meeting.
| 2015-10-18 | P | P | P | Review reports & finalize
| 2015-10-19 | P | P | P | Post agenda
| 2015-11-19 | P | P | P | DUR Board Meeting-Obtain recommendations from DURB
| 2015-11-20 | P | P | P | Work with University of Buffalo to research & develop reports for the Feb. DURB meeting.
| 12/14/15 1/21/16 | P | P | P | Implement 11/19/15 meeting recommendations prior authorization parameters
| 3/15/16 5/4/16 | P | P | P | Expand work plan per 2016 agenda
| 2016-03-25 | P | P | P | Review reports & finalize
| 2016-03-26 | P | P | P | Post April 27 DURB meeting agenda
| 2016-04-27 | P | P | P | DUR Board Meeting-Obtain recommendations from DURB
| 2016-05-02 | P | P | P | Work with University of Buffalo to research & develop reports and Agenda for the Sept. DURB meeting
| 2016-05-26 | P | P | P | Implement DURB Hep C recommendations from 4/27 meeting
| 2016-06-30 | P | P | P | Implement DURB PDP recommendations from 4/27 meeting
| 2016-08-13 | P | P | P | Review reports & finalize
| 2016-08-15 | P | P | P | Post September 15 DURB meeting agenda
| 2016-09-15 | P | P | P | DUR Board Meeting-Obtain recommendations from DURB
| 2016-09-19 | P | P | P | Work with University of Buffalo to research & develop reports and Agenda for the 2/16/2017 DURB meeting
| 2016-11-15 | P | P | P | Implement DURB PDP recommendations from 9/15 meeting
| 2017-01-14 | P | P | P | Review reports & finalize
| 2017-01-16 | P | P | P | Post February 16 DURB meeting agenda
| 2017-02-16 | P | P | P | DUR Board Meeting-Obtain recommendations from DURB
| 2017-02-23 | P | P | P | Work with University of Buffalo to research & develop reports and Agenda for the April DURB meeting
| 2017-04-20 | P | P | P | Implement DURB PDP recommendations from 2/16 meeting
| 2017-04-27 | 8 | 8 | 8 | DUR Board Meeting-Obtain recommendations from DURB
| April | 8 | 8 | 8 | Review reports & finalize
| April | 8 | 8 | 8 | Post April DURB meeting agenda
| April | 8 | 8 | 8 | DUR Board Meeting-Obtain recommendations from DURB
| April/May | 8 | 8 | 8 | Work with University of Buffalo to research & develop reports and Agenda for the next DURB meeting
| June | 8 | 8 | 8 | Implement DURB PDP recommendations from April meeting
8104 |  |  |  |  | Project Name: Implement Managed Care Pharmacy Efficiencies Division Lead: Team Lead: Mike Dembrosky Additional Staff: Description: Effective April 1, 2015 this proposal will reduce inappropriate prescribing of prescription drugs that do not meet clinically established/evidence based criteria for Mainstream Managed Care. Better utilization of clinical editing could potentially result in avoidable dollars spent by Managed Care plans. | $13.4M | Completed - Jan 2016
| 2015-06-05 | P | P | P | DOH to complete premium build up with the efficiency adjustment
| 7/6/15 9/25/15 12/16/15 | P | P | P | Provide rates to DOB and CMS for approval
| 2015-07-06 | P | P | P | Brief plans on premiums, which will include the efficiency adjustment
| 8/6/2015 10/30/15 12/18/15 | P | P | P | Receive DOB and CMS approval
| 8/6/2015 10/30/15 12/18/15 | P | P | P | Transmit Rate package to EMedNY for payment
8105 |  |  |  |  | Project Name: Specialty Pharmacy Vendor Division Lead: Janet Zachary-Elkind Team Lead: Carol Lindley Dan McNamara Additional Staff: Patty Keller, Monica Toohey, Dan McNamara, Tracy Berger, Mike Colabufo, Joan Sicard, Ron Bass Description: Implement a statewide Medicaid FFS Specialty Pharmacy Program | 1.2M | Completed
| 2015-05-01 | P | P | P | Initiate Cystic Fibrosis Antibiotics
| 6/1/15 9/1/15 | P | P | P | Initiate 1115(b)4 Waiver Identify Target Drugs
| 6/1/15 9/15/15 | P | P | P | Develop Cost Structure/Network Strategy Develop Criteria
| 6/12/15 10/1/15 | P | P | P | Determine Drug List QA List and Criteria w/ Clinical Partners
| 6/30/15 10/1/15 | P | P | P | Develop and Finalize Contract Strategy Develop Web Page
| 7/10/15 10/1/15 | P | P | P | Implement Contract Strategy Inform Providers
| 8/15/15 10/15/15 | P | P | P | Finalize Contract(s) Load and Test Criteria HID
| 9/1/15 11/1/15 10/16/15 | P | P | P | Implement Program First Wave (Rolling Implementations)

## Ph 5 Hospital Reimbursement
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2015-2016 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
8201 |  |  |  |  | Project Name: Establish Hospital Quality Pool Division Lead: John Ulberg Team Lead: Mike Ogborn Additional Staff: Janet Baggetta, Monique Grimm Description: Develop payment methodology for implementing a hospital Quality Pool investment in the inpatient and/or outpatient rates effective 4/1/2015 | $45.4M | Completed - February 2018
| 2015-03-25 | P | P | P | Federal Public Notice date
| 2015-05-11 | P | P | P | Meet with Hospitals Associations to discuss and develop methodology
| 2015-05-13 | P | P | P | Review Hospital Association recommendations
| 2015-06-30 | P | P | P | SPA submission date
| 8/31/15 10/30/15 1/29/16 4/29/16 6/10/16 | P | P | P | Finalize year 1 and year 2 distribution calculation using reporting compliance metrics only
| 7/2/15 9/15/15 11/16/15 2/19/16 5/31/16 | 8 | 8 | 8 | Update inpatient rates and rate sheets (eff 4/1/15 4/1/16)
| 8/31/16 11/14/16 12/26/16 | P | P | P | Pool payments included in Draft Premium Rates for Managed Care
| 9/30/16 12/12/16 2/27/17 | P | P | P | Pool payments included in Final Premium Rates for Managed Care
| 2017-04-30 | P | P | P | DOB Approval of Premium Rates for Managed Care
| 2017-05-31 | P | P | P | Pool Distributions by the Health Plans
| 7/15/15 9/22/15 11/23/15 2/29/16 6/10/16 9/30/16 12/31/16 3/31/17 5/31/17 6/16/17 7/6/17 | P | P | P | Draft Provider Communications (e.g. DAL, etc.)
| 7/31/15 9/30/15 11/30/15 3/4/16 6/15/16 | 8 | 8 | 8 | Release rates to the Medicaid Managed Care Plans on the DOH Website (prior to SPA approval)
| 10/15/15 12/15/15 3/31/16 7/31/16 10/31/16 2/28/16 4/30/17 7/31/17 9/30/17 11/30/17 2/28/18 3/31/18 | P | P | P | Finalize expanded metrics based on quality for subsequent years
| 6/30/15 10/30/15 12/30/15 4/15/16 8/15/16 11/30/16 6/30/17 | 8 | 8 | 8 | Regulation submission date
| 9/30/15 12/31/15 1/29/16 5/31/16 9/30/16 12/31/16 6/30/17 | 8 | 8 | 8 | SPA Approval by CMS (FFS) | There is a proposal to pay this entirely through MMC premiums which may eliminate the need for this SPA
| 12/31/15 2/28/16 6/30/16 10/31/16 2/28/17 6/30/17 | 8 | 8 | 8 | Regulation approval date
| 8/3/15 1/22/16 3/15/16 7/15/16 10/31/16 12/15/16 2/28/17 | 8 | 8 | 8 | Division of the Budget Approval | There is a proposal to pay this entirely through MMC premiums which may eliminate DOB approval of the pool payment in the FFS rates
| 10/15/15 1/29/16 3/22/16 7/29/16 11/15/16 12/31/16 3/31/17 | 8 | 8 | 8 | Post Rates to the HCS and DOH Website for Medicaid Fee-for-Service (Dependent upon DOB and SPA approval) | Timing is dependent upon whether or not the pool is paid through FFS
8202 |  |  |  |  | Project Name: Invest in Essential Community Hospitals Division Lead: John Ulberg Team Lead: Mike Ogborn Additional Staff: Janet Baggetta, Monique Grimm Description: Develop payment methodology for implementing a Essential/Sole Community provider investment in the inpatient and/or outpatient rates effective 6/1/2015 | $4.5M | Completed - February 2018
| 2015-03-25 | P | P | P | Federal Public Notice date
| 2015-05-11 | P | P | P | Meet with Hospitals Associations to discuss and develop methodology
| 2015-05-13 | P | P | P | Review Hospital Association recommendations
| 2015-06-30 | P | P | P | SPA submission date
| 8/31/15 10/30/15 1/29/16 4/29/16 6/10/16 | P | P | P | Finalize year 1 and year 2 distribution calculation using reporting compliance metrics only
| 7/2/15 9/15/15 11/16/15 2/19/16 5/31/16 | 8 | 8 | 8 | Update inpatient rates and rate sheets (eff 4/1/15 4/1/16)
| 8/31/16 11/14/16 12/26/16 | P | P | P | Pool payments included in Draft Premium Rates for Managed Care
| 9/30/16 12/12/16 2/27/17 | P | P | P | Pool payments included in Final Premium Rates for Managed Care
| 2017-04-30 | P | P | P | DOB Approval of Premium Rates for Managed Care
| 2017-05-31 | P | P | P | Pool Distributions by the Health Plans
| 7/15/15 9/22/15 11/23/15 2/29/16 6/10/16 9/30/16 12/31/16 3/31/17 5/31/17 6/16/17 7/6/17 | P | P | P | Draft Provider Communications (e.g. DAL, etc.)
| 11/30/17 2/28/18 3/31/18 | P | P | P | Finalize expanded metrics based on quality for subsequent years
| 7/31/15 9/30/15 11/30/15 3/4/16 6/15/16 | 8 | 8 | 8 | Release rates to the Medicaid Managed Care Plans on the DOH Website (prior to SPA approval)
| 6/30/15 10/30/15 12/30/15 4/15/16 8/15/16 11/30/16 6/30/17 | 8 | 8 | 8 | Regulation submission date
| 9/30/15 12/31/15 1/29/16 5/31/16 9/30/16 12/31/16 6/30/17 | 8 | 8 | 8 | SPA Approval by CMS (FFS) | There is a proposal to pay this entirely through MMC premiums which may eliminate the need for this SPA
| 12/31/15 2/28/16 6/30/16 10/31/16 2/28/17 6/30/17 | 8 | 8 | 8 | Regulation approval date
| 8/3/15 1/22/16 3/15/16 7/15/16 10/31/16 12/15/16 2/28/17 | 8 | 8 | 8 | Division of the Budget Approval | There is a proposal to pay this entirely through MMC premiums which may eliminate DOB approval of the pool payment in the FFS rates
| 10/15/15 1/29/16 3/22/16 7/29/16 11/15/16 12/31/16 3/31/17 | 8 | 8 | 8 | Post Rates to the HCS and DOH Website for Medicaid Fee-for-Service (Dependent upon DOB and SPA approval) | Timing is dependent upon whether or not the pool is paid through FFS
8203 |  |  |  |  | Project Name: Eliminate PPNO Rate Reduction Division Lead: John Ulberg Team Lead: Mike Ogborn Additional Staff: Janet Baggetta, Monique Grimm Description: Eliminate the reduction for potentially preventable negative outcomes from the inpatient acute rates effective 4/1/2015 | $25.5M | Completed May 2017
| 2015-03-25 | P | P | P | Federal Public Notice date
| 7/2/15 9/15/15 11/16/15 2/19/16 5/31/16 7/31/16 9/16/16 | P | P | P | Update inpatient rates and rate sheets (eff 4/1/15 1/1/16) |  | Payment for 4/1/15 - 12/31/15 PPNO to be paid through 2016 rates
| 7/15/15 9/22/15 11/23/15 2/29/16 6/10/16 8/7/16 9/23/16 11/4/16 11/28/16 | P | P | P | Draft Provider Communications (e.g. DAL, etc.)
| 7/31/15 9/30/15 11/30/15 3/4/16 6/20/16 8/15/16 10/14/16 11/10/16 12/15/16 3/31/17 4/30/17 5/6/17 | P | P | P | Release rates to the Medicaid Managed Care Plans on the DOH Website (prior to SPA approval) |  | Managed Care Implementation will be with the 1/1/17 rates due to Global Cap
| 8/3/15 1/22/16 3/15/16 7/15/16 7/31/16 8/22/16 10/31/16 11/30/16 12/31/16 2/3/17 3/31/17 5/15/17 | P | P | P | Division of the Budget Approval
| 10/15/15 1/29/16 3/22/16 7/29/16 8/15/16 8/29/16 10/28/16 11/10/16 12/15/16 1/31/17 2/17/17 4/14/17 1/20/17 | P | P | P | Post Rates to the HCS and DOH Website for Medicaid Fee-for-Service (Released Prior to Dependent upon DOB approval)
8204 |  |  |  |  | Project Name: Eliminate Across the Board Elective Deliveries Division Lead: John Ulberg Team Lead: Mike Ogborn Additional Staff: Janet Baggetta, Monique Grimm Description: Eliminated the reduction to the statewide base price associated with elective deliveries from the inpatient acute rates effective 4/1/2015 | $9.6M $28.8 | In Progress -To be implemented at the same time as MRT 's 8201 & 8203
| 2015-03-25 | P | P | P | Federal Public Notice date
| 2015-06-30 | P | P | P | SPA submission date
| 7/2/15 9/15/15 11/16/15 2/19/16 5/31/16 7/31/16 9/16/16 | P | P | P | Update inpatient rates and rate sheets (eff 4/1/15 1/1/16) |  | Payment for 4/1/15 - 12/31/15 elective deliveries to be paid through 2016 rates
| 7/15/15 9/22/15 11/23/15 2/29/16 6/10/16 8/7/16 9/23/16 11/4/16 3/15/17 6/30/17 10/31/17 12/22/17 3/31/18 7/31/18 10/1/18 12/1/18 | 8 | 8 | 8 | Draft Provider Communications (e.g. DAL, etc.) |  | Dependent upon SPA approval
| 7/31/15 9/30/15 11/30/15 3/4/16 6/20/16 8/15/16 10/14/16 11/10/16 12/15/16 3/31/17 4/30/17 5/5/17 | P | P | P | Release rates to the Medicaid Managed Care Plans on the DOH Website (prior to SPA approval) |  | Dependent upon completion of 1/1/17 rates (not being included in 1/1/16 rates for MMC)
| 10/15/15 12/15/15 4/15/16 6/30/16 10/31/16 12/31/16 2/28/17 5/31/17 8/31/17 11/30/17 2/28/18 6/30/18 7/31/18 9/30/18 11/30/18 | 8 | 8 | 8 | Regulation submission date
| 9/30/15 12/31/15 1/29/16 5/31/16 7/15/16 9/30/16 11/30/16 1/31/17 2/28/17 5/31/17 9/30/17 12/15/17 2/28/18 6/30/18 7/31/18 9/30/18 11/30/18 | 8 | 8 | 8 | SPA Approval by CMS
| 12/31/15 2/28/16 6/30/16 8/31/16 2/28/17 6/30/17 9/30/17 12/31/17 5/31/18 11/30/18 | 8 | 8 | 8 | Regulation approval date
| 8/3/15 1/22/16 3/15/16 7/15/16 7/31/16 10/31/16 12/31/16 2/28/17 4/30/17 7/31/17 10/15/17 1/15/18 3/31/18 7/31/18 9/30/18 12/31/18 | 8 | 8 | 8 | Division of the Budget Approval
| 10/15/15 1/29/16 3/22/16 7/29/16 8/15/16 11/15/16 1/15/17 3/15/17 5/31/17 8/15/17 10/31/17 1/22/18 4/7/18 8/7/18 10/7/18 1/7/19 | 8 | 8 | 8 | Post Rates to the HCS and DOH Website for Medicaid Fee-for-Service (Dependent upon DOB and SPA approval)

## Ph 5 Supportive Housing
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2015-2016 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
8301 |  |  |  |  | Project Name: Peer Training/Employment Linkages Division Lead: Division of Long-Term Care Team Lead: Liz Misa, Mark Kissinger Additional Staff: Denard Cummings, Emily Engel Description: Peer training and employment linkage program for individuals residing in MRT SH units |  | Cancelled
| 2015-06-15 | P | P | P | Schedule MRT SH subgroup meeting to discuss Peer Training
| 8/4/15 9/1/15 | P | P | P | Schedule second round of subgroup meetings
| 2015-11-30 | 8 | 8 | 8 | Convene group and create project next/DOH proposal steps based on group recommendations.
| 2016-04-01 | 8 | 8 | 8 | Review project progress and determine next steps
8302 |  |  |  |  | Project Name: Medical Respite and DSRIP Rental Subsidy Program Division Lead: Division of Long Term Care Division of Program Development and Management Team Lead: Liz Misa, Mark Kissinger Andrew Segal Additional Staff: Denard Cummings, Rachel Baron-VanCleve Description: Creating connections to permanent housing options for the DSRIP Transitional Supportive Housing Program |  | Suspended
| 2015-06-08 | P | P | P | Schedule MRT SH subgroup meeting to discuss DSRIP Transitional Housing Program
| 8/4/15 9/17/15 | P | P | P | Schedule second round of subgroup meetings
| 2015-11-30 | 8 | 8 | 8 | Convene group and create project next/DOH proposal steps based on group recommendations.
| 2016-02-11 | P | P | P | Meet with PPS that is implementing DSRIP 2.b.vi, Transitional Supportive Housing
| 2016-03-24 | P | P | P | Hold meeting with PPS, OMH and OASAS to establish program connections
| 2016-04-01 | P | P | P | Review project progress and determine next steps
| 2016-05-20 | P | P | P | Review proposal from PPS implementing DSRIP 2.b.vi, Transitional Supportive Housing and determine next steps
| 2016-06-23 | P | P | P | Determine procurement strategy
| 7/5/2016 9/1/2016 11/1/2016 12/15/16 2/15/17 TBD | 8 | 8 | 8 | Issue Request for Information Solicitation of Interest
| 4/1/2017 TBD | 8 | 8 | 8 | Review project and determine next steps
8303 |  |  |  |  | Project Name: Moving On Initiative Division Lead: Division of Long-Term Care Team Lead: Liz Misa, Mark Kissinger Additional Staff: Denard Cummings, Emily Engel Description: Moving-On initiative to transition supportive housing participants to less service intensive program with demonstrated capacity and desire. |  | Suspended
| 2015-06-15 | P | P | P | Schedule MRT SH subgroup meeting to discuss Moving On Initiative
| 8/4/15 9/1/15 | P | P | P | Schedule second round of subgroup meetings
| 2015-11-30 | 8 | 8 | 8 | Convene group and create project next/DOH proposal steps based on group recommendations.
| 2016-04-01 | 8 | 8 | 8 | Review project progress and determine next steps
8304 |  |  |  |  | Project Name: Access to Homes Division Lead: Liz Misa, Mark Kissinger Team Lead: Denard Cummings Additional Staff: Description: MRT Allocation to HCR for MRT Access to Home Program |  | Completed - Jan 2016
| 6/15/15 6/23/15 7/31/15 | P | P | P | Develop RFP
| 2015-09-21 | P | P | P | Applications received
| 2016-01-04 | P | P | P | Awards made
| 2016-01-04 | 8 | 8 | 8 | Contracts executed
8305 |  |  |  |  | Project Name: MRT Service and Operating Division Lead: Liz Misa, Mark Kissinger Team Lead: Denard Cummings Additional Staff: Description: MRT S&O fund |  | Cancelled
| 6/23/15 8/31/15 | 8 | 8 | 8 | Schedule a MRT Subgroup meeting to discuss. |  | Implemented by OMH RFP through JP Morgan settlement
8306 |  |  |  |  | Project Name: Medical Respite Program Division Lead: Division of Long-Term Care Team Lead: Liz Misa, Mark Kissinger Additional Staff: Denard Cummings Description: Workgroup looking into a medical respite model. |  | Merged - #9003
| 2015-06-08 | P | P | P | Schedule MRT SH subgroup meeting to discuss DSRIP Transitional Housing Program
| 8/4/15 9/17/15 | P | P | P | Schedule second round of subgroup meetings
| 2015-11-30 | 8 | 8 | 8 | Convene group and create project next/DOH proposal steps based on group recommendations.
| 2016-04-01 | 8 | 8 | 8 | Review project progress and determine next steps

## Ph 5 Care Mgt for All
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2015-2016 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
8401 |  |  |  |  | Project Name: Care Management Population & Benefit Expansion, Access to Services, and Consumer Rights Division Lead: DMC Team Lead: Joanne Martinez Patricia Sheppard Additional Staff: Nina Daratsos, Eric Planck Denise Urbano, Alisa Costa, Desirae Munn, and Joanne Martinez Description: Omnibus Medicaid Managed Care initiatives, eliminates many exempt/excluded populations, expands the benefit package, promotes access to services, and ensures consumer rights |  | In Progress -Merged from #1458
POPULATION EXPANSION
| 6/1/16 4/1/17 7/1/17 Under Review | 8 | 8 | 8 | Well Duals (Except "Partials") |  | DLTC MMC is lead for transition
| 4/1/16 5/1/17 7/1/17 UR | 8 | 8 | 8 | Identify population to be enrolled
| 4/1/16 5/1/17 7/1/17 UR | 8 | 8 | 8 | Assess systems impact
| 4/1/16 5/1/17 7/1/17 UR | 8 | 8 | 8 | Ongoing stakeholders meetings
| 5/1/16 4/1/17 7/1/17 UR | 8 | 8 | 8 | State issues policy guidance
| 6/1/16 4/1/17 7/1/17 UR | 8 | 8 | 8 | Effective date initial phase of enrollment
POPULATION AND BENEFIT EXPANSION
| 2016-07-01 | P | P | P | LT Chemical Abuse Program (Non Duals) (ROS) |  | Adult BH Team is lead
| 2016-07-01 | P | P | P | State Operated Psych Center (Non Duals) (ROS)
| 2016-07-01 | P | P | P | OMH County - District 97 Adults (Non Duals) (ROS)
| 2016-01-15 | P | P | P | Identify population to be enrolled
| 3/1/16 2/1/16 | P | P | P | Enrollment notices finalized
| 3/1/16 1/21/16 | P | P | P | Assess systems impact
| 3/1/16 1/21/16 | P | P | P | Update Scope of Benefits
| 2016-04-01 | P | P | P | Ongoing stakeholders meetings
| 2016-05-01 | P | P | P | Enrollment notices begin
| 2016-07-01 | P | P | P | Effective date initial phase of enrollment
POPULATION AND BENEFIT EXPANSION
| 12/1/16 1/1/17, 4/1/17 7/1/17 1/1/18 10/1/18, TBD | 8 | 8 | 8 | Assisted Living Program (Non Duals and Duals) (NYC) |  | DLTC is lead
| 12/1/16 1/1/17, 4/1/17 7/1/17 1/1/18 1/1/19, TBD | 8 | 8 | 8 | Assisted Living Program (Non Duals and Duals) (ROS) |  | DLTC is lead
| 9/1/2016, 12/1/16, 3/1/17 6/1/17 7/1/17 4/1/18 | 8 | 8 | 8 | Identify population to be enrolled |  | Just benefit coming into plan
| 9/1/2016, 12/1/16, 3/1/17 6/1/17 7/1/17 4/1/18, 8/1/18, TBD | 8 | 8 | 8 | Assess systems impact
| 9/1/2016, 12/1/16, 3/1/17 6/1/17 7/1/17 10/1/18, TBD | 8 | 8 | 8 | Ongoing stakeholders meetings
| 10/1/2016 12/1/16, 3/1/17 6/1/17 7/1/17 7/1/18, 10/1/18, TBD | 8 | 8 | 8 | Issue Policy Paper
| 12/1/16 1/1/17, 4/1/17, 7/1/17 1/1/18 10/1/18, TBD | 8 | 8 | 8 | Effective date initial phase of enrollment
| 2019-01-01 |  |  |  | POPULATION AND BENEFIT EXPANSION
| 1/1/2017 7/1/17 10/1/17 7/1/18 | 8 | 8 | 8 | OMH County - District 97 Kids (Non Duals) Statewide (NYC, Nassau, Suffolk) |  | Children's BH Team is lead
| 1/1/2017 7/1/17 10/1/17 TBD | 8 | 8 | 8 | RRSY (Residential Rehabilitation Services for Youth) (NYC, Nassau, Suffolk)
| 1/1/2017 7/1/17 10/1/17 7/1/18, Under review, 7/1/19 | 8 | 8 | 8 | B2H - All categories (Non Duals) Statewide (NYC, Nassau, Suffolk)
| 1/1/2017 7/1/17 10/1/17 1/1/19, Under review, 7/1/19 | 8 | 8 | 8 | Agency Based Per Diem Foster Care (Non Duals) Statewide (NYC, Nassau, Suffolk)
| 1/1/2017 7/1/17 10/1/17 7/1/18, Under review, 1/1/19, 4/1/19 | 8 | 8 | 8 | Care at Home I and II HCBS Waiver III (Duals and Non Duals) Statewide (NYC, Nassau, Suffolk)
| 7/1/2018, Under Review, 1/1/19, 4/1/19 | 8 | 8 | 8 | OPWDD Care at Home III (Non Duals) Statewide
| 7/1/2018, Under review, 1/1/19, 4/1/19 | 8 | 8 | 8 | OMH Seriously Emotionally Disturbed (SED) (Non Duals) Statewide
| 2015-04-01 | P | P | P | Ongoing stakeholders meetings
| 4/1/18 TBD 4/1/18 7/1/17 10/1/17 7/1/18, 1/1/19 | 8 | 8 | 8 | Contract Amendment
| 6/1/2016 7/1/17 10/1/17 7/1/17 3/1/18 UR, 10/1/18 | 8 | 8 | 8 | Assess systems impact
| 8/1/2016 7/1/17 10/1/17 7/1/17 10/2/17, 1/1/18 4/1/18 UR, 10/1/18, 12/1/19 | 8 | 8 | 8 | Enrollment notice development
| 10/1/2016 7/1/17 10/1/17 3/19/18 UR, 11/1/18, 12/1/18 | 8 | 8 | 8 | Enrollment notices begin
| 1/1/2017 7/1/17 | 8 | 8 | 8 | NHTD (Duals and Non Duals)
| 1/1/2017 7/1/17 | 8 | 8 | 8 | TBI Waiver (Duals and Non Duals)
| 12/1/2016 7/1/17 10/1/17 1/1/18 7/1/18, 1/1/19 | 8 | 8 | 8 | State issues policy guidance
POPULATION EXPANSION
| 1/1/17 1/1/18 4/1/18 1/1/19 under view TBD 1/1/22 | 8 | 8 | 8 | NHTD (Duals and Non Duals) |  | DLTC is lead
| 1/1/17 1/1/18 4/1/18 1/1/19 under review TBD 1/1/22 | 8 | 8 | 8 | TBI Waiver (Duals and Non Duals) |  | DLTC is lead
| 2018-04-01 | 8 | 8 | 8 | Contract Amendments
| 5/18/16 7/7/16 | P | P | P | Release Plan for public comment
| 2015-06-01 | P | P | P | Ongoing stakeholders meetings
| 2016-06-01 | 8 | 8 | 8 | Assess systems impact
| 6/18/16 8/15/16 | P | P | P | End Public Comment Period
| 2016-08-01 | 8 | 8 | 8 | Enrollment notice development
| 2016-07-08 | P | P | P | Consult with CMS Regional Staff on different authorities to assure coordination
| 2016-07-08 | P | P | P | Phase two Stakeholder meetings
| 10/1/2016 12/1/2016 3/1/17 4/1/18 7/1/21 9/1/18 under review 7/1/21 | 8 | 8 | 8 | Complete review of assessment tools
| 10/1/16 11/1/16 | 8 | 8 | 8 | Enrollment notices begin
| 3/1/17 12/1/16 | 8 | 8 | 8 | State issues policy guidance
| 12/1/2016 9/1/17 7/1/18 TBD 7/1/21 | 8 | 8 | 8 | Submit Plan to CMS
| 2017-01-01 | 8 | 8 | 8 | Effective date initial phase of enrollment
| 1/1/2017, 4/1/17 1/1/18 4/1/18 TBD 9/1/21 | 8 | 8 | 8 | CFCO Integrated into Managed Care
| 6/1/2017 6/1/18 TBD 9/1/21 | 8 | 8 | 8 | Submit 1115 Amendment as related to waivers
| 9/1/2017 11/1/2017 12/1/2017 3/1/18 TBD 9/1/21 | 8 | 8 | 8 | Plan Contract Amendments/RFA for RRDCs
| 9/1/2017 4/1/2018 9/1/18 TBD 9/1/21 | 8 | 8 | 8 | Begin Training Initiatives
| 10/1/2017 1/1/18 12/1/18 TBD 9/1/21 | 8 | 8 | 8 | State issues policy guidance
| 12/1/2017 2/1/18 TBD 9/1/21 | 8 | 8 | 8 | Enrollment notices begin
| 1/1/2018 4/1/18 TBD UNDER REVIEW UNTIL 9/1/21 | 8 | 8 | 8 | Effective date initial phase of enrollment
| 3/1/2018 1/1/18 4/1/18 TBD 9/1/21 | 8 | 8 | 8 | Mandatory Enrollment begins
| 4/1/2018 1/1/18 4/1/18 TBD 9/1/21 | 8 | 8 | 8 | Services in place
| 4/1/17 4/1/18 | 8 | 8 | 8 | Contract Amendments
| 1/1/2019 TBD 9/1/21 | 8 | 8 | 8 | Continue the NHTD/TBI Medicaid Managed Care carve-out until January 1, 2019
POPULATION AND BENEFIT EXPANSION
| 4/1/2017 10/1/17 Under Review | 8 | 8 | 8 | Nursing Home ("New" Duals and Non-Duals) (Statewide Kids)
| 11/1/2016 5/1/17 7/1/17 UR | 8 | 8 | 8 | Ongoing stakeholders meetings
| 3/1/2017 9/1/17 UR | 8 | 8 | 8 | State issues policy guidance
| 3/1/2017 9/1/17 UR | 8 | 8 | 8 | Assess systems impact
| 2017-04-01 | 8 | 8 | 8 | Enrollment assistance begins
| 4/1/2017 10/1/17 UR | 8 | 8 | 8 | Contract Amendments
| 4/1/2017 10/1/17 UR | 8 | 8 | 8 | Effective date initial phase of enrollment
POPULATION EXPANSION
| 7/1/2017 1/1/18 | 8 | 8 | 8 | OMH County - District 97 Kids (Non Duals) (ROS) | Merged above, now statewide | Children's BH Team is lead
| 7/1/2017 1/1/18 TBD | 8 | 8 | 8 | RRSY (Residential Rehabilitation Services for Youth) (ROS)
| 7/1/2017 1/1/18 | 8 | 8 | 8 | B2H - All categories (Non Duals) (ROS) | Merged above, now statewide
| 7/1/2017 1/1/18 1/1/19 | 8 | 8 | 8 | Agency Based Per Diem Foster Care (Non Duals) (ROS) | Merged above, now statewide
| 7/1/2017 1/1/18 | 8 | 8 | 8 | Care at Home I and II (Duals and Non Duals) (ROS) | Merged above, now statewide
| 4/1/15 4/1/16 | P | P | P | Ongoing stakeholders meetings
| 2/1/2017 8/1/17 | 8 | 8 | 8 | Assess systems impact
| 4/1/2017 10/1/17 | 8 | 8 | 8 | Contract Amendments
| 5/1/2017 11/1/17 | 8 | 8 | 8 | Enrollment notices begin
| 6/1/2017 12/1/17 | 8 | 8 | 8 | State issues policy guidance
POPULATION BENEFIT EXPANSION
| 12/1/2017 Under Review | 8 | 8 | 8 | Cancer Treatment Program
| 5/1/2017 7/1/17 UR | 8 | 8 | 8 | Assess systems impact
| 6/1/2017 UR | 8 | 8 | 8 | Notice Development
| 11/1/2017 UR | 8 | 8 | 8 | State issues policy guidance
| TBD 4/1/18 | 8 | 8 | 8 | Contract Amendments
POPULATION EXPANSION
| 12/1/2017 Under Review | 8 | 8 | 8 | Pre-Natal Care (during presumptive eligibility period)
| 5/1/2017 7/1/17 UR | 8 | 8 | 8 | Assess systems impact
| 6/1/2017 UR | 8 | 8 | 8 | Notice Development
| 11/1/2017 UR | 8 | 8 | 8 | State issues policy guidance
| TBD 4/1/18 | 8 | 8 | 8 | Contract Amendments
POPULATION EXPANSION
| 12/1/2017 Under Review | 8 | 8 | 8 | Returned Mails
| 6/1/2017 UR | 8 | 8 | 8 | Assess systems impact
| 11/1/2017 UR | 8 | 8 | 8 | State issues policy guidance
| TBD 4/1/18 | 8 | 8 | 8 | Contract Amendments
POPULATION EXPANSION
| 12/1/2017 Under Review | 8 | 8 | 8 | Spend downs (Non Duals)
| 5/1/2017 7/1/17 UR | 8 | 8 | 8 | Assess systems impact
| 6/1/2017 UR | 8 | 8 | 8 | Notice Development
| 11/1/2017 UR | 8 | 8 | 8 | State issues policy guidance
| TBD 4/1/18 | 8 | 8 | 8 | Contract Amendments
POPULATION EXPANSION
| 12/1/2017 Under Review | 8 | 8 | 8 | TPHI without Medicare
| 6/1/2017 UR | 8 | 8 | 8 | Assess systems impact
| 11/1/2017 UR | 8 | 8 | 8 | State issues policy guidance
| TBD 4/1/18 | 8 | 8 | 8 | Contract Amendments
POPULATION EXPANSION
| 12/1/2017 Under Review | 8 | 8 | 8 | Out of State Residents
| 6/1/2017 UR | 8 | 8 | 8 | Assess systems impact
| 11/1/2017 UR | 8 | 8 | 8 | State issues policy guidance
| TBD 4/1/18 | 8 | 8 | 8 | Contract Amendments
POPULATION EXPANSION
| Under Review |  |  |  | OMH District 97 Kids
POPULATION EXPANSION
| Under Review |  |  |  | RRSY (Residential Rehabilitation Services for Youth
POPULATION EXPANSION
| 10/1/2019 1/1/18 | 8 | 8 | 8 | Care at Home III, IV, VI (Non Duals) (ROS) | Merged with CAH 1 & 2 | Children's BH Team is lead
| 10/1/2018 10/1/17 | 8 | 8 | 8 | Ongoing stakeholders meetings
| 4/1/2019 7/1/17 | 8 | 8 | 8 | Assess systems impact
| TBD 4/1/18 1/1/18 | 8 | 8 | 8 | Contract Amendments
| 5/1/2019 8/1/17 | 8 | 8 | 8 | Notice development
| 8/1/2019 11/1/17 | 8 | 8 | 8 | Enrollment notices begin
| 9/1/2019 12/1/17 | 8 | 8 | 8 | State issues policy guidance
| 10/1/2019 1/1/18 | 8 | 8 | 8 | Effective date initial phase of enrollment
OPWDD
| 2016-03-01 | P | P | P | OPWDD-FIDA-IDD Multiple outreach and education events
| 2016-03-08 | P | P | P | OPWDD-FIDA-IDD Announcement notices mailing initiated
| 2016-04-01 | P | P | P | OPWDD Phase 1 (voluntary) Duals into OPWDD-FIDA-IDD (NYC, Nassau, Suffolk, Westchester, Rockland)
| 2018-04-01 | 8 | 8 | 8 | OPWDD Phase 2 (mandatory) Non Duals into DISCOs
| 2018-10-01 | 8 | 8 | 8 | OPWDD Phase 3 (mandatory) Non Duals into DISCOs (cont.)
| 2019-10-01 | 8 | 8 | 8 | OPWDD Phase 4 (mandatory) Non Duals into DISCOs (cont.)
added to 8401 |  |  |  |  | Project Name: School Based Health Centers carve out Division Lead: DPDM Team Lead: Jonathan Bick Additional Staff: Greg Allen, Connie Donohue Description: The Executive agrees to continue the SBHC Medicaid Managed Care carve-out until July 1, 2018. |  | Formerly 10403
| 2017-01-01 | P | P | P | State issued policy paper
| 2017-01-27 | P | P | P | FAQ's posted
| 2017-04-01 | P | P | P | Billing Guidance issued
| 1/1/2018 7/1/18, 7/1/2020 | 8 | 8 | 8 | Assess System Impact
| 4/1/2018, 4/1/2020 | 8 | 8 | 8 | Contract Amendment
| 5/1/2018, 11/1/2020 | 8 | 8 | 8 | Medicaid Update Article Issued
| 5/1/2018, 11/1/2020 | 8 | 8 | 8 | Update Scope of Benefits
| 6/1/2018 7/1/2020 | 8 | 8 | 8 | CMS approval
| 7/1/2018, 5/1/2020 | 8 | 8 | 8 | Stakeholder feedback
| 7/1/2018 1/1/2021 | 8 | 8 | 8 | Effective Date of Transition

## Boo Yah
Boo-Yah!

## Boo-yah (hidden)
BOO-YAH!